## Sheet1
Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA
Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT | Selected Group :- A-BLD INTERNAL PAINT
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 731601 | A-BLD INTERNAL PAINT | Dz 12nos) |  |  | 0 | 708293 | 31 | 0 | [6 empty] | 0.0000
2 | 731602 | A-BLD 1ST FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
3 | 731628 | B-BLD 1ST FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 11404 | 11404 | 2 | 731602 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
4 | 731651 | B-BLD 1ST FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 5256 | 5256 | 2 | 731602 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
5 | 731604 | A-BLD 2ND FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
6 | 731627 | B-BLD 2ND FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 5 | 731604 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
7 | 731652 | B-BLD 2ND FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 5 | 731604 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
8 | 731605 | A-BLD 3RD FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
9 | 731629 | B-BLD 3RD FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 8 | 731605 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
10 | 731653 | B-BLD 3RD FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 8 | 731605 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
11 | 731603 | A-BLD 4TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
12 | 731630 | B-BLD 4TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 11 | 731603 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
13 | 731654 | B-BLD 4TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 11 | 731603 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
14 | 731606 | A-BLD 5TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
15 | 731631 | B-BLD 5TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 14 | 731606 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
16 | 731655 | B-BLD 5TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 14 | 731606 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
17 | 731607 | A-BLD 6TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
18 | 731632 | B-BLD 6TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 17 | 731607 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
19 | 731656 | B-BLD 6TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 17 | 731607 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
20 | 731608 | A-BLD 7TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
21 | 731633 | B-BLD 7TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 20 | 731608 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
22 | 731657 | B-BLD 7TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 20 | 731608 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
23 | 731609 | A-BLD 8TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
24 | 731634 | B-BLD 8TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 23 | 731609 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
25 | 731658 | B-BLD 8TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 23 | 731609 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
26 | 731610 | A-BLD 9TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
27 | 731635 | B-BLD 9TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 26 | 731610 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
28 | 731659 | B-BLD 9TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 26 | 731610 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
29 | 731611 | A-BLD 10TH FLOOR FLAT -(REF) | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
30 | 731636 | B-BLD 10TH FLOOR FLAT -(REF) TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 29 | 731611 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
31 | 731660 | B-BLD 10TH FLOOR FLAT -(REF) OBD PAINT (M+L) | Sq.ft | 8313 | 8313 | 29 | 731611 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
32 | 731612 | A-BLD 11TH FLOOR FLAT -(REF) | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
33 | 731637 | B-BLD 11TH FLOOR FLAT -(REF) TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 32 | 731612 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
34 | 731661 | B-BLD 11TH FLOOR FLAT -(REF) OBD PAINT (M+L) | Sq.ft | 8313 | 8313 | 32 | 731612 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
35 | 731613 | A-BLD 12TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
36 | 731638 | B-BLD 12TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 35 | 731613 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
37 | 731662 | B-BLD 12TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 35 | 731613 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
38 | 731614 | A-BLD 13TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
39 | 731639 | B-BLD 13TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 38 | 731614 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
40 | 731663 | B-BLD 13TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 38 | 731614 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
41 | 731615 | A-BLD 14TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
42 | 731640 | B-BLD 14TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 41 | 731615 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
43 | 731664 | B-BLD 14TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 41 | 731615 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
44 | 731616 | A-BLD 15TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
45 | 731641 | B-BLD 15TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 44 | 731616 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
46 | 731665 | B-BLD 15TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 44 | 731616 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
47 | 731617 | A-BLD 16TH FLOOR FLAT -(REF) | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
48 | 731642 | B-BLD 16TH FLOOR FLAT -(REF) TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 47 | 731617 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
49 | 731666 | B-BLD 16TH FLOOR FLAT -(REF) OBD PAINT (M+L) | Sq.ft | 8313 | 8313 | 47 | 731617 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
50 | 731618 | A-BLD 17TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
51 | 731643 | B-BLD 17TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 50 | 731618 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
52 | 731667 | B-BLD 17TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 50 | 731618 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
53 | 731619 | A-BLD 18TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
54 | 731644 | B-BLD 18TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 53 | 731619 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
55 | 731668 | B-BLD 18TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 53 | 731619 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
56 | 731620 | A-BLD 19TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
57 | 731645 | B-BLD 19TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 56 | 731620 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
58 | 731669 | B-BLD 19TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 56 | 731620 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
59 | 731621 | A-BLD 20TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
60 | 731646 | B-BLD 20TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 59 | 731621 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
61 | 731670 | B-BLD 20TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 59 | 731621 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
62 | 731622 | A-BLD 21TH FLOOR FLAT -(REF) | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
63 | 731647 | B-BLD 21TH FLOOR FLAT -(REF) TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 62 | 731622 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
64 | 731671 | B-BLD 21TH FLOOR FLAT -(REF) OBD PAINT (M+L) | Sq.ft | 8313 | 8313 | 62 | 731622 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
65 | 731623 | A-BLD 22TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
66 | 731648 | B-BLD 22TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 65 | 731623 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
67 | 731672 | B-BLD 22TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 65 | 731623 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
68 | 731624 | A-BLD 23TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
69 | 731649 | B-BLD 23TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 68 | 731624 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
70 | 731673 | B-BLD 23TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 68 | 731624 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
71 | 731625 | A-BLD 24TH FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000
72 | 731650 | B-BLD 24TH FLOOR FLAT TRACTOR EMULSION PAINT | SQFT | 18336 | 18336 | 71 | 731625 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
73 | 731674 | B-BLD 24TH FLOOR FLAT OBD PAINT (M+L) | Sq.ft | 8323 | 8323 | 71 | 731625 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
74 | 731626 | A-BLD TERRACE FLOOR FLAT | Dz 12nos) |  |  | 1 | 731601 | 31 | 0 | [6 empty] | 0.0000