## Sheet1
Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA
Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY | Selected Group :- A.BLDG LOBY
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 731686 | A.BLDG LOBY | Dz 12nos) | 0.0000 | 0.0000 | 0 | 708293 | 31 | 0 | [6 empty] | 0.0000
2 | 731687 | A.BLDG 1ST FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
3 | 731688 | A.BLDG 1ST FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 2 | 731687 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
4 | 731737 | A.BLDG 1ST FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 2 | 731687 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
5 | 731762 | A.BLDG 1ST FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 265.0000 | 265.0000 | 2 | 731687 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
6 | 731689 | A.BLDG 2ND FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
7 | 731690 | A.BLDG 2ND FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 6 | 731689 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
8 | 731738 | A.BLDG 2ND FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 6 | 731689 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
9 | 731763 | A.BLDG 2ND FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 6 | 731689 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
10 | 731691 | A.BLDG 3RD FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
11 | 731692 | A.BLDG 3RD FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 10 | 731691 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
12 | 731740 | A.BLDG 3RD FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 10 | 731691 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
13 | 731764 | A.BLDG 3RD FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 10 | 731691 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
14 | 731693 | A.BLDG 4TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
15 | 731694 | A.BLDG 4TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 14 | 731693 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
16 | 731741 | A.BLDG 4TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 14 | 731693 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
17 | 731765 | A.BLDG 4TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 14 | 731693 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
18 | 731695 | A.BLDG 5TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
19 | 731696 | A.BLDG 5TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 18 | 731695 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
20 | 731742 | A.BLDG 5TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 18 | 731695 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
21 | 731766 | A.BLDG 5TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 18 | 731695 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
22 | 731697 | A.BLDG 6TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
23 | 731698 | A.BLDG 6TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 22 | 731697 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
24 | 731743 | A.BLDG 6TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 22 | 731697 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
25 | 731767 | A.BLDG 6TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 22 | 731697 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
26 | 731699 | A.BLDG 7TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
27 | 731700 | A.BLDG 7TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 26 | 731699 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
28 | 731744 | A.BLDG 7TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 26 | 731699 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
29 | 731768 | A.BLDG 7TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 26 | 731699 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
30 | 731701 | A.BLDG 8TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
31 | 731702 | A.BLDG 8TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 30 | 731701 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
32 | 731745 | A.BLDG 8TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 30 | 731701 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
33 | 731769 | A.BLDG 8TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 30 | 731701 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
34 | 731703 | A.BLDG 9TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
35 | 731704 | A.BLDG 9TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 34 | 731703 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
36 | 731746 | A.BLDG 9TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 34 | 731703 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
37 | 731770 | A.BLDG 9TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 34 | 731703 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
38 | 731705 | A.BLDG 10TH FL LOBY -(REF) | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
39 | 731706 | A.BLDG 10TH FL LOBY -(REF) OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 38 | 731705 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
40 | 731747 | A.BLDG 10TH FL LOBY -(REF) TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 38 | 731705 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
41 | 731771 | A.BLDG 10TH FL LOBY -(REF) 2MM TEXTURE WITH ACRYALIC PAINT ( | Sq.ft | 278.0000 | 278.0000 | 38 | 731705 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
42 | 731707 | A.BLDG 11TH FL LOBY -(REF) | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
43 | 731708 | A.BLDG 11TH FL LOBY -(REF) OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 42 | 731707 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
44 | 731748 | A.BLDG 11TH FL LOBY -(REF) TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 42 | 731707 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
45 | 731772 | A.BLDG 11TH FL LOBY -(REF) 2MM TEXTURE WITH ACRYALIC PAINT ( | Sq.ft | 278.0000 | 278.0000 | 42 | 731707 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
46 | 731709 | A.BLDG 12TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
47 | 731710 | A.BLDG 12TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 46 | 731709 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
48 | 731749 | A.BLDG 12TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 46 | 731709 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
49 | 731773 | A.BLDG 12TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 46 | 731709 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
50 | 731711 | A.BLDG 13TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
51 | 731712 | A.BLDG 13TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 50 | 731711 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
52 | 731750 | A.BLDG 13TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 50 | 731711 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
53 | 731774 | A.BLDG 13TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 50 | 731711 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
54 | 731713 | A.BLDG 14TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
55 | 731714 | A.BLDG 14TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 54 | 731713 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
56 | 731751 | A.BLDG 14TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 54 | 731713 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
57 | 731775 | A.BLDG 14TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 54 | 731713 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
58 | 731715 | A.BLDG 15TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
59 | 731716 | A.BLDG 15TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 58 | 731715 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
60 | 731752 | A.BLDG 15TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 58 | 731715 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
61 | 731776 | A.BLDG 15TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 58 | 731715 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
62 | 731717 | A.BLDG 16TH FL LOBY -(REF) | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
63 | 731718 | A.BLDG 16TH FL LOBY -(REF) OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 62 | 731717 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
64 | 731753 | A.BLDG 16TH FL LOBY -(REF) TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 62 | 731717 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
65 | 731777 | A.BLDG 16TH FL LOBY -(REF) 2MM TEXTURE WITH ACRYALIC PAINT ( | Sq.ft | 278.0000 | 278.0000 | 62 | 731717 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
66 | 731719 | A.BLDG 17TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
67 | 731720 | A.BLDG 17TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 66 | 731719 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
68 | 731754 | A.BLDG 17TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 66 | 731719 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
69 | 731778 | A.BLDG 17TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 66 | 731719 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
70 | 731721 | A.BLDG 18TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
71 | 731722 | A.BLDG 18TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 70 | 731721 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
72 | 731755 | A.BLDG 18TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 70 | 731721 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
73 | 731779 | A.BLDG 18TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 70 | 731721 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
74 | 731723 | A.BLDG 19TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
75 | 731724 | A.BLDG 19TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 74 | 731723 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
76 | 731756 | A.BLDG 19TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 74 | 731723 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
77 | 731780 | A.BLDG 19TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 74 | 731723 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
78 | 731725 | A.BLDG 20TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
79 | 731726 | A.BLDG 20TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 78 | 731725 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
80 | 731757 | A.BLDG 20TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 78 | 731725 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
81 | 731781 | A.BLDG 20TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 78 | 731725 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
82 | 731727 | A.BLDG 21TH FL LOBY -(REF) | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
83 | 731728 | A.BLDG 21TH FL LOBY -(REF) OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 82 | 731727 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
84 | 731758 | A.BLDG 21TH FL LOBY -(REF) TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 82 | 731727 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
85 | 731782 | A.BLDG 21TH FL LOBY -(REF) 2MM TEXTURE WITH ACRYALIC PAINT ( | Sq.ft | 278.0000 | 278.0000 | 82 | 731727 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
86 | 731729 | A.BLDG 22TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
87 | 731730 | A.BLDG 22TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 86 | 731729 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
88 | 731759 | A.BLDG 22TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 86 | 731729 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
89 | 731783 | A.BLDG 22TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 86 | 731729 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
90 | 731731 | A.BLDG 23TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
91 | 731732 | A.BLDG 23TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 90 | 731731 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
92 | 731760 | A.BLDG 23TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 90 | 731731 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
93 | 731784 | A.BLDG 23TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 90 | 731731 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
94 | 731733 | A.BLDG 24TH FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
95 | 731734 | A.BLDG 24TH FL LOBY OBD PAINT (M+L) | Sq.ft | 3333 | 3333 | 94 | 731733 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
96 | 731761 | A.BLDG 24TH FL LOBY TRACTOR EMULSION PAINT | SQFT | 3651.0000 | 3651.0000 | 94 | 731733 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
97 | 731785 | A.BLDG 24TH FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 278.0000 | 278.0000 | 94 | 731733 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
98 | 731735 | A.BLDG TERRACE FL LOBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731686 | 31 | 0 | [6 empty] | 0.0000
99 | 731736 | A.BLDG TERRACE FL LOBY OBD PAINT (M+L) | Sq.ft | 1885 | 1885 | 98 | 731735 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
100 | 731739 | A.BLDG TERRACE FL LOBY TRACTOR EMULSION PAINT | SQFT | 3954.0000 | 3954.0000 | 98 | 731735 | 4 | 94091 | TRACTOR EMULSION PAINT | [5 empty] | 0.0000
101 | 731786 | A.BLDG TERRACE FL LOBY 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 0.0000 | 0.0000 | 98 | 731735 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000