## Sheet1
Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA | Project :-41 ZILLENIA
Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT | Selected Group :- B-BLD OIL PAINT
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 731791 | B-BLD OIL PAINT | Dz 12nos) | 0.0000 | 0.0000 | 0 | 708293 | 31 | 0 | [6 empty] | 0.0000
2 | 731792 | A-BLD OIL PAINT 1ST FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
3 | 731793 | A-BLD OIL PAINT 1ST FLOOR OIL PAINT | SQFT | 2898 | 2898 | 2 | 731792 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
4 | 731794 | A-BLD OIL PAINT 2ND FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
5 | 731795 | A-BLD OIL PAINT 2ND FLOOR OIL PAINT | SQFT | 2898 | 2898 | 4 | 731794 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
6 | 731796 | A-BLD OIL PAINT 3RD FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
7 | 731797 | A-BLD OIL PAINT 3RD FLOOR OIL PAINT | SQFT | 2898 | 2898 | 6 | 731796 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
8 | 731798 | A-BLD OIL PAINT 4TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
9 | 731799 | A-BLD OIL PAINT 4TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 8 | 731798 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
10 | 731800 | A-BLD OIL PAINT 5TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
11 | 731801 | A-BLD OIL PAINT 5TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 10 | 731800 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
12 | 731802 | A-BLD OIL PAINT 6TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
13 | 731803 | A-BLD OIL PAINT 6TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 12 | 731802 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
14 | 731804 | A-BLD OIL PAINT 7TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
15 | 731805 | A-BLD OIL PAINT 7TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 14 | 731804 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
16 | 731806 | A-BLD OIL PAINT 8TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
17 | 731807 | A-BLD OIL PAINT 8TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 16 | 731806 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
18 | 731808 | A-BLD OIL PAINT 9TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
19 | 731809 | A-BLD OIL PAINT 9TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 18 | 731808 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
20 | 731810 | A-BLD OIL PAINT 10TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
21 | 731811 | A-BLD OIL PAINT 10TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 20 | 731810 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
22 | 731812 | A-BLD OIL PAINT 11TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
23 | 731813 | A-BLD OIL PAINT 11TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 22 | 731812 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
24 | 731814 | A-BLD OIL PAINT 12TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
25 | 731815 | A-BLD OIL PAINT 12TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 24 | 731814 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
26 | 731816 | A-BLD OIL PAINT 13TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
27 | 731817 | A-BLD OIL PAINT 13TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 26 | 731816 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
28 | 731818 | A-BLD OIL PAINT 14TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
29 | 731819 | A-BLD OIL PAINT 14TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 28 | 731818 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
30 | 731820 | A-BLD OIL PAINT 15TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
31 | 731821 | A-BLD OIL PAINT 15TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 30 | 731820 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
32 | 731822 | A-BLD OIL PAINT 16TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
33 | 731823 | A-BLD OIL PAINT 16TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 32 | 731822 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
34 | 731824 | A-BLD OIL PAINT 17TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
35 | 731825 | A-BLD OIL PAINT 17TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 34 | 731824 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
36 | 731826 | A-BLD OIL PAINT 18TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
37 | 731827 | A-BLD OIL PAINT 18TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 36 | 731826 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
38 | 731828 | A-BLD OIL PAINT 19TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
39 | 731829 | A-BLD OIL PAINT 19TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 38 | 731828 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
40 | 731830 | A-BLD OIL PAINT 20TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
41 | 731831 | A-BLD OIL PAINT 20TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 40 | 731830 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
42 | 731832 | A-BLD OIL PAINT 21TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
43 | 731833 | A-BLD OIL PAINT 21TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 42 | 731832 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
44 | 731834 | A-BLD OIL PAINT 22TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
45 | 731835 | A-BLD OIL PAINT 22TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 44 | 731834 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
46 | 731836 | A-BLD OIL PAINT 23TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
47 | 731837 | A-BLD OIL PAINT 23TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 46 | 731836 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000
48 | 731838 | A-BLD OIL PAINT 24TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 731791 | 31 | 0 | [6 empty] | 0.0000
49 | 731839 | A-BLD OIL PAINT 24TH FLOOR OIL PAINT | SQFT | 2898 | 2898 | 48 | 731838 | 4 | 94092 | OIL PAINT | [5 empty] | 0.0000