## MatLabCategoryVarianceDetails_1
Material/Labour Category Variance Details
Project Name : 41 ZOY
Task Name : A BLDG RCC
Page 1 of 1
Total Records: 273 Records 1 to 273
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | A BLDG FOOTING RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | A BLDG FOOTING RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | A BLDG FOOTING RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | A BLDG FOOTING RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 42.5 | 85078 | 3615815 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.5 | 42.5 | 3615815 | 3615815
5 | A BLDG FOOTING RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 6050 | 915.68 | 5539864 | 0 | 915.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 6050 | 5539864 | 5539864
6 | A BLDG FOOTING RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M25 Grade of Concrete | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | A BLDG FOOTING RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M30 Grade Concrete. | CUM | 840 | 7847 | 6591480 | 0 | 7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 840 | 6591480 | 6591480
8 | A BLDG FOOTING RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M40 Grade Concrete. | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | A BLDG FOOTING RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying PCC - M10 Grade Concrete | CUM | 110 | 5664 | 623040 | 0 | 5664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 623040 | 623040
10 | A BLDG RAFT RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | A BLDG RAFT RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | A BLDG RAFT RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | A BLDG RAFT RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 7.5 | 85078 | 638085 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 638085 | 638085
14 | A BLDG RAFT RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 1 | 915.68 | 915.68 | 0 | 915.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 915.68 | 915.68
15 | A BLDG RAFT RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)Providing & Laying M25 Grade of Concrete | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | A BLDG RAFT RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)Providing & Laying M30 Grade Concrete. | CUM | 200 | 7847 | 1569400 | 0 | 7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 1569400 | 1569400
17 | A BLDG RAFT RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)Providing & Laying M40 Grade Concrete. | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | A BLDG RE WALL RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | A BLDG RE WALL RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | A BLDG RE WALL RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | A BLDG RE WALL RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 9.75 | 85078 | 829510.5 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.75 | 9.75 | 829510.5 | 829510.5
22 | A BLDG RE WALL RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 910 | 915.68 | 833268.8 | 0 | 915.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910 | 910 | 833268.8 | 833268.8
23 | A BLDG RE WALL RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)Providing & Laying M25 Grade of Concrete | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | A BLDG RE WALL RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)Providing & Laying M30 Grade Concrete. | CUM | 130 | 7847 | 1020110 | 0 | 7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 130 | 1020110 | 1020110
25 | A BLDG RE WALL RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)Providing & Laying M40 Grade Concrete. | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
27 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
28 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
29 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 18.5 | 85078 | 1573943 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.5 | 18.5 | 1573943 | 1573943
30 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 375 | 915.68 | 343380 | 0 | 915.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 375 | 343380 | 343380
31 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)Providing & Laying M25 Grade of Concrete | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)Providing & Laying M30 Grade Concrete. | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) |  | Tentative | Labour | (L)Providing & Laying M40 Grade Concrete. | CUM | 50 | 8378 | 418900 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 418900 | 418900
34 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
35 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
36 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
37 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 32 | 85078 | 2722496 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 2722496 | 2722496
38 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 3600 | 915.68 | 3296448 | 0 | 915.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 3296448 | 3296448
39 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M25 Grade of Concrete | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M30 Grade Concrete. | CUM | 280 | 7847 | 2197160 | 0 | 7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 280 | 2197160 | 2197160
41 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M40 Grade Concrete. | CUM | 196 | 8378 | 1642088 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 196 | 1642088 | 1642088
42 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
43 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
44 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
45 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 33 | 85078 | 2807574 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 33 | 2807574 | 2807574
46 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 3600 | 915.68 | 3296448 | 0 | 915.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 3296448 | 3296448
47 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M25 Grade of Concrete | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M30 Grade Concrete. | CUM | 276 | 7847 | 2165772 | 0 | 7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276 | 276 | 2165772 | 2165772
49 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M40 Grade Concrete. | CUM | 209 | 8378 | 1751002 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209 | 209 | 1751002 | 1751002
50 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
51 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
52 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
53 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29 | 85078 | 2467262 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 2467262 | 2467262
54 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 3450 | 915.68 | 3159096 | 0 | 915.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3450 | 3450 | 3159096 | 3159096
55 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M25 Grade of Concrete | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M30 Grade Concrete. | CUM | 278 | 7847 | 2181466 | 0 | 7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 278 | 2181466 | 2181466
57 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M40 Grade Concrete. | CUM | 172.5 | 8378 | 1445205 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172.5 | 172.5 | 1445205 | 1445205
58 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
59 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
60 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
61 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29 | 85078 | 2467262 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 2467262 | 2467262
62 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 3450 | 915.68 | 3159096 | 0 | 915.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3450 | 3450 | 3159096 | 3159096
63 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M25 Grade of Concrete | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M30 Grade Concrete. | CUM | 272 | 7847 | 2134384 | 0 | 7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272 | 272 | 2134384 | 2134384
65 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M40 Grade Concrete. | CUM | 172.5 | 8378 | 1445205 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172.5 | 172.5 | 1445205 | 1445205
66 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
67 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
68 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
69 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30 | 85078 | 2552340 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 2552340 | 2552340
70 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 3600 | 915.68 | 3296448 | 0 | 915.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 3296448 | 3296448
71 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M25 Grade of Concrete | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M30 Grade Concrete. | CUM | 280 | 7847 | 2197160 | 0 | 7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 280 | 2197160 | 2197160
73 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M40 Grade Concrete. | CUM | 172 | 8378 | 1441016 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 172 | 1441016 | 1441016
74 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
75 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
76 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
77 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29 | 85078 | 2467262 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 2467262 | 2467262
78 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 3550 | 915.68 | 3250664 | 0 | 915.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3550 | 3550 | 3250664 | 3250664
79 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M25 Grade of Concrete | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M30 Grade Concrete. | CUM | 265 | 7847 | 2079455 | 0 | 7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 265 | 2079455 | 2079455
81 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | 0 | Tentative | Labour | (L)Providing & Laying M40 Grade Concrete. | CUM | 172 | 8378 | 1441016 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 172 | 1441016 | 1441016
82 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
83 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
84 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
85 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
86 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 32 | 85078 | 2722496 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 2722496 | 2722496
87 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
88 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
90 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
91 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
92 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
93 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
94 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 32 | 85078 | 2722496 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 2722496 | 2722496
95 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
96 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
97 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
98 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
99 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
100 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
101 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
102 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 32 | 85078 | 2722496 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 2722496 | 2722496
103 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
104 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
105 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
106 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
107 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
108 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
109 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
110 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 32 | 85078 | 2722496 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 2722496 | 2722496
111 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
112 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
113 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
114 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
115 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
116 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
117 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
118 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 32 | 85078 | 2722496 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 2722496 | 2722496
119 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
120 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
121 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
122 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
123 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
124 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
125 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
126 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 31 | 85078 | 2637418 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 2637418 | 2637418
127 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
128 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
129 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
130 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
131 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
132 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
133 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
134 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 31 | 85078 | 2637418 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 2637418 | 2637418
135 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
136 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
137 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
138 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
139 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
140 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
141 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
142 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 31 | 85078 | 2637418 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 2637418 | 2637418
143 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
144 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
145 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
146 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
147 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
148 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
149 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
150 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 31 | 85078 | 2637418 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 2637418 | 2637418
151 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
152 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
153 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
154 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
155 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
156 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
157 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
158 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 31 | 85078 | 2637418 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 2637418 | 2637418
159 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
160 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
161 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
162 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
163 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
164 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
165 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
166 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 31 | 85078 | 2637418 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 2637418 | 2637418
167 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
168 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
169 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
170 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
171 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
172 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
173 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
174 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30 | 85078 | 2552340 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 2552340 | 2552340
175 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
176 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
177 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
178 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
179 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
180 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
181 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
182 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30 | 85078 | 2552340 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 2552340 | 2552340
183 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
184 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
185 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
186 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
187 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
188 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
189 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
190 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30 | 85078 | 2552340 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 2552340 | 2552340
191 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
192 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
193 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
194 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
195 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
196 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
197 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
198 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30 | 85078 | 2552340 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 2552340 | 2552340
199 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
200 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
201 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
202 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
203 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
204 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
205 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
206 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30 | 85078 | 2552340 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 2552340 | 2552340
207 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
208 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
209 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
210 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
211 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
212 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
213 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
214 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30 | 85078 | 2552340 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 2552340 | 2552340
215 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
216 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
217 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
218 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
219 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
220 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
221 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
222 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29 | 85078 | 2467262 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 2467262 | 2467262
223 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
224 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
225 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
226 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
227 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
228 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
229 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
230 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29 | 85078 | 2467262 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 2467262 | 2467262
231 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
232 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
233 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
234 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
235 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
236 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
237 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
238 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29 | 85078 | 2467262 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 2467262 | 2467262
239 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
240 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
241 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
242 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
243 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
244 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
245 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
246 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29 | 85078 | 2467262 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 2467262 | 2467262
247 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
248 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
249 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
250 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
251 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
252 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
253 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
254 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29 | 85078 | 2467262 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 2467262 | 2467262
255 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
256 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
257 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
258 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
259 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
260 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
261 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
262 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 28 | 85078 | 2382184 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 2382184 | 2382184
263 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
264 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
265 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
266 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 3800 | 407.1 | 1546980 | 0 | 407.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 3800 | 1546980 | 1546980
267 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 20MM Coupler | NO | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
268 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 25MM Coupler | NO | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
269 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L- 32MM Coupler | NO | 1 | 94.4 | 94.4 | 0 | 94.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 94.4 | 94.4
270 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29 | 85078 | 2467262 | 0 | 85078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 2467262 | 2467262
271 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM30 Grade Concrete | CUM | 215 | 8260 | 1775900 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1775900 | 1775900
272 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM35 Grade Concrete | CUM | 1 | 8378 | 8378 | 0 | 8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8378 | 8378
273 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | 0 | Tentative | Labour | (L)Providing & Laying FFM40 Grade Concrete | CUM | 156 | 8673 | 1352988 | 0 | 8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 1352988 | 1352988
133869.25