## Sheet1
Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY | Project :- 41 ZOY
Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC | Selected Group :- A BLDG RCC
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
732928 | A BLDG FOOTING RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 0.0000 | 0.0000 | 818.001.001.001.002.001.001.001. | 40.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732928 | A BLDG FOOTING RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 0.0000 | 0.0000 | 818.001.001.001.002.001.001.001. | 60.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732928 | A BLDG FOOTING RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 0.0000 | 0.0000 | 818.001.001.001.002.001.001.001. | 80.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732928 | A BLDG FOOTING RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 42.5000 | 85078.0000 | 818.001.001.001.002.001.001.001. | 72100.0000 | Labour | 416 | 551565.0000 | C + SGST 18% I/P
732928 | A BLDG FOOTING RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167904 | Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 6050.0000 | 915.6800 | 818.001.001.001.002.001.001.001. | 776.0000 | Labour | 416 | 845064.0000 | C + SGST 18% I/P
732928 | A BLDG FOOTING RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166125 | Providing & Laying M25 Grade of Concrete | CUM | 0.0000 | 7611.0000 | 818.001.001.001.002.001.001.001. | 6450.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732928 | A BLDG FOOTING RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165401 | Providing & Laying M30 Grade Concrete. | CUM | 840.0000 | 7847.0000 | 818.001.001.001.002.001.001.001. | 6650.0000 | Labour | 416 | 1005480.0000 | C + SGST 18% I/P
732928 | A BLDG FOOTING RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166441 | Providing & Laying M40 Grade Concrete. | CUM | 0.0000 | 8378.0000 | 818.001.001.001.002.001.001.001. | 7100.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732928 | A BLDG FOOTING RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165393 | Providing & Laying PCC - M10 Grade Concrete | CUM | 110.0000 | 5664.0000 | 818.001.001.001.002.001.001.001. | 4800.0000 | Labour | 416 | 95040.0000 | C + SGST 18% I/P
732930 | A BLDG RAFT RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 0.0000 | 0.0000 | 818.001.001.001.002.001.002.001. | 40.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732930 | A BLDG RAFT RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 0.0000 | 0.0000 | 818.001.001.001.002.001.002.001. | 60.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732930 | A BLDG RAFT RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 0.0000 | 0.0000 | 818.001.001.001.002.001.002.001. | 80.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732930 | A BLDG RAFT RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 7.5000 | 85078.0000 | 818.001.001.001.002.001.002.001. | 72100.0000 | Labour | 416 | 97335.0000 | C + SGST 18% I/P
732930 | A BLDG RAFT RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167904 | Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 1.0000 | 915.6800 | 818.001.001.001.002.001.002.001. | 776.0000 | Labour | 416 | 139.6800 | C + SGST 18% I/P
732930 | A BLDG RAFT RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166125 | Providing & Laying M25 Grade of Concrete | CUM | 0.0000 | 7611.0000 | 818.001.001.001.002.001.002.001. | 6450.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732930 | A BLDG RAFT RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165401 | Providing & Laying M30 Grade Concrete. | CUM | 200.0000 | 7847.0000 | 818.001.001.001.002.001.002.001. | 6650.0000 | Labour | 416 | 239400.0000 | C + SGST 18% I/P
732930 | A BLDG RAFT RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166441 | Providing & Laying M40 Grade Concrete. | CUM | 0.0000 | 8378.0000 | 818.001.001.001.002.001.002.001. | 7100.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732932 | A BLDG RE WALL RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 0.0000 | 0.0000 | 818.001.001.001.002.001.003.001. | 40.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732932 | A BLDG RE WALL RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 0.0000 | 0.0000 | 818.001.001.001.002.001.003.001. | 60.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732932 | A BLDG RE WALL RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 0.0000 | 0.0000 | 818.001.001.001.002.001.003.001. | 80.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732932 | A BLDG RE WALL RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 9.7500 | 85078.0000 | 818.001.001.001.002.001.003.001. | 72100.0000 | Labour | 416 | 126535.5000 | C + SGST 18% I/P
732932 | A BLDG RE WALL RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167904 | Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 910.0000 | 915.6800 | 818.001.001.001.002.001.003.001. | 776.0000 | Labour | 416 | 127108.8000 | C + SGST 18% I/P
732932 | A BLDG RE WALL RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166125 | Providing & Laying M25 Grade of Concrete | CUM | 0.0000 | 7611.0000 | 818.001.001.001.002.001.003.001. | 6450.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732932 | A BLDG RE WALL RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165401 | Providing & Laying M30 Grade Concrete. | CUM | 130.0000 | 7847.0000 | 818.001.001.001.002.001.003.001. | 6650.0000 | Labour | 416 | 155610.0000 | C + SGST 18% I/P
732932 | A BLDG RE WALL RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166441 | Providing & Laying M40 Grade Concrete. | CUM | 0.0000 | 8378.0000 | 818.001.001.001.002.001.003.001. | 7100.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732934 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.001.004.001. | 40.0000 | Labour | 416 | 7.2000 | C + SGST 18% I/P
732934 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.001.004.001. | 60.0000 | Labour | 416 | 10.8000 | C + SGST 18% I/P
732934 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.001.004.001. | 80.0000 | Labour | 416 | 14.4000 | C + SGST 18% I/P
732934 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 18.5000 | 85078.0000 | 818.001.001.001.002.001.004.001. | 72100.0000 | Labour | 416 | 240093.0000 | C + SGST 18% I/P
732934 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167904 | Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 375.0000 | 915.6800 | 818.001.001.001.002.001.004.001. | 776.0000 | Labour | 416 | 52380.0000 | C + SGST 18% I/P
732934 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166125 | Providing & Laying M25 Grade of Concrete | CUM | 0.0000 | 7611.0000 | 818.001.001.001.002.001.004.001. | 6450.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732934 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165401 | Providing & Laying M30 Grade Concrete. | CUM | 0.0000 | 7847.0000 | 818.001.001.001.002.001.004.001. | 6650.0000 | Labour | 416 | 0.0000 | C + SGST 18% I/P
732934 | A BLDG COL. UPTO PLINTH RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166441 | Providing & Laying M40 Grade Concrete. | CUM | 50.0000 | 8378.0000 | 818.001.001.001.002.001.004.001. | 7100.0000 | Labour | 416 | 63900.0000 | C + SGST 18% I/P
732958 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.001.002. | 40.0000 | Labour | 0 | 7.2000
732958 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.001.002. | 60.0000 | Labour | 0 | 10.8000
732958 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.001.002. | 80.0000 | Labour | 0 | 14.4000
732958 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 32.0000 | 85078.0000 | 818.001.001.001.002.002.001.002. | 72100.0000 | Labour | 0 | 415296.0000
732958 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167904 | Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 3600.0000 | 915.6800 | 818.001.001.001.002.002.001.002. | 776.0000 | Labour | 0 | 502848.0000
732958 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166125 | Providing & Laying M25 Grade of Concrete | CUM | 0.0000 | 0.0000 | 818.001.001.001.002.002.001.002. | 6450.0000 | Labour | 0 | 0.0000
732958 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165401 | Providing & Laying M30 Grade Concrete. | CUM | 280.0000 | 7847.0000 | 818.001.001.001.002.002.001.002. | 6650.0000 | Labour | 0 | 335160.0000
732958 | A BLDG 1ST SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166441 | Providing & Laying M40 Grade Concrete. | CUM | 196.0000 | 8378.0000 | 818.001.001.001.002.002.001.002. | 7100.0000 | Labour | 0 | 250488.0000
732960 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.002.002. | 40.0000 | Labour | 0 | 7.2000
732960 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.002.002. | 60.0000 | Labour | 0 | 10.8000
732960 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.002.002. | 80.0000 | Labour | 0 | 14.4000
732960 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 33.0000 | 85078.0000 | 818.001.001.001.002.002.002.002. | 72100.0000 | Labour | 0 | 428274.0000
732960 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167904 | Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 3600.0000 | 915.6800 | 818.001.001.001.002.002.002.002. | 776.0000 | Labour | 0 | 502848.0000
732960 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166125 | Providing & Laying M25 Grade of Concrete | CUM | 0.0000 | 0.0000 | 818.001.001.001.002.002.002.002. | 6450.0000 | Labour | 0 | 0.0000
732960 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165401 | Providing & Laying M30 Grade Concrete. | CUM | 276.0000 | 7847.0000 | 818.001.001.001.002.002.002.002. | 6650.0000 | Labour | 0 | 330372.0000
732960 | A BLDG 2ND SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166441 | Providing & Laying M40 Grade Concrete. | CUM | 209.0000 | 8378.0000 | 818.001.001.001.002.002.002.002. | 7100.0000 | Labour | 0 | 267102.0000
732962 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.003.002. | 40.0000 | Labour | 0 | 7.2000
732962 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.003.002. | 60.0000 | Labour | 0 | 10.8000
732962 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.003.002. | 80.0000 | Labour | 0 | 14.4000
732962 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29.0000 | 85078.0000 | 818.001.001.001.002.002.003.002. | 72100.0000 | Labour | 0 | 376362.0000
732962 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167904 | Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 3450.0000 | 915.6800 | 818.001.001.001.002.002.003.002. | 776.0000 | Labour | 0 | 481896.0000
732962 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166125 | Providing & Laying M25 Grade of Concrete | CUM | 0.0000 | 0.0000 | 818.001.001.001.002.002.003.002. | 6450.0000 | Labour | 0 | 0.0000
732962 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165401 | Providing & Laying M30 Grade Concrete. | CUM | 278.0000 | 7847.0000 | 818.001.001.001.002.002.003.002. | 6650.0000 | Labour | 0 | 332766.0000
732962 | A BLDG 3RD SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166441 | Providing & Laying M40 Grade Concrete. | CUM | 172.5000 | 8378.0000 | 818.001.001.001.002.002.003.002. | 7100.0000 | Labour | 0 | 220455.0000
732964 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.004.002. | 40.0000 | Labour | 0 | 7.2000
732964 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.004.002. | 60.0000 | Labour | 0 | 10.8000
732964 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.004.002. | 80.0000 | Labour | 0 | 14.4000
732964 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29.0000 | 85078.0000 | 818.001.001.001.002.002.004.002. | 72100.0000 | Labour | 0 | 376362.0000
732964 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167904 | Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 3450.0000 | 915.6800 | 818.001.001.001.002.002.004.002. | 776.0000 | Labour | 0 | 481896.0000
732964 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166125 | Providing & Laying M25 Grade of Concrete | CUM | 0.0000 | 0.0000 | 818.001.001.001.002.002.004.002. | 6450.0000 | Labour | 0 | 0.0000
732964 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165401 | Providing & Laying M30 Grade Concrete. | CUM | 272.0000 | 7847.0000 | 818.001.001.001.002.002.004.002. | 6650.0000 | Labour | 0 | 325584.0000
732964 | A BLDG 4TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166441 | Providing & Laying M40 Grade Concrete. | CUM | 172.5000 | 8378.0000 | 818.001.001.001.002.002.004.002. | 7100.0000 | Labour | 0 | 220455.0000
732966 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.005.002. | 40.0000 | Labour | 0 | 7.2000
732966 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.005.002. | 60.0000 | Labour | 0 | 10.8000
732966 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.005.002. | 80.0000 | Labour | 0 | 14.4000
732966 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30.0000 | 85078.0000 | 818.001.001.001.002.002.005.002. | 72100.0000 | Labour | 0 | 389340.0000
732966 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167904 | Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 3600.0000 | 915.6800 | 818.001.001.001.002.002.005.002. | 776.0000 | Labour | 0 | 502848.0000
732966 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166125 | Providing & Laying M25 Grade of Concrete | CUM | 0.0000 | 0.0000 | 818.001.001.001.002.002.005.002. | 6450.0000 | Labour | 0 | 0.0000
732966 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165401 | Providing & Laying M30 Grade Concrete. | CUM | 280.0000 | 7847.0000 | 818.001.001.001.002.002.005.002. | 6650.0000 | Labour | 0 | 335160.0000
732966 | A BLDG 5TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166441 | Providing & Laying M40 Grade Concrete. | CUM | 172.0000 | 8378.0000 | 818.001.001.001.002.002.005.002. | 7100.0000 | Labour | 0 | 219816.0000
732968 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.006.002. | 40.0000 | Labour | 0 | 7.2000
732968 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.006.002. | 60.0000 | Labour | 0 | 10.8000
732968 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.006.002. | 80.0000 | Labour | 0 | 14.4000
732968 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29.0000 | 85078.0000 | 818.001.001.001.002.002.006.002. | 72100.0000 | Labour | 0 | 376362.0000
732968 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167904 | Providing & Fixing Ply Shuttering for RCC Work | Sq.Mtr | 3550.0000 | 915.6800 | 818.001.001.001.002.002.006.002. | 776.0000 | Labour | 0 | 495864.0000
732968 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166125 | Providing & Laying M25 Grade of Concrete | CUM | 0.0000 | 0.0000 | 818.001.001.001.002.002.006.002. | 6450.0000 | Labour | 0 | 0.0000
732968 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165401 | Providing & Laying M30 Grade Concrete. | CUM | 265.0000 | 7847.0000 | 818.001.001.001.002.002.006.002. | 6650.0000 | Labour | 0 | 317205.0000
732968 | A BLDG 6TH SLAB RCC WORK CONV. (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 166441 | Providing & Laying M40 Grade Concrete. | CUM | 172.0000 | 8378.0000 | 818.001.001.001.002.002.006.002. | 7100.0000 | Labour | 0 | 219816.0000
732970 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.007.001. | 345.0000 | Labour | 0 | 235980.0000
732970 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.007.001. | 40.0000 | Labour | 0 | 7.2000
732970 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.007.001. | 60.0000 | Labour | 0 | 10.8000
732970 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.007.001. | 80.0000 | Labour | 0 | 14.4000
732970 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 32.0000 | 85078.0000 | 818.001.001.001.002.002.007.001. | 72100.0000 | Labour | 0 | 415296.0000
732970 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.007.001. | 7000.0000 | Labour | 0 | 270900.0000
732970 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 0.0000 | 0.0000 | 818.001.001.001.002.002.007.001. | 7100.0000 | Labour | 0 | 0.0000
732970 | A BLDG 7TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.007.001. | 7350.0000 | Labour | 0 | 206388.0000
732972 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.008.001. | 345.0000 | Labour | 0 | 235980.0000
732972 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.008.001. | 40.0000 | Labour | 0 | 7.2000
732972 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.008.001. | 60.0000 | Labour | 0 | 10.8000
732972 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.008.001. | 80.0000 | Labour | 0 | 14.4000
732972 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 32.0000 | 85078.0000 | 818.001.001.001.002.002.008.001. | 72100.0000 | Labour | 0 | 415296.0000
732972 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.008.001. | 7000.0000 | Labour | 0 | 270900.0000
732972 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.008.001. | 7100.0000 | Labour | 0 | 1278.0000
732972 | A BLDG 8TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.008.001. | 7350.0000 | Labour | 0 | 206388.0000
732974 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.009.001. | 345.0000 | Labour | 0 | 235980.0000
732974 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.009.001. | 40.0000 | Labour | 0 | 7.2000
732974 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.009.001. | 60.0000 | Labour | 0 | 10.8000
732974 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.009.001. | 80.0000 | Labour | 0 | 14.4000
732974 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 32.0000 | 85078.0000 | 818.001.001.001.002.002.009.001. | 72100.0000 | Labour | 0 | 415296.0000
732974 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.009.001. | 7000.0000 | Labour | 0 | 270900.0000
732974 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.009.001. | 7100.0000 | Labour | 0 | 1278.0000
732974 | A BLDG 9TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.009.001. | 7350.0000 | Labour | 0 | 206388.0000
732976 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.010.001. | 345.0000 | Labour | 0 | 235980.0000
732976 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.010.001. | 40.0000 | Labour | 0 | 7.2000
732976 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.010.001. | 60.0000 | Labour | 0 | 10.8000
732976 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.010.001. | 80.0000 | Labour | 0 | 14.4000
732976 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 32.0000 | 85078.0000 | 818.001.001.001.002.002.010.001. | 72100.0000 | Labour | 0 | 415296.0000
732976 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.010.001. | 7000.0000 | Labour | 0 | 270900.0000
732976 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.010.001. | 7100.0000 | Labour | 0 | 1278.0000
732976 | A BLDG 10TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.010.001. | 7350.0000 | Labour | 0 | 206388.0000
732978 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.011.001. | 345.0000 | Labour | 0 | 235980.0000
732978 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.011.001. | 40.0000 | Labour | 0 | 7.2000
732978 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.011.001. | 60.0000 | Labour | 0 | 10.8000
732978 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.011.001. | 80.0000 | Labour | 0 | 14.4000
732978 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 32.0000 | 85078.0000 | 818.001.001.001.002.002.011.001. | 72100.0000 | Labour | 0 | 415296.0000
732978 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.011.001. | 7000.0000 | Labour | 0 | 270900.0000
732978 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.011.001. | 7100.0000 | Labour | 0 | 1278.0000
732978 | A BLDG 11TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.011.001. | 7350.0000 | Labour | 0 | 206388.0000
732980 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.012.001. | 345.0000 | Labour | 0 | 235980.0000
732980 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.012.001. | 40.0000 | Labour | 0 | 7.2000
732980 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.012.001. | 60.0000 | Labour | 0 | 10.8000
732980 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.012.001. | 80.0000 | Labour | 0 | 14.4000
732980 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 31.0000 | 85078.0000 | 818.001.001.001.002.002.012.001. | 72100.0000 | Labour | 0 | 402318.0000
732980 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.012.001. | 7000.0000 | Labour | 0 | 270900.0000
732980 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.012.001. | 7100.0000 | Labour | 0 | 1278.0000
732980 | A BLDG 12TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.012.001. | 7350.0000 | Labour | 0 | 206388.0000
732982 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.013.001. | 345.0000 | Labour | 0 | 235980.0000
732982 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.013.001. | 40.0000 | Labour | 0 | 7.2000
732982 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.013.001. | 60.0000 | Labour | 0 | 10.8000
732982 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.013.001. | 80.0000 | Labour | 0 | 14.4000
732982 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 31.0000 | 85078.0000 | 818.001.001.001.002.002.013.001. | 72100.0000 | Labour | 0 | 402318.0000
732982 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.013.001. | 7000.0000 | Labour | 0 | 270900.0000
732982 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.013.001. | 7100.0000 | Labour | 0 | 1278.0000
732982 | A BLDG 13TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.013.001. | 7350.0000 | Labour | 0 | 206388.0000
732984 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.014.001. | 345.0000 | Labour | 0 | 235980.0000
732984 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.014.001. | 40.0000 | Labour | 0 | 7.2000
732984 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.014.001. | 60.0000 | Labour | 0 | 10.8000
732984 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.014.001. | 80.0000 | Labour | 0 | 14.4000
732984 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 31.0000 | 85078.0000 | 818.001.001.001.002.002.014.001. | 72100.0000 | Labour | 0 | 402318.0000
732984 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.014.001. | 7000.0000 | Labour | 0 | 270900.0000
732984 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.014.001. | 7100.0000 | Labour | 0 | 1278.0000
732984 | A BLDG 14TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.014.001. | 7350.0000 | Labour | 0 | 206388.0000
732986 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.015.001. | 345.0000 | Labour | 0 | 235980.0000
732986 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.015.001. | 40.0000 | Labour | 0 | 7.2000
732986 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.015.001. | 60.0000 | Labour | 0 | 10.8000
732986 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.015.001. | 80.0000 | Labour | 0 | 14.4000
732986 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 31.0000 | 85078.0000 | 818.001.001.001.002.002.015.001. | 72100.0000 | Labour | 0 | 402318.0000
732986 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.015.001. | 7000.0000 | Labour | 0 | 270900.0000
732986 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.015.001. | 7100.0000 | Labour | 0 | 1278.0000
732986 | A BLDG 15TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.015.001. | 7350.0000 | Labour | 0 | 206388.0000
732988 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.016.001. | 345.0000 | Labour | 0 | 235980.0000
732988 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.016.001. | 40.0000 | Labour | 0 | 7.2000
732988 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.016.001. | 60.0000 | Labour | 0 | 10.8000
732988 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.016.001. | 80.0000 | Labour | 0 | 14.4000
732988 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 31.0000 | 85078.0000 | 818.001.001.001.002.002.016.001. | 72100.0000 | Labour | 0 | 402318.0000
732988 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.016.001. | 7000.0000 | Labour | 0 | 270900.0000
732988 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.016.001. | 7100.0000 | Labour | 0 | 1278.0000
732988 | A BLDG 16TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.016.001. | 7350.0000 | Labour | 0 | 206388.0000
732990 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.017.001. | 345.0000 | Labour | 0 | 235980.0000
732990 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.017.001. | 40.0000 | Labour | 0 | 7.2000
732990 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.017.001. | 60.0000 | Labour | 0 | 10.8000
732990 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.017.001. | 80.0000 | Labour | 0 | 14.4000
732990 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 31.0000 | 85078.0000 | 818.001.001.001.002.002.017.001. | 72100.0000 | Labour | 0 | 402318.0000
732990 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.017.001. | 7000.0000 | Labour | 0 | 270900.0000
732990 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.017.001. | 7100.0000 | Labour | 0 | 1278.0000
732990 | A BLDG 17TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.017.001. | 7350.0000 | Labour | 0 | 206388.0000
732992 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.018.001. | 345.0000 | Labour | 0 | 235980.0000
732992 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.018.001. | 40.0000 | Labour | 0 | 7.2000
732992 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.018.001. | 60.0000 | Labour | 0 | 10.8000
732992 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.018.001. | 80.0000 | Labour | 0 | 14.4000
732992 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30.0000 | 85078.0000 | 818.001.001.001.002.002.018.001. | 72100.0000 | Labour | 0 | 389340.0000
732992 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.018.001. | 7000.0000 | Labour | 0 | 270900.0000
732992 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.018.001. | 7100.0000 | Labour | 0 | 1278.0000
732992 | A BLDG 18TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.018.001. | 7350.0000 | Labour | 0 | 206388.0000
732994 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.019.001. | 345.0000 | Labour | 0 | 235980.0000
732994 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.019.001. | 40.0000 | Labour | 0 | 7.2000
732994 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.019.001. | 60.0000 | Labour | 0 | 10.8000
732994 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.019.001. | 80.0000 | Labour | 0 | 14.4000
732994 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30.0000 | 85078.0000 | 818.001.001.001.002.002.019.001. | 72100.0000 | Labour | 0 | 389340.0000
732994 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.019.001. | 7000.0000 | Labour | 0 | 270900.0000
732994 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.019.001. | 7100.0000 | Labour | 0 | 1278.0000
732994 | A BLDG 19TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.019.001. | 7350.0000 | Labour | 0 | 206388.0000
732996 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.020.001. | 345.0000 | Labour | 0 | 235980.0000
732996 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.020.001. | 40.0000 | Labour | 0 | 7.2000
732996 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.020.001. | 60.0000 | Labour | 0 | 10.8000
732996 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.020.001. | 80.0000 | Labour | 0 | 14.4000
732996 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30.0000 | 85078.0000 | 818.001.001.001.002.002.020.001. | 72100.0000 | Labour | 0 | 389340.0000
732996 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.020.001. | 7000.0000 | Labour | 0 | 270900.0000
732996 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.020.001. | 7100.0000 | Labour | 0 | 1278.0000
732996 | A BLDG 20TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.020.001. | 7350.0000 | Labour | 0 | 206388.0000
732998 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.021.001. | 345.0000 | Labour | 0 | 235980.0000
732998 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.021.001. | 40.0000 | Labour | 0 | 7.2000
732998 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.021.001. | 60.0000 | Labour | 0 | 10.8000
732998 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.021.001. | 80.0000 | Labour | 0 | 14.4000
732998 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30.0000 | 85078.0000 | 818.001.001.001.002.002.021.001. | 72100.0000 | Labour | 0 | 389340.0000
732998 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.021.001. | 7000.0000 | Labour | 0 | 270900.0000
732998 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.021.001. | 7100.0000 | Labour | 0 | 1278.0000
732998 | A BLDG 21TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.021.001. | 7350.0000 | Labour | 0 | 206388.0000
733000 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.022.001. | 345.0000 | Labour | 0 | 235980.0000
733000 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.022.001. | 40.0000 | Labour | 0 | 7.2000
733000 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.022.001. | 60.0000 | Labour | 0 | 10.8000
733000 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.022.001. | 80.0000 | Labour | 0 | 14.4000
733000 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30.0000 | 85078.0000 | 818.001.001.001.002.002.022.001. | 72100.0000 | Labour | 0 | 389340.0000
733000 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.022.001. | 7000.0000 | Labour | 0 | 270900.0000
733000 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.022.001. | 7100.0000 | Labour | 0 | 1278.0000
733000 | A BLDG 22TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.022.001. | 7350.0000 | Labour | 0 | 206388.0000
733002 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.023.001. | 345.0000 | Labour | 0 | 235980.0000
733002 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.023.001. | 40.0000 | Labour | 0 | 7.2000
733002 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.023.001. | 60.0000 | Labour | 0 | 10.8000
733002 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.023.001. | 80.0000 | Labour | 0 | 14.4000
733002 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 30.0000 | 85078.0000 | 818.001.001.001.002.002.023.001. | 72100.0000 | Labour | 0 | 389340.0000
733002 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.023.001. | 7000.0000 | Labour | 0 | 270900.0000
733002 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.023.001. | 7100.0000 | Labour | 0 | 1278.0000
733002 | A BLDG 23TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.023.001. | 7350.0000 | Labour | 0 | 206388.0000
733004 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.024.001. | 345.0000 | Labour | 0 | 235980.0000
733004 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.024.001. | 40.0000 | Labour | 0 | 7.2000
733004 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.024.001. | 60.0000 | Labour | 0 | 10.8000
733004 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.024.001. | 80.0000 | Labour | 0 | 14.4000
733004 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29.0000 | 85078.0000 | 818.001.001.001.002.002.024.001. | 72100.0000 | Labour | 0 | 376362.0000
733004 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.024.001. | 7000.0000 | Labour | 0 | 270900.0000
733004 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.024.001. | 7100.0000 | Labour | 0 | 1278.0000
733004 | A BLDG 24TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.024.001. | 7350.0000 | Labour | 0 | 206388.0000
733006 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.025.001. | 345.0000 | Labour | 0 | 235980.0000
733006 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.025.001. | 40.0000 | Labour | 0 | 7.2000
733006 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.025.001. | 60.0000 | Labour | 0 | 10.8000
733006 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.025.001. | 80.0000 | Labour | 0 | 14.4000
733006 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29.0000 | 85078.0000 | 818.001.001.001.002.002.025.001. | 72100.0000 | Labour | 0 | 376362.0000
733006 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.025.001. | 7000.0000 | Labour | 0 | 270900.0000
733006 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.025.001. | 7100.0000 | Labour | 0 | 1278.0000
733006 | A BLDG 25TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.025.001. | 7350.0000 | Labour | 0 | 206388.0000
733008 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.026.001. | 345.0000 | Labour | 0 | 235980.0000
733008 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.026.001. | 40.0000 | Labour | 0 | 7.2000
733008 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.026.001. | 60.0000 | Labour | 0 | 10.8000
733008 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.026.001. | 80.0000 | Labour | 0 | 14.4000
733008 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29.0000 | 85078.0000 | 818.001.001.001.002.002.026.001. | 72100.0000 | Labour | 0 | 376362.0000
733008 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.026.001. | 7000.0000 | Labour | 0 | 270900.0000
733008 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.026.001. | 7100.0000 | Labour | 0 | 1278.0000
733008 | A BLDG 26TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.026.001. | 7350.0000 | Labour | 0 | 206388.0000
733010 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.027.001. | 345.0000 | Labour | 0 | 235980.0000
733010 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.027.001. | 40.0000 | Labour | 0 | 7.2000
733010 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.027.001. | 60.0000 | Labour | 0 | 10.8000
733010 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.027.001. | 80.0000 | Labour | 0 | 14.4000
733010 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29.0000 | 85078.0000 | 818.001.001.001.002.002.027.001. | 72100.0000 | Labour | 0 | 376362.0000
733010 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.027.001. | 7000.0000 | Labour | 0 | 270900.0000
733010 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.027.001. | 7100.0000 | Labour | 0 | 1278.0000
733010 | A BLDG 27TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.027.001. | 7350.0000 | Labour | 0 | 206388.0000
733012 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.028.001. | 345.0000 | Labour | 0 | 235980.0000
733012 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.028.001. | 40.0000 | Labour | 0 | 7.2000
733012 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.028.001. | 60.0000 | Labour | 0 | 10.8000
733012 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.028.001. | 80.0000 | Labour | 0 | 14.4000
733012 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29.0000 | 85078.0000 | 818.001.001.001.002.002.028.001. | 72100.0000 | Labour | 0 | 376362.0000
733012 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.028.001. | 7000.0000 | Labour | 0 | 270900.0000
733012 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.028.001. | 7100.0000 | Labour | 0 | 1278.0000
733012 | A BLDG 28TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.028.001. | 7350.0000 | Labour | 0 | 206388.0000
733014 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.029.001. | 345.0000 | Labour | 0 | 235980.0000
733014 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.029.001. | 40.0000 | Labour | 0 | 7.2000
733014 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.029.001. | 60.0000 | Labour | 0 | 10.8000
733014 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.029.001. | 80.0000 | Labour | 0 | 14.4000
733014 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 28.0000 | 85078.0000 | 818.001.001.001.002.002.029.001. | 72100.0000 | Labour | 0 | 363384.0000
733014 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.029.001. | 7000.0000 | Labour | 0 | 270900.0000
733014 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.029.001. | 7100.0000 | Labour | 0 | 1278.0000
733014 | A BLDG 29TH SLAB RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.029.001. | 7350.0000 | Labour | 0 | 206388.0000
733016 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167908 | Fixing of Aluform Shuttering for RCC Work | Sq.Mtr | 4100 | 407.1000 | 818.001.001.001.002.002.030.001. | 345.0000 | Labour | 0 | 235980.0000
733016 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167901 | M+L- 20MM Coupler | NO | 1.0000 | 47.2000 | 818.001.001.001.002.002.030.001. | 40.0000 | Labour | 0 | 7.2000
733016 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167902 | M+L- 25MM Coupler | NO | 1.0000 | 70.8000 | 818.001.001.001.002.002.030.001. | 60.0000 | Labour | 0 | 10.8000
733016 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167903 | M+L- 32MM Coupler | NO | 1.0000 | 94.4000 | 818.001.001.001.002.002.030.001. | 80.0000 | Labour | 0 | 14.4000
733016 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 165561 | M+L-Cutting , Binding, Hooking, Tieing Of Steel Fe 500 | MT | 29.0000 | 85078.0000 | 818.001.001.001.002.002.030.001. | 72100.0000 | Labour | 0 | 376362.0000
733016 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167905 | Providing & Laying FFM30 Grade Concrete | CUM | 215.0000 | 8260.0000 | 818.001.001.001.002.002.030.001. | 7000.0000 | Labour | 0 | 270900.0000
733016 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167907 | Providing & Laying FFM35 Grade Concrete | CUM | 1.0000 | 8378.0000 | 818.001.001.001.002.002.030.001. | 7100.0000 | Labour | 0 | 1278.0000
733016 | A BLDG OHWT/LMR RCC WORK MIVAN (M+L) | Sq.Mtr | 1.0000 | 1.0000 | 167906 | Providing & Laying FFM40 Grade Concrete | CUM | 156.0000 | 8673.0000 | 818.001.001.001.002.002.030.001. | 7350.0000 | Labour | 0 | 206388.0000