## Sheet1
Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO | Project :-41 COSMO
Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK | Selected Group :- B BLDG. INTERNAL PAINTING WORK
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 710026 | B BLDG. INTERNAL PAINTING WORK | Dz 12nos) | 0.0000 | 0.0000 | 0 | 710016 | 31 | 0 | [6 empty] | 0.0000
2 | 710018 | B BLDG. BASE FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
3 | 710095 | B BLDG. BASE FLOOR OBD Paint (M+L) | Sft. | 23550.0000 | 23550.0000 | 2 | 710018 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
4 | 710098 | B BLDG. BASE FLOOR Oil Paint (M+L) | Sft. | 150.0000 | 150.0000 | 2 | 710018 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
5 | 710019 | B BLDG. GROUND FL. | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
6 | 710097 | B BLDG. GROUND FL. OBD Paint (M+L) | Sft. | 12155.2500 | 12155.2500 | 5 | 710019 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
7 | 710099 | B BLDG. GROUND FL. Oil Paint (M+L) | Sft. | 150.0000 | 150.0000 | 5 | 710019 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
8 | 710103 | B BLDG. GROUND FL. Texture for Column (M+L) | Sft. | 9701.1625 | 9701.1625 | 5 | 710019 | 4 | 92736 | Texture for Column (M+L) | [5 empty] | 0.0000
9 | 710020 | B BLDG. PODIUM FL. | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
10 | 710096 | B BLDG. PODIUM FL. OBD Paint (M+L) | Sft. | 14560.7500 | 14560.7500 | 9 | 710020 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
11 | 710100 | B BLDG. PODIUM FL. Oil Paint (M+L) | Sft. | 2000.0000 | 2000.0000 | 9 | 710020 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
12 | 710102 | B BLDG. PODIUM FL. Texture for Column (M+L) | Sft. | 8726.2250 | 8726.2250 | 9 | 710020 | 4 | 92736 | Texture for Column (M+L) | [5 empty] | 0.0000
13 | 710021 | B BLDG. 1ST FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
14 | 710023 | B BLDG. 1ST FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 13 | 710021 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
15 | 710024 | B BLDG. 1ST FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 13 | 710021 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
16 | 710025 | B BLDG. 1ST FLOOR Oil Paint (M+L) | Sft. | 2500.0000 | 2500.0000 | 13 | 710021 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
17 | 710027 | B BLDG. 2ND FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
18 | 710028 | B BLDG. 2ND FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 17 | 710027 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
19 | 710029 | B BLDG. 2ND FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 17 | 710027 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
20 | 710030 | B BLDG. 2ND FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 17 | 710027 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
21 | 710031 | B BLDG. 3RD FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
22 | 710032 | B BLDG. 3RD FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 21 | 710031 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
23 | 710033 | B BLDG. 3RD FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 21 | 710031 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
24 | 710034 | B BLDG. 3RD FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 21 | 710031 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
25 | 710035 | B BLDG. 4TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
26 | 710036 | B BLDG. 4TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 25 | 710035 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
27 | 710037 | B BLDG. 4TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 25 | 710035 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
28 | 710038 | B BLDG. 4TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 25 | 710035 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
29 | 710039 | B BLDG. 5TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
30 | 710040 | B BLDG. 5TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 29 | 710039 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
31 | 710041 | B BLDG. 5TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 29 | 710039 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
32 | 710042 | B BLDG. 5TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 29 | 710039 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
33 | 710043 | B BLDG. 6TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
34 | 710044 | B BLDG. 6TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 33 | 710043 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
35 | 710045 | B BLDG. 6TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 33 | 710043 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
36 | 710046 | B BLDG. 6TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 33 | 710043 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
37 | 710047 | B BLDG. 7TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
38 | 710048 | B BLDG. 7TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 37 | 710047 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
39 | 710049 | B BLDG. 7TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 37 | 710047 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
40 | 710050 | B BLDG. 7TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 37 | 710047 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
41 | 710051 | B BLDG. 8TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
42 | 710052 | B BLDG. 8TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 41 | 710051 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
43 | 710053 | B BLDG. 8TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 41 | 710051 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
44 | 710054 | B BLDG. 8TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 41 | 710051 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
45 | 710055 | B BLDG. 9TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
46 | 710056 | B BLDG. 9TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 45 | 710055 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
47 | 710057 | B BLDG. 9TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 45 | 710055 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
48 | 710058 | B BLDG. 9TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 45 | 710055 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
49 | 710059 | B BLDG. 10TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
50 | 710060 | B BLDG. 10TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 49 | 710059 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
51 | 710061 | B BLDG. 10TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 49 | 710059 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
52 | 710062 | B BLDG. 10TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 49 | 710059 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
53 | 710063 | B BLDG. 11TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
54 | 710064 | B BLDG. 11TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 53 | 710063 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
55 | 710065 | B BLDG. 11TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 53 | 710063 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
56 | 710066 | B BLDG. 11TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 53 | 710063 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
57 | 710067 | B BLDG. 12TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
58 | 710068 | B BLDG. 12TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 57 | 710067 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
59 | 710069 | B BLDG. 12TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 57 | 710067 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
60 | 710070 | B BLDG. 12TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 57 | 710067 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
61 | 710071 | B BLDG. 13TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
62 | 710072 | B BLDG. 13TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 61 | 710071 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
63 | 710073 | B BLDG. 13TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 61 | 710071 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
64 | 710074 | B BLDG. 13TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 61 | 710071 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
65 | 710075 | B BLDG. 14TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
66 | 710076 | B BLDG. 14TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 65 | 710075 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
67 | 710077 | B BLDG. 14TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 65 | 710075 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
68 | 710078 | B BLDG. 14TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 65 | 710075 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
69 | 710079 | B BLDG. 15TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
70 | 710080 | B BLDG. 15TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 69 | 710079 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
71 | 710081 | B BLDG. 15TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 69 | 710079 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
72 | 710082 | B BLDG. 15TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 69 | 710079 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
73 | 710083 | B BLDG. 16TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
74 | 710084 | B BLDG. 16TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 73 | 710083 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
75 | 710085 | B BLDG. 16TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 73 | 710083 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
76 | 710086 | B BLDG. 16TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 73 | 710083 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
77 | 710087 | B BLDG. 17TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
78 | 710088 | B BLDG. 17TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 77 | 710087 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
79 | 710089 | B BLDG. 17TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 77 | 710087 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
80 | 710090 | B BLDG. 17TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 77 | 710087 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
81 | 710091 | B BLDG. 18TH FLOOR | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
82 | 710092 | B BLDG. 18TH FLOOR EMULSION PAINT (M+L) | Sq.ft | 9337.3305 | 9337.3305 | 81 | 710091 | 4 | 55675 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
83 | 710093 | B BLDG. 18TH FLOOR OBD Paint (M+L) | Sft. | 2453.57 | 2453.57 | 81 | 710091 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
84 | 710094 | B BLDG. 18TH FLOOR Oil Paint (M+L) | Sft. | 983.6788 | 983.6788 | 81 | 710091 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
85 | 710135 | B BLDG. TERRACE FL. | Dz 12nos) | 0.0000 | 0.0000 | 1 | 710026 | 31 | 0 | [6 empty] | 0.0000
86 | 710136 | B BLDG. TERRACE FL. OBD Paint (M+L) | Sft. | 1777.5278 | 1777.5278 | 85 | 710135 | 4 | 38583 | OBD Paint (M+L) | [5 empty] | 0.0000
87 | 710137 | B BLDG. TERRACE FL. Oil Paint (M+L) | Sft. | 100.0000 | 100.0000 | 85 | 710135 | 4 | 38584 | Oil Paint (M+L) | [5 empty] | 0.0000
88 | 710147 | B BLDG. INTERNAL PAINTING WORK LIFT WHITE WASH | Sft. | 10563.2514 | 10563.2514 | 1 | 710026 | 4 | 55875 | LIFT WHITE WASH | [5 empty] | 0.0000