## Sheet1
Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT
Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L) | Selected Group :- F BLDG. PAINTING (M+L)
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 702723 | F BLDG. PAINTING (M+L) | Dz 12nos) | 0.0000 | 0.0000 | 0 | 701943 | 31 | 0 | [6 empty] | 102632.6400
2 | 725270 | F BLDG INTERNAL | Dz 12nos) | 0.0000 | 0.0000 | 1 | 702723 | 31 | 0 | [6 empty] | 0.0000
3 | 725271 | F BLDG 1ST FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
4 | 725272 | F BLDG 1ST FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 3 | 725271 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
5 | 725273 | F BLDG 1ST FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 3 | 725271 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
6 | 725274 | F BLDG 1ST FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 3 | 725271 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
7 | 732253 | F BLDG 1ST FL. FLAT OBD PAINT (M+L) | Sq.ft | 2651.0000 | 2651.0000 | 3 | 725271 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
8 | 725275 | F BLDG 2ND FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
9 | 725276 | F BLDG 2ND FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 8 | 725275 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
10 | 725277 | F BLDG 2ND FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 8 | 725275 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
11 | 725278 | F BLDG 2ND FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 8 | 725275 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
12 | 725279 | F BLDG 3RD FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
13 | 725280 | F BLDG 3RD FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 12 | 725279 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
14 | 725281 | F BLDG 3RD FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 12 | 725279 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
15 | 725282 | F BLDG 3RD FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 12 | 725279 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
16 | 725283 | F BLDG 4TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
17 | 725284 | F BLDG 4TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 16 | 725283 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
18 | 725285 | F BLDG 4TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 16 | 725283 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
19 | 725286 | F BLDG 4TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 16 | 725283 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
20 | 725287 | F BLDG 5TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
21 | 725288 | F BLDG 5TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 20 | 725287 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
22 | 725289 | F BLDG 5TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 20 | 725287 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
23 | 725290 | F BLDG 5TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 20 | 725287 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
24 | 725291 | F BLDG 6TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
25 | 725292 | F BLDG 6TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 24 | 725291 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
26 | 725293 | F BLDG 6TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 24 | 725291 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
27 | 725294 | F BLDG 6TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 24 | 725291 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
28 | 725295 | F BLDG 7TH REF. FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
29 | 725296 | F BLDG 7TH REF. FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 28 | 725295 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
30 | 725297 | F BLDG 7TH REF. FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 28 | 725295 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
31 | 725298 | F BLDG 7TH REF. FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 28 | 725295 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
32 | 725299 | F BLDG 8TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
33 | 725300 | F BLDG 8TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 32 | 725299 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
34 | 725301 | F BLDG 8TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 32 | 725299 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
35 | 725302 | F BLDG 8TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 32 | 725299 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
36 | 725303 | F BLDG 9TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
37 | 725304 | F BLDG 9TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 36 | 725303 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
38 | 725305 | F BLDG 9TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 36 | 725303 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
39 | 725306 | F BLDG 9TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 36 | 725303 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
40 | 725311 | F BLDG 10TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
41 | 725312 | F BLDG 10TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 40 | 725311 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
42 | 725313 | F BLDG 10TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 40 | 725311 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
43 | 725314 | F BLDG 10TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 40 | 725311 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
44 | 725307 | F BLDG 11TH REF. FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
45 | 725308 | F BLDG 11TH REF. FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 44 | 725307 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
46 | 725309 | F BLDG 11TH REF. FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 44 | 725307 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
47 | 725310 | F BLDG 11TH REF. FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 44 | 725307 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
48 | 725315 | F BLDG 12TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
49 | 725316 | F BLDG 12TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 48 | 725315 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
50 | 725317 | F BLDG 12TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 48 | 725315 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
51 | 725318 | F BLDG 12TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 48 | 725315 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
52 | 725319 | F BLDG 13TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
53 | 725320 | F BLDG 13TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 52 | 725319 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
54 | 725321 | F BLDG 13TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 52 | 725319 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
55 | 725322 | F BLDG 13TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 52 | 725319 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
56 | 725323 | F BLDG 14TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
57 | 725324 | F BLDG 14TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 56 | 725323 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
58 | 725325 | F BLDG 14TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 56 | 725323 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
59 | 725326 | F BLDG 14TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 56 | 725323 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
60 | 725327 | F BLDG 15TH REF. FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
61 | 725328 | F BLDG 15TH REF. FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 60 | 725327 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
62 | 725329 | F BLDG 15TH REF. FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 60 | 725327 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
63 | 725330 | F BLDG 15TH REF. FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 60 | 725327 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
64 | 725331 | F BLDG 16TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 2 | 725270 | 31 | 0 | [6 empty] | 0.0000
65 | 725332 | F BLDG 16TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 7970.0000 | 7970.0000 | 64 | 725331 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
66 | 725333 | F BLDG 16TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 864.6000 | 864.6000 | 64 | 725331 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
67 | 725334 | F BLDG 16TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 2906.7100 | 2906.7100 | 64 | 725331 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
68 | 725400 | F BLDG EXTERNAL | Dz 12nos) | 0.0000 | 0.0000 | 1 | 702723 | 31 | 0 | [6 empty] | 0.0000
69 | 725401 | F BLDG EXT. WALL | Dz 12nos) | 0.0000 | 0.0000 | 68 | 725400 | 31 | 0 | [6 empty] | 0.0000
70 | 725406 | F BLDG EXT. WALL 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 95107.8106 | 95107.8106 | 69 | 725401 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
71 | 725402 | F BLDG EXT. DUCT | Dz 12nos) | 0.0000 | 0.0000 | 68 | 725400 | 31 | 0 | [6 empty] | 0.0000
72 | 725405 | F BLDG EXT. DUCT ACRYALIC PAINT (M+L) | Sq.ft | 35000.0000 | 35000.0000 | 71 | 725402 | 4 | 93884 | ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
73 | 725403 | F BLDG SERVICE DUCT | Dz 12nos) | 0.0000 | 0.0000 | 68 | 725400 | 31 | 0 | [6 empty] | 0.0000
74 | 725404 | F BLDG SERVICE DUCT WHITE WASH PAINT (M+L) | Sq.ft | 12406.0000 | 12406.0000 | 73 | 725403 | 4 | 93885 | WHITE WASH PAINT (M+L) | [5 empty] | 0.0000
75 | 725414 | F BLDG PARKING FL. | Dz 12nos) | 0.0000 | 0.0000 | 1 | 702723 | 31 | 0 | [6 empty] | 0.0000
76 | 725422 | F BLDG BASE FL. | Dz 12nos) | 0.0000 | 0.0000 | 75 | 725414 | 31 | 0 | [6 empty] | 0.0000
77 | 725419 | F BLDG BASE FL. 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 1.0000 | 1.0000 | 76 | 725422 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
78 | 725420 | F BLDG BASE FL. OBD PAINT (M+L) | Sq.ft | 22672.0000 | 22672.0000 | 76 | 725422 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
79 | 725421 | F BLDG BASE FL. COURCE PUTTY (M+L) | Sq.ft | 22672.0000 | 22672.0000 | 76 | 725422 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
80 | 725426 | F BLDG GR. FL. | Dz 12nos) | 0.0000 | 0.0000 | 75 | 725414 | 31 | 0 | [6 empty] | 0.0000
81 | 725423 | F BLDG GR. FL. 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 15112.6560 | 15112.6560 | 80 | 725426 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
82 | 725424 | F BLDG GR. FL. OBD PAINT (M+L) | Sq.ft | 9923.0000 | 9923.0000 | 80 | 725426 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
83 | 725425 | F BLDG GR. FL. COURCE PUTTY (M+L) | Sq.ft | 9923.0000 | 9923.0000 | 80 | 725426 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
84 | 725418 | F BLDG PODIUM FL. | Dz 12nos) | 0.0000 | 0.0000 | 75 | 725414 | 31 | 0 | [6 empty] | 0.0000
85 | 725415 | F BLDG PODIUM FL. 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | Sq.ft | 0.0000 | 0.0000 | 84 | 725418 | 4 | 93880 | 2MM TEXTURE WITH ACRYALIC PAINT (M+L) | [5 empty] | 0.0000
86 | 725416 | F BLDG PODIUM FL. OBD PAINT (M+L) | Sq.ft | 15038.0000 | 15038.0000 | 84 | 725418 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
87 | 725417 | F BLDG PODIUM FL. COURCE PUTTY (M+L) | Sq.ft | 15038.0000 | 15038.0000 | 84 | 725418 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
88 | 725440 | F BLDG STAIRE | Dz 12nos) | 0.0000 | 0.0000 | 1 | 702723 | 31 | 0 | [6 empty] | 0.0000
89 | 725441 | F BLDG STAIRE OBD PAINT (M+L) | Sq.ft | 29698.0000 | 29698.0000 | 88 | 725440 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
90 | 732254 | F BLDG STAIRE COURCE PUTTY (M+L) | Sq.ft | 29698.0000 | 29698.0000 | 88 | 725440 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
91 | 725444 | F BLDG LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 702723 | 31 | 0 | [6 empty] | 0.0000
92 | 725445 | F BLDG 1ST FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
93 | 725446 | F BLDG 1ST FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 92 | 725445 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
94 | 725447 | F BLDG 1ST FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 92 | 725445 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
95 | 725448 | F BLDG 1ST FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
96 | 725449 | F BLDG 1ST FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 95 | 725448 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
97 | 725450 | F BLDG 1ST FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 95 | 725448 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
98 | 725451 | F BLDG 1ST FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
99 | 725452 | F BLDG 1ST FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 98 | 725451 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
100 | 725453 | F BLDG 1ST FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 98 | 725451 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
101 | 725454 | F BLDG 4TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
102 | 725455 | F BLDG 4TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 101 | 725454 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
103 | 725456 | F BLDG 4TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 101 | 725454 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
104 | 725457 | F BLDG 5TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
105 | 725458 | F BLDG 5TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 104 | 725457 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
106 | 725459 | F BLDG 5TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 104 | 725457 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
107 | 725460 | F BLDG 6TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
108 | 725461 | F BLDG 6TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 107 | 725460 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
109 | 725462 | F BLDG 6TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 107 | 725460 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
110 | 725463 | F BLDG 7TH REF. FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
111 | 725464 | F BLDG 7TH REF. FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 110 | 725463 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
112 | 725465 | F BLDG 7TH REF. FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 110 | 725463 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
113 | 725466 | F BLDG 8TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
114 | 725467 | F BLDG 8TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 113 | 725466 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
115 | 725468 | F BLDG 8TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 113 | 725466 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
116 | 725469 | F BLDG 9TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
117 | 725470 | F BLDG 9TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 116 | 725469 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
118 | 725471 | F BLDG 9TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 116 | 725469 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
119 | 725472 | F BLDG 10TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
120 | 725473 | F BLDG 10TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 119 | 725472 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
121 | 725474 | F BLDG 10TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 119 | 725472 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
122 | 725475 | F BLDG 11TH REFF. FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
123 | 725476 | F BLDG 11TH REFF. FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 122 | 725475 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
124 | 725477 | F BLDG 11TH REFF. FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 122 | 725475 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
125 | 725478 | F BLDG 12TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
126 | 725479 | F BLDG 12TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 125 | 725478 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
127 | 725480 | F BLDG 12TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 125 | 725478 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
128 | 725481 | F BLDG 13TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
129 | 725482 | F BLDG 13TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 128 | 725481 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
130 | 725483 | F BLDG 13TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 128 | 725481 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
131 | 725484 | F BLDG 14TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
132 | 725485 | F BLDG 14TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 131 | 725484 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
133 | 725486 | F BLDG 14TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 131 | 725484 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
134 | 725487 | F BLDG 15TH REFF. FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
135 | 725488 | F BLDG 15TH REFF. FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 134 | 725487 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
136 | 725489 | F BLDG 15TH REFF. FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 134 | 725487 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
137 | 725490 | F BLDG 16TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 91 | 725444 | 31 | 0 | [6 empty] | 0.0000
138 | 725491 | F BLDG 16TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 137 | 725490 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
139 | 725492 | F BLDG 16TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 2641.0000 | 2641.0000 | 137 | 725490 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000