## Sheet1
Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT
Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL | Selected Group :- E BLDG INTERNAL
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 725124 | E BLDG INTERNAL | Dz 12nos) | 0.0000 | 0.0000 | 0 | 702706 | 31 | 0 | [6 empty] | 0.0000
2 | 725138 | E BLDG 1ST FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
3 | 725139 | E BLDG 1ST FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 2 | 725138 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
4 | 725145 | E BLDG 1ST FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 2 | 725138 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
5 | 725147 | E BLDG 1ST FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 2 | 725138 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
6 | 725210 | E BLDG 2ND FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
7 | 725211 | E BLDG 2ND FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 6 | 725210 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
8 | 725212 | E BLDG 2ND FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 6 | 725210 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
9 | 725213 | E BLDG 2ND FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 6 | 725210 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
10 | 725214 | E BLDG 3RD FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
11 | 725215 | E BLDG 3RD FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 10 | 725214 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
12 | 725216 | E BLDG 3RD FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 10 | 725214 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
13 | 725217 | E BLDG 3RD FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 10 | 725214 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
14 | 725218 | E BLDG 4TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
15 | 725219 | E BLDG 4TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 14 | 725218 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
16 | 725220 | E BLDG 4TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 14 | 725218 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
17 | 725221 | E BLDG 4TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 14 | 725218 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
18 | 725222 | E BLDG 5TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
19 | 725223 | E BLDG 5TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 18 | 725222 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
20 | 725224 | E BLDG 5TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 18 | 725222 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
21 | 725225 | E BLDG 5TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 18 | 725222 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
22 | 725226 | E BLDG 6TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
23 | 725227 | E BLDG 6TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 22 | 725226 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
24 | 725228 | E BLDG 6TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 22 | 725226 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
25 | 725229 | E BLDG 6TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 22 | 725226 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
26 | 725230 | E BLDG 7TH REF. FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
27 | 725231 | E BLDG 7TH REF. FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 26 | 725230 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
28 | 725232 | E BLDG 7TH REF. FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 26 | 725230 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
29 | 725233 | E BLDG 7TH REF. FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 26 | 725230 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
30 | 725234 | E BLDG 8TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
31 | 725235 | E BLDG 8TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 30 | 725234 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
32 | 725236 | E BLDG 8TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 30 | 725234 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
33 | 725237 | E BLDG 8TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 30 | 725234 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
34 | 725238 | E BLDG 9TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
35 | 725239 | E BLDG 9TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 34 | 725238 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
36 | 725240 | E BLDG 9TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 34 | 725238 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
37 | 725241 | E BLDG 9TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 34 | 725238 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
38 | 725246 | E BLDG 10TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
39 | 725247 | E BLDG 10TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 38 | 725246 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
40 | 725248 | E BLDG 10TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 38 | 725246 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
41 | 725249 | E BLDG 10TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 38 | 725246 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
42 | 725242 | E BLDG 11TH REF. FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
43 | 725243 | E BLDG 11TH REF. FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 42 | 725242 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
44 | 725244 | E BLDG 11TH REF. FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 42 | 725242 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
45 | 725245 | E BLDG 11TH REF. FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 42 | 725242 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
46 | 725250 | E BLDG 12TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
47 | 725251 | E BLDG 12TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 46 | 725250 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
48 | 725252 | E BLDG 12TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 46 | 725250 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
49 | 725253 | E BLDG 12TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 46 | 725250 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
50 | 725254 | E BLDG 13TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
51 | 725255 | E BLDG 13TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 50 | 725254 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
52 | 725256 | E BLDG 13TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 50 | 725254 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
53 | 725257 | E BLDG 13TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 50 | 725254 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
54 | 725258 | E BLDG 14TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
55 | 725259 | E BLDG 14TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 54 | 725258 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
56 | 725260 | E BLDG 14TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 54 | 725258 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
57 | 725261 | E BLDG 14TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 54 | 725258 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
58 | 725262 | E BLDG 15TH REF. FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
59 | 725263 | E BLDG 15TH REF. FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 58 | 725262 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
60 | 725264 | E BLDG 15TH REF. FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 58 | 725262 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
61 | 725265 | E BLDG 15TH REF. FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 58 | 725262 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
62 | 725266 | E BLDG 16TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725124 | 31 | 0 | [6 empty] | 0.0000
63 | 725267 | E BLDG 16TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 19856.1054 | 19856.1054 | 62 | 725266 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
64 | 725268 | E BLDG 16TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1879.3559 | 1879.3559 | 62 | 725266 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
65 | 725269 | E BLDG 16TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 8870.0000 | 8870.0000 | 62 | 725266 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000