## Sheet1
Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT
Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL | Selected Group :- G BLDG INTERNAL
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 725335 | G BLDG INTERNAL | Dz 12nos) | 0.0000 | 0.0000 | 0 | 702740 | 31 | 0 | [6 empty] | 0.0000
2 | 725336 | G BLDG 1ST FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
3 | 725337 | G BLDG 1ST FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 2 | 725336 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
4 | 725338 | G BLDG 1ST FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 2 | 725336 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
5 | 725339 | G BLDG 1ST FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 2 | 725336 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
6 | 738806 | G BLDG 1ST FL. FLAT OBD PAINT (M+L) | Sq.ft | 6983.0000 | 6983.0000 | 2 | 725336 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
7 | 725340 | G BLDG 2ND FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
8 | 725341 | G BLDG 2ND FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 7 | 725340 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
9 | 725342 | G BLDG 2ND FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 7 | 725340 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
10 | 725343 | G BLDG 2ND FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 7 | 725340 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
11 | 725344 | G BLDG 3RD FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
12 | 725345 | G BLDG 3RD FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 11 | 725344 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
13 | 725346 | G BLDG 3RD FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 11 | 725344 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
14 | 725347 | G BLDG 3RD FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 11 | 725344 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
15 | 725348 | G BLDG 4TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
16 | 725349 | G BLDG 4TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 15 | 725348 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
17 | 725350 | G BLDG 4TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 15 | 725348 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
18 | 725351 | G BLDG 4TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 15 | 725348 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
19 | 725352 | G BLDG 5TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
20 | 725353 | G BLDG 5TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 19 | 725352 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
21 | 725354 | G BLDG 5TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 19 | 725352 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
22 | 725355 | G BLDG 5TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 19 | 725352 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
23 | 725356 | G BLDG 6TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
24 | 725357 | G BLDG 6TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 23 | 725356 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
25 | 725358 | G BLDG 6TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 23 | 725356 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
26 | 725359 | G BLDG 6TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 23 | 725356 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
27 | 725360 | G BLDG 7TH REF. FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
28 | 725361 | G BLDG 7TH REF. FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 27 | 725360 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
29 | 725362 | G BLDG 7TH REF. FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 27 | 725360 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
30 | 725363 | G BLDG 7TH REF. FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 27 | 725360 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
31 | 725364 | G BLDG 8TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
32 | 725365 | G BLDG 8TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 31 | 725364 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
33 | 725366 | G BLDG 8TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 31 | 725364 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
34 | 725367 | G BLDG 8TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 31 | 725364 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
35 | 725368 | G BLDG 9TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
36 | 725369 | G BLDG 9TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 35 | 725368 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
37 | 725370 | G BLDG 9TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 35 | 725368 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
38 | 725371 | G BLDG 9TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 35 | 725368 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
39 | 725376 | G BLDG 10TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
40 | 725377 | G BLDG 10TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 39 | 725376 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
41 | 725378 | G BLDG 10TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 39 | 725376 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
42 | 725379 | G BLDG 10TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 39 | 725376 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
43 | 725372 | G BLDG 11TH REF. FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
44 | 725373 | G BLDG 11TH REF. FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 43 | 725372 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
45 | 725374 | G BLDG 11TH REF. FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 43 | 725372 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
46 | 725375 | G BLDG 11TH REF. FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 43 | 725372 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
47 | 725380 | G BLDG 12TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
48 | 725381 | G BLDG 12TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 47 | 725380 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
49 | 725382 | G BLDG 12TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 47 | 725380 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
50 | 725383 | G BLDG 12TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 47 | 725380 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
51 | 725384 | G BLDG 13TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
52 | 725385 | G BLDG 13TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 51 | 725384 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
53 | 725386 | G BLDG 13TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 51 | 725384 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
54 | 725387 | G BLDG 13TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 51 | 725384 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
55 | 725388 | G BLDG 14TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
56 | 725389 | G BLDG 14TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 55 | 725388 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
57 | 725390 | G BLDG 14TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 55 | 725388 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
58 | 725391 | G BLDG 14TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 55 | 725388 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
59 | 725392 | G BLDG 15TH REF. FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
60 | 725393 | G BLDG 15TH REF. FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 59 | 725392 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
61 | 725394 | G BLDG 15TH REF. FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 59 | 725392 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
62 | 725395 | G BLDG 15TH REF. FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 59 | 725392 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
63 | 725396 | G BLDG 16TH FL. FLAT | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725335 | 31 | 0 | [6 empty] | 0.0000
64 | 725397 | G BLDG 16TH FL. FLAT EMULSION PAINT (M+L) | Sq.ft | 20390.3042 | 20390.3042 | 63 | 725396 | 4 | 93881 | EMULSION PAINT (M+L) | [5 empty] | 0.0000
65 | 725398 | G BLDG 16TH FL. FLAT ENAMEL OIL PAINT (M+L) | Sq.ft | 1342.0000 | 1342.0000 | 63 | 725396 | 4 | 93883 | ENAMEL OIL PAINT (M+L) | [5 empty] | 0.0000
66 | 725399 | G BLDG 16TH FL. FLAT COURCE PUTTY (M+L) | Sq.ft | 1231 | 1231 | 63 | 725396 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000