## Sheet1
Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT
Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY | Selected Group :- G BLDG LOBBY
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 725493 | G BLDG LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 0 | 702740 | 31 | 0 | [6 empty] | 0.0000
2 | 725494 | G BLDG 1ST FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
3 | 725495 | G BLDG 1ST FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 2 | 725494 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
4 | 725496 | G BLDG 1ST FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 2 | 725494 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
5 | 725497 | G BLDG 1ST FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
6 | 725498 | G BLDG 1ST FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 5 | 725497 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
7 | 725499 | G BLDG 1ST FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 5 | 725497 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
8 | 725500 | G BLDG 1ST FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
9 | 725501 | G BLDG 1ST FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 8 | 725500 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
10 | 725502 | G BLDG 1ST FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 8 | 725500 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
11 | 725503 | G BLDG 4TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
12 | 725504 | G BLDG 4TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 11 | 725503 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
13 | 725505 | G BLDG 4TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 11 | 725503 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
14 | 725506 | G BLDG 5TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
15 | 725507 | G BLDG 5TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 14 | 725506 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
16 | 725508 | G BLDG 5TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 14 | 725506 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
17 | 725509 | G BLDG 6TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
18 | 725510 | G BLDG 6TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 17 | 725509 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
19 | 725511 | G BLDG 6TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 17 | 725509 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
20 | 725512 | G BLDG 7TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
21 | 725513 | G BLDG 7TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 20 | 725512 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
22 | 725514 | G BLDG 7TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 20 | 725512 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
23 | 725515 | G BLDG 8TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
24 | 725516 | G BLDG 8TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 23 | 725515 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
25 | 725517 | G BLDG 8TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 23 | 725515 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
26 | 725518 | G BLDG 9TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
27 | 725519 | G BLDG 9TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 26 | 725518 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
28 | 725520 | G BLDG 9TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 26 | 725518 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
29 | 725521 | G BLDG 10TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
30 | 725522 | G BLDG 10TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 29 | 725521 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
31 | 725523 | G BLDG 10TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 29 | 725521 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
32 | 725524 | G BLDG 11TH REFF. FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
33 | 725525 | G BLDG 11TH REFF. FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 32 | 725524 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
34 | 725526 | G BLDG 11TH REFF. FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 32 | 725524 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
35 | 725527 | G BLDG 12TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
36 | 725528 | G BLDG 12TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 35 | 725527 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
37 | 725529 | G BLDG 12TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 35 | 725527 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
38 | 725530 | G BLDG 13TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
39 | 725531 | G BLDG 13TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 38 | 725530 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
40 | 725532 | G BLDG 13TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 38 | 725530 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
41 | 725533 | G BLDG 14TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
42 | 725534 | G BLDG 14TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 41 | 725533 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
43 | 725535 | G BLDG 14TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 41 | 725533 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
44 | 725536 | G BLDG 15TH REFF. FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
45 | 725537 | G BLDG 15TH REFF. FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 44 | 725536 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
46 | 725538 | G BLDG 15TH REFF. FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 44 | 725536 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
47 | 725539 | G BLDG 16TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725493 | 31 | 0 | [6 empty] | 0.0000
48 | 725540 | G BLDG 16TH FL. LOBBY OBD PAINT (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 47 | 725539 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
49 | 725541 | G BLDG 16TH FL. LOBBY COURCE PUTTY (M+L) | Sq.ft | 5045.0000 | 5045.0000 | 47 | 725539 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000