## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : EVITA KRISALA TOWNSHIP COMMON
Task Name : TEMP. PLUMBING
Page 1 of 1
Total Records: 20 Records 1 to 20
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Name | Task_QTY | Task_QTY_UNIT
1 | 00 ELECTRICAL | (M)2.5 sqmm 3 core copper flex. cable | MTR | 100 | 151.04 | 15104 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 15104 | 15104 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
2 | 00 PLUMBING | (M)1" PIPE CONNECTOR | NO | 32 | 41.3 | 1321.6 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 1321.6 | 1321.6 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
3 | 00 PLUMBING | (M)1" UPVC ELBOW | NOS | 12 | 1.18 | 14.16 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 14.16 | 14.16 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
4 | 00 PLUMBING | (M)1" UPVC TANK NIPPLE | NOS | 3 | 1.18 | 3.54 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3.54 | 3.54 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
5 | 00 PLUMBING | (M)10 HP Diesel Pump | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
6 | 00 PLUMBING | (M)3HP BOREWELL SUBMERCIBLE PUMP | SET | 3 | 23600 | 70800 | 3 | 3 | 57337.38 | 172012.14 | 0 | 0 | 0 | 0 | 0 | 3 | -101212.14 | 70800 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
7 | 00 PLUMBING | (M)5HP BOREWELL SUBMERCIBLE PUMP | SET | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
8 | 00 PLUMBING | (M)7.5 HP Diesel Pump | NO | 1 | 1.18 | 1.18 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
9 | 00 PLUMBING | (M)7.5HP OPENWELL SUBMERCIBLE PUMP | SET | 1 | 35400 | 35400 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 35400 | 35400 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
10 | 00 PLUMBING | (M)CURING PIPE | BUNDLE | 14 | 62.66 | 877.24 | 14 | 14 | 1437.66 | 20127.2 | 14 | 14 | 1357 | 18998 | 0 | 0 | -19249.96 | -18120.76 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
11 | 00 PLUMBING | (M)SINTEX TANK - 5000 LIT | NO | 2 | 5310 | 10620 | 2 | 2 | 25235 | 50470 | 1 | 1 | 25370 | 25370 | 0 | 1 | -39850 | -14750 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
12 | 00 PUMP | (M)16MM NYLON ROAP | KG | 90 | 218.3 | 19647 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 19647 | 19647 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
13 | 00 SANITARY | (M)SINTEX TANK (DOUBLE LAYER) | LTR | 10000 | 5.9 | 59000 | 5000 | 5000 | 5.31 | 26570 | 5000 | 5000 | 5.07 | 25350 | 5000 | 5000 | 32430 | 33650 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
14 | Marketing Material | (M)1.5 HP Single Phase Pump | Nos | 1 | 16900 | 16900 | 1 | 1 | 45247.1 | 45247.1 | 1 | 0 | 0 | 0 | 0 | 1 | -28347.1 | 16900 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
15 | Plumbing & Sanitary old | (M)1" UPVC PIPE | NOS | 20 | 1.18 | 23.6 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 23.6 | 23.6 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
16 | PUMP | (M)3 PHASE STARTER | NOS | 1 | 1.18 | 1.18 | 1 | 1 | 3634.4 | 3634.4 | 0 | 0 | 0 | 0 | 0 | 1 | -3633.22 | 1.18 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
17 | No category | (L)6" Dia Borewell Drilling In Soil, Murum & Hard Rock | Rft | 750 | 91.2 | 68400 | 0 | 300 | 75 | 22500 | 300 | 300 | 75 | 22500 | 450 | 450 | 45900 | 45900 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
18 | No category | (L)Providing & Fixing 7" Dia. Casing Pipe | Rft | 20 | 403 | 8060 | 0 | 20 | 340 | 6800 | 20 | 20 | 340 | 6800 | 0 | 0 | 1260 | 1260 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
19 | RAIN WATER HARVESTING | (L)FLUSHING | NO | 1 | 1062 | 1062 | 0 | 1 | 1000 | 1000 | 1 | 1 | 1000 | 1000 | 0 | 0 | 62 | 62 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250
20 | RAIN WATER HARVESTING | (L)STAP RATE | Rft | 105 | 94.4 | 9912 | 0 | 105 | 85 | 8925 | 105 | 105 | 85 | 8925 | 0 | 0 | 987 | 987 | TEMP. PLUMBING BOREWELL DRILLING 6" DIA | 250