## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : EVITA KRISALA TOWNSHIP COMMON
Task Name : RETAINING WALL
Page 1 of 1
Total Records: 11 Records 1 to 11
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Name | Task_QTY | Task_QTY_UNIT
1 | STEEL | (M)STEEL 10MM TMT FE 500 | KG | 33110 | 63.72 | 2109769.2 | 33110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33110 | 33110 | 2109769.2 | 2109769.2 | RETAINING WALL | 1
2 | STEEL | (M)STEEL 12MM TMT FE 500 | KG | 10620 | 63.72 | 676706.4 | 10620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10620 | 10620 | 676706.4 | 676706.4 | RETAINING WALL | 1
3 | EARTHWORK | (L)Excavation in Soft Soil soil & Murum | CUM | 653 | 106.2 | 69348.6 | 0 | 653 | 106.2 | 69348.6 | 0 | 0 | 0 | 0 | 0 | 653 | 0 | 69348.6 | RETAINING WALL | 1
4 | FILLING | (L)Backfilling work with Hard murum, compactor & water | Cu.Mtrs | 327 | 140 | 45780 | 0 | 327 | 147.5 | 48232.5 | 0 | 0 | 0 | 0 | 0 | 327 | -2452.5 | 45780 | RETAINING WALL | 1
5 | RCC WORK | (L)Binding of Reinforcement steel | KG | 43730 | 17.7 | 774021 | 0 | 43730 | 17.7 | 774021 | 0 | 0 | 0 | 0 | 0 | 43730 | 0 | 774021 | RETAINING WALL | 1
6 | RCC WORK | (L)M+L- Concreting - M-25 | CUM | 573.68 | 1.18 | 676.94 | 0 | 573.68 | 7670 | 4400125.6 | 0 | 0 | 0 | 0 | 0 | 573.68 | -4399448.66 | 676.94 | RETAINING WALL | 1
7 | RCC WORK | (L)M+L- PCC WORK - M10 | CUM | 53.43 | 6136 | 327846.48 | 0 | 53.43 | 6136 | 327846.48 | 0 | 0 | 0 | 0 | 0 | 53.43 | 0 | 327846.48 | RETAINING WALL | 1
8 | RCC WORK | (L)Providing and Laying Reinforcement Steel | KG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RETAINING WALL | 1
9 | RCC WORK | (L)RCC WORK - RETAINING WALL - M30 | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RETAINING WALL | 1
10 | RCC WORK | (L)SHUTTERING WORK - PCC | Sq.Mtr | 46.87 | 826 | 38714.62 | 0 | 46.87 | 826 | 38714.62 | 0 | 0 | 0 | 0 | 0 | 46.87 | 0 | 38714.62 | RETAINING WALL | 1
11 | RCC WORK | (L)SHUTTERING WORK - RETAINING WALL | Sq.Mtr | 2579.13 | 1032.5 | 2662951.73 | 0 | 2579.13 | 1032.5 | 2662951.73 | 0 | 0 | 0 | 0 | 0 | 2579.13 | -0.01 | 2662951.73 | RETAINING WALL | 1