## Dependencies637382668868516634_
Dependencies for Task
!! Kanix Residency !!!
Page 1 of 1
Total Records: 921 Records 1 To 921
Depend On Task | Reference | Task Name | Offset | Start Day
Building A Brick | Start | 01 Internal Plaster | 1 | 0
01 Internal Plaster | Start | 01 Internal Plaster | 1 | 0
BBM 115MM (CM 1:4) | Start | 01 Internal Plaster 2 | 0 | 0
1st Floor RCC slab & beam M20 | Start | 1st Floor RCC Pardi M20 | 0 | 0
1st Floor RCC Column M20 | Start | 1st Floor RCC slab & beam M20 | 0 | 0
1st Floor RCC Staircase | Start | 1st Floor RCC slab & beam M20 | 0 | 0
1st Floor RCC Column M20 | End | 1st Floor RCC Staircase | 0 | 0
A Bldg 4th floor Doors Frames | Start | A Bldg 4th floor Doors Door Shutter | 0 | 0
A Bldg 4th floor Doors Bath | Start | A Bldg 4th floor Doors Frames | 0 | 0
A 1st floor Doors Dry balcony | Start | A Building All. work Kitchen Work | 0 | 0
A 1st floor Doors Bath | Start | A 1st floor Doors Door Shutter | 0 | 0
A 1st Floor BBM - | Start | A 1st Flr.Int. Plaster Int. Wall | 2 | 0
A Bldg RCC for 1st slab | Start | A 1st Flr.Steel Steel | 1 | 0
A 1st Floor RCC Concrete for 2nd slab | Start | A 2nd Flr.Steel Steel | 1 | 0
A Bldg 2nd floor RCC For 3rd slab | Start | A 3rd Floor Steel Steel | 1 | 0
A Bldg RCC For 4th slab | Start | A 4th Floor Steel Steel | 1 | 0
A Bldg BBM 4th Floor | Start | A 4th Flr.Int.Plaster Int. Wall | 2 | 0
A Bldg BBM 4th Floor | Start | A 4th Flr.Mis. Siporex Blk.Masonry-650x2 | 8 | 0
A 1st Flr.Int. Plaster Int. Wall | Start | A bldg 1st floor POP Punning work | 2 | 0
A Bldg Parking Floor Painting Oil Paint | Start | A Bldg 1st Flr. Painting | 2 | 0
A 2nd Floor BBM 2nd Floor | Start | A Bldg 2nd flr.Int. Plaster Int. Wall | 2 | 0
A Bldg 2nd floor Doors Frames | Start | A Bldg 2nd floor Doors Door Shutter | 0 | 0
A Bldg 2nd floor Doors Bath | Start | A Bldg 2nd floor Doors Frames | 0 | 0
A Bldg 2nd flr.Int. Plaster Int. Wall | Start | A bldg 2nd floor POP Punning work | 2 | 0
A Bldg 1st Flr. Painting | Start | A Bldg 2nd Flr. Painting | 2 | 0
A Bldg 3rd floor Doors Frames | Start | A Bldg 3rd floor Doors Door Shutter | 0 | 0
A Bldg 3rd floor Doors Bath | Start | A Bldg 3rd floor Doors Frames | 0 | 0
A Bldg.3rd Flr.Int.Plaster Internal Plas | Start | A bldg 3rd floor POP Punning work | 2 | 0
A Bldg 2nd Flr. Painting | Start | A Bldg 3rd Flr. Painting | 2 | 0
A 4th Flr.Int.Plaster Int. Wall | Start | A bldg 4th floor POP Punning work | 2 | 0
A Bldg 3rd Flr. Painting | Start | A Bldg 4th Flr. Painting | 2 | 0
A 4TH FLOOR | Start | A Bldg BBM 8" Thk. | 8 | 0
A Bldg RCC for 1st slab | Start | A Bldg BBM BBM 8" Thk. | 10 | 0
A Bldg Painting - 1 Job | Start | A Bldg Labour Elevation, Chajja | 2 | 0
A Bldg BBM 4th Floor | Start | A Bldg Labour Fabrication | 1 | 0
A 4th Floor Steel Steel | End | A bldg OHWT & LMR Beam & Slab Concrete M | 1 | 0
A 4th Floor Steel Steel | End | A bldg OHWT & LMR Column Concrete M20 | 1 | 0
A 4th Floor Steel Steel | End | A bldg OHWT & LMR Column Steel | 1 | 0
A 4th Floor Steel Steel | End | A bldg OHWT & LMR Miscellaneous | 1 | 0
A 4th Floor Steel Steel | End | A bldg OHWT & LMR Slab & Beam Steel | 1 | 0
A Bldg.Painting Work External Painting | Start | A Bldg Painting - 1 Job | 2 | 0
A Bldg Parking Floor Painting External | Start | A Bldg Parking Floor Painting Oil Paint | 0 | 0
A Bldg Concrete- RCC M20 | Start | A Bldg Parking Flr.steel Steel | 1 | 0
A Bldg PCC Below Footing | Start | A Bldg Plinth Level Steel | 1 | 0
A Bldg Concrete- RCC M20 | Start | A Bldg UCR Masonary 18" UCR Masonary | 15 | 0
A 3RD FLOOR | Start | A Bldg.3rd Floor BBM 8" Thk. | 8 | 0
A Bldg 4th Flr. Painting | Start | A Bldg.Painting Work External Painting | 2 | 0
A Elen.Treatment Steel | Start | A Elen.Treatment BBM 6" Thk. | 2 | 0
A Elen.Treatment Steel | Start | A Elen.Treatment External Plaster | 3 | 0
A Elen.Treatment BBM 6" Thk. | Start | A Elen.Treatment Int. Plaster Wall | 3 | 0
A bldg RCC for OHWT & LMR | End | A Elen.Treatment RCC M20 | 1 | 0
A bldg RCC for OHWT & LMR | End | A Elen.Treatment Steel | 1 | 0
A 4th Floor Steel Steel | End | A Lab.Stairecase Cap RCC | 1 | 0
A 4th Floor Steel Steel | End | A Lab.Stairecase Cap RCC | 1 | 0
A Bldg BBM 4th Floor | Start | A Labour Diffrence BBM | 8 | 0
A-painthouse Stairecase Cap External Pla | Start | A Labour Diffrence Ext.plaster Lab. | 2 | 0
A 4th Flr.Int.Plaster Int. Wall | Start | A Labour Diffrence Int.Plaster | 2 | 0
A BLDG | Start | A PCC | 0 | 0
A 4th Floor Steel Steel | End | A Steel Diffrence Steel | 1 | 0
P1W1- Fifth Floor Granite Kitchen Otta(M+L)(SLK) | End | A- Flat 202 Gypsum butt finish incl NOC (M+L) | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A-1 14th Flr.Cornice/Pardi/Cill Steel | 0 | 0
P1W1- Gr. Fl. Fire Stair Granite Tread(SLK) | End | A-1 14th Flr.Cornice/Pardi/Cill Steel | 0 | 0
A Bldg BBM 4th Floor | Start | A-painthouse Stairecase Cap BBM 8" Thk. | 8 | 0
A Bldg.External Plaster Counteryard betw | Start | A-painthouse Stairecase Cap External Pla | 2 | 0
A 4th Flr.Int.Plaster Int. Wall | Start | A-painthouse Stairecase Cap Int. Plaster | 2 | 0
A 4th Floor Steel Steel | End | A-painthouse Stairecase Cap RCC M20 | 1 | 0
A 4th Floor Steel Steel | End | A-painthouse Stairecase Cap Steel | 1 | 0
A1 HYDRO-PNUEMATIC SYSTEM 04 COMMISSIONING & TESTING 20% | End | A1 FIRE DOORS | 0 | 0
A1 SOLAR SYSTEM 04 INSTALLATION, TESTING & COMMISSIONING | End | A1 HYDRO-PNUEMATIC SYSTEM | 0 | 0
A1 HYDRO-PNUEMATIC SYSTEM | End | A1 HYDRO-PNUEMATIC SYSTEM 01 WITH WORK ORDER - 20% | 0 | 0
A1 HYDRO-PNUEMATIC SYSTEM 03 INSTALLATION - 20% | End | A1 HYDRO-PNUEMATIC SYSTEM 04 COMMISSIONING & TESTING 20% | 0 | 0
FIRE DOORS (M+L) 02 INSTALLATION - 30% | End | A1 PIPED GAS SYSTEM | 0 | 0
A1-Building Services MCB Flat DG Supply | End | A1 SOLAR SYSTEM | 0 | 0
A1 SOLAR SYSTEM | End | A1 SOLAR SYSTEM 01 TANK AT SITE - 25% | 0 | 0
A1 SOLAR SYSTEM 01 TANK AT SITE - 25% | End | A1 SOLAR SYSTEM 02 COPPER PIPING 25% | 0 | 0
A1 SOLAR SYSTEM 02 COPPER PIPING 25% | End | A1 SOLAR SYSTEM 03 COLLECTOR AT SITE 25% | 0 | 0
A1 SOLAR SYSTEM 03 COLLECTOR AT SITE 25% | End | A1 SOLAR SYSTEM 04 INSTALLATION, TESTING & COMMISSIONING | 0 | 0
A1- 9th Floor Buffing (M+L) | End | A1- 10th Floor | 0 | 0
A1- Flat 1004 Melamine Polish (M+L) | End | A1- 10th Floor Buffing (M+L) | 0 | 0
Mobile Creche I.P.S. Flooring | End | A1- 11th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L | 0 | 0
A1- 10th Floor Buffing (M+L) | End | A1- 11th Floor | 0 | 0
A1- Flat 1104 Melamine Polish (M+L) | End | A1- 11th Floor Buffing (M+L) | 0 | 0
A1- 11th Floor Buffing (M+L) | End | A1- 12th Floor | 0 | 0
A1- Flat 1204 Melamine Polish (M+L) | End | A1- 12th Floor Buffing (M+L) | 0 | 0
A1- 12th Floor Buffing (M+L) | End | A1- 13th Floor | 0 | 0
A1- 13th Floor Buffing (M+L) | End | A1- 14th Floor | 0 | 0
P1W1- Gr. Fl. Parking RMC M20 Outsource | End | A1- 1st Floor Plumbing | 0 | 0
A1- Parking Floor Plumbing Parking Plumbing | End | A1- 1st Floor Plumbing | 0 | 0
A1-1st Floor (Lab) Int.CP sanitary ( Lab) | End | A1- 2nd Floor Plumbing | 0 | 0
P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | End | A1- 2nd Floor Plumbing | 0 | 0
A1- 2nd Floor ledge wall CLC Block Masonry 4" | End | A1- 2nd Floor (Lab) | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A1- 2nd Floor (Lab) | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A1- 2nd Floor (Lab) Int.CP sanitary ( Lab) | 0 | 0
A1- 2nd Floor (Lab) Internnal Plumbing (Lab) | End | A1- 2nd Floor (Lab) Int.CP sanitary ( Lab) | 0 | 0
A1- 2nd Floor (Lab) | End | A1- 2nd Floor (Lab) Internnal Plumbing (Lab) | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A1- 2nd Floor (Lab) Internnal Plumbing (Lab) | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A1- 2nd Floor ledge wall | 0 | 0
A1-204 Sanitaryware( Kit+2T) | End | A1- 2nd Floor ledge wall | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A1- 2nd Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | 0
A1- 2nd Floor ledge wall | End | A1- 2nd Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A1- 2nd Floor ledge wall CLC Block Masonry 4" | 0 | 0
A1- 2nd Floor ledge wall CLC Block Making 500 x 200 x 100 | End | A1- 2nd Floor ledge wall CLC Block Masonry 4" | 0 | 0
A1- 2nd Floor (Lab) Int.CP sanitary ( Lab) | End | A1- 3rd Floor Plumbing | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A1- 3rd Floor Plumbing | 0 | 0
A1- Flat 504 Melamine Polish (M+L) | End | A1- 5th Floor Buffing (M+L) | 0 | 0
A1- 5th Floor Buffing (M+L) | End | A1- 6th Floor | 0 | 0
A1- Flat 604 Melamine Polish (M+L) | End | A1- 6th Floor Buffing (M+L) | 0 | 0
A1- 6th Floor Buffing (M+L) | End | A1- 7th Floor | 0 | 0
A1- Flat 704 Melamine Polish (M+L) | End | A1- 7th Floor Buffing (M+L) | 0 | 0
A1- 7th Floor Buffing (M+L) | End | A1- 8th Floor | 0 | 0
A1- Flat 801 Melamine Polish (M+L) | End | A1- 8th Floor Buffing (M+L) | 0 | 0
A1- 8th Floor Buffing (M+L) | End | A1- 9th Floor | 0 | 0
A1- Flat 904 Melamine Polish (M+L) | End | A1- 9th Floor Buffing (M+L) | 0 | 0
A1- 10th Floor | End | A1- Flat 1001 | 0 | 0
A1- Flat 1001 | End | A1- Flat 1001 Melamine Polish (M+L) | 0 | 0
A1- Flat 1001 Melamine Polish (M+L) | End | A1- Flat 1002 | 0 | 0
A1- Flat 1002 | End | A1- Flat 1002 Melamine Polish (M+L) | 0 | 0
A1- Flat 1003 Melamine Polish (M+L) | End | A1- Flat 1004 | 0 | 0
A1- Flat 1004 | End | A1- Flat 1004 Melamine Polish (M+L) | 0 | 0
Door & windows Alu. Window & lou. (P.C) (M+L) | Start | A1- Flat 103 Gypsum plaster incl NOC (M+L) | 0 | 0
A1- 11th Floor | End | A1- Flat 1101 | 0 | 0
A1- Flat 1101 | End | A1- Flat 1101 Melamine Polish (M+L) | 0 | 0
A1- Flat 1101 Melamine Polish (M+L) | End | A1- Flat 1102 | 0 | 0
A1- Flat 1102 | End | A1- Flat 1102 Melamine Polish (M+L) | 0 | 0
A1- Flat 1102 Melamine Polish (M+L) | End | A1- Flat 1103 | 0 | 0
A1- Flat 1104 | End | A1- Flat 1104 Melamine Polish (M+L) | 0 | 0
A1- 12th Floor | End | A1- Flat 1201 | 0 | 0
A1- Flat 1201 | End | A1- Flat 1201 Melamine Polish (M+L) | 0 | 0
A1- Flat 1201 Melamine Polish (M+L) | End | A1- Flat 1202 | 0 | 0
A1- Flat 1202 | End | A1- Flat 1202 Melamine Polish (M+L) | 0 | 0
A1- Flat 1202 Melamine Polish (M+L) | End | A1- Flat 1203 | 0 | 0
A1- Flat 1203 | End | A1- Flat 1203 Melamine Polish (M+L) | 0 | 0
A1- Flat 1303 Melamine Polish (M+L) | End | A1- Flat 1301 | 0 | 0
A- Flat 202 Gypsum butt finish incl NOC (M+L) | End | A1- Flat 1301 Putty Plaster | 0 | 0
A1- Refuge Flat 1304 Melamine Polish (M+L) | End | A1- Flat 1302 | 0 | 0
A1- Flat 1302 | End | A1- Flat 1302 Melamine Polish (M+L) | 0 | 0
A1- Flat 1302 Melamine Polish (M+L) | End | A1- Flat 1303 | 0 | 0
A1- Flat 1303 | End | A1- Flat 1303 Melamine Polish (M+L) | 0 | 0
A1- 14th Floor | End | A1- Flat 1401 | 0 | 0
A1- Flat 1401 | End | A1- Flat 1401 Melamine Polish (M+L) | 0 | 0
A1- Flat 1401 Melamine Polish (M+L) | End | A1- Flat 1402 | 0 | 0
A1- Flat 1402 | End | A1- Flat 1402 Melamine Polish (M+L) | 0 | 0
A1- Flat 1402 Melamine Polish (M+L) | End | A1- Flat 1403 | 0 | 0
A1- Flat 1403 | End | A1- Flat 1403 Melamine Polish (M+L) | 0 | 0
A1- Flat 1403 Melamine Polish (M+L) | End | A1- Flat 1404 | 0 | 0
A1- Flat 1404 | End | A1- Flat 1404 Melamine Polish (M+L) | 0 | 0
Oct-15 | End | A1- Flat 303 | 0 | 0
Oct-15 | End | A1- Flat 303 Gypsum plaster incl NOC (M+L) | 0 | 0
A1- Flat 501 | End | A1- Flat 501 Melamine Polish (M+L) | 0 | 0
A1- Flat 501 Melamine Polish (M+L) | End | A1- Flat 502 | 0 | 0
A1- Flat 502 | End | A1- Flat 502 Melamine Polish (M+L) | 0 | 0
A1- Flat 502 Melamine Polish (M+L) | End | A1- Flat 503 | 0 | 0
A1- Flat 503 | End | A1- Flat 503 Melamine Polish (M+L) | 0 | 0
A1- Flat 503 Melamine Polish (M+L) | End | A1- Flat 504 | 0 | 0
A1- Flat 504 | End | A1- Flat 504 Melamine Polish (M+L) | 0 | 0
A1- Flat 601 Melamine Polish (M+L) | End | A1- Flat 602 | 0 | 0
A1- Flat 602 | End | A1- Flat 602 Melamine Polish (M+L) | 0 | 0
A1- Flat 602 Melamine Polish (M+L) | End | A1- Flat 603 | 0 | 0
A1- Flat 603 | End | A1- Flat 603 Melamine Polish (M+L) | 0 | 0
A1- Flat 603 Melamine Polish (M+L) | End | A1- Flat 604 | 0 | 0
A1- Flat 604 | End | A1- Flat 604 Melamine Polish (M+L) | 0 | 0
A1- 7th Floor | End | A1- Flat 701 | 0 | 0
A1- Flat 702 | End | A1- Flat 702 Melamine Polish (M+L) | 0 | 0
A1- Flat 702 Melamine Polish (M+L) | End | A1- Flat 703 | 0 | 0
A1- Flat 703 | End | A1- Flat 703 Melamine Polish (M+L) | 0 | 0
A1- Flat 703 Melamine Polish (M+L) | End | A1- Flat 704 | 0 | 0
A1- Flat 704 | End | A1- Flat 704 Melamine Polish (M+L) | 0 | 0
A1- Flat 803 Melamine Polish (M+L) | End | A1- Flat 801 | 0 | 0
A1- Flat 801 | End | A1- Flat 801 Melamine Polish (M+L) | 0 | 0
C2 GF Masonry BBM 6" Thk. | End | A1- Flat 802 | 0 | 0
A1- Flat 802 Melamine Polish (M+L) | End | A1- Flat 803 | 0 | 0
A1- Flat 803 | End | A1- Flat 803 Melamine Polish (M+L) | 0 | 0
A1- 9th Floor | End | A1- Flat 901 | 0 | 0
A1- Flat 901 | End | A1- Flat 901 Melamine Polish (M+L) | 0 | 0
A1- Flat 901 Melamine Polish (M+L) | End | A1- Flat 902 | 0 | 0
A1- Flat 903 | End | A1- Flat 903 Melamine Polish (M+L) | 0 | 0
A1- Flat 903 Melamine Polish (M+L) | End | A1- Flat 904 | 0 | 0
A1- Flat 904 | End | A1- Flat 904 Melamine Polish (M+L) | 0 | 0
A1-Plumbing & Sanitation | End | A1- Internal Plumbing | 0 | 0
A1- Misc. Item | End | A1- Misc. Item Melamine Polish (M+L) | 0 | 0
A1- Parking Floor Plumbing | End | A1- Parking Floor ledge wall | 0 | 0
P1W1- Gr. Fl. Parking RMC M20 Outsource | End | A1- Parking Floor ledge wall CLC Block Making 500 x 200 x 10 | 0 | 0
P1W1- Gr. Fl. Parking RMC M20 Outsource | End | A1- Parking Floor ledge wall CLC Block Masonry 4" | 0 | 0
A1- Parking Floor ledge wall CLC Block Making 500 x 200 x 10 | End | A1- Parking Floor ledge wall CLC Block Masonry 4" | 0 | 0
A1- Internal Plumbing | End | A1- Parking Floor Plumbing | 0 | 0
A1- Parking Floor ledge wall CLC Block Masonry 4" | End | A1- Parking Floor Plumbing Internnal Plumbing (Lab) | 0 | 0
P1W1- Gr. Fl. Parking RMC M20 Outsource | End | A1- Parking Floor Plumbing Internnal Plumbing (Lab) | 0 | 0
P1W1- Gr. Fl. Parking RMC M20 Outsource | End | A1- Parking Floor Plumbing Parking Plumbing | 0 | 0
A1- Parking Floor Plumbing Internnal Plumbing (Lab) | End | A1- Parking Floor Plumbing Parking Plumbing | 0 | 0
A1- 13th Floor | End | A1- Refuge Flat 1304 | 0 | 0
A1- Refuge Flat 1304 | End | A1- Refuge Flat 1304 Melamine Polish (M+L) | 0 | 0
A1- 8th Floor | End | A1- Refuge Flat 804 | 0 | 0
A1- Refuge Flat 804 | End | A1- Refuge Flat 804 Melamine Polish (M+L) | 0 | 0
P1W1- Gr. Fl. Parking RMC M20 Outsource | End | A1-101 | 0 | 0
A1- 1st Floor Plumbing | End | A1-101 | 0 | 0
A1-101 | End | A1-101 CP Fitting (Kit+2T) | 0 | 0
P1W1- Gr. Fl. Parking RMC M20 Outsource | End | A1-101 CP Fitting (Kit+2T) | 0 | 0
P1W1- Gr. Fl. Parking RMC M20 Outsource | End | A1-101 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
A1-101 CP Fitting (Kit+2T) | End | A1-101 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
A1-101 PVC/PPRC/GI/CI Concealed (Kit+2T) | End | A1-101 Sanitaryware( Kit+2T) | 0 | 0
P1W1- Gr. Fl. Parking RMC M20 Outsource | End | A1-101 Sanitaryware( Kit+2T) | 0 | 0
P1W1- Gr. Fl. Parking Tiling (Lab) | End | A1-102 CP Fitting (Kit+2T) | 0 | 0
P1W1- Gr. Fl. Parking Tiling (Lab) | End | A1-102 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
A1-102 CP Fitting (Kit+2T) | End | A1-102 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
A1-102 PVC/PPRC/GI/CI Concealed (Kit+2T) | End | A1-102 Sanitaryware( Kit+2T) | 0 | 0
P1W1- Gr. Fl. Parking Tiling (Lab) | End | A1-102 Sanitaryware( Kit+2T) | 0 | 0
P1W1- Gr. Fl. Parking Tiling (Lab) | End | A1-103 CP Fitting (Kit+2T) | 0 | 0
A1-102 Sanitaryware( Kit+2T) | End | A1-103 CP Fitting (Kit+2T) | 0 | 0
A1-103 CP Fitting (Kit+2T) | End | A1-103 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
P1W1- Gr. Fl. Parking Tiling (Lab) | End | A1-103 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
P1W1- Gr. Fl. Parking Tiling (Lab) | End | A1-103 Sanitaryware( Kit+2T) | 0 | 0
A1-103 PVC/PPRC/GI/CI Concealed (Kit+2T) | End | A1-103 Sanitaryware( Kit+2T) | 0 | 0
A1-103 Sanitaryware( Kit+2T) | End | A1-104 | 0 | 0
P1W1- Gr. Fl. Parking Tiling (Lab) | End | A1-104 | 0 | 0
P1W1- Gr. Fl. Parking Tiling (Lab) | End | A1-104 CP Fitting (Kit+2T) | 0 | 0
A1-104 | End | A1-104 CP Fitting (Kit+2T) | 0 | 0
A1-104 CP Fitting (Kit+2T) | End | A1-104 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
P1W1- Gr. Fl. Parking Tiling (Lab) | End | A1-104 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
A1-9th Floor ACCL | End | A1-10th Floor | 0 | 0
P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | End | A1-10th Floor ACCL | 0 | 0
A1-10th Floor MCB-DB (M)- 2BHK 2T | End | A1-10th Floor ACCL | 0 | 0
P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | End | A1-10th Floor MCB-DB (M)- 2BHK 2T | 0 | 0
A1-10th Floor Switches,Plates & Acc. (M+L) | End | A1-10th Floor MCB-DB (M)- 2BHK 2T | 0 | 0
A1-10th Floor | End | A1-10th Floor Slab conduiting (M+L) | 0 | 0
P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | End | A1-10th Floor Switches,Plates & Acc. (M+L) | 0 | 0
A1-10th Floor Slab conduiting (M+L) | End | A1-10th Floor Wall Dropping (M+L) | 0 | 0
A1-11th Floor MCB-DB (M)- 2BHK 2T | End | A1-11th Floor ACCL | 0 | 0
P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | End | A1-11th Floor ACCL | 0 | 0
P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | End | A1-11th Floor MCB-DB (M)- 2BHK 2T | 0 | 0
A1-11th Floor Switches,Plates & Acc. (M+L) | End | A1-11th Floor MCB-DB (M)- 2BHK 2T | 0 | 0
A1-10th Floor ACCL | End | A1-11th Floor Slab conduiting (M+L) | 0 | 0
P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | End | A1-11th Floor Slab conduiting (M+L) | 0 | 0
P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | End | A1-11th Floor Switches,Plates & Acc. (M+L) | 0 | 0
A1-11th Floor Wiring (M+L) | End | A1-11th Floor Switches,Plates & Acc. (M+L) | 0 | 0
A1-11th Floor Slab conduiting (M+L) | End | A1-11th Floor Wall Dropping (M+L) | 0 | 0
P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | End | A1-11th Floor Wall Dropping (M+L) | 0 | 0
P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | End | A1-11th Floor Wiring (M+L) | 0 | 0
A1-11th Floor Wall Dropping (M+L) | End | A1-11th Floor Wiring (M+L) | 0 | 0
A1-12th Floor MCB-DB (M)- 2BHK 2T | End | A1-12th Floor ACCL | 0 | 0
P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | End | A1-12th Floor ACCL | 0 | 0
P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | End | A1-12th Floor MCB-DB (M)- 2BHK 2T | 0 | 0
A1-12th Floor Wiring (M+L) | End | A1-12th Floor MCB-DB (M)- 2BHK 2T | 0 | 0
P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | End | A1-12th Floor Slab conduiting (M+L) | 0 | 0
P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | End | A1-12th Floor Wall Dropping (M+L) | 0 | 0
A1-12th Floor Slab conduiting (M+L) | End | A1-12th Floor Wall Dropping (M+L) | 0 | 0
P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | End | A1-12th Floor Wiring (M+L) | 0 | 0
A1-12th Floor Wall Dropping (M+L) | End | A1-12th Floor Wiring (M+L) | 0 | 0
A1-12th Floor ACCL | End | A1-13th Floor | 0 | 0
P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | End | A1-13th Floor | 0 | 0
A1-13th Floor MCB-DB (M)- 2BHK 2T | End | A1-13th Floor ACCL | 0 | 0
P1W1- Gr. Fl. Balcony | End | A1-13th Floor ACCL | 0 | 0
P1W1- Gr. Fl. Balcony | End | A1-13th Floor MCB-DB (M)- 2BHK 2T | 0 | 0
P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | End | A1-13th Floor Slab conduiting (M+L) | 0 | 0
A1-13th Floor | End | A1-13th Floor Slab conduiting (M+L) | 0 | 0
P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | End | A1-13th Floor Wall Dropping (M+L) | 0 | 0
A1-13th Floor Slab conduiting (M+L) | End | A1-13th Floor Wall Dropping (M+L) | 0 | 0
P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | End | A1-13th Floor Wiring (M+L) | 0 | 0
A1-13th Floor Wall Dropping (M+L) | End | A1-13th Floor Wiring (M+L) | 0 | 0
A1-13th Floor ACCL | End | A1-14th Floor | 0 | 0
P1W1- Gr. Fl. Balcony | End | A1-14th Floor | 0 | 0
P1W1- Gr. Fl. Balcony | End | A1-14th Floor ACCL | 0 | 0
A1-14th Floor MCB-DB (M)- 2BHK 2T | End | A1-14th Floor ACCL | 0 | 0
A1-14th Floor Switches,Plates & Acc. (M+L) | End | A1-14th Floor MCB-DB (M)- 2BHK 2T | 0 | 0
P1W1- Gr. Fl. Balcony | End | A1-14th Floor MCB-DB (M)- 2BHK 2T | 0 | 0
P1W1- Gr. Fl. Balcony | End | A1-14th Floor Switches,Plates & Acc. (M+L) | 0 | 0
A1-14th Floor Wiring (M+L) | End | A1-14th Floor Switches,Plates & Acc. (M+L) | 0 | 0
A1-14th Floor | End | A1-14th Floor Wall Dropping (M+L) | 0 | 0
P1W1- Gr. Fl. Balcony | End | A1-14th Floor Wall Dropping (M+L) | 0 | 0
P1W1- Gr. Fl. Balcony | End | A1-14th Floor Wiring (M+L) | 0 | 0
A1-14th Floor Wall Dropping (M+L) | End | A1-14th Floor Wiring (M+L) | 0 | 0
A1-1st Floor ledge wall CLC Block Making 500 x 200 x 100 | End | A1-1st Floor (Lab) | 0 | 0
P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | End | A1-1st Floor (Lab) | 0 | 0
P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | End | A1-1st Floor (Lab) Int.CP sanitary ( Lab) | 0 | 0
A1-1st Floor (Lab) Internnal Plumbing (Lab) | End | A1-1st Floor (Lab) Int.CP sanitary ( Lab) | 0 | 0
P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | End | A1-1st Floor (Lab) Internnal Plumbing (Lab) | 0 | 0
A1-1st Floor (Lab) | End | A1-1st Floor (Lab) Internnal Plumbing (Lab) | 0 | 0
P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | End | A1-1st Floor ledge wall | 0 | 0
P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | End | A1-1st Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | 0
A1-1st Floor ledge wall CLC Block Masonry 4" (OS) | End | A1-1st Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | 0
A1-1st Floor ledge wall | End | A1-1st Floor ledge wall CLC Block Masonry 4" (OS) | 0 | 0
P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | End | A1-1st Floor ledge wall CLC Block Masonry 4" (OS) | 0 | 0
P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | End | A1-201 | 0 | 0
A1- 2nd Floor Plumbing | End | A1-201 | 0 | 0
P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | End | A1-201 CP Fitting (Kit+2T) | 0 | 0
A1-201 | End | A1-201 CP Fitting (Kit+2T) | 0 | 0
P1W1- Gr.Fl. Pantry | End | A1-201 Sanitaryware( Kit+2T) | 0 | 0
P1W1- Gr.Fl. Pantry | End | A1-202 | 0 | 0
A1-201 Sanitaryware( Kit+2T) | End | A1-202 | 0 | 0
A1-202 | End | A1-202 CP Fitting (Kit+2T) | 0 | 0
P1W1- Gr.Fl. Pantry | End | A1-202 CP Fitting (Kit+2T) | 0 | 0
P1W1- Gr.Fl. Pantry | End | A1-202 Sanitaryware( Kit+2T) | 0 | 0
A1-202 CP Fitting (Kit+2T) | End | A1-202 Sanitaryware( Kit+2T) | 0 | 0
A1-202 Sanitaryware( Kit+2T) | End | A1-203 | 0 | 0
P1W1- Gr.Fl. Pantry | End | A1-203 | 0 | 0
P1W1- Gr.Fl. Pantry | End | A1-203 CP Fitting (Kit+2T) | 0 | 0
A1-203 | End | A1-203 CP Fitting (Kit+2T) | 0 | 0
A1-203 CP Fitting (Kit+2T) | End | A1-203 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
P1W1- Gr.Fl. Pantry | End | A1-203 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
P1W1- Gr.Fl. Pantry | End | A1-203 Sanitaryware( Kit+2T) | 0 | 0
A1-203 PVC/PPRC/GI/CI Concealed (Kit+2T) | End | A1-203 Sanitaryware( Kit+2T) | 0 | 0
A1-203 Sanitaryware( Kit+2T) | End | A1-204 | 0 | 0
P1W1- Gr.Fl. Pantry | End | A1-204 | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A1-204 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A1-204 Sanitaryware( Kit+2T) | 0 | 0
A1-204 PVC/PPRC/GI/CI Concealed (Kit+2T) | End | A1-204 Sanitaryware( Kit+2T) | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A1-301 CP Fitting (Kit+2T) | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A1-301 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
A1-301 CP Fitting (Kit+2T) | End | A1-301 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
A1-10th Floor Wall Dropping (M+L) | End | A1-601 Sanitaryware( Kit+2T) | 0 | 0
A1-11th Floor ACCL | End | A1-602 | 0 | 0
P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | End | A1-602 | 0 | 0
A1-13th Floor Wiring (M+L) | End | A1-602 CP Fitting (Kit+2T) | 0 | 0
P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | End | A1-602 CP Fitting (Kit+2T) | 0 | 0
A1-Earthing pits | End | A1-602 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
P1W1- Gr. Fl. Balcony | End | A1-602 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
A1-Common Area Mains Wiring (M+L) | End | A1-602 Sanitaryware( Kit+2T) | 0 | 0
P1W1- Gr. Fl. Balcony Tiling (Lab) | End | A1-602 Sanitaryware( Kit+2T) | 0 | 0
A1- Parking Floor ledge wall | End | A1-603 | 0 | 0
A1-101 Sanitaryware( Kit+2T) | End | A1-603 CP Fitting (Kit+2T) | 0 | 0
P1W1- Gr. Fl. Parking RMC M20 Outsource | End | A1-603 CP Fitting (Kit+2T) | 0 | 0
P1W1- Gr. Fl. Parking Tiling (Lab) | End | A1-603 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
A1-104 PVC/PPRC/GI/CI Concealed (Kit+2T) | End | A1-603 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
A1-201 CP Fitting (Kit+2T) | End | A1-603 Sanitaryware( Kit+2T) | 0 | 0
P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | End | A1-603 Sanitaryware( Kit+2T) | 0 | 0
A1-8th Floor MCB-DB (M)- 2BHK 2T | End | A1-604 | 0 | 0
P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | End | A1-604 | 0 | 0
A1-204 | End | A1-604 CP Fitting (Kit+2T) | 0 | 0
P1W1- Gr.Fl. Pantry | End | A1-604 CP Fitting (Kit+2T) | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A1-604 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
A1- 3rd Floor Plumbing | End | A1-604 PVC/PPRC/GI/CI Concealed (Kit+2T) | 0 | 0
A1-Flat 404 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | End | A1-8th Fl.Lobby | 0 | 0
A1-8th Floor Switches,Plates & Acc. (M+L) | End | A1-8th Floor MCB-DB (M)- 2BHK 2T | 0 | 0
P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | End | A1-8th Floor MCB-DB (M)- 2BHK 2T | 0 | 0
P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | End | A1-8th Floor Switches,Plates & Acc. (M+L) | 0 | 0
A1-8th Floor Wiring (M+L) | End | A1-8th Floor Switches,Plates & Acc. (M+L) | 0 | 0
A1-Flat 1104 Tile (M+L) Granite WHB Counter (M+L) | End | A1-8th Floor Wiring (M+L) | 0 | 0
P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | End | A1-8th Floor Wiring (M+L) | 0 | 0
P1W1- Gr.Fl. Main Lift Cladding Tiling (Lab) | End | A1-9th Floor | 0 | 0
A1-9th Floor MCB-DB (M)- 2BHK 2T | End | A1-9th Floor ACCL | 0 | 0
A1-9th Floor Switches,Plates & Acc. (M+L) | End | A1-9th Floor MCB-DB (M)- 2BHK 2T | 0 | 0
A1-9th Floor | End | A1-9th Floor Slab conduiting (M+L) | 0 | 0
A1-9th Floor Wall Dropping (M+L) | End | A1-9th Floor Switches,Plates & Acc. (M+L) | 0 | 0
A1-9th Floor Slab conduiting (M+L) | End | A1-9th Floor Wall Dropping (M+L) | 0 | 0
A1- Misc. Item Melamine Polish (M+L) | End | A1-Building Services | 0 | 0
A1-Building Services Auto Change Over Panel | End | A1-Building Services Bus Bar (Meter Room) | 0 | 0
A1-Building Services RETICULATED PIPED GAS SYSTEM | End | A1-Building Services FIRE DOOR | 0 | 0
A1-Building Services LIFT | End | A1-Building Services FIRE FIGHTING SYSTEM | 0 | 0
A1-Building Services FIRE DOOR | End | A1-Building Services HYDRO-PNEUMATIC SYSTEM | 0 | 0
A1-Building Services | End | A1-Building Services LIFT | 0 | 0
A1-Building Services HYDRO-PNEUMATIC SYSTEM | End | A1-Building Services Lift scaffolding | 0 | 0
A1-Building Services Bus Bar (Meter Room) | End | A1-Building Services MCB Flat DG Supply | 0 | 0
A1-Building Services SOLAR HOT WATER | End | A1-Building Services RETICULATED PIPED GAS SYSTEM | 0 | 0
A1-Building Services FIRE FIGHTING SYSTEM | End | A1-Building Services SOLAR HOT WATER | 0 | 0
P1W1- Gr. Fl. Balcony Tiling (Lab) | End | A1-Common Area | 0 | 0
P1W1- Gr. Fl. Balcony Tiling (Lab) | End | A1-Common Area Building Earthing (M+L) | 0 | 0
A1-Common Area | End | A1-Common Area Building Earthing (M+L) | 0 | 0
A1-Common Area Building Earthing (M+L) | End | A1-Common Area Building Electrical Testing (M+L) | 0 | 0
P1W1- Gr. Fl. Balcony Tiling (Lab) | End | A1-Common Area Building Electrical Testing (M+L) | 0 | 0
P1W1- Gr. Fl. Balcony Tiling (Lab) | End | A1-Common Area Flat testing & handing over | 0 | 0
A1-Common Area Meter Room Electrification (M+L) | End | A1-Common Area Flat testing & handing over | 0 | 0
P1W1- Gr. Fl. Balcony Tiling (Lab) | End | A1-Common Area Lift 2- Electrification (M+L) | 0 | 0
A1-Common Area Building Electrical Testing (M+L) | End | A1-Common Area Lift 2- Electrification (M+L) | 0 | 0
P1W1- Gr. Fl. Balcony Tiling (Lab) | End | A1-Common Area Lightening Arrestor (M+L) | 0 | 0
A1-Common Area Lift 2- Electrification (M+L) | End | A1-Common Area Lightening Arrestor (M+L) | 0 | 0
A1-Common Area Lightening Arrestor (M+L) | End | A1-Common Area Mains Conduiting (M+L) | 0 | 0
P1W1- Gr. Fl. Balcony Tiling (Lab) | End | A1-Common Area Mains Conduiting (M+L) | 0 | 0
P1W1- Gr. Fl. Balcony Tiling (Lab) | End | A1-Common Area Mains Wiring (M+L) | 0 | 0
A1-Common Area Flat testing & handing over | End | A1-Common Area Mains Wiring (M+L) | 0 | 0
A1-Common Area Mains Conduiting (M+L) | End | A1-Common Area Meter Room Electrification (M+L) | 0 | 0
P1W1- Gr. Fl. Balcony Tiling (Lab) | End | A1-Common Area Meter Room Electrification (M+L) | 0 | 0
A1-14th Floor ACCL | End | A1-Earthing pits | 0 | 0
P1W1- Gr. Fl. Balcony | End | A1-Earthing pits | 0 | 0
A1-Earthwork Site cleaning | Start | A1-Earthwork Back Filling | 0 | 0
A1-Earthwork Site cleaning | Start | A1-Earthwork Excavation in Bolder /Hard Murum | 0 | 0
A1-Earthwork Site cleaning | Start | A1-Earthwork Excavation in Manjra Rock | 0 | 0
A1-Earthwork Site cleaning | Start | A1-Earthwork Excavation in Soil/Soft Murum | 0 | 0
A1-Earthwork Site cleaning | Start | A1-Earthwork Royalty Charges | 0 | 0
P1W1- Gr.Fl. Lift Cladding | End | A1-Flat 1001 Tile (M+L) Granite Door Frame (M+L) | 0 | 0
P1W1- Gr. Fl. Fire Stair Granite Flooring(SLK) | End | A1-Flat 1001 Tile (M+L) Granite Kitchen Otta (M+L) | 0 | 0
P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | End | A1-Flat 1001 Tile (M+L) Granite Ledge wall (M+L) | 0 | 0
P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | End | A1-Flat 1001 Tile (M+L) Granite WHB Counter (M+L) | 0 | 0
P1W1- Gr. Fl. Balcony Tiling (Lab) | End | A1-Flat 1001 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | 0
P1W1- Gr.Fl. Main Lift Cladding Tiling (Lab) | End | A1-Flat 1001 Tile (M+L) Granite Window Jambs (M+L) | 0 | 0
P1W1- Gr. Fl. Balcony | End | A1-Flat 1001 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 0 | 0
P1W1- Gr. Fl. Parking Tiling (Lab) | End | A1-Flat 1002 Tile (M+L) Granite Door Frame (M+L) | 0 | 0
P1W1- Gr. Fl. Parking RMC M20 Outsource | End | A1-Flat 1002 Tile (M+L) Granite Kitchen Otta (M+L) | 0 | 0
P1W1- Gr.Fl. Pantry | End | A1-Flat 1002 Tile (M+L) Granite Ledge wall (M+L) | 0 | 0
P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | End | A1-Flat 1002 Tile (M+L) Granite WHB Counter (M+L) | 0 | 0
P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | End | A1-Flat 1002 Tile (M+L) Granite Window Jambs (M+L) | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | A1-Flat 1002 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 0 | 0
A1-Flat 1103 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | End | A1-Flat 1103 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | 0
P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | End | A1-Flat 1103 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | 0
P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | End | A1-Flat 1103 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 0 | 0
P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | End | A1-Flat 1104 Tile (M+L) | 0 | 0
A1-Flat 1103 Tile (M+L) Granite Window Cill upto 3"(M+L) | End | A1-Flat 1104 Tile (M+L) | 0 | 0
A1-Flat 1104 Tile (M+L) Granite Kitchen Otta (M+L) | End | A1-Flat 1104 Tile (M+L) Granite Door Frame (M+L) | 0 | 0
P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | End | A1-Flat 1104 Tile (M+L) Granite Door Frame (M+L) | 0 | 0
P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | End | A1-Flat 1104 Tile (M+L) Granite Kitchen Otta (M+L) | 0 | 0
A1-Flat 1104 Tile (M+L) | End | A1-Flat 1104 Tile (M+L) Granite Kitchen Otta (M+L) | 0 | 0
A1-Flat 1104 Tile (M+L) Granite Window Jambs (M+L) | End | A1-Flat 1104 Tile (M+L) Granite WHB Counter (M+L) | 0 | 0
P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | End | A1-Flat 1104 Tile (M+L) Granite WHB Counter (M+L) | 0 | 0
P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | End | A1-Flat 1104 Tile (M+L) Granite Window Jambs (M+L) | 0 | 0
A1-Flat 1104 Tile (M+L) Granite Door Frame (M+L) | End | A1-Flat 1104 Tile (M+L) Granite Window Jambs (M+L) | 0 | 0
P1W1- Gr. Fl. Electrical Room RMC M20 Outsource | End | A1-Flat 404 Tile (M+L) | 2 | 0
A1-Flat 404 Tile (M+L) Granite Kitchen Otta (M+L) | End | A1-Flat 404 Tile (M+L) Granite Door Frame (M+L) | 0 | 0
A1-Flat 404 Tile (M+L) | End | A1-Flat 404 Tile (M+L) Granite Kitchen Otta (M+L) | 0 | 0
A1-Flat 404 Tile (M+L) Granite WHB Counter (M+L) | End | A1-Flat 404 Tile (M+L) Granite Ledge wall (M+L) | 0 | 0
A1-Flat 404 Tile (M+L) Granite Window Jambs (M+L) | End | A1-Flat 404 Tile (M+L) Granite WHB Counter (M+L) | 0 | 0
A1-Flat 404 Tile (M+L) Granite Door Frame (M+L) | End | A1-Flat 404 Tile (M+L) Granite Window Jambs (M+L) | 0 | 0
A1-Flat 404 Tile (M+L) Granite Ledge wall (M+L) | End | A1-Flat 404 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 0 | 0
A1-Total MCB, DB (Lab) MCB, DB fixing (Lab) | End | A1-Misc.Light Fittings | 0 | 0
A1-Misc.Light Fittings | End | A1-Misc.Light Fittings Lobby Light Fitting | 0 | 0
A1-Misc.Light Fittings Parking Light Fitting | End | A1-Misc.Light Fittings Misc. Light Fitting (Lab) | 0 | 0
A1-Misc.Light Fittings Lobby Light Fitting | End | A1-Misc.Light Fittings Parking Light Fitting | 0 | 0
A1-Misc.Light Fittings Misc. Light Fitting (Lab) | End | A1-Plumbing & Sanitation | 0 | 0
A1- Flat 103 Gypsum plaster incl NOC (M+L) | End | A1-Refuge Flat-804 Refuge Ceramic Flooring | 0 | 0
AC-Terrace PART-03 Electrical Work | Start | AC-2nd Fl. PART-02 Electrical Work | 0 | 0
P1W1- Gr. Fl. Fire Stair | End | AC-3rd Fl. PART-04 Electrical Work | 0 | 0
P1W1- Gr.Fl.Ramp | End | AC-3rd Fl. PART-05 | 0 | 0
AC-Basement-2 PART-06 Switches,Plates & Acc. (M+L) | End | AC-BASEMENT-1 | 0 | 0
AC-BASEMENT-1 | End | AC-Basement-1 PART-01 | 0 | 0
AC-Basement-1 PART-01 Wiring (M+L) | End | AC-Basement-1 PART-01 Electrical Work | 0 | 0
AC-Basement-1 PART-01 Electrical Work | End | AC-Basement-1 PART-01 Slab conduiting (M+L) | 0 | 0
AC-Basement-1 PART-01 Wall Conduiting/Dropping | End | AC-Basement-1 PART-01 Switches,Plates & Acc. (M+L) | 0 | 0
AC-Basement-1 PART-01 Slab conduiting (M+L) | End | AC-Basement-1 PART-01 Wall Conduiting/Dropping | 0 | 0
AC-Basement-1 PART-01 | End | AC-Basement-1 PART-01 Wiring (M+L) | 0 | 0
AC-Basement-1 PART-01 Switches,Plates & Acc. (M+L) | End | AC-Basement-1 PART-02 | 0 | 0
AC-Basement-1 PART-02 Wiring (M+L) | End | AC-Basement-1 PART-02 Electrical Work | 0 | 0
AC-Basement-1 PART-02 Electrical Work | End | AC-Basement-1 PART-02 Slab conduiting (M+L) | 0 | 0
AC-Basement-1 PART-02 Wall Conduiting/Dropping | End | AC-Basement-1 PART-02 Switches,Plates & Acc. (M+L) | 0 | 0
AC-Basement-1 PART-02 Slab conduiting (M+L) | End | AC-Basement-1 PART-02 Wall Conduiting/Dropping | 0 | 0
AC-Basement-1 PART-02 Switches,Plates & Acc. (M+L) | End | AC-Basement-1 PART-03 | 0 | 0
AC-Basement-1 PART-03 Wiring (M+L) | End | AC-Basement-1 PART-03 Electrical Work | 0 | 0
AC-Basement-1 PART-03 Electrical Work | End | AC-Basement-1 PART-03 Slab conduiting (M+L) | 0 | 0
AC-Basement-1 PART-03 Slab conduiting (M+L) | End | AC-Basement-1 PART-03 Wall Conduiting/Dropping | 0 | 0
AC-Basement-1 PART-03 | End | AC-Basement-1 PART-03 Wiring (M+L) | 0 | 0
AC-Basement-2 PART-06 Wall Conduiting/Dropping | End | AC-Basement-2 PART-06 Switches,Plates & Acc. (M+L) | 0 | 0
AC-Basement-2 PART-06 Slab conduiting (M+L) | End | AC-Basement-2 PART-06 Wall Conduiting/Dropping | 0 | 0
AC-First Fl. PART-01 Electrical Work | End | AC-First Fl. PART-01 Slab conduiting (M+L) | 0 | 0
AC-First Fl. PART-01 Wall Conduiting/Dropping | End | AC-First Fl. PART-01 Switches,Plates & Acc. (M+L) | 0 | 0
AC-First Fl. PART-01 Slab conduiting (M+L) | End | AC-First Fl. PART-01 Wall Conduiting/Dropping | 0 | 0
AC-First Fl. PART-01 Switches,Plates & Acc. (M+L) | End | AC-First Fl. PART-02 | 0 | 0
AC-First Fl. PART-02 Wiring (M+L) | End | AC-First Fl. PART-02 Electrical Work | 0 | 0
AC-First Fl. PART-02 Wall Conduiting/Dropping | End | AC-First Fl. PART-02 Switches,Plates & Acc. (M+L) | 0 | 0
AC-First Fl. PART-02 Slab conduiting (M+L) | End | AC-First Fl. PART-02 Wall Conduiting/Dropping | 0 | 0
AC-First Fl. PART-02 | End | AC-First Fl. PART-02 Wiring (M+L) | 0 | 0
AC-First Fl. PART-02 Switches,Plates & Acc. (M+L) | End | AC-First Fl. PART-03 | 0 | 0
AC-First Fl. PART-03 Wiring (M+L) | End | AC-First Fl. PART-03 Electrical Work | 0 | 0
AC-First Fl. PART-03 Electrical Work | End | AC-First Fl. PART-03 Slab conduiting (M+L) | 0 | 0
AC-First Fl. PART-03 Slab conduiting (M+L) | End | AC-First Fl. PART-03 Wall Conduiting/Dropping | 0 | 0
AC-First Fl. PART-03 | End | AC-First Fl. PART-03 Wiring (M+L) | 0 | 0
AC-Terrace PART-01 Wall Conduiting/Dropping | Start | AC-Terrace PART-01 Switches,Plates & Acc. (M+L) | 0 | 0
P1W1- Eight Floor Balcony Tiling (Lab) | Start | AC-Terrace PART-01 Wall Conduiting/Dropping | 0 | 0
AC-Terrace PART-01 Switches,Plates & Acc. (M+L) | Start | AC-Terrace PART-02 | 0 | 0
AC-Terrace PART-02 Wiring (M+L) | Start | AC-Terrace PART-02 Electrical Work | 0 | 0
AC-Terrace PART-02 Electrical Work | Start | AC-Terrace PART-02 Slab conduiting (M+L) | 0 | 0
AC-Terrace PART-02 Wall Conduiting/Dropping | Start | AC-Terrace PART-02 Switches,Plates & Acc. (M+L) | 0 | 0
AC-Terrace PART-02 Slab conduiting (M+L) | Start | AC-Terrace PART-02 Wall Conduiting/Dropping | 0 | 0
AC-Terrace PART-02 | Start | AC-Terrace PART-02 Wiring (M+L) | 0 | 0
AC-Terrace PART-02 Switches,Plates & Acc. (M+L) | Start | AC-Terrace PART-03 | 0 | 0
AC-Terrace PART-03 Wiring (M+L) | Start | AC-Terrace PART-03 Electrical Work | 0 | 0
P1W1- Third Floor Granite Window Cill(M+L)(SLK) | Start | AC-Terrace PART-03 M.S. Door Frame | 0 | 0
AC-Terrace PART-03 | Start | AC-Terrace PART-03 Wiring (M+L) | 0 | 0
AC-Terrace PART-03 M.S. Door Frame | End | AC-Terrace PART-03 Wooden Door Frame | 0 | 0
B1 4th Flr-Toilet Flr.&Dado Master T-4bh | End | B1 4th Flr-Toilet Flr.&Dado Children T-4 | 0 | 0
B1 4th Flr-Toilet Flr.&Dado Master T-4bh | End | B1 4th Flr-Toilet Flr.&Dado ChildrenT-3b | 0 | 0
B1 4th Flr-Toilet Flr.&Dado Powder T-3bh | Start | B1 4th Flr-Toilet Flr.&Dado Master T-4bh | 0 | 0
B1 Bldg BBM Work-Parking Flr. BBM 6" Thk | Start | B1 Bldg BBM Work-Parking Flr. BBM 8" Thk | 2 | 0
Dec-15 Labour Liasioning | End | B1- Flat 501 | 0 | 0
B1 4th Flr-Toilet Flr.&Dado Master T-4bh | End | B2 1st Flr-Toilet Flr.&Dado | 0 | 0
C2 Window Sill-12" wide | End | Barracation | 0 | 0
Nov-15 Labour Liasioning | Start | Barracation Barrication work (Base line) | 0 | 0
1st Floor | Start | Brickwork & Plaster. Brickwork of 1st floor | 0 | 0
2nd Floor | Start | Brickwork & Plaster. Brickwork of 2nd floor | 0 | 0
C2 Dado Toilet Dado Fixing | Start | C2 Dado Kitchen | 0 | 0
C2 Dado Kitchen | Start | C2 Dado Kitchen Dado Fixing | 0 | 0
C2 Teracotta Tiling Riser with Groove & Chamfer edge polish | Start | C2 Dado Toilet | 0 | 0
C2 Teracotta Tiling Riser with Groove & Chamfer edge polish | End | C2 Dado Toilet | 0 | 0
C2 Dado Toilet | End | C2 Dado Toilet Dado Fixing | 0 | 0
C2 Dado Toilet | Start | C2 Dado Toilet Dado Fixing | 0 | 0
C2 Door-.900mX2.450m Door fittings | Start | C2 Door-.900mX2.450m | 0 | 0
C2 Door-.925mX2.450m | Start | C2 Door-.900mX2.450m Door fittings | 0 | 0
C2 Door-.925mX2.450m Door fittings | Start | C2 Door-.925mX2.450m | 0 | 0
C2 Folding Door-2.4mX2.75m | Start | C2 Door-.925mX2.450m Door fittings | 0 | 0
P1W1- Third Floor Electrical Room | End | C2 Excavation | 0 | 0
RCC | End | C2 FF Column | 0 | 0
C2 Folding Door-2.4mX2.75m FD1 | Start | C2 Folding Door-2.4mX2.75m | 0 | 0
Windows/Railing | Start | C2 Folding Door-2.4mX2.75m FD1 | 0 | 0
C2 RCC | Start | C2 Footing | 0 | 0
C2 Footing Shuttering for Footing | Start | C2 Footing Conrete pouring for Footing | 0 | 0
C2 Footing | Start | C2 Footing RCC M20 old | 0 | 0
C2 Footing RCC M20 old | Start | C2 Footing Shuttering for Footing | 0 | 0
W1- First Floor Main Lobby | Start | C2 Footing Shuttering for Footing | 0 | 0
C2 Footing Conrete pouring for Footing | Start | C2 Footing Steel | 0 | 0
P1W1- Seventh Floor Main Stair Granite Tread(SLK) | Start | C2 GF Beam+Slab+Staircase Steel | 0 | 0
C2 Guest Toilet | End | C2 GF Hackaid Hackaid Plast | 0 | 0
A1- 14th Fl Railing- Master Bed (M+L) | Start | C2 GF Steel Labour Steel Labour | 0 | 0
C2 Vittrified Tile Skirting Skirting | End | C2 Granite /Marble Skirting | 0 | 0
C2 Granite /Marble Skirting | End | C2 Granite /Marble Skirting Marble/Granite | 0 | 0
C2 Vitrified Flooring for Toilet Riser with Groove & Chamfer | Start | C2 Granite/Marble Flooring | 0 | 0
P1W1- Second Floor Balcony Balcony Flooring(SLK) | End | C2 Granite/Marble Flooring | 7 | 0
C2 Granite/Marble Flooring | Start | C2 Granite/Marble Flooring Flooring (N/A) | 0 | 0
C2 Granite/Marble Flooring | End | C2 Granite/Marble Flooring Flooring (N/A) | 0 | 0
C2 Water body E 503 10 x10 mm | Start | C2 Guest Toilet PVC | 0 | 0
C2 Guest Toilet PVC | Start | C2 Guest Toilet Sanitary (kOL) | 0 | 0
C2 Door-.900mX2.450m | Start | C2 Internal-.975mX2.45m Door fittings | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 | Start | C2 Labour Plumbing | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 PT Slab/ Beam | End | C2 Labour Plumbing | 0 | 0
P2W2-Above Terrace Slab+Stair | End | C2 M.Bed Toilet | 0 | 0
C2 Plinth Masonary 18" Thk.BBM- | Start | C2 PCC 4" thk.PCC M15 | 0 | 0
C2 Plinth Column Steel | Start | C2 Plinth Beam | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 | Start | C2 Plinth Beam | 0 | 0
C2 Servants Toilet PVC | End | C2 Plinth Beam Concrete pouring for Slab | 0 | 0
C2 Plinth Beam Concrete pouring for Slab | End | C2 Plinth Beam Steel | 0 | 0
C2 Footing Steel | Start | C2 Plinth Column | 0 | 0
C2 Plinth Column Shuttering for column | Start | C2 Plinth Column Concrete pouring for column | 0 | 0
C2 Plinth Column | Start | C2 Plinth Column RCC M20 old | 0 | 0
C2 Plinth Column RCC M20 old | Start | C2 Plinth Column Shuttering for column | 0 | 0
C2 Plinth Column Concrete pouring for column | Start | C2 Plinth Column Steel | 0 | 0
P1W1- Seventh Floor Main Stair Granite Tread(SLK) | Start | C2 Railing -Terraces | 0 | 0
C2 PCC 4" thk.PCC M15 | Start | C2 RCC | 0 | 0
P1W1- Fourth Floor Wooden patti fixing to sink (Lab) | End | C2 Servant Toilet | 0 | 0
C2 Servant Toilet | End | C2 Servant Toilet GI Pipes & Fittings | 0 | 0
C2 Servant Toilet GI Pipes & Fittings | End | C2 Servant Toilet Misc. | 0 | 0
C2 Guest Toilet Sanitary (kOL) | Start | C2 Servants Toilet | 0 | 0
Screen wall RCC M-20 | End | C2 Staircase Flooring (N/A) | 0 | 0
C2 Granite /Marble Skirting Marble/Granite | End | C2 Teracotta skirting | 0 | 0
C2 Teracotta skirting | End | C2 Teracotta skirting Skirting | 0 | 0
C2 Granite/Marble Flooring Flooring (N/A) | Start | C2 Teracotta Tiling | 0 | 0
C2 Granite/Marble Flooring Flooring (N/A) | End | C2 Teracotta Tiling | 0 | 0
C2 Teracotta Tiling | Start | C2 Teracotta Tiling Riser with Groove & Chamfer edge polish | 0 | 0
C2 Teracotta Tiling | End | C2 Teracotta Tiling Riser with Groove & Chamfer edge polish | 0 | 0
C2 Terrace Column Concrete pouring for column | End | C2 Terrace Column Shuttering for column | 0 | 0
C2 Plinth Beam Steel | End | C2 Terrace Column Steel | 0 | 0
C2 Terrace Column Shuttering for column | End | C2 Terrace Column Steel | 0 | 0
Plastering | End | C2 Terrace Internal | 0 | 0
C2 Terrace Internal | End | C2 Terrace Internal Tar Plaster | 0 | 0
C2 Terrace Steel Labour Steel Labour | End | C2 Terrace Masonry | 0 | 0
C2 Terrace Masonry | End | C2 Terrace Masonry BBM 6" Thk. | 0 | 0
C2 Terrace Column Steel | End | C2 Terrace Steel Labour | 0 | 0
C2 Terrace Steel Labour | End | C2 Terrace Steel Labour Steel Labour | 0 | 0
C2 Guest Toilet Sanitary (kOL) | Start | C2 Vitrified Flooring for Toilet | 0 | 0
C2 Staircase Flooring (N/A) | End | C2 Vittrified Tile Skirting | 0 | 0
C2 Vittrified Tile Skirting | End | C2 Vittrified Tile Skirting Skirting | 0 | 0
P1W1- Gr. Fl. Fire Stair Granite Flooring(SLK) | Start | C2 Water body | 0 | 0
C2 Dado Kitchen Dado Fixing | Start | C2 Water body | 0 | 0
C2 Water body | End | C2 Water body E 503 10 x10 mm | 0 | 0
C2 Water body | Start | C2 Water body E 503 10 x10 mm | 0 | 0
P1W1- Eight Floor Parking RMC M-20 Site | End | C2 Water body E 708 15 x15 mm | 0 | 0
C2 Water body E 503 10 x10 mm | End | C2 Water body E227 20 x20 mm | 0 | 0
C2 Water body E227 20 x20 mm | End | C2 Water body E501 20 x20 mm | 0 | 0
C2 Water body E501 20 x20 mm | End | C2 Water body E801 20 x20 mm | 0 | 0
C2 Water body E801 20 x20 mm | End | C2 Water body F 130 20 x20 mm | 0 | 0
P1W1- Fifth Floor Granite WHB Counter(M+L)(SLK) | End | C2 Water Froofing | 0 | 0
C2 Windows UPVC Sliding Window+mosquito net | Start | C2 Windows | 0 | 0
C2 Railing -Terraces | Start | C2 Windows Elevational Glazing | 0 | 0
C2 Windows Elevational Glazing | Start | C2 Windows UPVC Sliding Window+mosquito net | 0 | 0
Down comer system Air releasing valves 25mm dia (C) | End | C2 Windows UPVC Sliding Window+mosquito net | 0 | 0
P2W2- 8TH Lintel/Chajja Shuttering (Lab) | End | Down comer system Air releasing valves 25mm dia (C) | 0 | 0
Down comer system MS angle support (C) | End | Down comer system Butter fly valves 100mm dia (C) | 0 | 0
Down comer system Butter fly valves 100mm dia (C) | End | Down comer system Butter fly valves 80mm dia (C) | 0 | 0
P1W1- Eight Floor Electrical Room RMC M20 Plant/Production(C | End | Down comer system Enamel paint (hydrant paint) (C) | 0 | 0
P2W2-8TH Slab+Stair POUR-03 PT Slab/ Beam | End | Down comer system Fire brigade inlet (C) | 0 | 0
Down comer system Head booster pump 900LPM 35mtrs(C) | End | Down comer system Head booster pump 450LPM 35mtrs(C) | 0 | 0
Down comer system Air releasing valves 25mm dia (C) | End | Down comer system Head booster pump 900LPM 35mtrs(C) | 0 | 0
Down comer system Weather proof type MPCB box (C) | End | Down comer system Instrumentation board (C) | 0 | 0
Down comer system Pressure switches (C) | End | Down comer system MS angle support (C) | 0 | 0
Down comer system Non return valve 80 mm dia (C) | End | Down comer system MV cables 2C x 1.5 Sq.mm (C) | 0 | 0
Down comer system MV cables 2C x 1.5 Sq.mm (C) | End | Down comer system MV cables 4C x 6 Sq.mm (C) | 0 | 0
Down comer system Butter fly valves 80mm dia (C) | End | Down comer system Non return valve 80 mm dia (C) | 0 | 0
Down comer system Instrumentation board (C) | End | Down comer system Pressure switches (C) | 0 | 0
Down comer system Head booster pump 450LPM 35mtrs(C) | End | Down comer system Weather proof type MPCB box (C) | 0 | 0
P1W1- Eight Floor Parking RMC M20 Plant/Production(C) | End | Down comer system Y type strainer of 100mm dia (C) | 0 | 0
Brickwork & Plaster. | Start | External Plaster External Plaster | 0 | 0
LABOUR WORK - NOT IN USE ON INSTALLATION 100% | End | FIRE DOORS (M+L) | 0 | 0
FIRE DOORS (M+L) 03 HANDING OVER -15% | End | FIRE DOORS (M+L) 01 MATERIAL AT SITE - 55% | 0 | 0
FIRE DOORS (M+L) 01 MATERIAL AT SITE - 55% | End | FIRE DOORS (M+L) 02 INSTALLATION - 30% | 0 | 0
FIRE DOORS (M+L) | End | FIRE DOORS (M+L) 03 HANDING OVER -15% | 0 | 0
C2 Teracotta skirting Skirting | End | First Floor | 0 | 0
UPTO PLINTH | Start | FIRST SLAB RCC M30 | 0 | 0
P2W2- 8TH Lintel/Chajja Shuttering (Lab) | End | Flower bed 1632 rft Cladding | 0 | 0
Footing RCC Column M20 | Start | Footing RCC slab & beam M20 | 0 | 0
P2W2-Column+Lift(Sixth Fl.) Steel (Lab) | End | Fountain Back Filling (Lab) | 0 | 0
P2W2-Above Terrace Slab+Stair | End | Fountain RMC M-20 Plant /Production | 0 | 0
P2W2-8TH Slab+Stair POUR-03 | End | Fountain RMC M-20 Site | 0 | 0
K_Residency 00 SAKARIYA finishing | Start | K_Residency 00 SAKARIYA finishing | 0 | 0
K_Residency 00 SAKARIYA finishing | Start | K_Residency RCC_Rgv | 1 | 0
Labour for Carpentry Main Doors | Start | Labour for Carpentry Bedroom Doors | 0 | 0
A 1st floor Doors Main | Start | Labour for Carpentry Main Doors | 0 | 0
Labour for Carpentry Toilet & Dry Balcon | Start | Labour for Carpentry Micellaneous-Door | 0 | 0
Labour for Carpentry Bedroom Doors | Start | Labour for Carpentry Toilet & Dry Balcon | 0 | 0
A1 FIRE DOORS | End | LABOUR WORK - NOT IN USE | 0 | 0
LABOUR WORK - NOT IN USE | End | LABOUR WORK - NOT IN USE ON INSTALLATION 100% | 0 | 0
A Bldg Painting - 1 Job | Start | Mat.+Lab. External Painting | 2 | 0
Mat.+Lab. Internal Painting | Start | Mat.+Lab. Int+Ext Painting | 2 | 0
A Bldg Labour Elevation, Chajja | Start | Mat.+Lab. Internal Painting | 2 | 0
P1W1- Sixth Floor | End | P1W1- 3rd Fl. Attached Terrace | 0 | 0
P1W1- Gr. Fl. Balcony Balcony Flooring(SLK) | End | P1W1- 3rd Fl. Attached Terrace Box type W/P ( Lab.) | 0 | 0
P1W1- Sixth Floor AAC Block masonry 6"(SLK) | End | P1W1- 3rd Fl. Attached Terrace Chemical W/P | 0 | 0
P1W1- Sixth Floor AAC Block masonry 8"(SLK) | End | P1W1- 3rd Fl. Attached Terrace Screed W/P (SLK) | 0 | 0
P1W1- Basement AAC Block Masonry 4"(SLK) | End | P1W1- 3rd Fl.Curve Balcony | 0 | 0
P1W1- Fifth Floor | End | P1W1- 3rd Fl.Curve Balcony Box type W/P ( Lab.) | 0 | 0
P1W1- Fourth Floor 4" thk concrete block masonry(Lab-C) | End | P1W1- 3rd Fl.Curve Balcony Chemical W/P | 0 | 0
P1W1- Fourth Floor AAC Block Masonry 4"(SLK) | End | P1W1- 3rd Fl.Curve Balcony Screed W/P (SLK) | 0 | 0
C2 Terrace Column Shuttering for column | End | P1W1- 3rd Fl.Curve Planter Area Box type W/P ( Lab.) | 0 | 0
C2 Terrace Column Concrete pouring for column | End | P1W1- 3rd Fl.Curve Planter Area Screed W/P (SLK) | 0 | 0
P1W1- Fifth Floor AAC Block masonry 6"(SLK) | End | P1W1- 3rd Fl.Toilet | 0 | 0
P1W1- Fifth Floor AAC Block Masonry 4"(SLK) | End | P1W1- 3rd Fl.Toilet Box type W/P ( Lab.) | 0 | 0
P1W1- Fifth Floor AAC Block masonry 8"(SLK) | End | P1W1- 3rd Fl.Toilet Chemical W/P | 0 | 0
P1W1- Fifth Floor 4" thk concrete block masonry(Lab-C) | End | P1W1- 3rd Fl.Toilet Toilet w/p (SLK) | 0 | 0
Plastering | End | P1W1- 4th Fl.Curve Balcony | 0 | 0
C2 Terrace Steel Labour | End | P1W1- 4th Fl.Kitchen | 0 | 0
C2 Terrace Masonry BBM 6" Thk. | End | P1W1- 4th Fl.Kitchen Box type W/P ( Lab.) | 0 | 0
C2 Terrace Steel Labour Steel Labour | End | P1W1- 4th Fl.Kitchen Chemical W/P | 0 | 0
C2 Terrace Masonry | End | P1W1- 4th Fl.Kitchen Screed W/P (SLK) | 0 | 0
C2 Terrace Internal | End | P1W1- 4th Fl.Toilet Chemical W/P | 0 | 0
P1W1- Seventh Floor Marino Partition(M+L) | End | P1W1- Above Terrace | 0 | 0
P1W1- Above Terrace Toilet Door Fittings(C) | End | P1W1- Above Terrace Door Misc. | 0 | 0
P1W1- Above Terrace Toilet Door Shutter(C) | End | P1W1- Above Terrace Main Door Fittings(C) | 0 | 0
P1W1- Above Terrace | End | P1W1- Above Terrace Main Door Shutter(C) | 0 | 0
P1W1- Above Terrace Main Door Fittings(C) | End | P1W1- Above Terrace Marino Partition(M+L) | 0 | 0
P1W1- Above Terrace Main Door Fittings(C) | End | P1W1- Above Terrace Toilet Door Fittings(C) | 0 | 0
P1W1- Above Terrace Main Door Shutter(C) | End | P1W1- Above Terrace Toilet Door Shutter(C) | 0 | 0
P1W1- Seventh Floor Service Lift Cladding Granite Cladding ( | End | P1W1- Eight Floor Balcony | 0 | 0
P1W1- Seventh Floor Service Lift Cladding Tiling (Lab) | End | P1W1- Eight Floor Balcony Balcony Flooring(SLK) | 0 | 0
P1W1-Seventh Floor Ramp | End | P1W1- Eight Floor Balcony Balcony Skirting(SLK) | 0 | 0
P1W1-Seventh Floor Ramp Granite Flooring(SLK) | End | P1W1- Eight Floor Balcony Tiling (Lab) | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 RMC M-40 PT Site | End | P1W1- Eight Floor Electrical Room | 0 | 0
P1W1- Eight Floor Electrical Room | End | P1W1- Eight Floor Electrical Room RMC M20 Plant/Production(C | 0 | 0
P1W1- Seventh Floor Fire Stair Granite Tread(SLK) | End | P1W1- Eight Floor Main Lift Cladding Tiling (Lab) | 0 | 0
P1W1- Seventh Floor Electrical Room RMC M-20 Site | End | P1W1- Eight Floor Main Stair Granite Riser (SLK) | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 PT Slab/ Beam | Start | P1W1- Eight Floor Pantry | 0 | 0
Down comer system Enamel paint (hydrant paint) (C) | End | P1W1- Eight Floor Pantry Pantry Dado (SLK) | 0 | 0
P1W1- Third Floor Granite Window Cill(M+L)(SLK) | Start | P1W1- Eight Floor Parking | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 RMC M40 Plant/Production | Start | P1W1- Eight Floor Parking Epoxy Flooring | 0 | 0
C2 Plinth Beam | Start | P1W1- Eight Floor Parking Epoxy Flooring | 0 | 0
A1- 14th Fl Railing- Master Bed (M+L) | Start | P1W1- Eight Floor Parking RMC M-20 Site | 0 | 0
P1W1- Eight Floor Parking RMC M-20 Site | Start | P1W1- Eight Floor Parking RMC M20 Outsource | 0 | 0
P1W1- Eight Floor Parking | End | P1W1- Eight Floor Parking RMC M20 Plant/Production(C) | 0 | 0
P1W1- Seventh Floor Fire Stair Granite Skirting (SLK) | End | P1W1- Eight Floor Service Lift Cladding | 0 | 0
P1W1- Seventh Floor Fire Stair Tiling (Lab) | End | P1W1- Eight Floor Service Lift Cladding Granite Cladding (SL | 0 | 0
P1W1- Seventh Floor Lift Cladding | End | P1W1- Eight Floor Service Lift Cladding Tiling (Lab) | 0 | 0
P1W1- Third Floor Marino Partition(M+L) | End | P1W1- Eight Floor Toilet | 0 | 0
P2W2-Left Side Part-1 External Plaster(SLK) | End | P1W1- Eight Floor Toilet | 0 | 0
P1W1- Eight Floor Toilet | End | P1W1- Eight Floor Toilet Toilet Dado (SLK) | 0 | 0
P1W1- Eight Floor Toilet Toilet Dado (SLK) | End | P1W1- Eight Floor Toilet Toilet Flooring (SLK) | 0 | 0
P1W1- Gr. Fl. Electrical Room RMC M-20 Site | Start | P1W1- Fifth Fl. wall OBD Paint (M+L) | 0 | 0
P1W1- Fourth Floor Marino Partition(M+L) | End | P1W1- Fifth Floor | 0 | 0
P1W1- Fifth Floor Toilet Door Fittings(C) | End | P1W1- Fifth Floor Door Misc. | 0 | 0
P1W1- Fifth Floor Electrical Room RMC M20 Plant/Production(C | Start | P1W1- Fifth Floor Electrical Room | 0 | 0
C2 Footing Shuttering for Footing | Start | P1W1- Fifth Floor Electrical Room RMC M20 Plant/Production(C | 0 | 0
P1W1- Fifth Floor Toilet Door Shutter(C) | End | P1W1- Fifth Floor Main Door Fittings(C) | 0 | 0
P1W1- Fifth Floor | End | P1W1- Fifth Floor Main Door Shutter(C) | 0 | 0
P1W1- Fifth Floor Door Misc. | End | P1W1- Fifth Floor Marino Partition(M+L) | 0 | 0
P1W1- Gr. Fl. Electrical Room RMC M-20 Site | Start | P1W1- Fifth Floor Pantry Pantry Dado (SLK) | 21 | 0
P1W1- Fifth Floor Pantry Pantry Dado (SLK) | End | P1W1- Fifth Floor Pantry Tiling (Lab) | 2 | 0
P1W1- Fifth Floor Main Door Fittings(C) | End | P1W1- Fifth Floor Toilet Door Fittings(C) | 0 | 0
P1W1- Fifth Floor Main Door Shutter(C) | End | P1W1- Fifth Floor Toilet Door Shutter(C) | 0 | 0
P1W1- Ground Fl. Granite Window Cill(M+L)(SLK) | End | P1W1- First Floor | 0 | 0
P1W1- GLAZED DOOR | End | P1W1- First Floor | 0 | 0
P1W1- Ground Fl. | End | P1W1- First Floor Glass door(M+L) | 0 | 0
P1W1- First Floor | End | P1W1- First Floor Granite Kitchen Otta(M+L)(SLK) | 0 | 0
P1W1- First Floor Umbra Patti (M+L) | End | P1W1- First Floor Granite Ledge wall(M+L)(SLK) | 0 | 0
P1W1- First Floor Wooden patti fixing to sink (Lab) | End | P1W1- First Floor Granite Urinal partition (M+L) | 0 | 0
P1W1- First Floor Granite Ledge wall(M+L)(SLK) | End | P1W1- First Floor Granite WHB Counter(M+L)(SLK) | 0 | 0
P1W1- First Floor Granite WHB Counter(M+L)(SLK) | End | P1W1- First Floor Granite Window Cill(M+L)(SLK) | 0 | 0
P1W1- First Floor Granite Urinal partition (M+L) | End | P1W1- First Floor Umbra Patti (M+L) | 0 | 0
P1W1- First Floor Granite Kitchen Otta(M+L)(SLK) | End | P1W1- First Floor Wooden patti fixing to sink (Lab) | 0 | 0
P1W1- Third Floor Marino Partition(M+L) | End | P1W1- Fourth Floor | 0 | 0
C2 Terrace Column Steel | End | P1W1- Fourth Floor | 0 | 0
P1W1- Fourth Floor Toilet Door Fittings(C) | End | P1W1- Fourth Floor Door Misc. | 0 | 0
A1- Flat 302 Putty Plaster | End | P1W1- Fourth Floor Fire Stair | 0 | 0
C2 Servants Toilet PVC | End | P1W1- Fourth Floor Granite Ledge wall(M+L)(SLK) | 0 | 0
P1W1- Fourth Floor Toilet Door Shutter(C) | End | P1W1- Fourth Floor Main Door Fittings(C) | 0 | 0
P1W1- Fourth Floor | End | P1W1- Fourth Floor Main Door Shutter(C) | 0 | 0
P1W1- Fourth Floor Door Misc. | End | P1W1- Fourth Floor Marino Partition(M+L) | 0 | 0
P1W1- Fourth Floor Main Door Fittings(C) | End | P1W1- Fourth Floor Toilet Door Fittings(C) | 0 | 0
P1W1- Fourth Floor Main Door Shutter(C) | End | P1W1- Fourth Floor Toilet Door Shutter(C) | 0 | 0
C2 Terrace Internal Tar Plaster | End | P1W1- Fourth Floor Wooden patti fixing to sink (Lab) | 0 | 0
AC-3rd Fl. PART-04 Switches,Plates & Acc. (M+L) | End | P1W1- Gl.Fl Service Lift Cladding | 2 | 0
AC-3rd Fl. PART-04 Switches,Plates & Acc. (M+L) | End | P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | 0 | 0
P1W1- Gl.Fl Service Lift Cladding | Start | P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | 0 | 0
P1W1- Gl.Fl Service Lift Cladding Granite Cladding (SLK) | End | P1W1- Gl.Fl Service Lift Cladding Tiling (Lab) | 0 | 0
P1W1- Above Terrace Marino Partition(M+L) | End | P1W1- GLAZED DOOR | 0 | 0
AC-3rd Fl. PART-05 Wiring (M+L) | End | P1W1- Gr. Fl. Balcony | 0 | 0
P1W1- Gr.Fl.Ramp Tiling (Lab) | Start | P1W1- Gr. Fl. Balcony | 0 | 0
P1W1- Gr. Fl. Balcony | End | P1W1- Gr. Fl. Balcony Balcony Flooring(SLK) | 0 | 0
AC-3rd Fl. PART-05 Electrical Work | End | P1W1- Gr. Fl. Balcony Balcony Skirting(SLK) | 2 | 0
AC-3rd Fl. PART-05 Electrical Work | End | P1W1- Gr. Fl. Balcony Tiling (Lab) | 0 | 0
P1W1- Gr. Fl. Balcony Balcony Skirting(SLK) | Start | P1W1- Gr. Fl. Balcony Tiling (Lab) | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | P1W1- Gr. Fl. Electrical Room | 0 | 0
P1W1- First Floor | End | P1W1- Gr. Fl. Electrical Room RMC M-20 Site | 7 | 0
A1-Flat 404 Tile (M+L) | End | P1W1- Gr. Fl. Electrical Room RMC M-20 Site | 2 | 0
A1- Flat 103 Gypsum plaster incl NOC (M+L) | Start | P1W1- Gr. Fl. Electrical Room RMC M20 Outsource | 0 | 0
AC-3rd Fl. PART-06 Wall Conduiting/Dropping | Start | P1W1- Gr. Fl. Electrical Room RMC M20 Plant/Production(C) | 0 | 0
P1W1- Gr. Fl. Fire Stair Granite Tread(SLK) | End | P1W1- Gr. Fl. Fire Stair Granite Flooring(SLK) | 0 | 0
P1W1- Gr. Fl. Fire Stair | Start | P1W1- Gr. Fl. Fire Stair Granite Flooring(SLK) | 0 | 0
P1W1- Gr. Fl. Fire Stair Granite Flooring(SLK) | End | P1W1- Gr. Fl. Fire Stair Granite Riser (SLK) | 0 | 0
C2 Water body | Start | P1W1- Gr. Fl. Fire Stair Granite Skirting (SLK) | 0 | 0
AC-3rd Fl. PART-04 Slab conduiting (M+L) | End | P1W1- Gr. Fl. Fire Stair Tiling (Lab) | 0 | 0
P1W1- Gr. Fl. Parking Tiling (Lab) | End | P1W1- Gr. Fl. Main Entrance | 0 | 0
AC-3rd Fl. PART-06 | End | P1W1- Gr. Fl. Main Entrance Granite Flooring(SLK) | 2 | 0
AC-3rd Fl. PART-06 | End | P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | 0 | 0
P1W1- Gr. Fl. Main Entrance Granite Flooring(SLK) | Start | P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | 0 | 0
P1W1- Gr. Fl. Main Entrance Granite Skirting (SLK) | End | P1W1- Gr. Fl. Main Entrance Tiling (Lab) | 0 | 0
P1W1- Gr. Fl. Balcony Tiling (Lab) | End | P1W1- Gr. Fl. Parking | 0 | 0
AC-3rd Fl. PART-05 Switches,Plates & Acc. (M+L) | End | P1W1- Gr. Fl. Parking Epoxy Flooring | 2 | 0
AC-3rd Fl. PART-05 Wall Conduiting/Dropping | End | P1W1- Gr. Fl. Parking RMC M-20 Site | 2 | 0
AC-3rd Fl. PART-05 Wall Conduiting/Dropping | End | P1W1- Gr. Fl. Parking RMC M20 Outsource | 0 | 0
P1W1- Gr. Fl. Parking RMC M-20 Site | Start | P1W1- Gr. Fl. Parking RMC M20 Outsource | 0 | 0
AC-3rd Fl. PART-05 Switches,Plates & Acc. (M+L) | End | P1W1- Gr. Fl. Parking Tiling (Lab) | 0 | 0
P1W1- Gr. Fl. Parking Epoxy Flooring | Start | P1W1- Gr. Fl. Parking Tiling (Lab) | 0 | 0
P1W1- Gr. Fl. Parking RMC M20 Outsource | End | P1W1- Gr. Fl. Parking Vaccum Dewatering | 0 | 0
AC-3rd Fl. PART-04 Slab conduiting (M+L) | End | P1W1- Gr.Fl. Lift Cladding | 0 | 0
P1W1- Gr.Fl. Lift Cladding | End | P1W1- Gr.Fl. Main Lift Cladding | 0 | 0
AC-3rd Fl. PART-04 Wall Conduiting/Dropping | End | P1W1- Gr.Fl. Main Lift Cladding Granite Cladding (SLK) | 0 | 0
AC-3rd Fl. PART-04 Wall Conduiting/Dropping | End | P1W1- Gr.Fl. Main Lift Cladding Tiling (Lab) | 0 | 0
P1W1- Gr.Fl. Main Lift Cladding Granite Cladding (SLK) | Start | P1W1- Gr.Fl. Main Lift Cladding Tiling (Lab) | 0 | 0
P1W1- Gr.Fl. Toilet Tiling (Lab) | Start | P1W1- Gr.Fl. Pantry | 0 | 0
AC-3rd Fl. PART-06 Electrical Work | End | P1W1- Gr.Fl. Pantry | 0 | 0
AC-3rd Fl. PART-06 Slab conduiting (M+L) | End | P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | 0 | 0
P1W1- Gr.Fl. Pantry Vitrified Skirting(SLK) | Start | P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | End | P1W1- Gr.Fl. Pantry Tiling (Lab) | 0 | 0
P1W1- Gr.Fl. Pantry | End | P1W1- Gr.Fl. Pantry Vitrified Flooring(SLK) | 0 | 0
AC-3rd Fl. PART-06 Slab conduiting (M+L) | End | P1W1- Gr.Fl. Pantry Vitrified Skirting(SLK) | 0 | 0
AC-3rd Fl. PART-06 Wiring (M+L) | End | P1W1- Gr.Fl. Toilet | 2 | 0
AC-3rd Fl. PART-06 Electrical Work | End | P1W1- Gr.Fl. Toilet Tiling (Lab) | 0 | 0
P1W1- Gr.Fl. Toilet | Start | P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | 0 | 0
P1W1- Gr.Fl. Toilet Toilet Dado (SLK) | End | P1W1- Gr.Fl. Toilet Toilet Flooring (SLK) | 0 | 0
AC-3rd Fl. PART-05 | End | P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | 0 | 0
P1W1- Gr.Fl.Ramp | Start | P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | 0 | 0
P1W1- Gr.Fl.Ramp Granite Flooring(SLK) | End | P1W1- Gr.Fl.Ramp Granite Skirting (SLK) | 0 | 0
AC-3rd Fl. PART-05 Wiring (M+L) | End | P1W1- Gr.Fl.Ramp Tiling (Lab) | 2 | 0
P1W1- ROLLING SHUTTER | End | P1W1- Ground Fl. | 0 | 0
P1W1- ROLLING SHUTTER Rolling shutter-C | End | P1W1- Ground Fl. Glass door(M+L) | 0 | 0
P1W1- Third Floor Marino Partition(M+L) | Start | P1W1- Ground Fl. Granite WHB Counter(M+L)(SLK) | 0 | 0
A1- Flat 504 Melamine Polish (M+L) | Start | P1W1- Ground Fl. Granite WHB Counter(M+L)(SLK) | 0 | 0
P1W1- Ground Fl. Granite WHB Counter(M+L)(SLK) | End | P1W1- Ground Fl. Granite Window Cill(M+L)(SLK) | 0 | 0
P1W1- Above Terrace Toilet Door Fittings(C) | End | P1W1- ROLLING SHUTTER | 0 | 0
P1W1- Above Terrace Door Misc. | End | P1W1- ROLLING SHUTTER Rolling shutter-C | 0 | 0
P1W1- First Floor Granite Window Cill(M+L)(SLK) | End | P1W1- Second Floor | 0 | 0
P1W1- Gr. Fl. Electrical Room RMC M20 Outsource | End | P1W1- Second Floor Balcony Balcony Flooring(SLK) | 0 | 0
P1W1- Second Floor | End | P1W1- Second Floor Granite Kitchen Otta(M+L)(SLK) | 0 | 0
P1W1- Sixth Floor Marino Partition(M+L) | End | P1W1- Seventh Floor | 0 | 0
P1W1- Seventh Floor Toilet Door Fittings(C) | End | P1W1- Seventh Floor Door Misc. | 0 | 0
P1W1- Seventh Floor Toilet Toilet Dado (SLK) | End | P1W1- Seventh Floor Electrical Room RMC M-20 Site | 0 | 0
Screen wall RCC M-20 | End | P1W1- Seventh Floor Fire Stair Granite Skirting (SLK) | 0 | 0
Flower bed 1632 rft Cladding | End | P1W1- Seventh Floor Fire Stair Granite Tread(SLK) | 0 | 0
C2 Staircase Flooring (N/A) | End | P1W1- Seventh Floor Fire Stair Tiling (Lab) | 0 | 0
C2 Vittrified Tile Skirting | End | P1W1- Seventh Floor Lift Cladding | 0 | 0
P1W1- Seventh Floor Toilet Door Shutter(C) | End | P1W1- Seventh Floor Main Door Fittings(C) | 0 | 0
P1W1- Seventh Floor | End | P1W1- Seventh Floor Main Door Shutter(C) | 0 | 0
C2 Vittrified Tile Skirting Skirting | End | P1W1- Seventh Floor Main Lift Cladding | 0 | 0
C2 Granite /Marble Skirting | End | P1W1- Seventh Floor Main Lift Cladding Granite Cladding (SLK | 0 | 0
C2 Granite /Marble Skirting Marble/Granite | End | P1W1- Seventh Floor Main Lift Cladding Tiling (Lab) | 0 | 0
AC-2nd Fl. PART-02 Electrical Work | Start | P1W1- Seventh Floor Main Stair Granite Tread(SLK) | 0 | 0
P1W1- Seventh Floor Door Misc. | End | P1W1- Seventh Floor Marino Partition(M+L) | 0 | 0
C2 Teracotta skirting | End | P1W1- Seventh Floor Service Lift Cladding | 0 | 0
C2 Teracotta skirting Skirting | End | P1W1- Seventh Floor Service Lift Cladding Granite Cladding ( | 0 | 0
First Floor | End | P1W1- Seventh Floor Service Lift Cladding Tiling (Lab) | 0 | 0
P1W1- Seventh Floor Main Door Fittings(C) | End | P1W1- Seventh Floor Toilet Door Fittings(C) | 0 | 0
P1W1- Seventh Floor Main Door Shutter(C) | End | P1W1- Seventh Floor Toilet Door Shutter(C) | 0 | 0
P2W2-Column+Lift Above Terrace RMC M50 (Out Source) | End | P1W1- Seventh Floor Toilet Toilet Dado (SLK) | 0 | 0
P1W1- Fifth Floor Marino Partition(M+L) | End | P1W1- Sixth Floor | 0 | 0
Site Office & Store Tar Plaster | End | P1W1- Sixth Floor | 0 | 0
P1W1- Sixth Floor Toilet Door Shutter(C) | End | P1W1- Sixth Floor Main Door Fittings(C) | 0 | 0
P1W1- Sixth Floor | End | P1W1- Sixth Floor Main Door Shutter(C) | 0 | 0
P1W1- Sixth Floor Door Misc. | End | P1W1- Sixth Floor Marino Partition(M+L) | 0 | 0
P1W1- Sixth Floor | End | P1W1- Sixth Floor Service Lift Cladding | 0 | 0
P1W1- Sixth Floor Main Door Fittings(C) | End | P1W1- Sixth Floor Toilet Door Fittings(C) | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 PT Slab/ Beam | End | P1W1- Sixth Floor Toilet Door Fittings(C) | 0 | 0
P1W1- Sixth Floor Main Door Shutter(C) | End | P1W1- Sixth Floor Toilet Door Shutter(C) | 0 | 0
P1W1- 2nd Fl.Curve Planter Area Box type W/P ( Lab.) | End | P1W1- Third Floor | 0 | 0
C2 Servants Toilet PVC | End | P1W1- Third Floor Electrical Room | 0 | 0
P1W1- Gr.Fl. Pantry Pantry Dado (SLK) | Start | P1W1- Third Floor Granite Window Cill(M+L)(SLK) | 0 | 0
C2 Dado Toilet Dado Fixing | End | P1W1- Third Floor Service Lift Cladding Granite Cladding (SL | 0 | 0
P1W1- Third Floor | End | P1W1-3rd Fl.Kitchen | 0 | 0
P1W1- Seventh Floor Main Lift Cladding | End | P1W1-Eight Floor Ramp | 0 | 0
P1W1- Seventh Floor Main Lift Cladding Granite Cladding (SLK | End | P1W1-Eight Floor Ramp Granite Flooring(SLK) | 0 | 0
P1W1- Seventh Floor Main Lift Cladding Tiling (Lab) | End | P1W1-Eight Floor Ramp Granite Skirting (SLK) | 0 | 0
P1W1- Seventh Floor Service Lift Cladding | End | P1W1-Eight Floor Ramp Tiling (Lab) | 0 | 0
P1W1-Gr.Fl Alu.Windows NOC | End | P1W1-Gr.Fl Alu.Windows Glass Shutter Fixing | 0 | 0
P1W1- Ground Fl. Granite WHB Counter(M+L)(SLK) | End | P1W1-Gr.Fl Alu.Windows NOC | 0 | 0
P1W1-Gr.Fl.Alu.Ventilator Material Recieved | End | P1W1-Gr.Fl.Alu.Louvers | 0 | 0
P1W1-Gr.Fl Alu.Windows NOC | End | P1W1-Gr.Fl.Alu.Louvers | 0 | 0
P1W1-Gr.Fl.Alu.Ventilator NOC | Start | P1W1-Gr.Fl.Alu.Louvers Glass Shutter Fixing | 0 | 0
P1W1-Gr.Fl Alu.Windows Glass Shutter Fixing | End | P1W1-Gr.Fl.Alu.Louvers Material Recieved | 0 | 0
P1W1-Gr.Fl.Alu.Louvers Material Recieved | Start | P1W1-Gr.Fl.Alu.Louvers NOC | 0 | 0
P1W1-Gr.Fl Alu.Windows Glass Shutter Fixing | End | P1W1-Gr.Fl.Alu.Ventilator | 0 | 0
P1W1- Ground Fl. Granite WHB Counter(M+L)(SLK) | End | P1W1-Gr.Fl.Alu.Ventilator Material Recieved | 0 | 0
P1W1-Gr.Fl Alu.Windows NOC | End | P1W1-Gr.Fl.Alu.Ventilator Material Recieved | 0 | 0
P1W1-Gr.Fl.Alu.Ventilator | End | P1W1-Gr.Fl.Alu.Ventilator NOC | 0 | 0
RCC | End | P1W1-Seventh Floor Ramp | 0 | 0
C2 FF Column | End | P1W1-Seventh Floor Ramp Granite Flooring(SLK) | 0 | 0
P2W2- 8TH External Pardi Shuttering (Lab) | End | P1W1-Seventh Floor Ramp Tiling (Lab) | 0 | 0
C2 Terrace Internal Tar Plaster | End | P1W1-UGWT- RAFT RMC M40 Plant/Production (C) | 0 | 0
P2W2 - 8TH Slab Pour strip RMC M40 PT Outsource | End | P2W2 - 8TH Slab Pour strip PT Slab Grouting | 0 | 0
P2W2 - 8TH Slab Pour strip | End | P2W2 - 8TH Slab Pour strip RMC M-40 PT Site | 0 | 0
P2W2 - 8TH Slab Pour strip RMC M-40 PT Site | End | P2W2 - 8TH Slab Pour strip RMC M40 PT Outsource | 0 | 0
P2W2-8TH Slab+Stair POUR-01 Steel (Lab) | End | P2W2- 8TH External Pardi RMC M-40 Site | 0 | 0
P2W2-8TH Slab+Stair POUR-01 RMC M40 Plant/Production (C) | End | P2W2- 8TH External Pardi RMC M-40 Site(P) | 0 | 0
P2W2-8TH Slab+Stair POUR-01 RMC M-40 Site | End | P2W2- 8TH External Pardi RMC M40 Outsource | 0 | 0
P2W2-8TH Slab+Stair POUR-01 Steel (C) | End | P2W2- 8TH External Pardi RMC M40 Plant/Production (C) | 0 | 0
P2W2-Column+Lift(Sixth Fl.) Steel (Lab) | End | P2W2- 8TH External Pardi Shuttering (Lab) | 0 | 0
P2W2-Column+Lift(Sixth Fl.) RMC M60- Plant/Production(C) | End | P2W2- 8TH External Pardi Steel (C) | 0 | 0
P2W2-8TH Slab+Stair POUR-01 Shuttering (Lab) | End | P2W2- 8TH External Pardi Steel (Lab) | 0 | 0
P2W2 - 8TH Slab Pour strip PT Slab Grouting | End | P2W2- 8TH Lintel/Chajja | 0 | 0
P2W2- 8TH Lintel/Chajja RMC M20 Plant/Production(C) | End | P2W2- 8TH Lintel/Chajja RMC M-20 Site | 0 | 0
P2W2- 8TH Lintel/Chajja RMC M-20 Site | End | P2W2- 8TH Lintel/Chajja RMC M-20 Site(P) | 0 | 0
P2W2- 8TH Lintel/Chajja RMC M-20 Site(P) | End | P2W2- 8TH Lintel/Chajja RMC M20 Outsource | 0 | 0
P2W2- 8TH Lintel/Chajja Steel (Lab) | End | P2W2- 8TH Lintel/Chajja RMC M20 Plant/Production(C) | 0 | 0
P2W2- 8TH Lintel/Chajja | End | P2W2- 8TH Lintel/Chajja Shuttering (Lab) | 0 | 0
P2W2- 8TH Lintel/Chajja Shuttering (Lab) | End | P2W2- 8TH Lintel/Chajja Steel (C) | 0 | 0
P2W2- 8TH Lintel/Chajja Steel (C) | End | P2W2- 8TH Lintel/Chajja Steel (Lab) | 0 | 0
P2W2-8TH Slab+Stair POUR-01 RMC M-40 Site(P) | End | P2W2- 8TH Slab(Lab) | 0 | 0
P2W2-8TH Slab+Stair POUR-01 RMC M40 Outsource | End | P2W2- 8TH Slab(Lab) Concreting-Dept. Labour | 0 | 0
P2W2-8TH Slab+Stair POUR-01 PT Slab/ Beam | End | P2W2- Above Terrace | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 PT Slab Grouting | End | P2W2- Above Terrace Lintel/Chajja | 0 | 0
P2W2- Above Terrace Lintel/Chajja RMC M20 Plant/Production(C | End | P2W2- Above Terrace Lintel/Chajja RMC M-20 Site | 0 | 0
P2W2- Above Terrace Lintel/Chajja RMC M-20 Site | End | P2W2- Above Terrace Lintel/Chajja RMC M-20 Site(P) | 0 | 0
P2W2- Above Terrace Lintel/Chajja RMC M-20 Site(P) | End | P2W2- Above Terrace Lintel/Chajja RMC M20 Outsource | 0 | 0
P2W2- Above Terrace Lintel/Chajja Steel (Lab) | End | P2W2- Above Terrace Lintel/Chajja RMC M20 Plant/Production(C | 0 | 0
P2W2- Above Terrace Lintel/Chajja | End | P2W2- Above Terrace Lintel/Chajja Shuttering (Lab) | 0 | 0
P2W2- Above Terrace Lintel/Chajja Shuttering (Lab) | End | P2W2- Above Terrace Lintel/Chajja Steel (C) | 0 | 0
P2W2- Above Terrace Lintel/Chajja Steel (C) | End | P2W2- Above Terrace Lintel/Chajja Steel (Lab) | 0 | 0
P2W2-Above Terrace External Pardi RMC M40 Outsource | Start | P2W2- Above Terrace Slab(Lab) | 0 | 0
P2W2- Above Terrace Slab(Lab) | Start | P2W2- Above Terrace Slab(Lab) Concreting-Dept. Labour | 0 | 0
P2W2- Above Terrace Slab(Lab) Concreting-Dept. Labour | Start | P2W2- Concrete Pump | 0 | 0
P2W2- Concrete Pump | Start | P2W2- Concrete Pump Concrete Pump Operation | 0 | 0
P2W2-Back Side Part-2 External Plaster(SLK) | End | P2W2- Left Side | 0 | 0
C2 Painting Texture Paint | End | P2W2-7TH Slab+Stair POUR-03 RMC M-40 PT Site(P) | 0 | 0
P2W2-8TH Slab+Stair POUR-01 RMC M40 Outsource | End | P2W2-8TH Slab+Stair POUR-01 PT Slab/ Beam | 0 | 0
P2W2-8TH Slab+Stair POUR-01 RMC M40-PT Plant/Production(C) | End | P2W2-8TH Slab+Stair POUR-01 RMC M-40 PT Site | 0 | 0
P2W2-8TH Slab+Stair POUR-01 RMC M40 Plant/Production (C) | End | P2W2-8TH Slab+Stair POUR-01 RMC M-40 Site | 0 | 0
P2W2-8TH Slab+Stair POUR-01 RMC M-40 Site | End | P2W2-8TH Slab+Stair POUR-01 RMC M-40 Site(P) | 0 | 0
P2W2-8TH Slab+Stair POUR-01 RMC M-40 Site(P) | End | P2W2-8TH Slab+Stair POUR-01 RMC M40 Outsource | 0 | 0
P2W2-8TH Slab+Stair POUR-01 Steel (Lab) | End | P2W2-8TH Slab+Stair POUR-01 RMC M40 Plant/Production (C) | 0 | 0
P2W2-8TH Slab+Stair POUR-01 PT Slab/ Beam | End | P2W2-8TH Slab+Stair POUR-01 RMC M40-PT Plant/Production(C) | 0 | 0
P2W2-Column+Lift(Sixth Fl.) RMC M60- Plant/Production(C) | End | P2W2-8TH Slab+Stair POUR-01 Shuttering (Lab) | 0 | 0
P2W2-8TH Slab+Stair POUR-01 Shuttering (Lab) | End | P2W2-8TH Slab+Stair POUR-01 Steel (C) | 0 | 0
P2W2-8TH Slab+Stair POUR-01 Steel (C) | End | P2W2-8TH Slab+Stair POUR-01 Steel (Lab) | 0 | 0
C2 Painting Texture Paint | Start | P2W2-8TH Slab+Stair POUR-02 Buttering(SLK) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 Buttering(SLK) | Start | P2W2-8TH Slab+Stair POUR-02 Ponding(SLK) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 RMC M40 Outsource | Start | P2W2-8TH Slab+Stair POUR-02 PT Slab/ Beam | 0 | 0
P2W2-8TH Slab+Stair POUR-02 RMC M40 Plant/Production (C) | Start | P2W2-8TH Slab+Stair POUR-02 RMC M-40 Site | 0 | 0
P2W2-8TH Slab+Stair POUR-02 RMC M-40 Site | Start | P2W2-8TH Slab+Stair POUR-02 RMC M-40 Site(P) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 RMC M-40 Site(P) | Start | P2W2-8TH Slab+Stair POUR-02 RMC M40 Outsource | 0 | 0
P2W2-8TH Slab+Stair POUR-02 Steel (Lab) | Start | P2W2-8TH Slab+Stair POUR-02 RMC M40 Plant/Production (C) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 PT Slab/ Beam | Start | P2W2-8TH Slab+Stair POUR-02 RMC M40-PT Plant/Production(C) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 Ponding(SLK) | Start | P2W2-8TH Slab+Stair POUR-02 Shuttering (Lab) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 Shuttering (Lab) | Start | P2W2-8TH Slab+Stair POUR-02 Steel (C) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 Steel (C) | Start | P2W2-8TH Slab+Stair POUR-02 Steel (Lab) | 0 | 0
P1W1- Second Floor Granite Kitchen Otta(M+L)(SLK) | Start | P2W2-8TH Slab+Stair POUR-03 | 0 | 0
P2W2-8TH Slab+Stair POUR-03 | End | P2W2-8TH Slab+Stair POUR-03 Buttering(SLK) | 0 | 0
P2W2-8TH Slab+Stair POUR-03 Buttering(SLK) | End | P2W2-8TH Slab+Stair POUR-03 Ponding(SLK) | 0 | 0
P2W2-8TH Slab+Stair POUR-03 RMC M40 Outsource | End | P2W2-8TH Slab+Stair POUR-03 PT Slab/ Beam | 0 | 0
P2W2-8TH Slab+Stair POUR-03 RMC M40 Plant/Production (C) | End | P2W2-8TH Slab+Stair POUR-03 RMC M-40 Site | 0 | 0
P2W2-8TH Slab+Stair POUR-03 RMC M-40 Site | End | P2W2-8TH Slab+Stair POUR-03 RMC M-40 Site(P) | 0 | 0
P2W2-8TH Slab+Stair POUR-03 RMC M-40 Site(P) | End | P2W2-8TH Slab+Stair POUR-03 RMC M40 Outsource | 0 | 0
P2W2-8TH Slab+Stair POUR-03 Steel (Lab) | End | P2W2-8TH Slab+Stair POUR-03 RMC M40 Plant/Production (C) | 0 | 0
P2W2-8TH Slab+Stair POUR-03 Ponding(SLK) | End | P2W2-8TH Slab+Stair POUR-03 Shuttering (Lab) | 0 | 0
P2W2-8TH Slab+Stair POUR-03 Shuttering (Lab) | End | P2W2-8TH Slab+Stair POUR-03 Steel (C) | 0 | 0
P2W2-8TH Slab+Stair POUR-03 Steel (C) | End | P2W2-8TH Slab+Stair POUR-03 Steel (Lab) | 0 | 0
P2W2-8TH Slab+Stair POUR-03 | Start | P2W2-Above Terrace External Pardi Buttering(SLK) | 0 | 0
P2W2-Above Terrace External Pardi RMC M40 Plant/Production ( | Start | P2W2-Above Terrace External Pardi RMC M-40 Site | 0 | 0
P2W2-Above Terrace External Pardi RMC M-40 Site | Start | P2W2-Above Terrace External Pardi RMC M-40 Site(P) | 0 | 0
P2W2-Above Terrace External Pardi RMC M-40 Site(P) | Start | P2W2-Above Terrace External Pardi RMC M40 Outsource | 0 | 0
P2W2-Above Terrace External Pardi Steel (Lab) | Start | P2W2-Above Terrace External Pardi RMC M40 Plant/Production ( | 0 | 0
P2W2-Above Terrace External Pardi Buttering(SLK) | Start | P2W2-Above Terrace External Pardi Shuttering (Lab) | 0 | 0
P2W2-Above Terrace External Pardi Shuttering (Lab) | Start | P2W2-Above Terrace External Pardi Steel (C) | 0 | 0
P2W2-Above Terrace External Pardi Steel (C) | Start | P2W2-Above Terrace External Pardi Steel (Lab) | 0 | 0
P1W1-Gr.Fl.Alu.Louvers NOC | Start | P2W2-Above Terrace Slab+Stair | 0 | 0
P1W1- Ground Fl. Glass door(M+L) | End | P2W2-Back Side Part-1 External plaster (Lab) | 0 | 0
P1W1- First Floor | End | P2W2-Back Side Part-2 | 0 | 0
P2W2-Back Side Part-2 | End | P2W2-Back Side Part-2 External plaster (Lab) | 0 | 0
P2W2-Back Side Part-1 External plaster (Lab) | End | P2W2-Back Side Part-2 External Plaster(SLK) | 0 | 0
P2W2-8TH Slab+Stair POUR-01 RMC M40-PT Plant/Production(C) | End | P2W2-Column+Lift Above Terrace | 0 | 0
P2W2-8TH Slab+Stair POUR-01 RMC M-40 PT Site | End | P2W2-Column+Lift Above Terrace Buttering(SLK) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 RMC M40 Outsource | End | P2W2-Column+Lift Above Terrace RMC M-50 Site | 0 | 0
P2W2-8TH Slab+Stair POUR-02 PT Slab/ Beam | End | P2W2-Column+Lift Above Terrace RMC M-50 Site(P) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 Steel (Lab) | End | P2W2-Column+Lift Above Terrace RMC M-60 Site | 0 | 0
P2W2-8TH Slab+Stair POUR-02 RMC M40 Plant/Production (C) | End | P2W2-Column+Lift Above Terrace RMC M-60 Site(P) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 RMC M40-PT Plant/Production(C) | End | P2W2-Column+Lift Above Terrace RMC M50 (Out Source) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 RMC M-40 Site(P) | End | P2W2-Column+Lift Above Terrace RMC M50- Plant/Production(C) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 RMC M-40 Site | End | P2W2-Column+Lift Above Terrace RMC M60 Outsource | 0 | 0
P2W2-8TH Slab+Stair POUR-02 Steel (C) | End | P2W2-Column+Lift Above Terrace RMC M60- Plant/Production(C) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 Buttering(SLK) | End | P2W2-Column+Lift Above Terrace Shuttering (Lab) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 Ponding(SLK) | End | P2W2-Column+Lift Above Terrace Steel (C) | 0 | 0
P2W2-8TH Slab+Stair POUR-02 Shuttering (Lab) | End | P2W2-Column+Lift Above Terrace Steel (Lab) | 0 | 0
P2W2-Column+Lift(Sixth Fl.) Steel (Lab) | End | P2W2-Column+Lift(Sixth Fl.) RMC M60- Plant/Production(C) | 0 | 0
P2W2-Back Side Part-2 External plaster (Lab) | End | P2W2-Left Side Part-1 | 0 | 0
P2W2- Left Side | End | P2W2-Left Side Part-1 External Plaster(SLK) | 0 | 0
EXCAVATION EXCAVATION IN SOIL | Start | PCC PCC 1:3:6 | 0 | 0
C2 Terrace Masonry BBM 6" Thk. | End | Plastering | 0 | 0
First Floor | End | RCC | 0 | 0
AC-Terrace PART-01 Wall Conduiting/Dropping | End | Road Side Flower bed CLC Block Making 500 x 200 x 150 | 0 | 0
P2W2-Above Terrace Slab+Stair | End | Sample Preparation Terrace w/p (SLK) | 0 | 0
Flower bed 1632 rft Cladding | End | Screen wall RCC M-20 | 0 | 0
Excavation Exca.in soft rock | Start | TEST GROUP Column Concrete | 1 | 0
EXCAVATION EXCAVATION IN SOIL | Start | UPTO PLINTH RCC M30 | 0 | 0
P1W1- Third Floor Service Lift Cladding Granite Cladding (SL | End | W1- First Floor Main Lobby | 0 | 0
C2 Granite/Marble Flooring | End | W1- First Floor Main Lobby | 7 | 0
W1- First Floor Main Lobby Marble flooring (SLK) | End | W1- First Floor Main Lobby | 1 | 0
P1W1- Second Floor Balcony Balcony Flooring(SLK) | End | W1- First Floor Main Lobby Marble flooring (SLK) | 0 | 0
C2 Granite/Marble Flooring | End | W1- First Floor Main Lobby Marble flooring (SLK) | 1 | 0
P2W2-Above Terrace Slab+Stair | Start | W2-Above Terrace Slab+Stair POUR-01 | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 | Start | W2-Above Terrace Slab+Stair POUR-01 Buttering(SLK) | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 Buttering(SLK) | Start | W2-Above Terrace Slab+Stair POUR-01 Ponding(SLK) | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 RMC M40 PT Outsource | End | W2-Above Terrace Slab+Stair POUR-01 PT Slab Grouting | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 RMC M40 Outsource | Start | W2-Above Terrace Slab+Stair POUR-01 PT Slab/ Beam | 0 | 0
P2W2- 8TH Lintel/Chajja Shuttering (Lab) | End | W2-Above Terrace Slab+Stair POUR-01 RMC M-40 PT Site | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 RMC M-40 PT Site | End | W2-Above Terrace Slab+Stair POUR-01 RMC M-40 PT Site(P) | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 RMC M40 Plant/Production | Start | W2-Above Terrace Slab+Stair POUR-01 RMC M-40 Site | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 RMC M-40 Site | Start | W2-Above Terrace Slab+Stair POUR-01 RMC M-40 Site(P) | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 RMC M-40 Site(P) | Start | W2-Above Terrace Slab+Stair POUR-01 RMC M40 Outsource | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 Steel (Lab) | Start | W2-Above Terrace Slab+Stair POUR-01 RMC M40 Plant/Production | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 RMC M-40 PT Site(P) | End | W2-Above Terrace Slab+Stair POUR-01 RMC M40 PT Outsource | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 Ponding(SLK) | Start | W2-Above Terrace Slab+Stair POUR-01 Shuttering (Lab) | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 Shuttering (Lab) | Start | W2-Above Terrace Slab+Stair POUR-01 Steel (C) | 0 | 0
W2-Above Terrace Slab+Stair POUR-01 Steel (C) | Start | W2-Above Terrace Slab+Stair POUR-01 Steel (Lab) | 0 | 0
C2 Windows | Start | Windows/Railing | 0 | 0