## Task Category Variance637368925
Task Category Variance
Project Name : !! Kanix Residency !!!
Task Name : mahi test 11122 3
Page 1 of 1
Total Records: 134 Records 1 to 134
Sr_No | Category_Name | Description_Mat_Lab | Unit | Estimated_Qty (1) | Estimated_Rate | Estimated_Amount (1) | PO_WO_Qty (2) | PO_WO_Rate | PO_WO_Amount (2) | Issue_RABil_Qty (3) | Issue_RABil_Rate | Issue_RABill_Amount (3) | QtyDiff (1-2) | QtyDiff (1-3) | AmtDiff (1-2) | AmtDiff (1-3)
1 | No category | (M)CEMENT 53 GRADE | Bags | 120 | 300 | 36000 | 27 | 0 | 0 | 0.1 | 283.52 | 28.35 | 93 | 119.9 | 36000 | 35971.648
2 | No category | (M)STEEL TMT 8 MM | Kgs | 32.8349 | 40 | 1313.4 | 0 | 0 | 0 | 0 | 0 | 0 | 32.8349 | 32.8349 | 1313.396 | 1313.396
3 | No category | (M)Bricks 6" | Each | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | No category | (M)3" x 2 " x 10' Wooden Batton | Bags | 30 | 4092259.38 | 122767781.4 | 10.2 | 0 | 0 | -8.82 | 9.02 | -79.57 | 19.8 | 38.82 | 122767781.4 | 122767860.9657
5 | No category | (M)Bricks 10'' | Sq.Ft | 200 | 1000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 200000 | 200000
6 | No category | (M)CEMENT12 | cum | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0
7 | No category | (M)CEMENT 43 GRADE9336 | Bags | 269 | 22744.98 | 6118400 | 11 | 0 | 0 | 52 | 421.54 | 21920.28 | 258 | 217 | 6118400 | 6096479.725
8 | No category | (M)COMPRESSION TESTING MACHINE - 100 TONS | No. | 20 | 200000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 4000000 | 4000000
9 | No category | (M)53 Grade cement | Bag of 50 Kg_C | 1000 | 350 | 350000 | 0 | 0 | 0 | 1 | 10 | 10 | 1000 | 999 | 350000 | 349990
10 | No category | (M)Brick 6" | Inches | 90 | 23.6 | 2124 | 41 | 0 | 0 | 20 | 702.61 | 14052.22 | 49 | 70 | 2124 | -11928.22
11 | No category | (M)LIFT AUTOMATIC 8 FLOORS | No. | 10 | 963000 | 9630000 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 9630000 | 9630000
12 | No category | (M)ACCESSORIES KIT FOR CONSTELLATION | No. | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0
13 | No category | (M)AAA | cum | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0
14 | No category | (M)A_JCB | No. | 50 | 1000000 | 50000000 | 0 | 0 | 0 | 6 | 991.98 | 5951.9 | 50 | 44 | 50000000 | 49994048.1
15 | No category | (L)M20 Concrete Labour | Cu.Mtrs | 12 | 12 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 144 | 144
16 | No category | (L)A_Labour for Wall | Sq.Ft | 2000 | 12 | 24000 | 1995 | 118 | 235410 | 0 | 0 | 0 | 5 | 2000 | -211410 | 24000
17 | No category | (L)PCC Labour (M-10) | Cu.Ft | 260 | 199.61 | 51899.11 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 260 | 51899.11 | 51899.11
18 | No category |  | Day | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 51 | 0 | 0
19 | Site Preparation | (M)aa_Sand | Kgs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Site Preparation | (M)Brick 6" | Inches | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Site Preparation | (M)Bricks 10'' | Sq.Ft | 12 | 1000 | 12000 | 3 | 0 | 0 | 0 | 0 | 0 | 9 | 12 | 12000 | 12000
22 | Site Preparation | (M)s | Bags | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Site Preparation | (M)BLACK CEMENT | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Site Preparation | (M)CEMENT 33 GRADE-BAGS | Bags | 5 | 100 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 500 | 500
25 | Site Preparation | (M)CEMENT 53 GRADE - BAGS | 01 Bag | 15 | 500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 7500 | 7500
26 | Site Preparation | (L)BBM 1st floor | Sq.Ft | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Excavation | (M)Aggreegate3/4" | Cum_C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Excavation | (M)30005new | 0001 BaG | 200 | 1 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 200 | 200
29 | Excavation | (M)Cement 43 grade- M1 | Bag of 50 Kg_H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Excavation | (M)Aggregate 1/2" | Cum_H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Excavation | (M)RMC M35 GRADE | Bag of 50 kg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Excavation | (M)aa_Sand | Kgs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Excavation | (L)In hard murum | Dz 12nos) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Excavation | (L)pranav test labor | No. | 12 | 0 | 0 | 1 | 11.2 | 11.2 | 0 | 0 | 0 | 11 | 12 | -11.2 | 0
35 | Excavation | (L)IN SOFT ROCK | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | Excavation | (L)abcd_labour | Day | 200 | 12 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 2400 | 2400
37 | Excavation |  | Hour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | Excavation |  | Day | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 51 | 0 | 0
39 | PCC | (M)Brick 6" | Inches | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | PCC | (M)Aggregate 1/2" | Cum_C | 10440 | 11 | 114840 | 0 | 0 | 0 | 0 | 0 | 0 | 10440 | 10440 | 114840 | 114840
41 | PCC | (M)BISON PANEL 12 MM THK | Sq.Ft | 12528 | 11.8 | 147830.4 | 0 | 0 | 0 | 0 | 0 | 0 | 12528 | 12528 | 147830.4 | 147830.4
42 | PCC | (M)COARSE AGGREGATE 20 MM | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | PCC | (M)CEMENT 43 GRADE9336 | Bags | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | PCC | (M)Cement 99 Grade | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | PCC | (M)NATURAL SAND | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | PCC | (M)ARALDITE | Kgs | 12528 | 700 | 8769600 | 0 | 0 | 0 | 0 | 0 | 0 | 12528 | 12528 | 8769600 | 8769600
47 | PCC | (M)ABRO TAPE | Bundle | 104310 | 150 | 15646500 | 0 | 0 | 0 | 0 | 0 | 0 | 104310 | 104310 | 15646500 | 15646500
48 | PCC | (M)00AA Brick Size 6 | 01AA_PerPiece | 208800000 | 6 | 1252800000 | 0 | 0 | 0 | 0 | 0 | 0 | 208800000 | 208800000 | 1252800000 | 1252800000
49 | PCC | (L)PCC Labour (M-10) | Cu.Ft | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | PCC |  | Day | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | RCC Pro | (M)NATURAL SAND | Cu.Mtrs | 746.4 | 826 | 616526.4 | 0 | 0 | 0 | 0 | 0 | 0 | 746.4 | 746.4 | 616526.4 | 616526.4
52 | RCC Pro | (M)COARSE AGGREGATE 20 MM | CUM | 933 | 23.6 | 22018.8 | 0 | 0 | 0 | 0 | 0 | 0 | 933 | 933 | 22018.8 | 22018.8
53 | RCC Pro | (M)CEMENT 43 GRADE9336 | Bags | 380.664 | 23600 | 8983670.4 | 0 | 0 | 0 | 0 | 0 | 0 | 380.664 | 380.664 | 8983670.4 | 8983670.4
54 | RCC Pro | (M)Cement 99 Grade | No. | 3267500 | 500 | 1633750000 | 0 | 0 | 0 | 0 | 0 | 0 | 3267500 | 3267500 | 1633750000 | 1633750000
55 | RCC Pro | (M)SANLA | Bags | 24880 | 80 | 1990400 | 0 | 0 | 0 | 0 | 0 | 0 | 24880 | 24880 | 1990400 | 1990400
56 | RCC Pro | (L)Labour W/P Work | Sq.Ft | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | RCC Pro | (L)BBM 1st floor | Sq.Ft | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | RCC Pro | (L)Lab for column above Plinth - Cu. Mt | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | RCC Pro |  | Day | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | RCC Pro |  | Day | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | BrickWork Pro | (M)Brick 6" | Inches | 261000000 | 17.7 | 4619700000 | 0 | 0 | 0 | 0 | 0 | 0 | 261000000 | 261000000 | 4619700000 | 4619700000
62 | BrickWork Pro | (M)XYZ CEMENT 43 GRDE | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | BrickWork Pro | (M)BRICK 4" | Inches | 187920000 | 11.8 | 2217456000 | 0 | 0 | 0 | 0 | 0 | 0 | 187920000 | 187920000 | 2217456000 | 2217456000
64 | BrickWork Pro | (M)CEMENT 43 GRADE9336 | Bags | 7830000 | 23600 | 184788000000 | 0 | 0 | 0 | 6 | 450.1 | 2700.6 | 7830000 | 7829994 | 184788000000 | 184787997299.4
65 | BrickWork Pro | (M)Cement 99 Grade | No. | 783000 | 500 | 391500000 | 0 | 0 | 0 | 0 | 0 | 0 | 783000 | 783000 | 391500000 | 391500000
66 | BrickWork Pro | (M)STONE DUST | Cu.Ft | 3288600 | 14 | 46040400 | 0 | 0 | 0 | 0 | 0 | 0 | 3288600 | 3288600 | 46040400 | 46040400
67 | BrickWork Pro | (M)NATURAL SAND | Cu.Mtrs | 15660000 | 826 | 12935160000 | 0 | 0 | 0 | 0 | 0 | 0 | 15660000 | 15660000 | 12935160000 | 12935160000
68 | BrickWork Pro | (M)s | Bags | 229680 | 360 | 82684800 | 0 | 0 | 0 | 0 | 0 | 0 | 229680 | 229680 | 82684800 | 82684800
69 | BrickWork Pro | (M)Crushed Sand - Bag of 50 Kg_C | Cum_C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | BrickWork Pro | (M)s | Bags | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | BrickWork Pro | (L)BBM Labour Work | Sq.Ft | 313200000 | 8 | 2505600000 | 0 | 0 | 0 | 0 | 0 | 0 | 313200000 | 313200000 | 2505600000 | 2505600000
72 | BrickWork Pro | (L)BBM 1st floor | Sq.Ft | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | BrickWork Pro | (L)Material For Meter Board | Rs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | BrickWork Pro | (L)All LAbour | Bag 2016 | 114840 | 150 | 17226000 | 0 | 0 | 0 | 0 | 0 | 0 | 114840 | 114840 | 17226000 | 17226000
75 | BrickWork Pro | (L)abcd_labour | Day | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | BrickWork Pro | (L)Test May 19 Concrete Labour | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | BrickWork Pro | (L)Brick work working | Sq.Ft | 52200000 | 53.1 | 2771820000 | 50000 | 550 | 27500000 | 0 | 0 | 0 | 52150000 | 52200000 | 2744320000 | 2771820000
78 | BrickWork Pro |  | Day | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | BrickWork Pro |  | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | Painting | (M)ACRALYIC PLASTIC EMULSION | Sq.Ft | 100 | 4.5 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 450 | 450
81 | Painting | (L)For plastic paint | Sq.Ft | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | Tiling | (M)STEEL MS 06 MM | Kgs | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | 0
83 | Tiling | (M)SYMPHONY BLANCO 25 X 40 CM | Sq.Ft | 10 | 35 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 350 | 350
84 | Tiling | (M)STONELO BLANCO 40 X 40 CM | Sq.Ft | 10 | 35 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 350 | 350
85 | Tiling | (M)MINERVA GRAY | Sq.Ft | 10 | 35 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 350 | 350
86 | Tiling | (M)SYMPHONY BLUE 25 X 40 CM | Box | 10 | 355 | 3550 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 3550 | 3550
87 | Tiling | (M)GRANITE JAM AT DOOR PORTION | Sq.Ft | 10 | 35 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 350 | 350
88 | Tiling | (L)Labour for RCC Pardi | R.Ft | 100 | 55 | 5500 | 20 | 256 | 5120 | 0 | 0 | 0 | 80 | 100 | 380 | 5500
89 | Solling |  | Hour | 26050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26050 | 26050 | 0 | 0
90 | Solling |  | Day | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Internal Plaster | (M)CEMENT 43 GRADE9336 | Bags | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Internal Plaster | (L)Labour for RCC Columns001 | RFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | Internal Plaster |  | Trip | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | RMC | (M)COARSE AGGREGATE 20 MM | CUM | 10272960 | 23.6 | 242441856 | 0 | 0 | 0 | 0 | 0 | 0 | 10272960 | 10272960 | 242441856 | 242441856
95 | RMC | (M)CEMENT 43 GRADE9336 | Bags | 4280400 | 23600 | 101017440000 | 0 | 0 | 0 | 2 | 450.1 | 900.2 | 4280400 | 4280398 | 101017440000 | 101017439099.8
96 | RMC | (M)RMC M10 GRADE - CU.MTRS | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | RMC | (M)RMC M25 GRADE - CU.MTRS | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | RMC | (M)s | Cu.Cm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | RMC | (M)RMC M30 GRADE - CU.MTRS | Cu.Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | RMC | (L)METER CHARGES | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | Foundation | (M)Brick 6" | Inches | 100 | 35.4 | 3540 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 3540 | 3540
102 | Foundation | (M)RMC M25 GRADE - CU.MTRS | Cu.Mtrs | 10 | 4450 | 44500 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 44500 | 44500
103 | Foundation | (L)building labour123 - Dz 12nos) | BAG 2017 | 1 | 510 | 510 | 0.2 | 1180 | 236 | 0 | 0 | 0 | 0.8 | 1 | 274 | 510
104 | Foundation | (L)All LAbour | Bag 2016 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
105 | Foundation |  | Day | 51 | 1000 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 51 | 51000 | 51000
106 | Foundation |  | Day | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 51 | 0 | 0
107 | Finishing | (M)CEMENT 43 GRADE9336 | Bags | 2937 | 23600 | 69313200 | 0 | 0 | 0 | 220 | 450 | 99000 | 2937 | 2717 | 69313200 | 69214200
108 | Finishing | (M)NATURAL SAND | Cu.Mtrs | 801 | 826 | 661626 | 0 | 0 | 0 | 0 | 0 | 0 | 801 | 801 | 661626 | 661626
109 | Finishing | (L)All LAbour | Bag 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | Finishing | (L)All LAbour | Bag 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | Finishing | (L)abcd_labour | Day | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | Finishing | (L)ABCD_LABOUR | Day | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | Finishing | (L)A_Swa | Sq.Ft | 10 | 0.28 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 2.8 | 2.8
114 | 0001 Brick Wall Building | (M)T1_cement | Bags | 10 | 300 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 3000 | 3000
115 | 0001 Brick Wall Building | (L)02 Test Brickwork Labour | No. | 1000 | 12 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 12000 | 12000
116 | !!! Test Cat | (M)CEMENT 43 GRADE9336 | Bags | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | abcde | (M)s | 0001 BaG | 55 | 23 | 1265 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 1265 | 1265
118 | abcde | (M)s | 0001A_Bag of 100 Kg | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 222 | 0 | 0
119 | abcde | (M)s | Bags | 2 | 200 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 400 | 400
120 | abcde | (M)s | Cu.Mtrs | 444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 444 | 444 | 0 | 0
121 | abcde | (M)65 mm dia. ( PPR 75 MM OD- 2 1/2") | 0001A_Nos, | 456 | 6666666666 | 3039999999696 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 456 | 3039999999696 | 3039999999696
122 | abcde | (M)A_JCB | No. | 33 | 1000000 | 33000000 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 33 | 33000000 | 33000000
123 | abcde | (M)1.SAMPLE MATERIAL | Guntha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | abcde | (M)11550 | 01 Bag | 10 | 682 | 6820 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 6820 | 6820
125 | abcde | (M)< SU_SAND> - Bag of 50 kg | 01AA_PerPiece | 55 | 20 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 1100 | 1100
126 | abcde | (M)aa_Sand | 01AA_PerBag | 3 | 50 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 150 | 150
127 | abcde | (M)00AACement Grade A | 01AA_PerBag | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | abcde | (M)Bricks_Pro | No. | 456 | 10 | 4560 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 456 | 4560 | 4560
129 | abcde | (M)Cement_Pro | No. | 10 | 10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 100 | 100
130 | abcde | (M)abcd 123 333 | 0001 BaG | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
131 | abcde | (M)abcd jkhkll | 01AA_PerBag | 2 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 40 | 40
132 | abcde | (L)Brick Work Pro | No. | 10 | 100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 1000 | 1000
133 | abcde | (L)RCC 2 | Sq.Ft | 10 | 100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 1000 | 1000
134 | abcde | (L)Plaster_Pro | Sq.Ft | 10 | 100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 1000 | 1000