## Task Details637397344604532297_
Task Details
Project Name : A SAMPLE PROJECT 3
Task Name : CONSTRUCTION
Total Records: 13876 Records 1 to 2000
Page 1 of 7
Task (1) | Qty (2) | Unit (3) | Planned Start (4) | Planned Finish (5) | Actual Start (6) | Actual Finish (7) | Planned Duration (8)=(4)-(5) Days | Actual Duration (9)=(6)-(7) Days | Start Variance (10)=(4)-(6) Days | Finish Variance (11)=(4)-(5) Days | Remark
CONSTRUCTION | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
ZERO PHASE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
SITE SETUP | 1464100 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
SURVEY | 97869 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Survey Survey (Base line) | 82800 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Survey Flyash Brick Masonry 9" | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Survey Tar Plaster | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
ENTRANCE GATE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Entrance Gate Entrance gate (Base line) | 40882 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Entrance Gate Fabrication (M+L) | 8725 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
SITE OFFICE & STORE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store Site office/Godown/store(Base) | 159386 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store UCR Masonary | 0 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store RMC M10 | 11.5 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store 4" Thk Flyash BM | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store Double Coat-Sand face | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store I.P.S. Flooring | 86.4 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store CLC Block Masonry 6" | 654 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store CLC Block Making 500 x 200 x 150 | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store Fab. Charges (M+L) | 100000 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store Furniture | 0 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store Alu. Window & lou. (P.C) (M+L) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
TILE GODOWN | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Tile Godown Fabrication (M+L) | 61294.35 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store Painting (Dev) | 55923 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store Misc civil work Lab | 120685 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store Site Office Ceramic Flooring | 360 | Sq.ft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Site Office & Store Tar Plaster | 357 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
BARRACATION | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Barracation Barrication work (Base line) | 343668 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Barracation RMC M-10 Site | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Barracation RMC M-10 Plant /Production | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Barracation RMC M-10 Plant /Production | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Barracation RMC M-10 Site | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Barracation Barrication work | 1 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
TEMP. ELECTRICAL | 1303129 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Temp. Electrical Temperory Electrical (base) | 37556.4 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Temp. Electrical Electrical Work | 11139 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Temp. Electrical Electrical (M+L : Job) | 126468 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
TEMP. PLUMBING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Temp. Plumbing Temp Plumbing (Base line) | 405580 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Temp. Plumbing GI Pipes & Fittings | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Temp. Plumbing Plumbing (Lab) | 74731 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Temp. Plumbing Plumbing | 0 | Nos | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Temp. Plumbing Excavation | 303.18 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
STEEL YARD | 135071 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Steel Yard Steel Yard (Base) | 149543.28 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Steel Yard Tar Plaster | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Steel Yard 9" Thk. BBM | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Steel Yard RMC M5 | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
CONCRETE THIYYA | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Concrete Thiyya RMC M20 | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Steel Yard Plum Concrete (40%) RMC-M10 | 6.5 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
LABOUR CAMP | 273507 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Labour Camp Labour camp (Base line) | 0 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Labour Camp Plumbing | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Labour Camp PCC M-10 | 0 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Labour Camp Labour Hutment Fabrication (M+L) | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Labour Camp Lab hut Fabri - Remove & Refix (Lab) | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Labour Camp Misc. Plumbing | 0 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Labour Camp Electrical (M+L : Job) | 0 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Labour Camp Misc civil work Lab | 0 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Labour Camp Toilet Cleaning (Lab) | 0 | Month. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Labour Camp PEST CONTROL | 15 | Month. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Labour Camp Electrical Work | 0 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
TESTING + LAB | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Testing + Lab Testing+Laboratory (Base line) | 11464 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
TESTING LAB EQUIPMENT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Testing Lab Equipment Misc. | 1 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
CUBE CURING TANK | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Cube Curing Tank RMC M10 | 1.05 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Cube Curing Tank 6" Thk Flyash BM | 167.5 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Cube Curing Tank Tar Plaster | 102 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Cube Curing Tank W/P Plaster | 269.5 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Cube Curing Tank Lum-Sum | 0 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Cube Curing Tank Misc civil work Lab | 0 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Testing + Lab Soil Testing | 0 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
TEMPORARY ROADS | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Temporary Roads Temp Road (Base line) | 51811 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Temporary Roads Temporary road | 0 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Temporary Roads Roller (10T) | 0 | Day | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
TOWER CRANE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Tower Crane Tower crane (Baseline) | 20700 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Tower Crane Steel | 0 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Tower Crane RMC M20 | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Tower Crane RMC M30 | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Tower Crane Fixing Work | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Tower Crane Fabrication (M+L) | 0 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
MOBILE CRECHE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Mobile Creche Mobile Cerche (Base line) | 248033 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Mobile Creche 6" Thk Flyash BM | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Mobile Creche RMC M5 | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Mobile Creche RMC M10 | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Mobile Creche I.P.S. Flooring | 0 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
DEBRIES CHUTE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Debries Chute Debries Chute (Base line) | 6232 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Debries Chute Misc. Material | 1 | Bag | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Debries Chute Plum Concrete (40%) RCC-M10 | 54 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
HARDWARE & TOOLS | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Hardware & Tools Hardware and Tools(Base line) | 19344 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Hardware & Tools Misc. | 1 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
REPAIRING WORK | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Repairing work Repair work (Base line) | 183358 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Repairing work Repairing Charges | 11787 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
MACHINARY HIRING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Machinary Hiring Machinary Hiring (Base line) | 82797 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Machinary Hiring Machinery | 0 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Machinary Hiring Local Trip- Conc. Tempo/Truck | 0 | Trip | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Machinary Hiring Poclain Breaker EX210 | 0 | Hour | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Machinary Hiring Poclain Bucket EX210 | 0 | Hour | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Machinary Hiring Dumper (3 Brass) | 0 | Hour | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Machinary Hiring Farana Crane - 14 Ton | 0 | Shift | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
CLC BLOCK SHIFTING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
CLC Block Shifting CLC Block Shifting | 600 | Trip | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
SAFETY MATERIAL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Safety Material Safety Materials(Base line) | 337190 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Safety Material Misc. | 0 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Safety Material Fabrication (M+L) | 26094 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Safety Material Installation Charges | 73895.6 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
PAINTING SIGN BOARD | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Painting sign board Painting sign board (Base Line) | 2000 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Painting sign board Signage & Name Board | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Painting sign board Pole Fixing (Lab) | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Painting sign board Fabrication Work | 4458.84 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
SCAFHOLDING | 25000 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Scafholding Scaffolding (Base line) | 0 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Scafholding Scaffolding for garbage chute | 1100 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
DEPT LABOUR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Dept labour Dept.Labour (Base line) | 0 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Dept labour Dept. Labour work | 51811 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
MISC | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Misc Misc. (Base line) | 0 | Lump-Sum | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
Misc Misc. Fabrication | 35580.74 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
SITE OFFICE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
SALES OFFICE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
CENTRAL STORE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
STEEL YARD | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
RMC PRODUCTION PLANT | 0 | Dz 12nos) | 06 Aug 2016 |  |  |  | 0 | 0 | 0 | 0
RMC PRODUCTION PLANT RMC M-25 Plant /Production | 6 | Cum. | 24 Dec 2019 | 24 Dec 2019 |  |  | 0 | 0 | 0 | 0
PHASE I | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
TOWER A1 | 25 | No Unit | 05 Jun 2015 | 30 Dec 2016 |  |  | 574 | 0 | 0 | 0
A1-EARTHWORK | 0 | No Unit | 05 Jun 2015 | 23 Jul 2015 |  |  | 48 | 0 | 0 | 0
A1-Earthwork Site cleaning | 6 | Day | 05 Jun 2015 | 06 Jun 2015 | 12 Dec 2019 | 16 Aug 2015 | 1 | 0 | 1651 | 71
A1-Earthwork Excavation in Soil/Soft Murum | 647.22 | Cum. | 08 Jun 2015 | 09 Jun 2015 | 07 Jun 2015 | 19 Aug 2015 | 1 | 73 | 0 | 71
A1-Earthwork Royalty Charges | 0 | R.S. | 05 Jun 2015 | 05 Jun 2015 | 27 Aug 2015 | 09 Sep 2015 | 0 | 13 | 83 | 96
A1-Earthwork Excavation in Bolder /Hard Murum | 1164.99 | Cum. | 10 Jun 2015 | 15 Jun 2015 | 09 Jun 2015 | 19 Aug 2015 | 5 | 71 | 0 | 65
A1-Earthwork Excavation in Rock | 0 | Cum. | 15 Jun 2015 | 22 Jun 2015 | 04 Jun 2020 | 16 Aug 2015 | 7 | 0 | 1816 | 55
A1-Earthwork Excavation in Manjra Rock | 0 | Cum. | 15 Jun 2015 | 25 Jun 2015 | 13 Jun 2015 | 16 Aug 2015 | 10 | 64 | 0 | 52
A1-Earthwork Back Filling | 1883.41 | Cum. | 04 Jul 2015 | 13 Jul 2015 | 09 Jul 2015 | 25 Sep 2015 | 9 | 78 | 5 | 74
A1-Earthwork Antitermite Treatment | 6461.84 | Sft. | 24 Jun 2015 | 27 Jun 2015 | 25 Jun 2015 | 20 Aug 2015 | 3 | 56 | 1 | 54
A1-Earthwork Rubble Soling 9`` | 4755.48 | Sft. | 15 Jul 2015 | 23 Jul 2015 | 21 Jul 2015 | 25 Sep 2015 | 8 | 66 | 6 | 64
A1-Earthwork Carting away | 89508.7437 | Cft | 08 Jun 2015 | 06 Jul 2015 | 07 Jun 2015 | 21 Aug 2015 | 28 | 75 | 0 | 46
A1-Earthwork Carting away | 93025.1587 | Cft | 08 Jun 2015 | 06 Jul 2015 | 07 Jun 2015 | 24 Aug 2015 | 28 | 78 | 0 | 49
A1-LINE OUT | 0 | No Unit | 27 Jun 2015 | 27 Jun 2015 |  |  | 0 | 0 | 0 | 0
A1-Line out PCC M-10 | 50 | Cft | 27 Jun 2015 | 27 Jun 2015 | 24 Jun 2015 | 06 Aug 2015 | 0 | 43 | 0 | 40
A1-W/P -PLINTH | 0 | No Unit | 13 Jul 2015 | 20 Jul 2015 |  |  | 7 | 0 | 0 | 0
A1-W/P -plinth Box Type W/P(C) | 1077.43 | Sft. | 13 Jul 2015 | 20 Jul 2015 | 04 Jul 2015 | 24 Aug 2015 | 7 | 51 | 0 | 35
A1-W/P -plinth W/P plaster(C) | 734.75 | Sft. | 13 Jul 2015 | 20 Jul 2015 | 04 Jul 2015 | 24 Aug 2015 | 7 | 51 | 0 | 35
A1- M & P | 0 | No Unit | 02 Jul 2015 | 06 Jul 2015 |  |  | 4 | 0 | 0 | 0
A1- M & P BBM 9" | 318.8 | Sft. | 02 Jul 2015 | 06 Jul 2015 | 26 Aug 2015 | 27 Aug 2015 | 4 | 1 | 55 | 52
A1-PLUM CONCRETE | 0 | No Unit | 29 Jun 2015 | 03 Jul 2015 |  |  | 4 | 0 | 0 | 0
A1-Plum Concrete Plum Concrete RCC M10 (60P, 40C) | 0 | Cft | 29 Jun 2015 | 03 Jul 2015 | 26 Aug 2015 | 27 Aug 2015 | 4 | 1 | 58 | 55
A1-Earthwork Shifting of Rabit by tractor (Morter Was | 36097.41 | Cft | 08 Jun 2015 | 06 Jul 2015 | 07 Jun 2015 | 21 Aug 2015 | 28 | 75 | 0 | 46
A1-Earthwork Excavation in Soil/Soft Murum | 400 | Cum. | 06 Aug 2016 |  | 15 Mar 2019 |  | 0 | 0 | 951 | 0
A1-RCC | 0 | No Unit | 22 Jun 2015 | 14 Jul 2016 |  |  | 388 | 0 | 0 | 0
A1-PLINTH | 0 | No Unit | 29 Jun 2015 | 09 Oct 2015 |  |  | 102 | 0 | 0 | 0
A1- FOOTING | 0 | No Unit | 29 Jun 2015 | 04 Jul 2015 |  |  | 5 | 0 | 0 | 0
A1- Footing Steel | 5.248 | M.T. | 29 Jun 2015 | 04 Jul 2015 | 29 Jun 2015 | 12 Aug 2015 | 5 | 44 | 0 | 39
A1- Footing RMC M-10 Site | 27.71 | Cum. | 29 Jun 2015 | 04 Jul 2015 | 29 Jun 2015 | 26 Aug 2015 | 5 | 58 | 0 | 53
A1- Footing RMC M-30 Site | 0 | Cum. | 29 Jun 2015 | 04 Jul 2015 | 29 Jun 2015 | 16 Aug 2015 | 5 | 48 | 0 | 43
A1- Footing Buttering | 3 | Slab | 29 Jun 2015 | 04 Jul 2015 | 29 Jun 2015 | 16 Aug 2015 | 5 | 48 | 0 | 43
A1- Footing RMC M-25 Site | 103.6 | Cum. | 29 Jun 2015 | 04 Jul 2015 | 01 Jul 2015 | 26 Aug 2015 | 5 | 56 | 2 | 53
A1- Footing Buttering | 100 | Slab | 06 Aug 2016 |  | 04 Oct 2019 |  | 0 | 0 | 1154 | 0
A1- Footing RCC FOOTIN NO 1 M 40 G | 100 | CUM | 06 Aug 2016 |  | 26 Feb 2020 |  | 0 | 0 | 1299 | 0
A1- COL. UP TO PLINTH | 0 | No Unit | 01 Jul 2015 | 07 Jul 2015 |  |  | 6 | 0 | 0 | 0
A1- Col. Up to Plinth Steel | 11.09 | M.T. | 01 Jul 2015 | 07 Jul 2015 | 02 Jul 2015 | 21 Aug 2015 | 6 | 50 | 1 | 45
A1- Col. Up to Plinth RMC M-30 Site | 41.48 | Cum. | 01 Jul 2015 | 07 Jul 2015 | 02 Jul 2015 | 26 Aug 2015 | 6 | 55 | 1 | 50
A1- Col. Up to Plinth RCC M-30 | 0 | Cft | 01 Jul 2015 | 07 Jul 2015 | 02 Jul 2015 | 16 Aug 2015 | 6 | 45 | 1 | 40
A-1 PLINTH BEAM/ TIE BEAM | 0 | No Unit | 03 Jul 2015 | 14 Jul 2015 |  |  | 11 | 0 | 0 | 0
A-1 Plinth Beam/ Tie Beam Steel | 2.28 | M.T. | 03 Jul 2015 | 14 Jul 2015 | 15 Jul 2015 | 16 Aug 2015 | 11 | 32 | 12 | 33
A-1 Plinth Beam/ Tie Beam RMC M-10 Site | 10.106 | Cum. | 03 Jul 2015 | 14 Jul 2015 | 29 Nov 2019 | 16 Aug 2015 | 11 | 0 | 1610 | 33
A-1 Plinth Beam/ Tie Beam RMC M-20 Site | 15.16 | Cum. | 03 Jul 2015 | 14 Jul 2015 | 15 Jul 2015 | 16 Aug 2015 | 11 | 32 | 12 | 33
A-1 Plinth Beam/ Tie Beam Buttering | 1 | Slab | 03 Jul 2015 | 14 Jul 2015 | 15 Jul 2015 | 16 Aug 2015 | 11 | 32 | 12 | 33
A1-PLINTH FL. PCC | 0 | No Unit | 06 Oct 2015 | 09 Oct 2015 |  |  | 3 | 0 | 0 | 0
A1-Plinth Fl. PCC RMC M-10 Site | 30.84 | Cum. | 06 Oct 2015 | 09 Oct 2015 | 07 Jul 2015 | 14 Oct 2015 | 3 | 99 | 0 | 5
A1-RCC PLINTH (LAB) | 0 | No Unit | 03 Jul 2015 | 16 Jul 2015 |  |  | 13 | 0 | 0 | 0
A1-RCC Plinth (Lab) RCC Plinth (Lab) | 64403 | Sft. | 03 Jul 2015 | 16 Jul 2015 | 29 Jun 2015 | 28 Sep 2015 | 13 | 91 | 0 | 74
A1- Footing Steel | 5.248 | M.T. | 06 Aug 2016 |  | 06 Aug 2016 | 06 Aug 2016 | 0 | 0 | 0 | 42586
A1 1ST SLAB (STILT FL.) | 0 | No Unit | 24 Jul 2015 | 31 Aug 2015 |  |  | 38 | 0 | 0 | 0
A-1- STILT COLUMN | 0 | No Unit | 24 Jul 2015 | 06 Aug 2015 |  |  | 13 | 0 | 0 | 0
A-1- Stilt column Steel | 11.04 | M.T. | 24 Jul 2015 | 06 Aug 2015 | 15 Jul 2015 | 21 Aug 2015 | 13 | 37 | 0 | 15
A-1- Stilt column RCC M-30 | 1400.8 | Cft | 24 Jul 2015 | 06 Aug 2015 | 15 Jul 2015 | 26 Aug 2015 | 13 | 42 | 0 | 20
A1-1ST SLAB (STILT FL.) | 0 | No Unit | 30 Jul 2015 | 21 Aug 2015 |  |  | 22 | 0 | 0 | 0
A1-1st Slab (Stilt Fl.) Steel | 9.115 | M.T. | 30 Jul 2015 | 13 Aug 2015 | 30 Jul 2015 | 21 Aug 2015 | 14 | 22 | 0 | 8
A1-1st Slab (Stilt Fl.) RMC M-20 Site | 72.1 | Cum. | 14 Aug 2015 | 17 Aug 2015 | 16 Aug 2015 | 17 Aug 2015 | 3 | 1 | 2 | 0
A1-1st Slab (Stilt Fl.) RCC M-20 | 162 | Cft | 31 Jul 2015 | 04 Aug 2015 | 08 Aug 2015 | 25 Aug 2015 | 4 | 17 | 8 | 21
A1-1st Slab (Stilt Fl.) RMC M-30 Site | 18.51 | Cum. | 14 Aug 2015 | 17 Aug 2015 | 16 Aug 2015 | 17 Aug 2015 | 3 | 1 | 2 | 0
A1-1st Slab (Stilt Fl.) Buttering | 1 | Slab | 14 Aug 2015 | 17 Aug 2015 | 16 Aug 2015 | 17 Aug 2015 | 3 | 1 | 2 | 0
A1-1st Slab (Stilt Fl.) Ponding | 1 | Slab | 18 Aug 2015 | 18 Aug 2015 | 16 Aug 2015 | 17 Aug 2015 | 0 | 1 | 0 | 0
A1-1st Slab (Stilt Fl.) RCC Slab (Lab) | 64403 | Sft. | 30 Jul 2015 | 21 Aug 2015 | 16 Aug 2015 | 28 Sep 2015 | 22 | 43 | 17 | 38
A-1- STILT FLR.CORNICE/PARDI/CILL | 0 | No Unit | 07 Aug 2015 | 31 Aug 2015 |  |  | 24 | 0 | 0 | 0
A-1- Stilt Flr.Cornice/Pardi/Cill Steel | 0.05 | M.T. | 07 Aug 2015 | 31 Aug 2015 | 16 Sep 2015 | 25 Sep 2015 | 24 | 9 | 40 | 25
A-1- Stilt Flr.Cornice/Pardi/Cill RCC M-20 | 19.29 | Cft | 07 Aug 2015 | 31 Aug 2015 | 16 Sep 2015 | 25 Sep 2015 | 24 | 9 | 40 | 25
A1- 2ND SLAB (1ST FL.) | 0 | No Unit | 25 Aug 2015 | 28 Oct 2015 |  |  | 64 | 0 | 0 | 0
A-1 1ST FL. COLUMN | 0 | No Unit | 25 Aug 2015 | 04 Sep 2015 |  |  | 10 | 0 | 0 | 0
A-1 1st Fl. column Steel | 7.44 | M.T. | 25 Aug 2015 | 02 Sep 2015 | 27 Aug 2015 | 28 Aug 2015 | 8 | 1 | 2 | 0
A-1 1st Fl. column RCC M-30 | 1211.63 | Cft | 25 Aug 2015 | 04 Sep 2015 | 18 Aug 2015 | 03 Sep 2015 | 10 | 16 | 0 | 0
A-1- 2ND SLAB (1ST FL.) | 0 | No Unit | 25 Aug 2015 | 16 Sep 2015 |  |  | 22 | 0 | 0 | 0
A-1- 2nd Slab (1st Fl.) Steel | 7.9 | M.T. | 01 Sep 2015 | 11 Sep 2015 | 21 Aug 2015 | 03 Sep 2015 | 10 | 13 | 0 | 0
A-1- 2nd Slab (1st Fl.) RMC M-20 Site | 77.57 | Cum. | 12 Sep 2015 | 14 Sep 2015 | 03 Sep 2015 | 08 Sep 2015 | 2 | 5 | 0 | 0
A-1- 2nd Slab (1st Fl.) RCC M-20 | 303.51 | Cft | 31 Aug 2015 | 03 Sep 2015 | 24 Aug 2015 | 08 Sep 2015 | 3 | 15 | 0 | 5
A-1- 2nd Slab (1st Fl.) RMC M-30 Site | 10.25 | Cum. | 12 Sep 2015 | 14 Sep 2015 | 03 Sep 2015 | 08 Sep 2015 | 2 | 5 | 0 | 0
A-1- 2nd Slab (1st Fl.) Buttering | 1 | Slab | 12 Sep 2015 | 14 Sep 2015 | 03 Sep 2015 | 03 Sep 2015 | 2 | 0 | 0 | 0
A-1- 2nd Slab (1st Fl.) Ponding | 1 | Slab | 15 Sep 2015 | 15 Sep 2015 | 04 Sep 2015 | 04 Sep 2015 | 0 | 0 | 0 | 0
A-1- 2nd Slab (1st Fl.) RCC Slab (Lab) | 64403 | Sft. | 25 Aug 2015 | 16 Sep 2015 | 03 Sep 2015 | 30 Nov 2015 | 22 | 88 | 9 | 75
A-1 1ST FLR.CORNICE/PARDI/CILL | 0 | No Unit | 17 Sep 2015 | 28 Oct 2015 |  |  | 41 | 0 | 0 | 0
A-1 1st Flr.Cornice/Pardi/Cill Steel | 0.3008 | M.T. | 17 Sep 2015 | 28 Oct 2015 | 08 Oct 2015 | 30 Oct 2015 | 41 | 22 | 21 | 2
A-1 1st Flr.Cornice/Pardi/Cill RCC M-20 | 66.7 | Cft | 17 Sep 2015 | 28 Oct 2015 | 08 Oct 2015 | 03 Nov 2015 | 41 | 26 | 21 | 6
A1- 3RD SLAB (2ND FL.) | 0 | No Unit | 15 Sep 2015 | 16 Nov 2015 |  |  | 62 | 0 | 0 | 0
A-1 2ND FL. COLUMN | 0 | No Unit | 15 Sep 2015 | 25 Sep 2015 |  |  | 10 | 0 | 0 | 0
A-1 2nd Fl. column Steel | 6.75 | M.T. | 15 Sep 2015 | 25 Sep 2015 | 01 Sep 2015 | 09 Sep 2015 | 10 | 8 | 0 | 0
A-1 2nd Fl. column RCC M-30 | 1072.76 | Cft | 15 Sep 2015 | 25 Sep 2015 | 04 Sep 2015 | 15 Sep 2015 | 10 | 11 | 0 | 0
A-1- 3RD SLAB (2ND FL.) | 7.1859 | No Unit | 15 Sep 2015 | 09 Oct 2015 |  |  | 24 | 0 | 0 | 0
A-1- 3rd Slab (2nd Fl.) Steel | 7.1 | M.T. | 21 Sep 2015 | 01 Oct 2015 | 07 Sep 2015 | 16 Sep 2015 | 10 | 9 | 0 | 0
A-1- 3rd Slab (2nd Fl.) RMC M-20 Site | 77.88 | Cum. | 03 Oct 2015 | 05 Oct 2015 | 16 Sep 2015 | 18 Sep 2015 | 2 | 2 | 0 | 0
A-1- 3rd Slab (2nd Fl.) RCC M-20 | 205.7 | Cft | 21 Sep 2015 | 24 Sep 2015 | 10 Sep 2015 | 16 Sep 2015 | 3 | 6 | 0 | 0
A-1- 3rd Slab (2nd Fl.) RMC M-30 Site | 9.06 | Cum. | 03 Oct 2015 | 05 Oct 2015 | 16 Sep 2015 | 18 Sep 2015 | 2 | 2 | 0 | 0
A-1- 3rd Slab (2nd Fl.) Buttering | 1 | Slab | 03 Oct 2015 | 05 Oct 2015 | 16 Sep 2015 | 18 Sep 2015 | 2 | 2 | 0 | 0
A-1- 3rd Slab (2nd Fl.) Ponding | 1 | Slab | 06 Oct 2015 | 06 Oct 2015 | 16 Sep 2015 | 18 Sep 2015 | 0 | 2 | 0 | 0
A-1- 3rd Slab (2nd Fl.) RCC Slab (Lab) | 64403 | Sft. | 15 Sep 2015 | 09 Oct 2015 | 16 Sep 2015 | 30 Nov 2015 | 24 | 75 | 1 | 52
A-1 2ND FLR.CORNICE/PARDI/CILL | 9.014 | No Unit | 07 Oct 2015 | 16 Nov 2015 |  |  | 40 | 0 | 0 | 0
A-1 2nd Flr.Cornice/Pardi/Cill Steel | 0.1452 | M.T. | 07 Oct 2015 | 16 Nov 2015 | 21 Oct 2015 | 03 Nov 2015 | 40 | 13 | 14 | 0
A-1 2nd Flr.Cornice/Pardi/Cill RCC M-20 | 38.19 | Cft | 07 Oct 2015 | 16 Nov 2015 | 21 Oct 2015 | 03 Nov 2015 | 40 | 13 | 14 | 0
A1- 4TH SLAB (3RD FL.) | 0 | No Unit | 06 Oct 2015 | 07 Dec 2015 |  |  | 62 | 0 | 0 | 0
A-1 3RD FL. COLUMN | 0 | No Unit | 06 Oct 2015 | 14 Oct 2015 |  |  | 8 | 0 | 0 | 0
A-1 3rd Fl. column Steel | 5.8 | M.T. | 06 Oct 2015 | 14 Oct 2015 | 15 Sep 2015 | 25 Sep 2015 | 8 | 10 | 0 | 0
A-1 3rd Fl. column RCC M-30 | 958.13 | Cft | 06 Oct 2015 | 14 Oct 2015 | 18 Sep 2015 | 30 Sep 2015 | 8 | 12 | 0 | 0
A-1- 4TH SLAB (3RD FL.) | 0 | No Unit | 06 Oct 2015 | 29 Oct 2015 |  |  | 23 | 0 | 0 | 0
A-1- 4th Slab (3rd Fl.) Steel | 7.098 | M.T. | 09 Oct 2015 | 22 Oct 2015 | 21 Sep 2015 | 30 Sep 2015 | 13 | 9 | 0 | 0
A-1- 4th Slab (3rd Fl.) RMC M-20 Site | 81.48 | Cum. | 23 Oct 2015 | 24 Oct 2015 | 30 Sep 2015 | 01 Oct 2015 | 1 | 1 | 0 | 0
A-1- 4th Slab (3rd Fl.) RCC M-20 | 184.17 | Cft | 12 Oct 2015 | 15 Oct 2015 | 24 Sep 2015 | 30 Sep 2015 | 3 | 6 | 0 | 0
A-1- 4th Slab (3rd Fl.) RMC M-30 Site | 8.11 | Cum. | 23 Oct 2015 | 24 Oct 2015 | 30 Sep 2015 | 01 Oct 2015 | 1 | 1 | 0 | 0
A-1- 4th Slab (3rd Fl.) Buttering | 1 | Slab | 23 Oct 2015 | 24 Oct 2015 | 30 Sep 2015 | 30 Sep 2015 | 1 | 0 | 0 | 0
A-1- 4th Slab (3rd Fl.) Ponding | 1 | Slab | 23 Oct 2015 | 23 Oct 2015 | 01 Oct 2015 | 01 Oct 2015 | 0 | 0 | 0 | 0
A-1- 4th Slab (3rd Fl.) RCC Slab (Lab) | 64403 | Sft. | 06 Oct 2015 | 29 Oct 2015 | 30 Sep 2015 | 13 Dec 2015 | 23 | 74 | 0 | 45
A-1 3RD FLR.CORNICE/PARDI/CILL | 0 | No Unit | 28 Oct 2015 | 07 Dec 2015 |  |  | 40 | 0 | 0 | 0
A-1 3rd Flr.Cornice/Pardi/Cill Steel | 0.1988 | M.T. | 28 Oct 2015 | 07 Dec 2015 | 30 Oct 2015 | 10 Nov 2015 | 40 | 11 | 2 | 0
A-1 3rd Flr.Cornice/Pardi/Cill RCC M-20 | 52.31 | Cft | 28 Oct 2015 | 07 Dec 2015 | 05 Nov 2015 | 10 Nov 2015 | 40 | 5 | 8 | 0
A1- 5TH SLAB (4TH FL.) | 0 | No Unit | 26 Oct 2015 | 26 Dec 2015 |  |  | 61 | 0 | 0 | 0
A-1 4TH FL. COLUMN | 948 | No Unit | 26 Oct 2015 | 05 Nov 2015 |  |  | 10 | 0 | 0 | 0
A-1 4th Fl. column Steel | 5.3292 | M.T. | 26 Oct 2015 | 05 Nov 2015 | 28 Sep 2015 | 10 Oct 2015 | 10 | 12 | 0 | 0
A-1 4th Fl. column RCC M-30 | 958.13 | Cft | 26 Oct 2015 | 05 Nov 2015 | 01 Oct 2015 | 10 Oct 2015 | 10 | 9 | 0 | 0
A-1- 5TH SLAB (4TH FL.) | 0 | No Unit | 26 Oct 2015 | 16 Nov 2015 |  |  | 21 | 0 | 0 | 0
A-1- 5th Slab (4th Fl.) Steel | 6.4838 | M.T. | 31 Oct 2015 | 12 Nov 2015 | 04 Oct 2015 | 14 Oct 2015 | 12 | 10 | 0 | 0
A-1- 5th Slab (4th Fl.) RMC M-20 Site | 78.49 | Cum. | 13 Nov 2015 | 14 Nov 2015 | 14 Oct 2015 | 14 Oct 2015 | 1 | 0 | 0 | 0
A-1- 5th Slab (4th Fl.) RCC M-20 | 184.17 | Cft | 31 Oct 2015 | 04 Nov 2015 | 09 Oct 2015 | 14 Oct 2015 | 4 | 5 | 0 | 0
A-1- 5th Slab (4th Fl.) RMC M-30 Site | 8.11 | Cum. | 13 Nov 2015 | 14 Nov 2015 | 14 Oct 2015 | 14 Oct 2015 | 1 | 0 | 0 | 0
A-1- 5th Slab (4th Fl.) Buttering | 1 | Slab | 13 Nov 2015 | 14 Nov 2015 | 14 Oct 2015 | 14 Oct 2015 | 1 | 0 | 0 | 0
A-1- 5th Slab (4th Fl.) Ponding | 1 | Slab | 16 Nov 2015 | 16 Nov 2015 | 15 Oct 2015 | 17 Oct 2015 | 0 | 2 | 0 | 0
A-1- 5th Slab (4th Fl.) RCC Slab (Lab) | 64403 | Sft. | 26 Oct 2015 | 14 Nov 2015 | 14 Oct 2015 | 13 Dec 2015 | 19 | 60 | 0 | 29
A-1-4TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 17 Nov 2015 | 26 Dec 2015 |  |  | 39 | 0 | 0 | 0
A-1-4th Flr.Cornice/Pardi/Cill Steel | 0.1236 | M.T. | 17 Nov 2015 | 26 Dec 2015 | 02 Dec 2015 | 09 Dec 2015 | 39 | 7 | 15 | 0
A-1-4th Flr.Cornice/Pardi/Cill RCC M-20 | 36.06 | Cft | 17 Nov 2015 | 26 Dec 2015 | 28 Nov 2015 | 09 Dec 2015 | 39 | 11 | 11 | 0
A1- 6TH SLAB (5TH FL.) | 0 | No Unit | 16 Nov 2015 | 19 Jan 2016 |  |  | 64 | 0 | 0 | 0
A-1 5TH FL. COLUMN | 7.1859 | No Unit | 16 Nov 2015 | 26 Nov 2015 |  |  | 10 | 0 | 0 | 0
A-1 5th Fl. column Steel | 5.774 | M.T. | 16 Nov 2015 | 26 Nov 2015 | 10 Oct 2015 | 26 Oct 2015 | 10 | 16 | 0 | 0
A-1 5th Fl. column RCC M-25 | 954.72 | Cft | 16 Nov 2015 | 26 Nov 2015 | 14 Oct 2015 | 26 Oct 2015 | 10 | 12 | 0 | 0
A-1- 6TH SLAB (5TH FL.) | 7.1859 | No Unit | 16 Nov 2015 | 08 Dec 2015 |  |  | 22 | 0 | 0 | 0
A-1- 6th Slab (5th Fl.) Steel | 7.285 | M.T. | 21 Nov 2015 | 04 Dec 2015 | 16 Oct 2015 | 30 Oct 2015 | 13 | 14 | 0 | 0
A-1- 6th Slab (5th Fl.) RMC M-20 Site | 82.48 | Cum. | 05 Dec 2015 | 07 Dec 2015 | 28 Oct 2015 | 30 Oct 2015 | 2 | 2 | 0 | 0
A-1- 6th Slab (5th Fl.) RCC M-20 | 184.17 | Cft | 21 Nov 2015 | 25 Nov 2015 | 24 Oct 2015 | 30 Oct 2015 | 4 | 6 | 0 | 0
A-1- 6th Slab (5th Fl.) RMC M-25 Site | 8.08 | Cum. | 05 Dec 2015 | 07 Dec 2015 | 28 Oct 2015 | 30 Oct 2015 | 2 | 2 | 0 | 0
A-1- 6th Slab (5th Fl.) Buttering | 1 | Slab | 05 Dec 2015 | 07 Dec 2015 | 28 Oct 2015 | 30 Oct 2015 | 2 | 2 | 0 | 0
A-1- 6th Slab (5th Fl.) Ponding | 1 | Slab | 08 Dec 2015 | 08 Dec 2015 | 30 Oct 2015 | 30 Oct 2015 | 0 | 0 | 0 | 0
A-1- 6th Slab (5th Fl.) RCC Slab (Lab) | 64403 | Sft. | 16 Nov 2015 | 05 Dec 2015 | 28 Oct 2015 | 04 Feb 2016 | 19 | 99 | 0 | 61
A-1 5TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 09 Dec 2015 | 19 Jan 2016 |  |  | 41 | 0 | 0 | 0
A-1 5th Flr.Cornice/Pardi/Cill Steel | 0.1988 | M.T. | 09 Dec 2015 | 19 Jan 2016 | 09 Dec 2015 | 09 Dec 2015 | 41 | 0 | 0 | 0
A-1 5th Flr.Cornice/Pardi/Cill RCC M-20 | 52.31 | Cft | 09 Dec 2015 | 19 Jan 2016 | 07 Dec 2015 | 09 Dec 2015 | 41 | 2 | 0 | 0
A1- 7TH SLAB (6TH FL.) | 0 | No Unit | 08 Dec 2015 | 06 Feb 2016 |  |  | 60 | 0 | 0 | 0
A-1 6TH FL. COLUMN | 0 | No Unit | 08 Dec 2015 | 16 Dec 2015 |  |  | 8 | 0 | 0 | 0
A-1 6th Fl. column Steel | 5.035 | M.T. | 08 Dec 2015 | 16 Dec 2015 | 26 Oct 2015 | 02 Nov 2015 | 8 | 7 | 0 | 0
A-1 6th Fl. column RCC M-25 | 922.26 | Cft | 08 Dec 2015 | 16 Dec 2015 | 30 Oct 2015 | 10 Nov 2015 | 8 | 11 | 0 | 0
A-1- 7TH SLAB (6TH FL.) | 7.1859 | No Unit | 08 Dec 2015 | 29 Dec 2015 |  |  | 21 | 0 | 0 | 0
A-1- 7th Slab (6th Fl.) Steel | 6.4838 | M.T. | 11 Dec 2015 | 25 Dec 2015 | 02 Nov 2015 | 10 Nov 2015 | 14 | 8 | 0 | 0
A-1- 7th Slab (6th Fl.) RMC M-20 Site | 78.49 | Cum. | 26 Dec 2015 | 28 Dec 2015 | 10 Nov 2015 | 10 Nov 2015 | 2 | 0 | 0 | 0
A-1- 7th Slab (6th Fl.) RCC M-20 | 184.17 | Cft | 14 Dec 2015 | 17 Dec 2015 | 07 Nov 2015 | 10 Nov 2015 | 3 | 3 | 0 | 0
A-1- 7th Slab (6th Fl.) RMC M-25 Site | 7.8 | Cum. | 26 Dec 2015 | 28 Dec 2015 | 10 Nov 2015 | 10 Nov 2015 | 2 | 0 | 0 | 0
A-1- 7th Slab (6th Fl.) Buttering | 1 | Slab | 26 Dec 2015 | 28 Dec 2015 | 10 Nov 2015 | 10 Nov 2015 | 2 | 0 | 0 | 0
A-1- 7th Slab (6th Fl.) Ponding | 1 | Slab | 29 Dec 2015 | 29 Dec 2015 | 10 Nov 2015 | 14 Nov 2015 | 0 | 4 | 0 | 0
A-1- 7th Slab (6th Fl.) RCC Slab (Lab) | 64403 | Sft. | 08 Dec 2015 | 28 Dec 2015 | 10 Nov 2015 | 25 Jan 2016 | 20 | 76 | 0 | 28
A-1 6TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 26 Dec 2015 | 06 Feb 2016 |  |  | 42 | 0 | 0 | 0
A-1 6th Flr.Cornice/Pardi/Cill Steel | 0.1236 | M.T. | 26 Dec 2015 | 06 Feb 2016 | 11 Dec 2015 | 28 Dec 2015 | 42 | 17 | 0 | 0
A-1 6th Flr.Cornice/Pardi/Cill RCC M-20 | 36.06 | Cft | 26 Dec 2015 | 06 Feb 2016 | 11 Dec 2015 | 28 Dec 2015 | 42 | 17 | 0 | 0
A1- 8TH SLAB (7TH FL.) | 0 | No Unit | 29 Dec 2015 | 26 Feb 2016 |  |  | 59 | 0 | 0 | 0
A-1 7TH FL. COLUMN | 0 | No Unit | 29 Dec 2015 | 06 Jan 2016 |  |  | 8 | 0 | 0 | 0
A-1 7th Fl. column Steel | 4.902 | M.T. | 29 Dec 2015 | 06 Jan 2016 | 09 Nov 2015 | 14 Nov 2015 | 8 | 5 | 0 | 0
A-1 7th Fl. column RCC M-25 | 918.84 | Cft | 29 Dec 2015 | 06 Jan 2016 | 13 Nov 2015 | 28 Nov 2015 | 8 | 15 | 0 | 0
A-1- 8TH SLAB (7TH FL.) | 0 | No Unit | 29 Dec 2015 | 22 Jan 2016 |  |  | 24 | 0 | 0 | 0
A-1- 8th Slab (7th Fl.) Steel | 7.098 | M.T. | 05 Jan 2016 | 12 Jan 2016 | 14 Nov 2015 | 28 Nov 2015 | 7 | 14 | 0 | 0
A-1- 8th Slab (7th Fl.) RMC M-20 Site | 83.5 | Cum. | 13 Jan 2016 | 14 Jan 2016 | 27 Nov 2015 | 28 Nov 2015 | 1 | 1 | 0 | 0
A-1- 8th Slab (7th Fl.) RCC M-20 | 184.17 | Cft | 05 Jan 2016 | 08 Jan 2016 | 23 Nov 2015 | 28 Nov 2015 | 3 | 5 | 0 | 0
A-1- 8th Slab (7th Fl.) RMC M-25 Site | 7.77 | Cum. | 13 Jan 2016 | 14 Jan 2016 | 27 Nov 2015 | 28 Nov 2015 | 1 | 1 | 0 | 0
A-1- 8th Slab (7th Fl.) Buttering | 1 | Slab | 13 Jan 2016 | 14 Jan 2016 | 27 Nov 2015 | 28 Nov 2015 | 1 | 1 | 0 | 0
A-1- 8th Slab (7th Fl.) Ponding | 1 | Slab | 15 Jan 2016 | 15 Jan 2016 | 28 Nov 2015 | 28 Nov 2015 | 0 | 0 | 0 | 0
A-1- 8th Slab (7th Fl.) RCC Slab (Lab) | 64403 | Sft. | 29 Dec 2015 | 22 Jan 2016 | 27 Nov 2015 | 25 Jan 2016 | 24 | 59 | 0 | 3
A-1 7TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 16 Jan 2016 | 26 Feb 2016 |  |  | 41 | 0 | 0 | 0
A-1 7th Flr.Cornice/Pardi/Cill Steel | 0.1988 | M.T. | 16 Jan 2016 | 26 Feb 2016 | 28 Dec 2015 | 18 Jan 2016 | 41 | 21 | 0 | 0
A-1 7th Flr.Cornice/Pardi/Cill RCC M-20 | 52.31 | Cft | 16 Jan 2016 | 26 Feb 2016 | 28 Dec 2015 | 18 Jan 2016 | 41 | 21 | 0 | 0
A1- 9TH SLAB (8TH FL.) | 0 | No Unit | 15 Jan 2016 | 15 Mar 2016 |  |  | 60 | 0 | 0 | 0
A-1 8TH FL. COLUMN | 0 | No Unit | 15 Jan 2016 | 22 Jan 2016 |  |  | 7 | 0 | 0 | 0
A-1 8th Fl. column Steel | 4.913 | M.T. | 15 Jan 2016 | 22 Jan 2016 | 23 Nov 2015 | 09 Dec 2015 | 7 | 16 | 0 | 0
A-1 8th Fl. column RCC M-25 | 918.84 | Cft | 15 Jan 2016 | 22 Jan 2016 | 28 Nov 2015 | 09 Dec 2015 | 7 | 11 | 0 | 0
A-1- 9TH SLAB (8TH FL.) | 0 | No Unit | 15 Jan 2016 | 09 Feb 2016 |  |  | 25 | 0 | 0 | 0
A-1- 9th Slab (8th Fl.) Steel | 6.4838 | M.T. | 21 Jan 2016 | 29 Jan 2016 | 01 Dec 2015 | 09 Dec 2015 | 8 | 8 | 0 | 0
A-1- 9th Slab (8th Fl.) RMC M-20 Site | 78.23 | Cum. | 30 Jan 2016 | 01 Feb 2016 | 11 Dec 2015 | 11 Dec 2015 | 2 | 0 | 0 | 0
A-1- 9th Slab (8th Fl.) RCC M-20 | 184.17 | Cft | 21 Jan 2016 | 25 Jan 2016 | 08 Dec 2015 | 09 Dec 2015 | 4 | 1 | 0 | 0
A-1- 9th Slab (8th Fl.) RMC M-25 Site | 7.77 | Cum. | 30 Jan 2016 | 01 Feb 2016 | 11 Dec 2015 | 11 Dec 2015 | 2 | 0 | 0 | 0
A-1- 9th Slab (8th Fl.) Buttering | 1 | Slab | 30 Jan 2016 | 01 Feb 2016 | 11 Dec 2015 | 11 Dec 2015 | 2 | 0 | 0 | 0
A-1- 9th Slab (8th Fl.) Ponding | 1 | Slab | 02 Feb 2016 | 02 Feb 2016 | 11 Dec 2015 | 11 Dec 2015 | 0 | 0 | 0 | 0
A-1- 9th Slab (8th Fl.) RCC Slab (Lab) | 64403 | Sft. | 15 Jan 2016 | 09 Feb 2016 | 11 Dec 2015 | 25 Jan 2016 | 25 | 45 | 0 | 0
A-1 8TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 03 Feb 2016 | 15 Mar 2016 |  |  | 41 | 0 | 0 | 0
A-1 8th Flr.Cornice/Pardi/Cill Steel | 0.1236 | M.T. | 03 Feb 2016 | 15 Mar 2016 | 17 Jan 2016 | 18 Jan 2016 | 41 | 1 | 0 | 0
A-1 8th Flr.Cornice/Pardi/Cill RCC M-20 | 36.06 | Cft | 03 Feb 2016 | 15 Mar 2016 | 17 Jan 2016 | 18 Jan 2016 | 41 | 1 | 0 | 0
A1-10TH SLAB (9TH FL.) | 0 | No Unit | 02 Feb 2016 | 31 Mar 2016 |  |  | 58 | 0 | 0 | 0
A-1 9TH FL. COLUMN | 7.754 | No Unit | 02 Feb 2016 | 09 Feb 2016 |  |  | 7 | 0 | 0 | 0
A-1 9th Fl. column Steel | 4.679 | M.T. | 02 Feb 2016 | 09 Feb 2016 | 09 Dec 2015 | 17 Dec 2015 | 7 | 8 | 0 | 0
A-1 9th Fl. column RCC M-25 | 979.83 | Cft | 02 Feb 2016 | 09 Feb 2016 | 12 Dec 2015 | 23 Dec 2015 | 7 | 11 | 0 | 0
A-1- 10TH SLAB (9TH FL.) | 0 | No Unit | 02 Feb 2016 | 22 Feb 2016 |  |  | 20 | 0 | 0 | 0
A-1- 10th Slab (9th Fl.) Steel | 7.098 | M.T. | 08 Feb 2016 | 15 Feb 2016 | 14 Dec 2015 | 24 Dec 2015 | 7 | 10 | 0 | 0
A-1- 10th Slab (9th Fl.) RMC M-20 Site | 82.22 | Cum. | 16 Feb 2016 | 17 Feb 2016 | 23 Dec 2015 | 24 Dec 2015 | 1 | 1 | 0 | 0
A-1- 10th Slab (9th Fl.) RCC M-20 | 184.17 | Cft | 08 Feb 2016 | 11 Feb 2016 | 20 Dec 2015 | 03 Jan 2016 | 3 | 14 | 0 | 0
A-1- 10th Slab (9th Fl.) RMC M-25 Site | 7.47 | Cum. | 16 Feb 2016 | 17 Feb 2016 | 23 Dec 2015 | 24 Dec 2015 | 1 | 1 | 0 | 0
A-1- 10th Slab (9th Fl.) Buttering | 1 | Slab | 16 Feb 2016 | 17 Feb 2016 | 23 Dec 2015 | 24 Dec 2015 | 1 | 1 | 0 | 0
A-1- 10th Slab (9th Fl.) Ponding | 1 | Slab | 18 Feb 2016 | 18 Feb 2016 | 24 Dec 2015 | 24 Dec 2015 | 0 | 0 | 0 | 0
A-1- 10th Slab (9th Fl.) RCC Slab (Lab) | 64403 | Sft. | 02 Feb 2016 | 22 Feb 2016 | 23 Dec 2015 | 17 Mar 2016 | 20 | 85 | 0 | 24
A-1 9TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 19 Feb 2016 | 31 Mar 2016 |  |  | 41 | 0 | 0 | 0
A-1 9th Flr.Cornice/Pardi/Cill Steel | 0.1988 | M.T. | 19 Feb 2016 | 31 Mar 2016 | 25 Jan 2016 | 04 Feb 2016 | 41 | 10 | 0 | 0
A-1 9th Flr.Cornice/Pardi/Cill RCC M-20 | 52.31 | Cft | 19 Feb 2016 | 31 Mar 2016 | 25 Jan 2016 | 04 Feb 2016 | 41 | 10 | 0 | 0
A1-11TH SLAB (10TH FL.) | 0 | No Unit | 18 Feb 2016 | 16 Apr 2016 |  |  | 58 | 0 | 0 | 0
A-1 10TH FL. COLUMN | 0 | No Unit | 18 Feb 2016 | 25 Feb 2016 |  |  | 7 | 0 | 0 | 0
A-1 10th Fl. column Steel | 4.6247 | M.T. | 18 Feb 2016 | 25 Feb 2016 | 22 Dec 2015 | 06 Jan 2016 | 7 | 15 | 0 | 0
A-1 10th Fl. column RCC M-25 | 979.83 | Cft | 18 Feb 2016 | 25 Feb 2016 | 24 Dec 2015 | 06 Jan 2016 | 7 | 13 | 0 | 0
A-1- 11 SLAB (10TH FL.) | 0 | No Unit | 18 Feb 2016 | 14 Mar 2016 |  |  | 25 | 0 | 0 | 0
A-1- 11 Slab (10th Fl.) Steel | 6.4838 | M.T. | 24 Feb 2016 | 02 Mar 2016 | 26 Dec 2015 | 06 Jan 2016 | 7 | 11 | 0 | 0
A-1- 11 Slab (10th Fl.) RMC M-20 Site | 78.23 | Cum. | 03 Mar 2016 | 04 Mar 2016 | 07 Jan 2016 | 07 Jan 2016 | 1 | 0 | 0 | 0
A-1- 11 Slab (10th Fl.) RCC M-20 | 184.17 | Cft | 24 Feb 2016 | 27 Feb 2016 | 03 Jan 2016 | 06 Jan 2016 | 3 | 3 | 0 | 0
A-1- 11 Slab (10th Fl.) RMC M-25 Site | 7.47 | Cum. | 03 Mar 2016 | 04 Mar 2016 | 07 Jan 2016 | 07 Jan 2016 | 1 | 0 | 0 | 0
A-1- 11 Slab (10th Fl.) Buttering | 1 | Slab | 03 Mar 2016 | 04 Mar 2016 | 07 Jan 2016 | 07 Jan 2016 | 1 | 0 | 0 | 0
A-1- 11 Slab (10th Fl.) Ponding | 1 | Slab | 05 Mar 2016 | 05 Mar 2016 | 08 Jan 2016 | 13 Jan 2016 | 0 | 5 | 0 | 0
A-1- 11 Slab (10th Fl.) RCC Slab (Lab) | 64403 | Sft. | 18 Feb 2016 | 14 Mar 2016 | 07 Jan 2016 | 03 May 2016 | 25 | 117 | 0 | 50
A-1 10TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 08 Mar 2016 | 16 Apr 2016 |  |  | 39 | 0 | 0 | 0
A-1 10th Flr.Cornice/Pardi/Cill Steel | 0.11 | M.T. | 08 Mar 2016 | 16 Apr 2016 | 11 Feb 2016 | 03 May 2016 | 39 | 82 | 0 | 17
A-1 10th Flr.Cornice/Pardi/Cill RCC M-20 | 30 | Cft | 08 Mar 2016 | 16 Apr 2016 | 11 Feb 2016 | 26 Mar 2016 | 39 | 44 | 0 | 0
A1-12TH SLAB (11TH FL.) | 0 | No Unit | 05 Mar 2016 | 02 May 2016 |  |  | 58 | 0 | 0 | 0
A-1 -11TH FL. COLUMN | 0 | No Unit | 05 Mar 2016 | 12 Mar 2016 |  |  | 7 | 0 | 0 | 0
A-1 -11th Fl. column Steel | 4.5959 | M.T. | 05 Mar 2016 | 12 Mar 2016 | 05 Jan 2016 | 14 Jan 2016 | 7 | 9 | 0 | 0
A-1 -11th Fl. column RCC M-25 | 976.41 | Cft | 05 Mar 2016 | 12 Mar 2016 | 18 Jan 2016 | 18 Jan 2016 | 7 | 0 | 0 | 0
A-1- 12TH SLAB (11TH FL.) | 0 | No Unit | 05 Mar 2016 | 30 Mar 2016 |  |  | 25 | 0 | 0 | 0
A-1- 12th Slab (11th Fl.) Steel | 7.098 | M.T. | 12 Mar 2016 | 18 Mar 2016 | 11 Jan 2016 | 18 Jan 2016 | 6 | 7 | 0 | 0
A-1- 12th Slab (11th Fl.) RMC M-20 Site | 82.22 | Cum. | 19 Mar 2016 | 21 Mar 2016 | 24 Jan 2016 | 24 Jan 2016 | 2 | 0 | 0 | 0
A-1- 12th Slab (11th Fl.) RCC M-20 | 184.17 | Cft | 12 Mar 2016 | 16 Mar 2016 | 20 Jan 2016 | 04 Feb 2016 | 4 | 15 | 0 | 0
A-1- 12th Slab (11th Fl.) RMC M-25 Site | 7.44 | Cum. | 19 Mar 2016 | 21 Mar 2016 | 24 Jan 2016 | 24 Jan 2016 | 2 | 0 | 0 | 0
A-1- 12th Slab (11th Fl.) Buttering | 1 | Slab | 19 Mar 2016 | 21 Mar 2016 | 24 Jan 2016 | 24 Jan 2016 | 2 | 0 | 0 | 0
A-1- 12th Slab (11th Fl.) Ponding | 1 | Slab | 22 Mar 2016 | 22 Mar 2016 | 25 Jan 2016 | 04 Feb 2016 | 0 | 10 | 0 | 0
A-1- 12th Slab (11th Fl.) RCC Slab (Lab) | 64403 | Sft. | 05 Mar 2016 | 30 Mar 2016 | 23 Jan 2016 | 03 May 2016 | 25 | 101 | 0 | 34
A-1 11TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 23 Mar 2016 | 02 May 2016 |  |  | 40 | 0 | 0 | 0
A-1 11th Flr.Cornice/Pardi/Cill Steel | 0.16 | M.T. | 23 Mar 2016 | 02 May 2016 | 11 Mar 2016 | 03 May 2016 | 40 | 53 | 0 | 1
A-1 11th Flr.Cornice/Pardi/Cill RCC M-20 | 45 | Cft | 23 Mar 2016 | 02 May 2016 | 11 Mar 2016 | 26 Mar 2016 | 40 | 15 | 0 | 0
A1-13TH SLAB (12TH FL.) | 0 | No Unit | 22 Mar 2016 | 01 Apr 2016 |  |  | 10 | 0 | 0 | 0
A-1 12TH FL. COLUMN | 0 | No Unit | 22 Mar 2016 | 28 Mar 2016 |  |  | 6 | 0 | 0 | 0
A-1 12th Fl. column Steel | 4.4063 | M.T. | 22 Mar 2016 | 28 Mar 2016 | 19 Jan 2016 | 04 Feb 2016 | 6 | 16 | 0 | 0
A-1 12th Fl. column RCC M-25 | 947.37 | Cft | 22 Mar 2016 | 28 Mar 2016 | 25 Jan 2016 | 12 Feb 2016 | 6 | 18 | 0 | 0
A-1- 13TH SLAB (12TH FL.) | 0 | No Unit | 22 Mar 2016 | 01 Apr 2016 |  |  | 10 | 0 | 0 | 0
A-1- 13th Slab (12th Fl.) Steel | 6.4838 | M.T. | 28 Mar 2016 | 30 Mar 2016 | 27 Jan 2016 | 04 Feb 2016 | 2 | 8 | 0 | 0
A-1- 13th Slab (12th Fl.) RMC M-20 Site | 82.23 | Cum. | 31 Mar 2016 | 31 Mar 2016 | 12 Feb 2016 | 13 Feb 2016 | 0 | 1 | 0 | 0
A-1- 13th Slab (12th Fl.) RCC M-20 | 175 | Cft | 28 Mar 2016 | 31 Mar 2016 | 09 Feb 2016 | 12 Feb 2016 | 3 | 3 | 0 | 0
A-1- 13th Slab (12th Fl.) RMC M-25 Site | 7 | Cum. | 31 Mar 2016 | 31 Mar 2016 | 12 Feb 2016 | 13 Feb 2016 | 0 | 1 | 0 | 0
A-1- 13th Slab (12th Fl.) Buttering | 1 | Slab | 31 Mar 2016 | 31 Mar 2016 | 12 Feb 2016 | 13 Feb 2016 | 0 | 1 | 0 | 0
A-1- 13th Slab (12th Fl.) Ponding | 1 | Slab | 01 Apr 2016 | 01 Apr 2016 | 13 Feb 2016 | 13 Feb 2016 | 0 | 0 | 0 | 0
A-1- 13th Slab (12th Fl.) RCC Slab (Lab) | 64403 | Sft. | 22 Mar 2016 | 30 Mar 2016 | 12 Feb 2016 | 30 Jun 2016 | 8 | 139 | 0 | 92
A-1 12TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 22 Mar 2016 | 22 Mar 2016 |  |  | 0 | 0 | 0 | 0
A-1 12th Flr.Cornice/Pardi/Cill Steel | 0.1 | M.T. | 22 Mar 2016 | 22 Mar 2016 | 14 Apr 2016 | 30 Jun 2016 | 0 | 77 | 23 | 100
A-1 12th Flr.Cornice/Pardi/Cill RCC M-20 | 25 | Cft | 22 Mar 2016 | 22 Mar 2016 | 14 Apr 2016 | 30 Jun 2016 | 0 | 77 | 23 | 100
A1-14TH SLAB (13TH FL.) | 184.17 | No Unit | 23 Mar 2016 | 28 Jun 2016 |  |  | 97 | 0 | 0 | 0
A-1 13TH FL. COLUMN | 0 | No Unit | 23 Mar 2016 | 30 Mar 2016 |  |  | 7 | 0 | 0 | 0
A-1 13th Fl. column Steel | 4.3806 | M.T. | 23 Mar 2016 | 30 Mar 2016 | 06 Feb 2016 | 30 Jun 2016 | 7 | 145 | 0 | 92
A-1 13th Fl. column RCC M-25 | 943.95 | Cft | 23 Mar 2016 | 30 Mar 2016 | 16 Feb 2016 | 30 Jun 2016 | 7 | 135 | 0 | 92
A-1- 14TH SLAB (13TH FL.) | 0 | No Unit | 23 Mar 2016 | 18 May 2016 |  |  | 56 | 0 | 0 | 0
A-1- 14th Slab (13th Fl.) Steel | 6.62 | M.T. | 07 May 2016 | 16 May 2016 | 28 Mar 2016 | 13 Sep 2016 | 9 | 169 | 0 | 120
A-1- 14th Slab (13th Fl.) RMC M-20 Site | 107 | Cum. | 17 May 2016 | 17 May 2016 | 12 Apr 2016 | 09 Sep 2016 | 0 | 150 | 0 | 115
A-1- 14th Slab Concreting | 175 | Cft | 29 Mar 2016 | 01 Apr 2016 | 04 Apr 2016 | 09 Sep 2016 | 3 | 158 | 6 | 161
A-1- 14th Slab (13th Fl.) RMC M-25 Site | 7 | Cum. | 17 May 2016 | 17 May 2016 | 12 Apr 2016 | 09 Sep 2016 | 0 | 150 | 0 | 115
A-1- 14th Slab (13th Fl.) Buttering | 1 | Slab | 17 May 2016 | 17 May 2016 | 12 Apr 2016 | 09 Sep 2016 | 0 | 150 | 0 | 115
A-1- 14th Slab (13th Fl.) Ponding | 1 | Slab | 18 May 2016 | 18 May 2016 | 13 Apr 2016 | 09 Sep 2016 | 0 | 149 | 0 | 114
A-1- 14th Slab (13th Fl.) RCC Slab (Lab) | 64403 | Sft. | 23 Mar 2016 | 07 Apr 2016 | 22 Oct 2016 | 16 Dec 2016 | 15 | 55 | 213 | 253
A-1- 14th Slab (13th Fl.) Misc. Shuttering | 25000 | Job | 23 May 2015 |  | 12 Dec 2016 | 26 Dec 2016 | 0 | 14 | 569 | 42728
A-1 13TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 19 May 2016 | 28 Jun 2016 |  |  | 40 | 0 | 0 | 0
A-1 13th Flr.Cornice/Pardi/Cill Steel | 0 | M.T. | 19 May 2016 | 28 Jun 2016 | 09 Apr 2016 | 13 Sep 2016 | 40 | 157 | 0 | 77
A-1 13th Flr.Cornice/Pardi/Cill RCC M-20 | 25 | Cft | 19 May 2016 | 28 Jun 2016 | 09 Apr 2016 | 13 Sep 2016 | 40 | 157 | 0 | 77
A1-15TH SLAB (14TH FL.) | 0 | No Unit | 18 May 2016 | 14 Jul 2016 |  |  | 57 | 0 | 0 | 0
A-1 14TH FL. COLUMN | 0 | No Unit | 18 May 2016 | 25 May 2016 |  |  | 7 | 0 | 0 | 0
A-1 14th Fl. column Steel | 3.369 | M.T. | 18 May 2016 | 25 May 2016 | 16 Apr 2016 | 13 Sep 2016 | 7 | 150 | 0 | 111
A-1 14th Fl. column RCC M-25 | 943.95 | Cft | 18 May 2016 | 25 May 2016 | 20 Apr 2016 | 13 Sep 2016 | 7 | 146 | 0 | 111
A-1- 15TH SLAB (14TH FL.) | 4.6247 | No Unit | 18 May 2016 | 07 Jun 2016 |  |  | 20 | 0 | 0 | 0
A-1- 15th Slab (14th Fl.) Steel | 6 | M.T. | 24 May 2016 | 01 Jun 2016 | 20 Apr 2016 | 13 Sep 2016 | 8 | 146 | 0 | 104
A-1- 15th Slab (14th Fl.) RMC M-20 Site | 21 | Cum. | 02 Jun 2016 | 02 Jun 2016 | 02 May 2016 | 13 Sep 2016 | 0 | 134 | 0 | 103
A-1- 15th Slab (14th Fl.) RCC M-20 | 175 | Cft | 23 May 2016 | 26 May 2016 | 25 Apr 2016 | 13 Sep 2016 | 3 | 141 | 0 | 110
A-1- 15th Slab (14th Fl.) RMC M-25 Site | 3.5 | Cum. | 02 Jun 2016 | 02 Jun 2016 | 02 May 2016 | 13 Sep 2016 | 0 | 134 | 0 | 103
A-1- 15th Slab (14th Fl.) Buttering | 1 | Slab | 02 Jun 2016 | 02 Jun 2016 | 02 May 2016 | 13 Sep 2016 | 0 | 134 | 0 | 103
A-1- 15th Slab (14th Fl.) Ponding | 1 | Slab | 03 Jun 2016 | 03 Jun 2016 | 13 Jun 2016 | 13 Sep 2016 | 0 | 92 | 10 | 102
A-1- 15th Slab (14th Fl.) RCC Slab (Lab) | 64403 | Sft. | 18 May 2016 | 07 Jun 2016 | 24 Sep 2016 | 24 Sep 2016 | 20 | 0 | 129 | 109
A-1 14TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 04 Jun 2016 | 14 Jul 2016 |  |  | 40 | 0 | 0 | 0
A-1 14th Flr.Cornice/Pardi/Cill Steel | 0 | M.T. | 04 Jun 2016 | 14 Jul 2016 | 13 Sep 2016 | 17 Aug 2016 | 40 | 0 | 101 | 34
A-1 14th Flr.Cornice/Pardi/Cill RCC M-20 | 0 | Cft | 04 Jun 2016 | 14 Jul 2016 | 17 Aug 2016 | 17 Aug 2016 | 40 | 0 | 74 | 34
A1- ABOVE TERRACE | 0 | No Unit | 03 Jun 2016 | 13 Jul 2016 |  |  | 40 | 0 | 0 | 0
A1-ABOVE TERRACE COL. | 15.485 | No Unit | 03 Jun 2016 | 08 Jun 2016 |  |  | 5 | 0 | 0 | 0
A1-Above Terrace Col. Steel | 1.813 | M.T. | 03 Jun 2016 | 08 Jun 2016 | 30 Apr 2016 | 30 Jun 2016 | 5 | 61 | 0 | 22
A1-Above Terrace Col. RCC M-25 | 120 | Cft | 03 Jun 2016 | 08 Jun 2016 | 03 Jun 2016 | 13 Jun 2016 | 5 | 10 | 0 | 5
A1-Above Terrace Col. RCC M10 | 451.69 | Cft | 23 May 2015 |  | 09 Sep 2016 | 26 Oct 2016 | 0 | 47 | 475 | 42667
A1- OHWT+ LMR | 0 | No Unit | 09 Jun 2016 | 01 Jul 2016 |  |  | 22 | 0 | 0 | 0
A1- OHWT+ LMR Steel | 4.35 | M.T. | 09 Jun 2016 | 01 Jul 2016 | 06 Jun 2016 | 30 Jun 2016 | 22 | 24 | 0 | 0
A1- OHWT+ LMR RMC M-25 Site | 17 | Cum. | 09 Jun 2016 | 01 Jul 2016 | 30 Jul 2016 | 17 Aug 2016 | 22 | 18 | 51 | 47
A1- OHWT+ LMR RMC M-20 Site | 55 | Cum. | 09 Jun 2016 | 01 Jul 2016 | 30 Jul 2016 | 17 Aug 2016 | 22 | 18 | 51 | 47
A1- OHWT+ LMR RCC M-20 | 50 | Cft | 09 Jun 2016 | 01 Jul 2016 | 07 Jun 2016 | 30 Jun 2016 | 22 | 23 | 0 | 0
A1- OHWT+ LMR Buttering | 1 | Slab | 09 Jun 2016 | 01 Jul 2016 | 30 Jul 2016 | 17 Aug 2016 | 22 | 18 | 51 | 47
A1- OHWT+ LMR Ponding | 1 | Slab | 09 Jun 2016 | 01 Jul 2016 | 30 Jul 2016 | 17 Aug 2016 | 22 | 18 | 51 | 47
A1- OHWT+ LMR RCC Slab (Lab) | 64403 | Sft. | 09 Jun 2016 | 01 Jul 2016 | 16 Jun 2016 | 17 Aug 2016 | 22 | 62 | 7 | 47
A1-TERRACE LIN/CORNICE/PARDI/CILL | 0 | No Unit | 02 Jul 2016 | 09 Jul 2016 |  |  | 7 | 0 | 0 | 0
A1-Terrace Lin/Cornice/Pardi/Cill Steel | 0 | M.T. | 02 Jul 2016 | 09 Jul 2016 | 14 Jul 2016 | 17 Aug 2016 | 7 | 34 | 12 | 39
A1-Terrace Lin/Cornice/Pardi/Cill RCC M-20 | 25 | Cft | 02 Jul 2016 | 09 Jul 2016 | 17 Aug 2016 | 17 Aug 2016 | 7 | 0 | 46 | 39
A1-ELEVATIONAL SLAB | 0 | No Unit | 02 Jul 2016 | 13 Jul 2016 |  |  | 11 | 0 | 0 | 0
A1-Elevational Slab Steel | 0 | M.T. | 02 Jul 2016 | 13 Jul 2016 | 25 Jun 2016 | 17 Aug 2016 | 11 | 53 | 0 | 35
A1-Elevational Slab RCC M-20 | 158.61 | Cft | 02 Jul 2016 | 13 Jul 2016 | 30 Jun 2016 | 17 Aug 2016 | 11 | 48 | 0 | 35
A1- CONCRETE PUMP | 0 | No Unit | 29 Jun 2015 | 13 Jul 2016 |  |  | 380 | 0 | 0 | 0
A1- Concrete Pump Concrete Pump Operation | 15 | Month. | 29 Jun 2015 | 13 Jul 2016 | 18 Aug 2015 | 24 Sep 2016 | 380 | 403 | 50 | 73
A1- RCC FARMA | 0 | No Unit | 06 Jul 2015 | 28 Jul 2015 |  |  | 22 | 0 | 0 | 0
A1- RCC Farma Misc. | 1 | Job | 06 Jul 2015 | 28 Jul 2015 | 26 Aug 2015 | 24 Sep 2016 | 22 | 395 | 51 | 424
A1-SHUTTERING MATERIAL | 0 | No Unit | 06 Jul 2015 | 28 Jul 2015 |  |  | 22 | 0 | 0 | 0
A1-Shuttering Material Shuttering Material - M.S | 0 | Sft. | 06 Jul 2015 | 28 Jul 2015 | 28 Aug 2015 | 30 Jun 2016 | 22 | 307 | 53 | 338
A1-COVER BLOCK | 0 | No Unit | 22 Jun 2015 | 10 Jun 2016 |  |  | 354 | 0 | 0 | 0
A1-Cover Block Cover Block 50 mm | 795 | No. | 22 Jun 2015 | 10 Jun 2016 | 07 Jul 2015 | 24 Sep 2016 | 354 | 445 | 15 | 106
A1-Cover Block Cover Block 40 mm | 14416 | No. | 22 Jun 2015 | 10 Jun 2016 | 07 Jul 2015 | 24 Sep 2016 | 354 | 445 | 15 | 106
A1-Cover Block Cover Block 20 mm | 24151 | No. | 22 Jun 2015 | 10 Jun 2016 | 07 Jul 2015 | 24 Sep 2016 | 354 | 445 | 15 | 106
A1-MASONRY | 0 | No Unit | 12 Aug 2015 | 27 Jul 2016 |  |  | 350 | 0 | 0 | 0
A1-PARKING FLOOR | 0 | No Unit | 18 Aug 2015 | 09 Oct 2015 |  |  | 52 | 0 | 0 | 0
A1-Parking Floor CLC Block Masonry 4" | 0 | Sft. | 01 Oct 2015 | 09 Oct 2015 | 07 Sep 2015 | 14 Sep 2015 | 8 | 7 | 0 | 0
A1-Parking Floor CLC Block Masonry 6" | 1433.65 | Sft. | 01 Oct 2015 | 09 Oct 2015 | 07 Sep 2015 | 05 Nov 2015 | 8 | 59 | 0 | 27
A1-Parking Floor Masonry (Lab) | 62960 | Sft. | 01 Oct 2015 | 09 Oct 2015 | 26 Sep 2015 | 24 Dec 2015 | 8 | 89 | 0 | 76
A1-1ST FLOOR | 0 | No Unit | 22 Sep 2015 | 02 Nov 2015 |  |  | 41 | 0 | 0 | 0
A1-1st Floor CLC Block Masonry 4" | 161.99 | Sft. | 27 Oct 2015 | 02 Nov 2015 |  | 27 Oct 2015 | 6 | 42302 | 0 | 0 | Brickwork consist of 4" first class bricks shall be laid in the mortar (1:6). Work shall be constructed strictly according to drawing and specifications accompanying the estimate. Bricks required for brickwork in cement or lime, mortars shall be thoroughly soaked in clean water immediately before use for one hour or till the complete cessation of air bubbles whichever is later, in brick-lined or steel tanks of sufficient size.
A1-1st Floor CLC Block Masonry 6" | 533.678 | Sft. | 15 Oct 2015 | 02 Nov 2015 |  | 27 Oct 2015 | 18 | 42302 | 0 | 0
A1-1st Floor Masonry (Lab) | 62960 | Sft. | 15 Oct 2015 | 02 Nov 2015 | 24 Dec 2015 | 24 Dec 2015 | 18 | 0 | 70 | 52
A1-1st Floor BBM 6" | 1000 | Sft. | 06 Aug 2016 |  | 20 Jan 2018 |  | 0 | 0 | 532 | 0
A1-1st Floor Brickwork 150 MM | 100 | Sq.mtr. | 06 Aug 2016 |  | 20 Mar 2020 |  | 0 | 0 | 1322 | 0
A1-2ND FLOOR | 0 | No Unit | 10 Oct 2015 | 10 Nov 2015 |  |  | 31 | 0 | 0 | 0
A1-2nd Floor CLC Block Masonry 4" | 161.99 | Sft. | 04 Nov 2015 | 10 Nov 2015 | 14 Oct 2015 | 05 Nov 2015 | 6 | 22 | 0 | 0
A1-2nd Floor CLC Block Masonry 6" | 4398.84 | Sft. | 23 Oct 2015 | 10 Nov 2015 | 14 Oct 2015 | 05 Nov 2015 | 18 | 22 | 0 | 0
A1-2nd Floor Masonry (Lab) | 62960 | Sft. | 23 Oct 2015 | 10 Nov 2015 | 14 Oct 2015 | 24 Dec 2015 | 18 | 71 | 0 | 44
A1-3RD FLOOR | 0 | No Unit | 28 Oct 2015 | 30 Nov 2015 |  |  | 33 | 0 | 0 | 0
A1-3rd Floor CLC Block Masonry 4" | 161.99 | Sft. | 24 Nov 2015 | 30 Nov 2015 | 02 Nov 2015 | 02 Dec 2015 | 6 | 30 | 0 | 2
A1-3rd Floor CLC Block Masonry 6" | 4333.44 | Sft. | 12 Nov 2015 | 30 Nov 2015 | 02 Nov 2015 | 02 Dec 2015 | 18 | 30 | 0 | 2
A1-3rd Floor Masonry (Lab) | 62960 | Sft. | 12 Nov 2015 | 30 Nov 2015 | 02 Nov 2015 | 24 Dec 2015 | 18 | 52 | 0 | 24
A1-4TH FLOOR | 0 | No Unit | 17 Nov 2015 | 21 Dec 2015 |  |  | 34 | 0 | 0 | 0
A1-4th Floor CLC Block Masonry 4" | 161.99 | Sft. | 15 Dec 2015 | 21 Dec 2015 | 19 Nov 2015 | 17 Dec 2015 | 6 | 28 | 0 | 0
A1-4th Floor CLC Block Masonry 6" | 4398.84 | Sft. | 03 Dec 2015 | 21 Dec 2015 | 19 Nov 2015 | 17 Dec 2015 | 18 | 28 | 0 | 0
A1-4th Floor Masonry (Lab) | 62960 | Sft. | 03 Dec 2015 | 21 Dec 2015 | 19 Nov 2015 | 04 Feb 2016 | 18 | 77 | 0 | 45
A1-5TH FLOOR | 0 | No Unit | 10 Dec 2015 | 13 Jan 2016 |  |  | 34 | 0 | 0 | 0
A1-5th Floor CLC Block Masonry 4" | 161.99 | Sft. | 07 Jan 2016 | 13 Jan 2016 | 15 Dec 2015 | 28 Dec 2015 | 6 | 13 | 0 | 0
A1-5th Floor CLC Block Masonry 6" | 4279.22 | Sft. | 25 Dec 2015 | 13 Jan 2016 | 15 Dec 2015 | 28 Dec 2015 | 19 | 13 | 0 | 0
A1-5th Floor Masonry (Lab) | 62960 | Sft. | 25 Dec 2015 | 13 Jan 2016 | 15 Dec 2015 | 04 Feb 2016 | 19 | 51 | 0 | 22
A1-6TH FLOOR | 0 | No Unit | 30 Dec 2015 | 04 Feb 2016 |  |  | 36 | 0 | 0 | 0
A1-6th Floor CLC Block Masonry 4" | 216.2 | Sft. | 29 Jan 2016 | 04 Feb 2016 | 23 Dec 2015 | 31 Dec 2015 | 6 | 8 | 0 | 0
A1-6th Floor CLC Block Masonry 6" | 4344.62 | Sft. | 16 Jan 2016 | 04 Feb 2016 | 23 Dec 2015 | 31 Dec 2015 | 19 | 8 | 0 | 0
A1-6th Floor Masonry (Lab) | 62960 | Sft. | 16 Jan 2016 | 04 Feb 2016 | 23 Dec 2015 | 04 Feb 2016 | 19 | 43 | 0 | 0
A1-7TH FLOOR | 0 | No Unit | 20 Jan 2016 | 20 Feb 2016 |  |  | 31 | 0 | 0 | 0
A1-7th Floor CLC Block Masonry 4" | 216.2 | Sft. | 15 Feb 2016 | 20 Feb 2016 | 28 Dec 2015 | 04 Feb 2016 | 5 | 38 | 0 | 0
A1-7th Floor CLC Block Masonry 6" | 4179.22 | Sft. | 03 Feb 2016 | 20 Feb 2016 | 28 Dec 2015 | 04 Feb 2016 | 17 | 38 | 0 | 0
A1-7th Floor Masonry (Lab) | 62960 | Sft. | 03 Feb 2016 | 20 Feb 2016 | 28 Dec 2015 | 04 Feb 2016 | 17 | 38 | 0 | 0
A1-8TH FLOOR | 0 | No Unit | 10 Feb 2016 | 09 Mar 2016 |  |  | 28 | 0 | 0 | 0
A1-8th Floor CLC Block Masonry 4" | 205.36 | Sft. | 02 Mar 2016 | 09 Mar 2016 | 05 Jan 2016 | 04 Feb 2016 | 7 | 30 | 0 | 0
A1-8th Floor CLC Block Masonry 6" | 3990.49 | Sft. | 19 Feb 2016 | 09 Mar 2016 | 05 Jan 2016 | 04 Feb 2016 | 19 | 30 | 0 | 0
A1-8th Floor Masonry (Lab) | 62960 | Sft. | 19 Feb 2016 | 09 Mar 2016 | 05 Jan 2016 | 17 Mar 2016 | 19 | 72 | 0 | 8
A1-9TH FLOOR | 134.45 | No Unit | 01 Mar 2016 | 30 Mar 2016 |  |  | 29 | 0 | 0 | 0
A1-9th Floor CLC Block Masonry 4" | 216.2 | Sft. | 19 Mar 2016 | 25 Mar 2016 | 14 Jan 2016 | 04 Feb 2016 | 6 | 21 | 0 | 0
A1-9th Floor CLC Block Masonry 6" | 4179.22 | Sft. | 08 Mar 2016 | 30 Mar 2016 | 14 Jan 2016 | 04 Feb 2016 | 22 | 21 | 0 | 0
A1-9th Floor Masonry (Lab) | 62960 | Sft. | 08 Mar 2016 | 25 Mar 2016 | 14 Jan 2016 | 17 Mar 2016 | 17 | 63 | 0 | 0
A1-9th Floor CLC Block Masonry 6" | 0 | Sft. | 08 Mar 2016 | 25 Mar 2016 | 12 Feb 2016 | 12 Feb 2016 | 17 | 0 | 0 | 0
A1-10TH FLOOR | 0 | No Unit | 16 Mar 2016 | 11 Apr 2016 |  |  | 26 | 0 | 0 | 0
A1-10th Floor CLC Block Masonry 4" | 162 | Sft. | 05 Apr 2016 | 11 Apr 2016 | 03 Feb 2016 | 12 Feb 2016 | 6 | 9 | 0 | 0
A1-10th Floor CLC Block Masonry 6" | 4398.84 | Sft. | 24 Mar 2016 | 11 Apr 2016 | 03 Feb 2016 | 20 Apr 2016 | 18 | 77 | 0 | 9
A1-10th Floor Masonry (Lab) | 62960 | Sft. | 24 Mar 2016 | 11 Apr 2016 | 03 Feb 2016 | 17 Mar 2016 | 18 | 43 | 0 | 0
A1-11TH FLOOR | 0 | No Unit | 28 Mar 2016 | 20 May 2016 |  |  | 53 | 0 | 0 | 0
A1-11th Floor CLC Block Masonry 4" | 216.2 | Sft. | 14 May 2016 | 20 May 2016 | 23 Feb 2016 | 20 Apr 2016 | 6 | 57 | 0 | 0
A1-11th Floor CLC Block Masonry 6" | 4333.44 | Sft. | 08 Apr 2016 | 26 Apr 2016 | 23 Feb 2016 | 20 Apr 2016 | 18 | 57 | 0 | 0
A1-11th Floor Masonry (Lab) | 62960 | Sft. | 08 Apr 2016 | 26 Apr 2016 | 23 Feb 2016 | 23 Apr 2016 | 18 | 60 | 0 | 0
A1-12TH FLOOR | 0 | No Unit | 08 Apr 2016 | 06 May 2016 |  |  | 28 | 0 | 0 | 0
A1-12th Floor CLC Block Masonry 4" | 0 | Sft. | 30 Apr 2016 | 06 May 2016 | 16 Jun 2016 | 16 Jun 2016 | 6 | 0 | 47 | 41
A1-12th Floor CLC Block Masonry 6" | 0 | Sft. | 19 Apr 2016 | 06 May 2016 | 16 Jun 2016 | 16 Jun 2016 | 17 | 0 | 58 | 41
A1-12th Floor Masonry (Lab) | 62960 | Sft. | 19 Apr 2016 | 06 May 2016 | 16 Jun 2016 | 30 Jun 2016 | 17 | 14 | 58 | 55
A1-12th Floor AAC Block Masonry 150mm | 4398.84 | Sft. | 25 Jun 2014 |  | 11 Mar 2020 | 01 Jul 2016 | 0 | 0 | 2086 | 42550
A1-12th Floor AAC Block Masonry 100mm | 216.2 | Sft. | 25 Jun 2014 |  | 06 Jun 2016 | 30 Jun 2016 | 0 | 24 | 712 | 42549
A1-13TH FLOOR | 0 | No Unit | 14 Apr 2016 | 22 Jun 2016 |  |  | 69 | 0 | 0 | 0
A1-13th Floor CLC Block Masonry 4" | 0 | Sft. | 14 Jun 2016 | 22 Jun 2016 | 30 Jul 2016 | 30 Jul 2016 | 8 | 0 | 46 | 38
A1-13th Floor CLC Block Masonry 6" | 0 | Sft. | 04 Jun 2016 | 22 Jun 2016 | 30 Jul 2016 | 30 Jul 2016 | 18 | 0 | 56 | 38
A1-13th Floor Masonry (Lab) | 62960 | Sft. | 04 Jun 2016 | 22 Jun 2016 | 05 Oct 2016 | 03 Nov 2016 | 18 | 29 | 123 | 134
A1-13th Floor AAC Block Masonry 150mm | 4333.44 | Sft. | 25 Jun 2014 |  | 29 Jun 2016 | 03 Nov 2016 | 0 | 127 | 735 | 42675
A1-13th Floor AAC Block Masonry 100mm | 216.2 | Sft. | 25 Jun 2014 |  | 29 Jun 2016 | 03 Nov 2016 | 0 | 127 | 735 | 42675
A1-14TH FLOOR | 0 | No Unit | 26 Apr 2016 | 08 Jul 2016 |  |  | 73 | 0 | 0 | 0
A1-14th Floor CLC Block Masonry 4" | 0 | Sft. | 29 Jun 2016 | 07 Jul 2016 | 30 Jul 2016 | 30 Jul 2016 | 8 | 0 | 31 | 23
A1-14th Floor CLC Block Masonry 6" | 0 | Sft. | 21 Jun 2016 | 08 Jul 2016 | 30 Jul 2016 | 30 Jul 2016 | 17 | 0 | 39 | 22
A1-14th Floor Masonry (Lab) | 62960 | Sft. | 21 Jun 2016 | 08 Jul 2016 | 03 Nov 2016 | 12 Jan 2017 | 17 | 70 | 135 | 188
A1-14th Floor AAC Block Masonry 150mm | 4398.84 | Sft. | 25 Jun 2014 |  | 06 Jul 2016 | 03 Nov 2016 | 0 | 120 | 742 | 42675
A1-14th Floor AAC Block Masonry 100mm | 216.2 | Sft. | 25 Jun 2014 |  | 06 Jul 2016 | 03 Nov 2016 | 0 | 120 | 742 | 42675
A1-ABOVE TERRACE | 0 | No Unit | 14 Apr 2016 | 25 Jul 2016 |  |  | 102 | 0 | 0 | 0
A1-Above Terrace CLC Block Masonry 4" | 0 | Sft. | 16 Jul 2016 | 25 Jul 2016 | 20 Jul 2016 | 20 Jul 2016 | 9 | 0 | 4 | 0
A1-Above Terrace CLC Block Masonry 6" | 0 | Sft. | 16 Jul 2016 | 25 Jul 2016 | 18 Jul 2016 | 20 Jul 2016 | 9 | 2 | 2 | 0
A1-Above Terrace Above Terrace Masonry (Lab) | 62960 | Sft. | 16 Jul 2016 | 25 Jul 2016 | 18 Jul 2016 | 03 Nov 2016 | 9 | 108 | 2 | 101
A1-Above Terrace AAC Block Masonry 150mm | 2751.9 | Sft. | 25 Jun 2014 |  | 18 Jul 2016 | 03 Nov 2016 | 0 | 108 | 754 | 42675
A1-LIFT WALL | 0 | No Unit | 14 Apr 2016 | 27 Jul 2016 |  |  | 104 | 0 | 0 | 0
A1-Lift Wall CLC Block Masonry 6" | 552.36 | Sft. | 16 Jul 2016 | 27 Jul 2016 | 10 Jun 2016 | 13 Jun 2016 | 11 | 3 | 0 | 0
A1-ELEVATIONAL SIDE WALL | 0 | No Unit | 14 Apr 2016 | 25 Jul 2016 |  |  | 102 | 0 | 0 | 0
A1-Elevational Side Wall CLC Block Masonry 6" | 0 | Sft. | 16 Jul 2016 | 25 Jul 2016 | 13 Jun 2016 | 13 Jun 2016 | 9 | 0 | 0 | 0
A1-CLC BLOCK SHIFTING | 0 | No Unit | 12 Aug 2015 | 27 Jun 2016 |  |  | 320 | 0 | 0 | 0
A1-CLC Block shifting CLC Block shiffting | 0 | NO | 12 Aug 2015 | 27 Jun 2016 | 09 May 2016 | 03 Nov 2016 | 320 | 178 | 271 | 129
A1-PLASTER | 0 | No Unit | 20 Oct 2015 | 03 Dec 2016 |  |  | 410 | 0 | 0 | 0
A1-INTERNAL PLASTER | 0 | No Unit | 04 Nov 2015 | 03 Dec 2016 |  |  | 395 | 0 | 0 | 0
A1- GYPSUM/PUTTY PLASTER | 0 | No Unit | 23 Nov 2015 | 26 Nov 2016 |  |  | 369 | 0 | 0 | 0
A1-PARKING FLOOR | 0 | No Unit | 24 Oct 2016 | 29 Oct 2016 |  |  | 5 | 0 | 0 | 0
A1-ENTRANCE LOBBY | 0 | No Unit | 24 Oct 2016 | 26 Oct 2016 |  |  | 2 | 0 | 0 | 0
A1-Entrance lobby Entrance lobby | 56695 | Sft. | 24 Oct 2016 | 26 Oct 2016 | 11 Apr 2016 | 12 Jan 2017 | 2 | 276 | 0 | 78
A1-ELECTRICAL METER ROOM | 0 | No Unit | 27 Oct 2016 | 29 Oct 2016 |  |  | 2 | 0 | 0 | 0
A1-Electrical meter room Electrical meter room | 56695 | Sft. | 27 Oct 2016 | 29 Oct 2016 | 12 Jan 2017 | 28 Jan 2017 | 2 | 16 | 77 | 91
A1-Parking Floor Putty Plaster | 56695 | Sft. | 25 Oct 2016 | 26 Oct 2016 | 07 Mar 2016 | 12 Jan 2017 | 1 | 311 | 0 | 78
A1-1ST FLOOR | 0 | No Unit | 02 Dec 2015 | 11 Mar 2016 |  |  | 100 | 0 | 0 | 0
A1- FLAT 101 | 0 | No Unit | 02 Dec 2015 | 25 Feb 2016 |  |  | 85 | 0 | 0 | 0
A1- Flat 101 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 02 Dec 2015 | 07 Dec 2015 | 09 Dec 2015 | 18 Feb 2016 | 5 | 71 | 7 | 73
A1- Flat 101 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 09 Feb 2016 | 10 Feb 2016 | 26 Feb 2016 | 16 Mar 2016 | 1 | 19 | 17 | 35
A1- Flat 101 Putty Plaster | 56695 | Sft. | 22 Feb 2016 | 25 Feb 2016 | 29 Feb 2016 | 16 Mar 2016 | 3 | 16 | 7 | 20
A1- FLAT 102 | 0 | No Unit | 08 Dec 2015 | 01 Mar 2016 |  |  | 84 | 0 | 0 | 0
A1- Flat 102 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 08 Dec 2015 | 12 Dec 2015 | 09 Dec 2015 | 18 Feb 2016 | 4 | 71 | 1 | 68
A1- Flat 102 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 11 Feb 2016 | 12 Feb 2016 | 16 Mar 2016 | 23 Apr 2016 | 1 | 38 | 34 | 71
A1- Flat 102 Putty Plaster | 56695 | Sft. | 26 Feb 2016 | 01 Mar 2016 | 16 Mar 2016 | 23 Apr 2016 | 4 | 38 | 19 | 53
A1- FLAT 103 | 0 | No Unit | 14 Dec 2015 | 05 Mar 2016 |  |  | 82 | 0 | 0 | 0
A1- Flat 103 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 14 Dec 2015 | 18 Dec 2015 | 09 Dec 2015 | 18 Feb 2016 | 4 | 71 | 0 | 62
A1- Flat 103 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 13 Feb 2016 | 15 Feb 2016 | 30 Mar 2016 | 23 Apr 2016 | 2 | 24 | 46 | 68
A1- Flat 103 Putty Plaster | 56695 | Sft. | 02 Mar 2016 | 05 Mar 2016 | 30 Mar 2016 | 23 Apr 2016 | 3 | 24 | 28 | 49
A1- FLAT 104 | 0 | No Unit | 19 Dec 2015 | 11 Mar 2016 |  |  | 83 | 0 | 0 | 0
A1- Flat 104 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 19 Dec 2015 | 24 Dec 2015 | 09 Dec 2015 | 18 Feb 2016 | 5 | 71 | 0 | 56
A1- Flat 104 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 16 Feb 2016 | 17 Feb 2016 | 26 Feb 2016 | 16 Mar 2016 | 1 | 19 | 10 | 28
A1- Flat 104 Putty Plaster | 56695 | Sft. | 08 Mar 2016 | 11 Mar 2016 | 29 Feb 2016 | 16 Mar 2016 | 3 | 16 | 0 | 5
A1- 1ST FL. COMMON PASSAGE | 0 | No Unit | 01 Feb 2016 | 01 Mar 2016 |  |  | 29 | 0 | 0 | 0
A1- 1st Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 01 Feb 2016 | 03 Feb 2016 | 12 Feb 2016 | 16 Mar 2016 | 2 | 33 | 11 | 42
A1- 1st Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 22 Feb 2016 | 22 Feb 2016 | 23 Jun 2016 | 27 Jun 2016 | 0 | 4 | 122 | 126
A1- 1st Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 29 Feb 2016 | 01 Mar 2016 | 08 Jun 2016 | 27 Jun 2016 | 1 | 19 | 100 | 118
A1-2ND FLOOR | 0 | No Unit | 10 Dec 2015 | 25 Mar 2016 |  |  | 106 | 0 | 0 | 0
A- FLAT 201 | 0 | No Unit | 10 Dec 2015 | 09 Mar 2016 |  |  | 90 | 0 | 0 | 0
A- Flat 201 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 10 Dec 2015 | 15 Dec 2015 | 30 Dec 2015 | 16 Mar 2016 | 5 | 77 | 20 | 92
A- Flat 201 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 18 Feb 2016 | 19 Feb 2016 | 26 Feb 2016 | 16 Mar 2016 | 1 | 19 | 8 | 26
A- Flat 201 Putty Plaster | 56695 | Sft. | 04 Mar 2016 | 09 Mar 2016 | 29 Feb 2016 | 16 Mar 2016 | 5 | 16 | 0 | 7
A- FLAT 202 | 0 | No Unit | 16 Dec 2015 | 14 Mar 2016 |  |  | 89 | 0 | 0 | 0
A- Flat 202 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 16 Dec 2015 | 21 Dec 2015 | 30 Dec 2015 | 18 Feb 2016 | 5 | 50 | 14 | 59
A- Flat 202 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 20 Feb 2016 | 22 Feb 2016 | 16 Mar 2016 | 23 Apr 2016 | 2 | 38 | 25 | 61
A- Flat 202 Putty Plaster | 56695 | Sft. | 10 Mar 2016 | 14 Mar 2016 | 16 Mar 2016 | 23 Apr 2016 | 4 | 38 | 6 | 40
A- FLAT 203 | 0 | No Unit | 22 Dec 2015 | 18 Mar 2016 |  |  | 87 | 0 | 0 | 0
A- Flat 203 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 22 Dec 2015 | 26 Dec 2015 | 30 Dec 2015 | 18 Feb 2016 | 4 | 50 | 8 | 54
A- Flat 203 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 23 Feb 2016 | 24 Feb 2016 | 30 Mar 2016 | 23 Apr 2016 | 1 | 24 | 36 | 59
A- Flat 203 Putty Plaster | 56695 | Sft. | 15 Mar 2016 | 18 Mar 2016 | 30 Mar 2016 | 23 Apr 2016 | 3 | 24 | 15 | 36
A- FLAT 204 | 0 | No Unit | 28 Dec 2015 | 23 Mar 2016 |  |  | 86 | 0 | 0 | 0
A- Flat 204 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 28 Dec 2015 | 02 Jan 2016 | 30 Dec 2015 | 18 Feb 2016 | 5 | 50 | 2 | 47
A- Flat 204 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 25 Feb 2016 | 26 Feb 2016 | 26 Feb 2016 | 16 Mar 2016 | 1 | 19 | 1 | 19
A- Flat 204 Putty Plaster | 56695 | Sft. | 19 Mar 2016 | 23 Mar 2016 | 29 Feb 2016 | 16 Mar 2016 | 4 | 16 | 0 | 0
A1- 2ND FL. COMMON PASSAGE | 0 | No Unit | 09 Feb 2016 | 25 Mar 2016 |  |  | 45 | 0 | 0 | 0
A1- 2nd Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 09 Feb 2016 | 11 Feb 2016 | 12 Feb 2016 | 16 Mar 2016 | 2 | 33 | 3 | 34
A1- 2nd Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 02 Mar 2016 | 02 Mar 2016 | 23 Jun 2016 | 27 Jun 2016 | 0 | 4 | 113 | 117
A1- 2nd Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 24 Mar 2016 | 25 Mar 2016 | 08 Jun 2016 | 27 Jun 2016 | 1 | 19 | 76 | 94
A1-3RD FLOOR | 0 | No Unit | 30 Dec 2015 | 19 Apr 2016 |  |  | 111 | 0 | 0 | 0
A1- FLAT 301 | 0 | No Unit | 30 Dec 2015 | 05 Apr 2016 |  |  | 97 | 0 | 0 | 0
A1- Flat 301 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 30 Dec 2015 | 05 Jan 2016 | 30 Dec 2015 | 18 Feb 2016 | 6 | 50 | 0 | 44
A1- Flat 301 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 27 Feb 2016 | 29 Feb 2016 | 16 Mar 2016 | 16 Mar 2016 | 2 | 0 | 18 | 16
A1- Flat 301 Putty Plaster | 56695 | Sft. | 01 Apr 2016 | 05 Apr 2016 | 16 Mar 2016 | 16 Mar 2016 | 4 | 0 | 0 | 0
A1- FLAT 302 | 0 | No Unit | 06 Jan 2016 | 09 Apr 2016 |  |  | 94 | 0 | 0 | 0
A1- Flat 302 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 06 Jan 2016 | 11 Jan 2016 | 30 Dec 2015 | 18 Feb 2016 | 5 | 50 | 0 | 38
A1- Flat 302 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 02 Mar 2016 | 03 Mar 2016 | 30 Mar 2016 | 23 Apr 2016 | 1 | 24 | 28 | 51
A1- Flat 302 Putty Plaster | 56695 | Sft. | 06 Apr 2016 | 09 Apr 2016 | 16 Mar 2016 | 23 Apr 2016 | 3 | 38 | 0 | 14
A1- FLAT 303 | 0 | No Unit | 12 Jan 2016 | 14 Apr 2016 |  |  | 93 | 0 | 0 | 0
A1- Flat 303 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 12 Jan 2016 | 16 Jan 2016 | 30 Dec 2015 | 18 Feb 2016 | 4 | 50 | 0 | 33
A1- Flat 303 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 04 Mar 2016 | 05 Mar 2016 | 30 Mar 2016 | 23 Apr 2016 | 1 | 24 | 26 | 49
A1- Flat 303 Putty Plaster | 56695 | Sft. | 11 Apr 2016 | 14 Apr 2016 | 30 Mar 2016 | 23 Apr 2016 | 3 | 24 | 0 | 9
A1- FLAT 304 | 0 | No Unit | 18 Jan 2016 | 19 Apr 2016 |  |  | 92 | 0 | 0 | 0
A1- Flat 304 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 18 Jan 2016 | 22 Jan 2016 | 30 Dec 2015 | 18 Feb 2016 | 4 | 50 | 0 | 27
A1- Flat 304 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 09 Mar 2016 | 10 Mar 2016 | 16 Mar 2016 | 16 Mar 2016 | 1 | 0 | 7 | 6
A1- Flat 304 Putty Plaster | 56695 | Sft. | 15 Apr 2016 | 19 Apr 2016 | 16 Mar 2016 | 16 Mar 2016 | 4 | 0 | 0 | 0
A1- 3RD FL. COMMON PASSAGE | 0 | No Unit | 29 Feb 2016 | 28 Mar 2016 |  |  | 28 | 0 | 0 | 0
A1- 3rd Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 29 Feb 2016 | 02 Mar 2016 | 12 Feb 2016 | 16 Mar 2016 | 2 | 33 | 0 | 14
A1- 3rd Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 14 Mar 2016 | 14 Mar 2016 | 23 Jun 2016 | 27 Jun 2016 | 0 | 4 | 101 | 105
A1- 3rd Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 26 Mar 2016 | 28 Mar 2016 | 08 Jun 2016 | 27 Jun 2016 | 2 | 19 | 74 | 91
A1-4TH FLOOR | 0 | No Unit | 21 Jan 2016 | 17 May 2016 |  |  | 117 | 0 | 0 | 0
A1- FLAT 401 | 0 | No Unit | 21 Jan 2016 | 03 May 2016 |  |  | 103 | 0 | 0 | 0
A1- Flat 401 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 21 Jan 2016 | 27 Jan 2016 | 22 Jan 2016 | 16 Mar 2016 | 6 | 54 | 1 | 49
A1- Flat 401 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 11 Mar 2016 | 12 Mar 2016 | 16 Mar 2016 | 23 Apr 2016 | 1 | 38 | 5 | 42
A1- Flat 401 Putty Plaster | 56695 | Sft. | 29 Apr 2016 | 03 May 2016 | 16 Mar 2016 | 16 Mar 2016 | 4 | 0 | 0 | 0
A1- FLAT 402 | 0 | No Unit | 28 Jan 2016 | 07 May 2016 |  |  | 100 | 0 | 0 | 0
A1- Flat 402 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 28 Jan 2016 | 02 Feb 2016 | 22 Jan 2016 | 18 Feb 2016 | 5 | 27 | 0 | 16
A1- Flat 402 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 23 Mar 2016 | 24 Mar 2016 | 30 Mar 2016 | 23 Apr 2016 | 1 | 24 | 7 | 30
A1- Flat 402 Putty Plaster | 56695 | Sft. | 04 May 2016 | 07 May 2016 | 16 Mar 2016 | 23 Apr 2016 | 3 | 38 | 0 | 0
A1- FLAT 403 | 0 | No Unit | 03 Feb 2016 | 12 May 2016 |  |  | 99 | 0 | 0 | 0
A1- Flat 403 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 03 Feb 2016 | 08 Feb 2016 | 22 Jan 2016 | 18 Feb 2016 | 5 | 27 | 0 | 10
A1- Flat 403 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 30 Mar 2016 | 31 Mar 2016 | 30 Mar 2016 | 23 Apr 2016 | 1 | 24 | 0 | 23
A1- Flat 403 Putty Plaster | 56695 | Sft. | 09 May 2016 | 12 May 2016 | 30 Mar 2016 | 23 Apr 2016 | 3 | 24 | 0 | 0
A1- FLAT 404 | 0 | No Unit | 09 Feb 2016 | 17 May 2016 |  |  | 98 | 0 | 0 | 0
A1- Flat 404 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 09 Feb 2016 | 13 Feb 2016 | 22 Jan 2016 | 18 Feb 2016 | 4 | 27 | 0 | 5
A1- Flat 404 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 06 Apr 2016 | 07 Apr 2016 | 16 Mar 2016 | 16 Mar 2016 | 1 | 0 | 0 | 0
A1- Flat 404 Putty Plaster | 56695 | Sft. | 13 May 2016 | 17 May 2016 | 16 Mar 2016 | 16 Mar 2016 | 4 | 0 | 0 | 0
A1- 4TH FL. COMMON PASSAGE | 0 | No Unit | 22 Mar 2016 | 07 Apr 2016 |  |  | 16 | 0 | 0 | 0
A1- 4th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 22 Mar 2016 | 24 Mar 2016 | 12 Feb 2016 | 23 Apr 2016 | 2 | 71 | 0 | 30
A1- 4th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 25 Mar 2016 | 25 Mar 2016 | 23 Jun 2016 | 27 Jun 2016 | 0 | 4 | 90 | 94
A1- 4th Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 06 Apr 2016 | 07 Apr 2016 | 08 Jun 2016 | 27 Jun 2016 | 1 | 19 | 63 | 81
A1-5TH FLOOR | 0 | No Unit | 13 Feb 2016 | 17 May 2016 |  |  | 94 | 0 | 0 | 0
A1- FLAT 501 | 0 | No Unit | 13 Feb 2016 | 03 May 2016 |  |  | 80 | 0 | 0 | 0
A1- Flat 501 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 13 Feb 2016 | 18 Feb 2016 | 12 Feb 2016 | 16 Mar 2016 | 5 | 33 | 0 | 27
A1- Flat 501 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 13 Apr 2016 | 14 Apr 2016 | 30 Mar 2016 | 23 Apr 2016 | 1 | 24 | 0 | 9
A1- Flat 501 Putty Plaster | 56695 | Sft. | 29 Apr 2016 | 03 May 2016 | 30 Mar 2016 | 27 Jun 2016 | 4 | 89 | 0 | 55
A1- FLAT 502 | 0 | No Unit | 19 Feb 2016 | 07 May 2016 |  |  | 78 | 0 | 0 | 0
A1- Flat 502 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 19 Feb 2016 | 24 Feb 2016 | 12 Feb 2016 | 16 Mar 2016 | 5 | 33 | 0 | 21
A1- Flat 502 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 14 Apr 2016 | 15 Apr 2016 | 30 Mar 2016 | 23 Apr 2016 | 1 | 24 | 0 | 8
A1- Flat 502 Putty Plaster | 56695 | Sft. | 04 May 2016 | 07 May 2016 | 30 Mar 2016 | 27 Jun 2016 | 3 | 89 | 0 | 51
A1- FLAT 503 | 0 | No Unit | 25 Feb 2016 | 12 May 2016 |  |  | 77 | 0 | 0 | 0
A1- Flat 503 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 25 Feb 2016 | 01 Mar 2016 | 22 Jan 2016 | 18 Feb 2016 | 5 | 27 | 0 | 0
A1- Flat 503 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 27 Apr 2016 | 28 Apr 2016 | 30 Mar 2016 | 23 Apr 2016 | 1 | 24 | 0 | 0
A1- Flat 503 Putty Plaster | 56695 | Sft. | 09 May 2016 | 12 May 2016 | 30 Mar 2016 | 27 Jun 2016 | 3 | 89 | 0 | 46
A1- FLAT 504 | 0 | No Unit | 02 Mar 2016 | 17 May 2016 |  |  | 76 | 0 | 0 | 0
A1- Flat 504 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 02 Mar 2016 | 08 Mar 2016 | 22 Jan 2016 | 18 Feb 2016 | 6 | 27 | 0 | 0
A1- Flat 504 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 04 May 2016 | 05 May 2016 | 30 Mar 2016 | 23 Apr 2016 | 1 | 24 | 0 | 0
A1- Flat 504 Putty Plaster | 56695 | Sft. | 13 May 2016 | 17 May 2016 | 30 Mar 2016 | 27 Jun 2016 | 4 | 89 | 0 | 41
A1- 5TH FL. COMMON PASSAGE | 0 | No Unit | 05 Apr 2016 | 05 May 2016 |  |  | 30 | 0 | 0 | 0
A1- 5th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 13 Apr 2016 | 15 Apr 2016 | 30 Mar 2016 | 23 Apr 2016 | 2 | 24 | 0 | 8
A1- 5th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 05 Apr 2016 | 05 Apr 2016 | 23 Jun 2016 | 27 Jun 2016 | 0 | 4 | 79 | 83
A1- 5th Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 04 May 2016 | 05 May 2016 | 08 Jun 2016 | 27 Jun 2016 | 1 | 19 | 35 | 53
A1-6TH FLOOR | 0 | No Unit | 05 Mar 2016 | 01 Jun 2016 |  |  | 88 | 0 | 0 | 0
A1- FLAT 601 | 0 | No Unit | 05 Mar 2016 | 18 May 2016 |  |  | 74 | 0 | 0 | 0
A1- Flat 601 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 05 Mar 2016 | 11 Mar 2016 | 01 Mar 2016 | 16 Mar 2016 | 6 | 15 | 0 | 5
A1- Flat 601 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 03 May 2016 | 04 May 2016 | 10 May 2016 | 27 Jun 2016 | 1 | 48 | 7 | 54
A1- Flat 601 Putty Plaster | 56695 | Sft. | 14 May 2016 | 18 May 2016 | 29 Apr 2016 | 27 Jun 2016 | 4 | 59 | 0 | 40
A1- FLAT 602 | 0 | No Unit | 12 Mar 2016 | 23 May 2016 |  |  | 72 | 0 | 0 | 0
A1- Flat 602 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 12 Mar 2016 | 17 Mar 2016 | 01 Mar 2016 | 16 Mar 2016 | 5 | 15 | 0 | 0
A1- Flat 602 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 04 May 2016 | 05 May 2016 | 10 May 2016 | 27 Jun 2016 | 1 | 48 | 6 | 53
A1- Flat 602 Putty Plaster | 56695 | Sft. | 19 May 2016 | 23 May 2016 | 10 May 2016 | 21 Jul 2016 | 4 | 72 | 0 | 59
A1- FLAT 603 | 0 | No Unit | 18 Mar 2016 | 27 May 2016 |  |  | 70 | 0 | 0 | 0
A1- Flat 603 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 18 Mar 2016 | 23 Mar 2016 | 12 Feb 2016 | 16 Mar 2016 | 5 | 33 | 0 | 0
A1- Flat 603 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 06 May 2016 | 07 May 2016 | 10 May 2016 | 27 Jun 2016 | 1 | 48 | 4 | 51
A1- Flat 603 Putty Plaster | 56695 | Sft. | 24 May 2016 | 27 May 2016 | 10 May 2016 | 21 Jul 2016 | 3 | 72 | 0 | 55
A1- FLAT 604 | 0 | No Unit | 24 Mar 2016 | 01 Jun 2016 |  |  | 69 | 0 | 0 | 0
A1- Flat 604 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 24 Mar 2016 | 29 Mar 2016 | 12 Feb 2016 | 16 Mar 2016 | 5 | 33 | 0 | 0
A1- Flat 604 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 09 May 2016 | 10 May 2016 | 10 May 2016 | 27 Jun 2016 | 1 | 48 | 1 | 48
A1- Flat 604 Putty Plaster | 56695 | Sft. | 28 May 2016 | 01 Jun 2016 | 29 Apr 2016 | 27 Jun 2016 | 4 | 59 | 0 | 26
A1- 6TH FL. COMMON PASSAGE | 0 | No Unit | 03 May 2016 | 27 May 2016 |  |  | 24 | 0 | 0 | 0
A1- 6th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 04 May 2016 | 06 May 2016 | 30 Mar 2016 | 23 Apr 2016 | 2 | 24 | 0 | 0
A1- 6th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 03 May 2016 | 03 May 2016 | 23 Jun 2016 | 09 Aug 2016 | 0 | 47 | 51 | 98
A1- 6th Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 26 May 2016 | 27 May 2016 | 08 Jun 2016 | 27 Jun 2016 | 1 | 19 | 13 | 31
A1-7TH FLOOR | 0 | No Unit | 27 Feb 2016 | 18 Jun 2016 |  |  | 112 | 0 | 0 | 0
A1- FLAT 701 | 0 | No Unit | 27 Feb 2016 | 17 May 2016 |  |  | 80 | 0 | 0 | 0
A1- Flat 701 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 27 Feb 2016 | 03 Mar 2016 | 01 Mar 2016 | 16 Mar 2016 | 5 | 15 | 3 | 13
A1- Flat 701 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 11 May 2016 | 12 May 2016 | 10 May 2016 | 27 Jun 2016 | 1 | 48 | 0 | 46
A1- Flat 701 Putty Plaster | 56695 | Sft. | 13 May 2016 | 17 May 2016 | 10 May 2016 | 27 Jun 2016 | 4 | 48 | 0 | 41
A1- FLAT 702 | 0 | No Unit | 04 Mar 2016 | 21 May 2016 |  |  | 78 | 0 | 0 | 0
A1- Flat 702 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 04 Mar 2016 | 10 Mar 2016 | 01 Mar 2016 | 16 Mar 2016 | 6 | 15 | 0 | 6
A1- Flat 702 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 13 May 2016 | 14 May 2016 | 10 May 2016 | 27 Jun 2016 | 1 | 48 | 0 | 44
A1- Flat 702 Putty Plaster | 56695 | Sft. | 18 May 2016 | 21 May 2016 | 10 May 2016 | 27 Jun 2016 | 3 | 48 | 0 | 37
A1- FLAT 703 | 0 | No Unit | 11 Mar 2016 | 26 May 2016 |  |  | 76 | 0 | 0 | 0
A1- Flat 703 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 11 Mar 2016 | 16 Mar 2016 | 01 Mar 2016 | 16 Mar 2016 | 5 | 15 | 0 | 0
A1- Flat 703 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 17 May 2016 | 18 May 2016 | 10 May 2016 | 27 Jun 2016 | 1 | 48 | 0 | 40
A1- Flat 703 Putty Plaster | 56695 | Sft. | 23 May 2016 | 26 May 2016 | 10 May 2016 | 21 Jul 2016 | 3 | 72 | 0 | 56
A1- FLAT 704 | 0 | No Unit | 17 Mar 2016 | 31 May 2016 |  |  | 75 | 0 | 0 | 0
A1- Flat 704 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 17 Mar 2016 | 22 Mar 2016 | 01 Mar 2016 | 16 Mar 2016 | 5 | 15 | 0 | 0
A1- Flat 704 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 18 May 2016 | 19 May 2016 | 10 May 2016 | 27 Jun 2016 | 1 | 48 | 0 | 39
A1- Flat 704 Putty Plaster | 56695 | Sft. | 27 May 2016 | 31 May 2016 | 10 May 2016 | 27 Jun 2016 | 4 | 48 | 0 | 27
A1- 7TH FL. COMMON PASSAGE | 0 | No Unit | 27 Apr 2016 | 18 Jun 2016 |  |  | 52 | 0 | 0 | 0
A1- 7th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 27 Apr 2016 | 29 Apr 2016 | 30 Mar 2016 | 23 Apr 2016 | 2 | 24 | 0 | 0
A1- 7th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 25 May 2016 | 25 May 2016 | 30 Jul 2016 | 09 Aug 2016 | 0 | 10 | 66 | 76
A1- 7th Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 17 Jun 2016 | 18 Jun 2016 | 08 Jun 2016 | 27 Jun 2016 | 1 | 19 | 0 | 9
A1-8TH FLOOR | 0 | No Unit | 08 Apr 2016 | 27 Jul 2016 |  |  | 110 | 0 | 0 | 0
A1- FLAT 801 | 0 | No Unit | 08 Apr 2016 | 13 Jul 2016 |  |  | 96 | 0 | 0 | 0
A1- Flat 801 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 08 Apr 2016 | 13 Apr 2016 | 16 Mar 2016 | 23 Apr 2016 | 5 | 38 | 0 | 10
A1- Flat 801 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 08 Jun 2016 | 09 Jun 2016 | 23 Jun 2016 | 27 Jun 2016 | 1 | 4 | 15 | 18
A1- Flat 801 Putty Plaster | 56695 | Sft. | 09 Jul 2016 | 13 Jul 2016 | 10 May 2016 | 28 Jun 2016 | 4 | 49 | 0 | 0
A1- FLAT 802 | 0 | No Unit | 14 Apr 2016 | 18 Jul 2016 |  |  | 95 | 0 | 0 | 0
A1- Flat 802 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 14 Apr 2016 | 19 Apr 2016 | 16 Mar 2016 | 23 Apr 2016 | 5 | 38 | 0 | 4
A1- Flat 802 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 30 May 2016 | 31 May 2016 | 23 Jun 2016 | 27 Jun 2016 | 1 | 4 | 24 | 27
A1- Flat 802 Putty Plaster | 56695 | Sft. | 14 Jul 2016 | 18 Jul 2016 | 10 May 2016 | 27 Jun 2016 | 4 | 48 | 0 | 0
A1- FLAT 803 | 0 | No Unit | 20 Apr 2016 | 22 Jul 2016 |  |  | 93 | 0 | 0 | 0
A1- Flat 803 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 20 Apr 2016 | 25 Apr 2016 | 16 Mar 2016 | 16 Mar 2016 | 5 | 0 | 0 | 0
A1- Flat 803 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 03 Jun 2016 | 04 Jun 2016 | 23 Jun 2016 | 27 Jun 2016 | 1 | 4 | 20 | 23
A1- Flat 803 Putty Plaster | 56695 | Sft. | 19 Jul 2016 | 22 Jul 2016 | 10 May 2016 | 28 Jun 2016 | 3 | 49 | 0 | 0
A1- REFUGE FLAT 804 | 0 | No Unit | 26 Apr 2016 | 27 Jul 2016 |  |  | 92 | 0 | 0 | 0
A1- Refuge Flat 804 Gypsum plaster incl NOC (M+L) | 0 | Sft. | 26 Apr 2016 | 30 Apr 2016 | 16 Mar 2016 | 27 Jun 2016 | 4 | 103 | 0 | 58
A1- Refuge Flat 804 Gypsum butt finish incl NOC (M+L) | 0 | Sft. | 12 May 2016 | 13 May 2016 | 23 Jun 2016 | 27 Jun 2016 | 1 | 4 | 42 | 45
A1- Refuge Flat 804 Putty Plaster | 0 | Sft. | 23 Jul 2016 | 27 Jul 2016 | 10 May 2016 | 28 Jun 2016 | 4 | 49 | 0 | 0
A1- 8TH FL. COMMON PASSAGE | 0 | No Unit | 06 Jun 2016 | 18 Jul 2016 |  |  | 42 | 0 | 0 | 0
A1- 8th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 06 Jun 2016 | 08 Jun 2016 | 07 Jun 2016 | 27 Jun 2016 | 2 | 20 | 1 | 19
A1- 8th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 16 Jun 2016 | 16 Jun 2016 | 30 Jul 2016 | 09 Aug 2016 | 0 | 10 | 44 | 54
A1- 8th Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 16 Jul 2016 | 18 Jul 2016 | 08 Jun 2016 | 27 Jun 2016 | 2 | 19 | 0 | 0
A1-9TH FLOOR | 0 | No Unit | 30 Apr 2016 | 27 Aug 2016 |  |  | 119 | 0 | 0 | 0
A1- FLAT 901 | 0 | No Unit | 30 Apr 2016 | 12 Aug 2016 |  |  | 104 | 0 | 0 | 0
A1- Flat 901 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 30 Apr 2016 | 05 May 2016 | 21 Apr 2016 | 23 Apr 2016 | 5 | 2 | 0 | 0
A1- Flat 901 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 14 Jun 2016 | 15 Jun 2016 | 23 Jun 2016 | 27 Jun 2016 | 1 | 4 | 9 | 12
A1- Flat 901 Putty Plaster | 56695 | Sft. | 09 Aug 2016 | 12 Aug 2016 | 23 Jun 2016 | 27 Jun 2016 | 3 | 4 | 0 | 0
A1- Flat 901 Gypsum plaster incl NOC (M+L) | 0 | Sft. | 30 Apr 2016 | 05 May 2016 | 21 Apr 2016 | 23 Apr 2016 | 5 | 2 | 0 | 0
A1- FLAT 902 | 0 | No Unit | 06 May 2016 | 18 Aug 2016 |  |  | 104 | 0 | 0 | 0
A1- Flat 902 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 06 May 2016 | 11 May 2016 | 21 Apr 2016 | 23 Apr 2016 | 5 | 2 | 0 | 0
A1- Flat 902 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 21 Jun 2016 | 22 Jun 2016 | 23 Jun 2016 | 27 Jun 2016 | 1 | 4 | 2 | 5
A1- Flat 902 Putty Plaster | 56695 | Sft. | 13 Aug 2016 | 18 Aug 2016 | 23 Jun 2016 | 28 Jun 2016 | 5 | 5 | 0 | 0
A1- FLAT 903 | 0 | No Unit | 12 May 2016 | 23 Aug 2016 |  |  | 103 | 0 | 0 | 0
A1- Flat 903 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 12 May 2016 | 17 May 2016 | 30 Mar 2016 | 23 Apr 2016 | 5 | 24 | 0 | 0
A1- Flat 903 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 28 Jun 2016 | 29 Jun 2016 | 23 Jun 2016 | 27 Jun 2016 | 1 | 4 | 0 | 0
A1- Flat 903 Putty Plaster | 56695 | Sft. | 19 Aug 2016 | 23 Aug 2016 | 23 Jun 2016 | 28 Jun 2016 | 4 | 5 | 0 | 0
A1- FLAT 904 | 0 | No Unit | 18 May 2016 | 27 Aug 2016 |  |  | 101 | 0 | 0 | 0
A1- Flat 904 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 18 May 2016 | 23 May 2016 | 16 Mar 2016 | 16 Mar 2016 | 5 | 0 | 0 | 0
A1- Flat 904 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 12 Jul 2016 | 13 Jul 2016 | 23 Jun 2016 | 27 Jun 2016 | 1 | 4 | 0 | 0
A1- Flat 904 Putty Plaster | 56695 | Sft. | 24 Aug 2016 | 27 Aug 2016 | 23 Jun 2016 | 27 Jun 2016 | 3 | 4 | 0 | 0
A1- 9TH FL. COMMON PASSAGE | 0 | No Unit | 28 Jun 2016 | 20 Aug 2016 |  |  | 53 | 0 | 0 | 0
A1- 9th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 28 Jun 2016 | 30 Jun 2016 | 07 Jun 2016 | 27 Jun 2016 | 2 | 20 | 0 | 0
A1- 9th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 15 Jul 2016 | 15 Jul 2016 | 30 Jul 2016 | 09 Aug 2016 | 0 | 10 | 15 | 25
A1- 9th Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 19 Aug 2016 | 20 Aug 2016 | 30 Jul 2016 | 09 Aug 2016 | 1 | 10 | 0 | 0
A1-10TH FLOOR | 0 | No Unit | 12 May 2016 | 24 Sep 2016 |  |  | 135 | 0 | 0 | 0
A1- FLAT 1001 | 0 | No Unit | 12 May 2016 | 10 Sep 2016 |  |  | 121 | 0 | 0 | 0
A1- Flat 1001 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 12 May 2016 | 17 May 2016 | 23 Apr 2016 | 23 Apr 2016 | 5 | 0 | 0 | 0
A1- Flat 1001 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 19 Jul 2016 | 20 Jul 2016 | 30 Jun 2016 | 30 Jun 2016 | 1 | 0 | 0 | 0
A1- Flat 1001 Putty Plaster | 56695 | Sft. | 07 Sep 2016 | 10 Sep 2016 | 13 Jul 2016 | 27 Jul 2016 | 3 | 14 | 0 | 0
A1- FLAT 1002 | 0 | No Unit | 18 May 2016 | 15 Sep 2016 |  |  | 120 | 0 | 0 | 0
A1- Flat 1002 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 18 May 2016 | 23 May 2016 | 23 Apr 2016 | 23 Apr 2016 | 5 | 0 | 0 | 0
A1- Flat 1002 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 26 Jul 2016 | 27 Jul 2016 | 27 Jun 2016 | 28 Jun 2016 | 1 | 1 | 0 | 0
A1- Flat 1002 Putty Plaster | 56695 | Sft. | 12 Sep 2016 | 15 Sep 2016 | 28 Jun 2016 | 28 Jun 2016 | 3 | 0 | 0 | 0
A1- FLAT 1003 | 0 | No Unit | 24 May 2016 | 20 Sep 2016 |  |  | 119 | 0 | 0 | 0
A1- Flat 1003 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 24 May 2016 | 28 May 2016 | 23 Apr 2016 | 23 Apr 2016 | 4 | 0 | 0 | 0
A1- Flat 1003 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 02 Aug 2016 | 03 Aug 2016 | 30 Jun 2016 | 30 Jun 2016 | 1 | 0 | 0 | 0
A1- Flat 1003 Putty Plaster | 56695 | Sft. | 16 Sep 2016 | 20 Sep 2016 | 13 Jul 2016 | 27 Jul 2016 | 4 | 14 | 0 | 0
A1- FLAT 1004 | 0 | No Unit | 30 May 2016 | 24 Sep 2016 |  |  | 117 | 0 | 0 | 0
A1- Flat 1004 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 30 May 2016 | 03 Jun 2016 | 30 Mar 2016 | 23 Apr 2016 | 4 | 24 | 0 | 0
A1- Flat 1004 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 17 Aug 2016 | 18 Aug 2016 | 30 Jun 2016 | 30 Jun 2016 | 1 | 0 | 0 | 0
A1- Flat 1004 Putty Plaster | 56695 | Sft. | 21 Sep 2016 | 24 Sep 2016 | 13 Jul 2016 | 27 Jul 2016 | 3 | 14 | 0 | 0
A1- 10TH FL. COMMON PASSAGE | 0 | No Unit | 09 Jul 2016 | 14 Sep 2016 |  |  | 67 | 0 | 0 | 0
A1- 10th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 09 Jul 2016 | 12 Jul 2016 | 30 Jul 2016 | 09 Aug 2016 | 3 | 10 | 21 | 28
A1- 10th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L | 56695 | Sft. | 18 Aug 2016 | 18 Aug 2016 | 10 Mar 2017 |  | 0 | 0 | 204 | 0
A1- 10th Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 13 Sep 2016 | 14 Sep 2016 | 30 Jul 2016 | 09 Aug 2016 | 1 | 10 | 0 | 0
A1-11TH FLOOR | 0 | No Unit | 27 May 2016 | 22 Oct 2016 |  |  | 148 | 0 | 0 | 0
A1- FLAT 1101 | 0 | No Unit | 27 May 2016 | 08 Oct 2016 |  |  | 134 | 0 | 0 | 0
A1- Flat 1101 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 27 May 2016 | 01 Jun 2016 | 14 Jun 2016 | 27 Jun 2016 | 5 | 13 | 18 | 26
A1- Flat 1101 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 18 Aug 2016 | 19 Aug 2016 | 08 Jul 2016 | 06 Aug 2016 | 1 | 29 | 0 | 0
A1- Flat 1101 Putty Plaster | 56695 | Sft. | 05 Oct 2016 | 08 Oct 2016 | 09 Aug 2016 | 09 Aug 2016 | 3 | 0 | 0 | 0
A1- FLAT 1102 | 0 | No Unit | 02 Jun 2016 | 13 Oct 2016 |  |  | 133 | 0 | 0 | 0
A1- Flat 1102 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 02 Jun 2016 | 07 Jun 2016 | 14 Jun 2016 | 27 Jun 2016 | 5 | 13 | 12 | 20
A1- Flat 1102 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 31 Aug 2016 | 01 Sep 2016 | 08 Jul 2016 | 06 Aug 2016 | 1 | 29 | 0 | 0
A1- Flat 1102 Putty Plaster | 56695 | Sft. | 10 Oct 2016 | 13 Oct 2016 | 25 Aug 2016 | 08 Sep 2016 | 3 | 14 | 0 | 0
A1- FLAT 1103 | 0 | No Unit | 08 Jun 2016 | 18 Oct 2016 |  |  | 132 | 0 | 0 | 0
A1- Flat 1103 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 08 Jun 2016 | 13 Jun 2016 | 14 Jun 2016 | 27 Jun 2016 | 5 | 13 | 6 | 14
A1- Flat 1103 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 07 Sep 2016 | 08 Sep 2016 | 08 Jul 2016 | 06 Aug 2016 | 1 | 29 | 0 | 0
A1- Flat 1103 Putty Plaster | 56695 | Sft. | 14 Oct 2016 | 18 Oct 2016 | 25 Aug 2016 | 08 Sep 2016 | 4 | 14 | 0 | 0
A1- FLAT 1104 | 0 | No Unit | 14 Jun 2016 | 22 Oct 2016 |  |  | 130 | 0 | 0 | 0
A1- Flat 1104 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 14 Jun 2016 | 18 Jun 2016 | 14 Jun 2016 | 27 Jun 2016 | 4 | 13 | 0 | 9
A1- Flat 1104 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 14 Sep 2016 | 15 Sep 2016 | 08 Jul 2016 | 22 Aug 2016 | 1 | 45 | 0 | 0
A1- Flat 1104 Putty Plaster | 56695 | Sft. | 19 Oct 2016 | 22 Oct 2016 | 25 Aug 2016 | 08 Sep 2016 | 3 | 14 | 0 | 0
A1- 11TH FL. COMMON PASSAGE | 0 | No Unit | 25 Jul 2016 | 17 Oct 2016 |  |  | 84 | 0 | 0 | 0
A1- 11th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 25 Jul 2016 | 27 Jul 2016 | 08 Jul 2016 | 09 Aug 2016 | 2 | 32 | 0 | 13
A1- 11th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L | 56695 | Sft. | 12 Sep 2016 | 12 Sep 2016 | 10 Mar 2017 |  | 0 | 0 | 179 | 0
A1- 11th Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 15 Oct 2016 | 17 Oct 2016 | 09 Aug 2016 | 09 Aug 2016 | 2 | 0 | 0 | 0
A1-12TH FLOOR | 0 | No Unit | 07 Jun 2016 | 31 Oct 2016 |  |  | 146 | 0 | 0 | 0
A1- FLAT 1201 | 0 | No Unit | 07 Jun 2016 | 24 Sep 2016 |  |  | 109 | 0 | 0 | 0
A1- Flat 1201 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 07 Jun 2016 | 11 Jun 2016 | 28 Jun 2016 | 13 Jul 2016 | 4 | 15 | 21 | 32
A1- Flat 1201 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 21 Sep 2016 | 22 Sep 2016 | 28 Jun 2016 | 22 Aug 2016 | 1 | 55 | 0 | 0
A1- Flat 1201 Putty Plaster | 56695 | Sft. | 21 Sep 2016 | 24 Sep 2016 | 25 Aug 2016 | 16 Dec 2016 | 3 | 113 | 0 | 83
A1- FLAT 1202 | 0 | No Unit | 13 Jun 2016 | 29 Sep 2016 |  |  | 108 | 0 | 0 | 0
A1- Flat 1202 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 13 Jun 2016 | 17 Jun 2016 | 20 Jul 2016 | 17 Aug 2016 | 4 | 28 | 37 | 61
A1- Flat 1202 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 28 Sep 2016 | 29 Sep 2016 | 17 Aug 2016 | 22 Aug 2016 | 1 | 5 | 0 | 0
A1- Flat 1202 Putty Plaster | 56695 | Sft. | 26 Sep 2016 | 29 Sep 2016 | 25 Aug 2016 | 16 Dec 2016 | 3 | 113 | 0 | 78
A1- FLAT 1203 | 0 | No Unit | 18 Jun 2016 | 06 Oct 2016 |  |  | 110 | 0 | 0 | 0
A1- Flat 1203 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 18 Jun 2016 | 23 Jun 2016 | 20 Jul 2016 | 17 Aug 2016 | 5 | 28 | 32 | 55
A1- Flat 1203 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 05 Oct 2016 | 06 Oct 2016 | 17 Aug 2016 | 29 Nov 2016 | 1 | 104 | 0 | 54
A1- Flat 1203 Putty Plaster | 56695 | Sft. | 30 Sep 2016 | 04 Oct 2016 | 25 Aug 2016 | 16 Dec 2016 | 4 | 113 | 0 | 73
A1- FLAT 1204 | 0 | No Unit | 24 Jun 2016 | 13 Oct 2016 |  |  | 111 | 0 | 0 | 0
A1- Flat 1204 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 24 Jun 2016 | 29 Jun 2016 | 20 Jul 2016 | 17 Aug 2016 | 5 | 28 | 26 | 49
A1- Flat 1204 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 12 Oct 2016 | 13 Oct 2016 | 17 Aug 2016 | 29 Nov 2016 | 1 | 104 | 0 | 47
A1- Flat 1204 Putty Plaster | 56695 | Sft. | 05 Oct 2016 | 08 Oct 2016 | 25 Aug 2016 | 16 Dec 2016 | 3 | 113 | 0 | 69
A1- 12TH FL. COMMON PASSAGE | 0 | No Unit | 04 Aug 2016 | 31 Oct 2016 |  |  | 88 | 0 | 0 | 0
A1- 12th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 04 Aug 2016 | 06 Aug 2016 | 09 Aug 2016 | 29 Nov 2016 | 2 | 112 | 5 | 115
A1- 12th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L | 56695 | Sft. | 15 Oct 2016 | 15 Oct 2016 | 10 Mar 2017 |  | 0 | 0 | 146 | 0
A1- 12th Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 29 Oct 2016 | 31 Oct 2016 | 22 Nov 2016 | 12 Jan 2017 | 2 | 51 | 24 | 73
A1-13TH FLOOR | 0 | No Unit | 25 Jun 2016 | 08 Nov 2016 |  |  | 136 | 0 | 0 | 0
A1- FLAT 1301 | 0 | No Unit | 25 Jun 2016 | 18 Oct 2016 |  |  | 115 | 0 | 0 | 0
A1- Flat 1301 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 25 Jun 2016 | 30 Jun 2016 | 05 Oct 2016 | 29 Nov 2016 | 5 | 55 | 102 | 152
A1- Flat 1301 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 14 Oct 2016 | 15 Oct 2016 | 22 Nov 2016 | 29 Nov 2016 | 1 | 7 | 39 | 45
A1- Flat 1301 Putty Plaster | 56695 | Sft. | 14 Oct 2016 | 18 Oct 2016 | 22 Nov 2016 | 16 Dec 2016 | 4 | 24 | 39 | 59
A1- FLAT 1302 | 0 | No Unit | 01 Jul 2016 | 22 Oct 2016 |  |  | 113 | 0 | 0 | 0
A1- Flat 1302 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 01 Jul 2016 | 06 Jul 2016 | 13 Oct 2016 | 29 Nov 2016 | 5 | 47 | 104 | 146
A1- Flat 1302 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 12 Oct 2016 | 13 Oct 2016 | 22 Nov 2016 | 29 Nov 2016 | 1 | 7 | 41 | 47
A1- Flat 1302 Putty Plaster | 56695 | Sft. | 19 Oct 2016 | 22 Oct 2016 | 22 Nov 2016 | 16 Dec 2016 | 3 | 24 | 34 | 55
A1- FLAT 1303 | 0 | No Unit | 07 Jul 2016 | 27 Oct 2016 |  |  | 112 | 0 | 0 | 0
A1- Flat 1303 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 07 Jul 2016 | 12 Jul 2016 | 14 Nov 2016 | 29 Nov 2016 | 5 | 15 | 130 | 140
A1- Flat 1303 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 14 Oct 2016 | 15 Oct 2016 | 22 Nov 2016 | 29 Nov 2016 | 1 | 7 | 39 | 45
A1- Flat 1303 Putty Plaster | 56695 | Sft. | 24 Oct 2016 | 27 Oct 2016 | 22 Nov 2016 | 16 Dec 2016 | 3 | 24 | 29 | 50
A1- REFUGE FLAT 1304 | 0 | No Unit | 13 Jul 2016 | 01 Nov 2016 |  |  | 111 | 0 | 0 | 0
A1- Refuge Flat 1304 Gypsum plaster incl NOC (M+L) | 0 | Sft. | 13 Jul 2016 | 18 Jul 2016 | 05 Oct 2016 | 29 Nov 2016 | 5 | 55 | 84 | 134
A1- Refuge Flat 1304 Gypsum butt finish incl NOC (M+L) | 0 | Sft. | 23 Sep 2016 | 24 Sep 2016 | 22 Nov 2016 | 29 Nov 2016 | 1 | 7 | 60 | 66
A1- Refuge Flat 1304 Putty Plaster | 0 | Sft. | 28 Oct 2016 | 01 Nov 2016 | 22 Nov 2016 | 16 Dec 2016 | 4 | 24 | 25 | 45
A1- 13TH FL. COMMON PASSAGE | 0 | No Unit | 24 Aug 2016 | 08 Nov 2016 |  |  | 76 | 0 | 0 | 0
A1- 13th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 24 Aug 2016 | 26 Aug 2016 | 20 Sep 2016 | 29 Nov 2016 | 2 | 70 | 27 | 95
A1- 13th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L | 56695 | Sft. | 29 Oct 2016 | 29 Oct 2016 | 22 Nov 2016 | 29 Nov 2016 | 0 | 7 | 24 | 31
A1- 13th Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 07 Nov 2016 | 08 Nov 2016 | 22 Nov 2016 | 12 Jan 2017 | 1 | 51 | 15 | 65
A1-14TH FLOOR | 0 | No Unit | 12 Jul 2016 | 22 Nov 2016 |  |  | 133 | 0 | 0 | 0
A1- FLAT 1401 | 0 | No Unit | 12 Jul 2016 | 05 Nov 2016 |  |  | 116 | 0 | 0 | 0
A1- Flat 1401 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 12 Jul 2016 | 16 Jul 2016 | 29 Nov 2016 | 16 Dec 2016 | 4 | 17 | 140 | 153
A1- Flat 1401 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 14 Oct 2016 | 15 Oct 2016 | 29 Nov 2016 | 16 Dec 2016 | 1 | 17 | 46 | 62
A1- Flat 1401 Putty Plaster | 56695 | Sft. | 02 Nov 2016 | 05 Nov 2016 | 29 Nov 2016 | 16 Dec 2016 | 3 | 17 | 27 | 41
A1- FLAT 1402 | 0 | No Unit | 18 Jul 2016 | 10 Nov 2016 |  |  | 115 | 0 | 0 | 0
A1- Flat 1402 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 18 Jul 2016 | 22 Jul 2016 | 29 Nov 2016 | 16 Dec 2016 | 4 | 17 | 134 | 147
A1- Flat 1402 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 17 Oct 2016 | 18 Oct 2016 | 29 Nov 2016 | 16 Dec 2016 | 1 | 17 | 43 | 59
A1- Flat 1402 Putty Plaster | 56695 | Sft. | 07 Nov 2016 | 10 Nov 2016 | 29 Nov 2016 | 16 Dec 2016 | 3 | 17 | 22 | 36
A1- FLAT 1403 | 0 | No Unit | 23 Jul 2016 | 15 Nov 2016 |  |  | 115 | 0 | 0 | 0
A1- Flat 1403 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 23 Jul 2016 | 28 Jul 2016 | 11 Apr 2016 | 23 Apr 2016 | 5 | 12 | 0 | 0
A1- Flat 1403 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 19 Oct 2016 | 20 Oct 2016 | 23 Jun 2016 | 27 Jun 2016 | 1 | 4 | 0 | 0
A1- Flat 1403 Putty Plaster | 56695 | Sft. | 11 Nov 2016 | 15 Nov 2016 | 23 Jun 2016 | 28 Jun 2016 | 4 | 5 | 0 | 0
A1- FLAT 1404 | 0 | No Unit | 29 Jul 2016 | 19 Nov 2016 |  |  | 113 | 0 | 0 | 0
A1- Flat 1404 Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 29 Jul 2016 | 03 Aug 2016 | 05 Oct 2016 | 29 Nov 2016 | 5 | 55 | 68 | 118
A1- Flat 1404 Gypsum butt finish incl NOC (M+L) | 56695 | Sft. | 21 Oct 2016 | 22 Oct 2016 | 05 Oct 2016 | 29 Nov 2016 | 1 | 55 | 0 | 38
A1- Flat 1404 Putty Plaster | 56695 | Sft. | 16 Nov 2016 | 19 Nov 2016 | 05 Oct 2016 | 16 Dec 2016 | 3 | 72 | 0 | 27
A1- 14TH FL. COMMON PASSAGE | 0 | No Unit | 09 Sep 2016 | 22 Nov 2016 |  |  | 74 | 0 | 0 | 0
A1- 14th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 56695 | Sft. | 09 Sep 2016 | 12 Sep 2016 | 20 Sep 2016 | 29 Nov 2016 | 3 | 70 | 11 | 78
A1- 14th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L | 56695 | Sft. | 07 Nov 2016 | 07 Nov 2016 | 22 Nov 2016 | 29 Nov 2016 | 0 | 7 | 15 | 22
A1- 14th Fl. COMMON PASSAGE Putty Plaster | 56695 | Sft. | 21 Nov 2016 | 22 Nov 2016 | 22 Nov 2016 | 12 Jan 2017 | 1 | 51 | 1 | 51
A1-TOP TERRACE FLOOR | 0 | No Unit | 26 Jul 2016 | 26 Nov 2016 |  |  | 123 | 0 | 0 | 0
A1-TOP TERRACE COMMON PASSAGE | 0 | No Unit | 26 Jul 2016 | 24 Nov 2016 |  |  | 121 | 0 | 0 | 0
A1-Top Terrace Common Passage Gypsum plaster incl NOC (M+L) | 0 | Sft. | 26 Jul 2016 | 28 Jul 2016 | 22 Nov 2016 | 16 Dec 2016 | 2 | 24 | 119 | 141
A1-Top Terrace Common Passage Gypsum butt finish incl NOC (M | 0 | Sft. | 08 Nov 2016 | 08 Nov 2016 | 22 Nov 2016 | 16 Dec 2016 | 0 | 24 | 14 | 38
A1-Top Terrace Common Passage Putty Plaster | 0 | Sft. | 23 Nov 2016 | 24 Nov 2016 | 22 Nov 2016 | 12 Jan 2017 | 1 | 51 | 0 | 49
A1-LMR | 0 | No Unit | 29 Jul 2016 | 26 Nov 2016 |  |  | 120 | 0 | 0 | 0
A1-LMR Gypsum plaster incl NOC (M+L) | 0 | Sft. | 29 Jul 2016 | 30 Jul 2016 | 29 Nov 2016 | 16 Dec 2016 | 1 | 17 | 123 | 139
A1-LMR Gypsum butt finish incl NOC (M+L) | 0 | Sft. | 29 Jul 2016 | 30 Jul 2016 | 29 Nov 2016 | 16 Dec 2016 | 1 | 17 | 123 | 139
A1-LMR Putty Plaster | 0 | Sft. | 25 Nov 2016 | 26 Nov 2016 | 29 Nov 2016 | 16 Dec 2016 | 1 | 17 | 4 | 20
A1-SCAFFOLDING | 0 | No Unit | 23 Nov 2015 | 23 Nov 2015 |  |  | 0 | 0 | 0 | 0
A1-Scaffolding Scaffolding (Base line) | 66911.89 | R.S. | 23 Nov 2015 | 23 Nov 2015 | 11 May 2016 | 25 Jan 2017 | 0 | 259 | 170 | 429
A1-Scaffolding Misc. scaffolding | 8088.11 | Job | 25 Jun 2014 |  | 07 Jun 2016 | 25 Jan 2017 | 0 | 232 | 713 | 42758
A1-TAR PLASTER | 54 | No Unit | 23 Nov 2015 | 03 Dec 2016 |  |  | 376 | 0 | 0 | 0
A1- PARKING FLOOR | 0 | No Unit | 23 Jul 2016 | 25 Jul 2016 |  |  | 2 | 0 | 0 | 0
A1- Parking Floor Tar Plaster | 321.48 | Sft. | 23 Jul 2016 | 25 Jul 2016 | 27 Oct 2015 | 26 Dec 2015 | 2 | 60 | 0 | 0
A1- Parking Floor Int. Plaster (Lab) | 62960 | Sft. | 23 Jul 2016 | 25 Jul 2016 | 27 Oct 2015 | 28 Dec 2015 | 2 | 62 | 0 | 0
A1- 1ST FLOOR | 0 | No Unit | 23 Nov 2015 | 29 Jul 2016 |  |  | 249 | 0 | 0 | 0
A1- FLAT 101 | 8.5 | No Unit | 23 Nov 2015 | 25 Nov 2015 |  |  | 2 | 0 | 0 | 0
A1- Flat 101 Tar Plaster | 745.22 | Sft. | 23 Nov 2015 | 25 Nov 2015 | 24 Nov 2015 | 09 Dec 2015 | 2 | 15 | 1 | 14
A1- FLAT 102 | 0 | No Unit | 26 Nov 2015 | 28 Nov 2015 |  |  | 2 | 0 | 0 | 0
A1- Flat 102 Tar Plaster | 745.22 | Sft. | 26 Nov 2015 | 28 Nov 2015 | 24 Nov 2015 | 09 Dec 2015 | 2 | 15 | 0 | 11
A1- FLAT 103 | 0 | No Unit | 30 Nov 2015 | 02 Dec 2015 |  |  | 2 | 0 | 0 | 0
A1- Flat 103 Tar Plaster | 745.22 | Sft. | 30 Nov 2015 | 02 Dec 2015 | 24 Nov 2015 | 09 Dec 2015 | 2 | 15 | 0 | 7
A1- FLAT 104 | 0 | No Unit | 03 Dec 2015 | 05 Dec 2015 |  |  | 2 | 0 | 0 | 0
A1- Flat 104 Tar Plaster | 745.22 | Sft. | 03 Dec 2015 | 05 Dec 2015 | 24 Nov 2015 | 09 Dec 2015 | 2 | 15 | 0 | 4
A1- 1ST FLOOR LOBBY | 0 | No Unit | 28 Jul 2016 | 29 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1- 1st Floor Lobby Tar Plaster | 101.05 | Sft. | 28 Jul 2016 | 29 Jul 2016 | 17 Jan 2016 | 12 Feb 2016 | 1 | 26 | 0 | 0
A1- 1st Floor Int. Plaster (Lab) | 62960 | Sft. | 23 Nov 2015 | 05 Dec 2015 | 24 Nov 2015 | 28 Dec 2015 | 12 | 34 | 1 | 23
A1- 1st Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 23 Nov 2015 | 05 Dec 2015 | 17 Jan 2016 | 30 Jun 2016 | 12 | 165 | 55 | 208
A1- 2ND FLOOR | 0 | No Unit | 01 Dec 2015 | 01 Aug 2016 |  |  | 244 | 0 | 0 | 0
A1- FLAT 201 | 0 | No Unit | 01 Dec 2015 | 03 Dec 2015 |  |  | 2 | 0 | 0 | 0
A1- Flat 201 Tar Plaster | 745.22 | Sft. | 01 Dec 2015 | 03 Dec 2015 | 01 Dec 2015 | 09 Dec 2015 | 2 | 8 | 0 | 6
A1- FLAT 202 | 0 | No Unit | 04 Dec 2015 | 07 Dec 2015 |  |  | 3 | 0 | 0 | 0
A1- Flat 202 Tar Plaster | 745.22 | Sft. | 04 Dec 2015 | 07 Dec 2015 | 01 Dec 2015 | 09 Dec 2015 | 3 | 8 | 0 | 2
A1- FLAT 203 | 0 | No Unit | 08 Dec 2015 | 10 Dec 2015 |  |  | 2 | 0 | 0 | 0
A1- Flat 203 Tar Plaster | 745.22 | Sft. | 08 Dec 2015 | 10 Dec 2015 | 01 Dec 2015 | 09 Dec 2015 | 2 | 8 | 0 | 0
A1- FLAT 204 | 0 | No Unit | 11 Dec 2015 | 14 Dec 2015 |  |  | 3 | 0 | 0 | 0
A1- Flat 204 Tar Plaster | 745.22 | Sft. | 11 Dec 2015 | 14 Dec 2015 | 01 Dec 2015 | 09 Dec 2015 | 3 | 8 | 0 | 0
A1- 2ND FLOOR LOBBY | 0 | No Unit | 30 Jul 2016 | 01 Aug 2016 |  |  | 2 | 0 | 0 | 0
A1- 2nd Floor Lobby Tar Plaster | 101.05 | Sft. | 30 Jul 2016 | 01 Aug 2016 | 17 Jan 2016 | 12 Feb 2016 | 2 | 26 | 0 | 0
A1- 2nd Floor Int. Plaster (Lab) | 62960 | Sft. | 01 Dec 2015 | 14 Dec 2015 | 09 Dec 2015 | 28 Dec 2015 | 13 | 19 | 8 | 14
A1- 2nd Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 15 Dec 2015 | 28 Dec 2015 | 17 Jan 2016 | 30 Jun 2016 | 13 | 165 | 33 | 185
A1- 3RD FLOOR | 0 | No Unit | 21 Dec 2015 | 03 Aug 2016 |  |  | 226 | 0 | 0 | 0
A1- FLAT 301 | 0 | No Unit | 21 Dec 2015 | 23 Dec 2015 |  |  | 2 | 0 | 0 | 0
A1- Flat 301 Tar Plaster | 745.22 | Sft. | 21 Dec 2015 | 23 Dec 2015 | 09 Dec 2015 | 26 Dec 2015 | 2 | 17 | 0 | 3
A1- FLAT 302 | 0 | No Unit | 24 Dec 2015 | 26 Dec 2015 |  |  | 2 | 0 | 0 | 0
A1- Flat 302 Tar Plaster | 745.22 | Sft. | 24 Dec 2015 | 26 Dec 2015 | 09 Dec 2015 | 26 Dec 2015 | 2 | 17 | 0 | 0
A1- FLAT 303 | 0 | No Unit | 28 Dec 2015 | 30 Dec 2015 |  |  | 2 | 0 | 0 | 0
A1- Flat 303 Tar Plaster | 745.22 | Sft. | 28 Dec 2015 | 30 Dec 2015 | 09 Dec 2015 | 26 Dec 2015 | 2 | 17 | 0 | 0
A1- FLAT 304 | 0 | No Unit | 01 Jan 2016 | 04 Jan 2016 |  |  | 3 | 0 | 0 | 0
A1- Flat 304 Tar Plaster | 745.22 | Sft. | 01 Jan 2016 | 04 Jan 2016 | 09 Dec 2015 | 26 Dec 2015 | 3 | 17 | 0 | 0
A1- 3RD FLOOR LOBBY | 0 | No Unit | 02 Aug 2016 | 03 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- 3rd Floor Lobby Tar Plaster | 101.05 | Sft. | 02 Aug 2016 | 03 Aug 2016 | 09 Dec 2015 | 12 Feb 2016 | 1 | 65 | 0 | 0
A1- 3rd Floor Int. Plaster (Lab) | 62960 | Sft. | 21 Dec 2015 | 04 Jan 2016 | 09 Dec 2015 | 12 Feb 2016 | 14 | 65 | 0 | 39
A1- 3rd Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 21 Dec 2015 | 04 Jan 2016 | 17 Jan 2016 | 30 Jun 2016 | 14 | 165 | 27 | 178
A1- 4TH FLOOR | 0 | No Unit | 12 Jan 2016 | 05 Aug 2016 |  |  | 206 | 0 | 0 | 0
A1- FLAT 401 | 0 | No Unit | 12 Jan 2016 | 14 Jan 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 401 Tar Plaster | 745.22 | Sft. | 12 Jan 2016 | 14 Jan 2016 | 30 Dec 2015 | 17 Jan 2016 | 2 | 18 | 0 | 3
A1- FLAT 402 | 0 | No Unit | 15 Jan 2016 | 18 Jan 2016 |  |  | 3 | 0 | 0 | 0
A1- Flat 402 Tar Plaster | 745.22 | Sft. | 15 Jan 2016 | 18 Jan 2016 | 30 Dec 2015 | 17 Jan 2016 | 3 | 18 | 0 | 0
A1- FLAT 403 | 0 | No Unit | 19 Jan 2016 | 21 Jan 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 403 Tar Plaster | 745.22 | Sft. | 19 Jan 2016 | 21 Jan 2016 | 30 Dec 2015 | 17 Jan 2016 | 2 | 18 | 0 | 0
A1- FLAT 404 | 0 | No Unit | 22 Jan 2016 | 25 Jan 2016 |  |  | 3 | 0 | 0 | 0
A1- Flat 404 Tar Plaster | 745.22 | Sft. | 22 Jan 2016 | 25 Jan 2016 | 30 Dec 2015 | 30 Dec 2015 | 3 | 0 | 0 | 0
A1- 4TH FLOOR LOBBY | 0 | No Unit | 04 Aug 2016 | 05 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- 4th Floor Lobby Tar Plaster | 101.05 | Sft. | 04 Aug 2016 | 05 Aug 2016 | 03 Feb 2016 | 12 Feb 2016 | 1 | 9 | 0 | 0
A1- 4th Floor Int. Plaster (Lab) | 62960 | Sft. | 12 Jan 2016 | 25 Jan 2016 | 07 Jan 2016 | 17 Mar 2016 | 13 | 70 | 0 | 52
A1- 4th Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 12 Jan 2016 | 25 Jan 2016 | 09 May 2016 | 30 Jun 2016 | 13 | 52 | 118 | 157
A1- 5TH FLOOR | 0 | No Unit | 04 Feb 2016 | 08 Aug 2016 |  |  | 186 | 0 | 0 | 0
A1- FLAT 501 | 0 | No Unit | 04 Feb 2016 | 06 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 501 Tar Plaster | 745.22 | Sft. | 04 Feb 2016 | 06 Feb 2016 | 07 Jan 2016 | 17 Jan 2016 | 2 | 10 | 0 | 0
A1- FLAT 502 | 0 | No Unit | 08 Feb 2016 | 10 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 502 Tar Plaster | 745.22 | Sft. | 08 Feb 2016 | 10 Feb 2016 | 07 Jan 2016 | 17 Jan 2016 | 2 | 10 | 0 | 0
A1- FLAT 503 | 0 | No Unit | 11 Feb 2016 | 13 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 503 Tar Plaster | 745.22 | Sft. | 11 Feb 2016 | 13 Feb 2016 | 07 Jan 2016 | 17 Jan 2016 | 2 | 10 | 0 | 0
A1- FLAT 504 | 0 | No Unit | 15 Feb 2016 | 17 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 504 Tar Plaster | 745.22 | Sft. | 15 Feb 2016 | 17 Feb 2016 | 07 Jan 2016 | 17 Jan 2016 | 2 | 10 | 0 | 0
A1- 5TH FLOOR LOBBY | 0 | No Unit | 06 Aug 2016 | 08 Aug 2016 |  |  | 2 | 0 | 0 | 0
A1- 5th Floor Lobby Tar Plaster | 101.05 | Sft. | 06 Aug 2016 | 08 Aug 2016 | 03 Feb 2016 | 12 Feb 2016 | 2 | 9 | 0 | 0
A1- 5th Floor Int. Plaster (Lab) | 62960 | Sft. | 04 Feb 2016 | 17 Feb 2016 | 17 Jan 2016 | 17 Mar 2016 | 13 | 60 | 0 | 29
A1- 5th Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 04 Feb 2016 | 17 Feb 2016 | 09 May 2016 | 30 Jun 2016 | 13 | 52 | 95 | 134
A1- 6TH FLOOR | 0 | No Unit | 25 Feb 2016 | 10 Aug 2016 |  |  | 167 | 0 | 0 | 0
A1- FLAT 601 | 0 | No Unit | 25 Feb 2016 | 27 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 601 Tar Plaster | 650 | Sft. | 25 Feb 2016 | 27 Feb 2016 | 22 Jan 2016 | 12 Feb 2016 | 2 | 21 | 0 | 0
A1- FLAT 602 | 0 | No Unit | 29 Feb 2016 | 02 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 602 Tar Plaster | 650 | Sft. | 29 Feb 2016 | 02 Mar 2016 | 22 Jan 2016 | 12 Feb 2016 | 2 | 21 | 0 | 0
A1- FLAT 603 | 0 | No Unit | 03 Mar 2016 | 05 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 603 Tar Plaster | 650 | Sft. | 03 Mar 2016 | 05 Mar 2016 | 22 Jan 2016 | 12 Feb 2016 | 2 | 21 | 0 | 0
A1- FLAT 604 | 0 | No Unit | 08 Mar 2016 | 10 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 604 Tar Plaster | 650 | Sft. | 08 Mar 2016 | 10 Mar 2016 | 22 Jan 2016 | 12 Feb 2016 | 2 | 21 | 0 | 0
A1- 6TH FLOOR LOBBY | 0 | No Unit | 09 Aug 2016 | 10 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- 6th Floor Lobby Tar Plaster | 101.05 | Sft. | 09 Aug 2016 | 10 Aug 2016 | 03 Feb 2016 | 12 Feb 2016 | 1 | 9 | 0 | 0
A1- 6th Floor Int. Plaster (Lab) | 62960 | Sft. | 25 Feb 2016 | 10 Mar 2016 | 03 Feb 2016 | 17 Mar 2016 | 14 | 43 | 0 | 7
A1- 6th Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 25 Feb 2016 | 10 Mar 2016 | 09 May 2016 | 30 Jun 2016 | 14 | 52 | 74 | 112
A1- 7TH FLOOR | 0 | No Unit | 22 Feb 2016 | 12 Aug 2016 |  |  | 172 | 0 | 0 | 0
A1- FLAT 701 | 0 | No Unit | 22 Feb 2016 | 24 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 701 Tar Plaster | 650 | Sft. | 22 Feb 2016 | 24 Feb 2016 | 17 Feb 2016 | 27 Feb 2016 | 2 | 10 | 0 | 3
A1- FLAT 702 | 0 | No Unit | 25 Feb 2016 | 27 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 702 Tar Plaster | 650 | Sft. | 25 Feb 2016 | 27 Feb 2016 | 17 Feb 2016 | 27 Feb 2016 | 2 | 10 | 0 | 0
A1- FLAT 703 | 0 | No Unit | 29 Feb 2016 | 02 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 703 Tar Plaster | 650 | Sft. | 29 Feb 2016 | 02 Mar 2016 | 17 Feb 2016 | 27 Feb 2016 | 2 | 10 | 0 | 0
A1- FLAT 704 | 0 | No Unit | 03 Mar 2016 | 05 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 704 Tar Plaster | 650 | Sft. | 03 Mar 2016 | 05 Mar 2016 | 17 Feb 2016 | 27 Feb 2016 | 2 | 10 | 0 | 0
A1- 7TH FLOOR LOBBY | 0 | No Unit | 11 Aug 2016 | 12 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- 7th Floor Lobby Tar Plaster | 101.05 | Sft. | 11 Aug 2016 | 12 Aug 2016 | 23 Mar 2016 | 14 Apr 2016 | 1 | 22 | 0 | 0
A1- 7th Floor Int. Plaster (Lab) | 62960 | Sft. | 22 Feb 2016 | 05 Mar 2016 | 27 Feb 2016 | 17 Mar 2016 | 12 | 19 | 5 | 12
A1- 7th Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 22 Feb 2016 | 05 Mar 2016 | 09 May 2016 | 30 Jun 2016 | 12 | 52 | 77 | 117
A1- 8TH FLOOR | 0 | No Unit | 08 Mar 2016 | 16 Aug 2016 |  |  | 161 | 0 | 0 | 0
A1- REFUGE FLAT 804 | 0 | No Unit | 30 Mar 2016 | 01 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1- Refuge Flat 804 Tar Plaster | 0 | Sft. | 30 Mar 2016 | 01 Apr 2016 | 26 Feb 2016 | 22 Aug 2016 | 2 | 178 | 0 | 143
A1- FLAT 802 | 0 | No Unit | 08 Mar 2016 | 10 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 802 Tar Plaster | 650 | Sft. | 08 Mar 2016 | 10 Mar 2016 | 26 Feb 2016 | 27 Feb 2016 | 2 | 1 | 0 | 0
A1- FLAT 803 | 0 | No Unit | 11 Mar 2016 | 14 Mar 2016 |  |  | 3 | 0 | 0 | 0
A1- Flat 803 Tar Plaster | 650 | Sft. | 11 Mar 2016 | 14 Mar 2016 | 26 Feb 2016 | 27 Feb 2016 | 3 | 1 | 0 | 0
A1- FLAT 801 | 0 | No Unit | 15 Mar 2016 | 17 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 801 Tar Plaster | 650 | Sft. | 15 Mar 2016 | 17 Mar 2016 | 26 Feb 2016 | 27 Feb 2016 | 2 | 1 | 0 | 0
A1- 8TH FLOOR LOBBY | 0 | No Unit | 13 Aug 2016 | 16 Aug 2016 |  |  | 3 | 0 | 0 | 0
A1- 8th Floor Lobby Tar Plaster | 101.05 | Sft. | 13 Aug 2016 | 16 Aug 2016 | 23 Mar 2016 | 14 Apr 2016 | 3 | 22 | 0 | 0
A1- 8th Floor Int. Plaster (Lab) | 62960 | Sft. | 30 Mar 2016 | 12 Apr 2016 | 27 Feb 2016 | 17 Mar 2016 | 13 | 19 | 0 | 0
A1- 8th Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 30 Mar 2016 | 12 Apr 2016 | 09 May 2016 | 30 Jun 2016 | 13 | 52 | 40 | 79
A1- 9TH FLOOR | 0 | No Unit | 11 Mar 2016 | 18 Aug 2016 |  |  | 160 | 0 | 0 | 0
A1- FLAT 901 | 0 | No Unit | 11 Mar 2016 | 14 Mar 2016 |  |  | 3 | 0 | 0 | 0
A1- Flat 901 Tar Plaster | 650 | Sft. | 11 Mar 2016 | 14 Mar 2016 | 01 Mar 2016 | 14 Apr 2016 | 3 | 44 | 0 | 31
A1- FLAT 902 | 0 | No Unit | 15 Mar 2016 | 17 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 902 Tar Plaster | 650 | Sft. | 15 Mar 2016 | 17 Mar 2016 | 01 Mar 2016 | 14 Apr 2016 | 2 | 44 | 0 | 28
A1- FLAT 903 | 0 | No Unit | 18 Mar 2016 | 21 Mar 2016 |  |  | 3 | 0 | 0 | 0
A1- Flat 903 Tar Plaster | 650 | Sft. | 18 Mar 2016 | 21 Mar 2016 | 01 Mar 2016 | 14 Apr 2016 | 3 | 44 | 0 | 24
A1- FLAT 904 | 0 | No Unit | 22 Mar 2016 | 24 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 904 Tar Plaster | 650 | Sft. | 22 Mar 2016 | 24 Mar 2016 | 01 Mar 2016 | 14 Apr 2016 | 2 | 44 | 0 | 21
A1- 9TH FLOOR LOBBY | 0 | No Unit | 17 Aug 2016 | 18 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- 9th Floor Lobby Tar Plaster | 101.05 | Sft. | 17 Aug 2016 | 18 Aug 2016 | 23 Mar 2016 | 14 Apr 2016 | 1 | 22 | 0 | 0
A1- 9th Floor Int. Plaster (Lab) | 62960 | Sft. | 11 Mar 2016 | 24 Mar 2016 | 01 Mar 2016 | 17 Mar 2016 | 13 | 16 | 0 | 0
A1- 9th Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 11 Mar 2016 | 24 Mar 2016 | 09 May 2016 | 30 Jun 2016 | 13 | 52 | 59 | 98
A1- 10TH FLOOR | 0 | No Unit | 22 Mar 2016 | 20 Aug 2016 |  |  | 151 | 0 | 0 | 0
A1- FLAT 1001 | 0 | No Unit | 22 Mar 2016 | 24 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1001 Tar Plaster | 650 | Sft. | 22 Mar 2016 | 24 Mar 2016 | 14 Mar 2016 | 14 Apr 2016 | 2 | 31 | 0 | 21
A1- FLAT 1002 | 0 | No Unit | 25 Mar 2016 | 28 Mar 2016 |  |  | 3 | 0 | 0 | 0
A1- Flat 1002 Tar Plaster | 650 | Sft. | 25 Mar 2016 | 28 Mar 2016 | 14 Mar 2016 | 14 Apr 2016 | 3 | 31 | 0 | 17
A1- FLAT 1003 | 0 | No Unit | 29 Mar 2016 | 31 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1003 Tar Plaster | 650 | Sft. | 29 Mar 2016 | 31 Mar 2016 | 14 Mar 2016 | 14 Apr 2016 | 2 | 31 | 0 | 14
A1- FLAT 1004 | 0 | No Unit | 29 Mar 2016 | 31 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1004 Tar Plaster | 650 | Sft. | 29 Mar 2016 | 31 Mar 2016 | 14 Mar 2016 | 14 Apr 2016 | 2 | 31 | 0 | 14
A1- 10TH FLOOR LOBBY | 0 | No Unit | 19 Aug 2016 | 20 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- 10th Floor Lobby Tar Plaster | 101.05 | Sft. | 19 Aug 2016 | 20 Aug 2016 | 30 Mar 2016 | 14 Apr 2016 | 1 | 15 | 0 | 0
A1- 10th Floor Int. Plaster (Lab) | 62960 | Sft. | 22 Mar 2016 | 04 Apr 2016 | 23 Apr 2016 | 03 May 2016 | 13 | 10 | 32 | 29
A1- 10th Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 22 Mar 2016 | 04 Apr 2016 | 09 May 2016 | 12 Jan 2017 | 13 | 248 | 48 | 283
A1- 11TH FLOOR | 0 | No Unit | 29 Mar 2016 | 23 Aug 2016 |  |  | 147 | 0 | 0 | 0
A1- FLAT 1101 | 0 | No Unit | 29 Mar 2016 | 31 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1101 Tar Plaster | 650 | Sft. | 29 Mar 2016 | 31 Mar 2016 | 11 Apr 2016 | 14 Apr 2016 | 2 | 3 | 13 | 14
A1- FLAT 1102 | 0 | No Unit | 29 Mar 2016 | 31 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1102 Tar Plaster | 650 | Sft. | 29 Mar 2016 | 31 Mar 2016 | 11 Apr 2016 | 14 Apr 2016 | 2 | 3 | 13 | 14
A1- FLAT 1103 | 0 | No Unit | 29 Mar 2016 | 31 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1103 Tar Plaster | 650 | Sft. | 29 Mar 2016 | 31 Mar 2016 | 11 Apr 2016 | 14 Apr 2016 | 2 | 3 | 13 | 14
A1- FLAT 1104 | 0 | No Unit | 29 Mar 2016 | 31 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1104 Tar Plaster | 650 | Sft. | 29 Mar 2016 | 31 Mar 2016 | 11 Apr 2016 | 14 Apr 2016 | 2 | 3 | 13 | 14
A1- 11TH FLOOR LOBBY | 0 | No Unit | 22 Aug 2016 | 23 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- 11th Floor Lobby Tar Plaster | 101.05 | Sft. | 22 Aug 2016 | 23 Aug 2016 | 23 Apr 2016 | 03 May 2016 | 1 | 10 | 0 | 0
A1- 11th Floor Int. Plaster (Lab) | 62960 | Sft. | 29 Mar 2016 | 11 Apr 2016 | 14 Apr 2016 | 03 May 2016 | 13 | 19 | 16 | 22
A1- 11th Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 29 Mar 2016 | 11 Apr 2016 | 30 Jun 2016 | 25 Jan 2017 | 13 | 209 | 93 | 289
A1- 12TH FLOOR | 0 | No Unit | 28 May 2016 | 25 Aug 2016 |  |  | 89 | 0 | 0 | 0
A1- FLAT 1201 | 0 | No Unit | 28 May 2016 | 31 May 2016 |  |  | 3 | 0 | 0 | 0
A1- Flat 1201 Tar Plaster | 650 | Sft. | 28 May 2016 | 31 May 2016 | 10 Jun 2016 | 30 Jun 2016 | 3 | 20 | 13 | 30
A1- FLAT 1202 | 0 | No Unit | 01 Jun 2016 | 03 Jun 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1202 Tar Plaster | 650 | Sft. | 01 Jun 2016 | 03 Jun 2016 | 10 Jun 2016 | 20 Jul 2016 | 2 | 40 | 9 | 47
A1- FLAT 1203 | 0 | No Unit | 04 Jun 2016 | 07 Jun 2016 |  |  | 3 | 0 | 0 | 0
A1- Flat 1203 Tar Plaster | 650 | Sft. | 04 Jun 2016 | 07 Jun 2016 | 10 Jun 2016 | 20 Jul 2016 | 3 | 40 | 6 | 43
A1- FLAT 1204 | 0 | No Unit | 08 Jun 2016 | 10 Jun 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1204 Tar Plaster | 650 | Sft. | 08 Jun 2016 | 10 Jun 2016 | 10 Jun 2016 | 30 Jun 2016 | 2 | 20 | 2 | 20
A1- 12TH FLOOR LOBBY | 0 | No Unit | 24 Aug 2016 | 25 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- 12th Floor Lobby Tar Plaster | 101.05 | Sft. | 24 Aug 2016 | 25 Aug 2016 | 14 Jun 2016 | 20 Jul 2016 | 1 | 36 | 0 | 0
A1- 12th Floor Int. Plaster (Lab) | 62960 | Sft. | 28 May 2016 | 10 Jun 2016 | 14 Jun 2016 | 27 Jul 2016 | 13 | 43 | 17 | 47
A1- 12th Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 28 May 2016 | 10 Jun 2016 | 14 Jun 2016 | 25 Jan 2017 | 13 | 225 | 17 | 229
A1- 13TH FLOOR | 0 | No Unit | 23 Jun 2016 | 27 Aug 2016 |  |  | 65 | 0 | 0 | 0
A1-REFUGE FLAT 1304 | 0 | No Unit | 23 Jun 2016 | 25 Jun 2016 |  |  | 2 | 0 | 0 | 0
A1-Refuge Flat 1304 Tar Plaster | 0 | Sft. | 23 Jun 2016 | 25 Jun 2016 | 11 Dec 2016 | 30 Dec 2016 | 2 | 19 | 171 | 188
A1- FLAT 1302 | 0 | No Unit | 27 Jun 2016 | 29 Jun 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1302 Tar Plaster | 650 | Sft. | 27 Jun 2016 | 29 Jun 2016 | 13 Sep 2016 | 30 Dec 2016 | 2 | 108 | 78 | 184
A1- FLAT 1303 | 0 | No Unit | 30 Jun 2016 | 02 Jul 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1303 Tar Plaster | 650 | Sft. | 30 Jun 2016 | 02 Jul 2016 | 07 Oct 2016 | 30 Dec 2016 | 2 | 84 | 99 | 181
A1- FLAT 1301 | 0 | No Unit | 04 Jul 2016 | 06 Jul 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1301 Tar Plaster | 650 | Sft. | 04 Jul 2016 | 06 Jul 2016 | 13 Sep 2016 | 30 Dec 2016 | 2 | 108 | 71 | 177
A1- 13TH FLOOR LOBBY | 0 | No Unit | 26 Aug 2016 | 27 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- 13th Floor Lobby Tar Plaster | 101.05 | Sft. | 26 Aug 2016 | 27 Aug 2016 | 09 Jul 2016 | 20 Jul 2016 | 1 | 11 | 0 | 0
A1- 13th Floor Int. Plaster (Lab) | 62960 | Sft. | 23 Jun 2016 | 06 Jul 2016 | 28 Jun 2016 | 12 Jan 2017 | 13 | 198 | 5 | 190
A1- 13th Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 23 Jun 2016 | 06 Jul 2016 | 11 Dec 2016 | 25 Jan 2017 | 13 | 45 | 171 | 203
A1- 14TH FLOOR | 0 | No Unit | 09 Jul 2016 | 30 Aug 2016 |  |  | 52 | 0 | 0 | 0
A1- FLAT 1401 | 0 | No Unit | 09 Jul 2016 | 12 Jul 2016 |  |  | 3 | 0 | 0 | 0
A1- Flat 1401 Tar Plaster | 650 | Sft. | 09 Jul 2016 | 12 Jul 2016 | 11 Dec 2016 | 30 Dec 2016 | 3 | 19 | 155 | 171
A1- FLAT 1402 | 0 | No Unit | 13 Jul 2016 | 15 Jul 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1402 Tar Plaster | 650 | Sft. | 13 Jul 2016 | 15 Jul 2016 | 11 Dec 2016 | 30 Dec 2016 | 2 | 19 | 151 | 168
A1- FLAT 1403 | 0 | No Unit | 16 Jul 2016 | 19 Jul 2016 |  |  | 3 | 0 | 0 | 0
A1- Flat 1403 Tar Plaster | 650 | Sft. | 16 Jul 2016 | 19 Jul 2016 | 11 Dec 2016 | 30 Dec 2016 | 3 | 19 | 148 | 164
A1- FLAT 1404 | 0 | No Unit | 20 Jul 2016 | 22 Jul 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1404 Tar Plaster | 650 | Sft. | 20 Jul 2016 | 22 Jul 2016 | 11 Dec 2016 | 30 Dec 2016 | 2 | 19 | 144 | 161
A1- 14TH FLOOR LOBBY | 0 | No Unit | 29 Aug 2016 | 30 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- 14th Floor Lobby Tar Plaster | 101.05 | Sft. | 29 Aug 2016 | 30 Aug 2016 | 09 Jul 2016 | 20 Jul 2016 | 1 | 11 | 0 | 0
A1- 14th Floor Int. Plaster (Lab) | 62960 | Sft. | 09 Jul 2016 | 22 Jul 2016 | 28 Jun 2016 | 12 Jan 2017 | 13 | 198 | 0 | 174
A1- 14th Floor Tar Plaster due to Uneven Thickness | 62960 | Sft. | 09 Jul 2016 | 22 Jul 2016 | 11 Dec 2016 | 12 Jan 2017 | 13 | 32 | 155 | 174
A1- TAR PLATSRE FOR ELECTRICAL, PLUMBING, | 0 | No Unit | 17 Nov 2016 | 03 Dec 2016 |  |  | 16 | 0 | 0 | 0
A1- Tar platsre for Electrical, Plumbing, Tar Plaster | 1300 | Sft. | 17 Nov 2016 | 03 Dec 2016 | 10 May 2016 | 12 Jan 2017 | 16 | 247 | 0 | 40
A1-TOP TERRACE FLOOR | 0 | No Unit | 31 Aug 2016 | 01 Sep 2016 |  |  | 1 | 0 | 0 | 0
A1- TOP FLOOR LOBBY | 0 | No Unit | 31 Aug 2016 | 01 Sep 2016 |  |  | 1 | 0 | 0 | 0
A1- Top Floor Lobby Tar Plaster | 0 | Sft. | 31 Aug 2016 | 01 Sep 2016 | 08 Sep 2016 | 12 Jan 2017 | 1 | 126 | 8 | 133
A1-CEMENT GHOTAI PLASTER | 0 | No Unit | 04 Nov 2015 | 05 Aug 2016 |  |  | 275 | 0 | 0 | 0
A1-PARKING FLOOR | 0 | No Unit | 30 Jul 2016 | 03 Aug 2016 |  |  | 4 | 0 | 0 | 0
A1-PARKING FLOOR LOBBY | 0 | No Unit | 30 Jul 2016 | 30 Jul 2016 |  |  | 0 | 0 | 0 | 0
A1-Parking Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 30 Jul 2016 | 30 Jul 2016 | 15 Dec 2015 | 03 May 2016 | 0 | 140 | 0 | 0
A1-PARKING FLOOR MAIN STAIR | 0 | No Unit | 01 Aug 2016 | 01 Aug 2016 |  |  | 0 | 0 | 0 | 0
A1-Parking Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 01 Aug 2016 | 01 Aug 2016 | 15 Dec 2015 | 29 Dec 2015 | 0 | 14 | 0 | 0
A1-PARKING FLOOR FIRE STAIR | 59.56 | No Unit | 02 Aug 2016 | 02 Aug 2016 |  |  | 0 | 0 | 0 | 0
A1-Parking Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 02 Aug 2016 | 02 Aug 2016 | 15 Dec 2015 | 29 Dec 2015 | 0 | 14 | 0 | 0
A1-PARKING FLOOR METER ROOM | 0 | No Unit | 03 Aug 2016 | 03 Aug 2016 |  |  | 0 | 0 | 0 | 0
A1-Parking Floor Meter Room Cement Ghotai Plaster (Skirting) | 151.52 | Sft. | 03 Aug 2016 | 03 Aug 2016 | 15 Dec 2015 | 03 May 2016 | 0 | 140 | 0 | 0
A1-1ST FLOOR | 0 | No Unit | 04 Nov 2015 | 13 Nov 2015 |  |  | 9 | 0 | 0 | 0
A1-101 | 0 | No Unit | 04 Nov 2015 | 05 Nov 2015 |  |  | 1 | 0 | 0 | 0
A1-101 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 04 Nov 2015 | 05 Nov 2015 | 03 Nov 2015 | 10 Nov 2015 | 1 | 7 | 0 | 5
A1-102 | 0 | No Unit | 06 Nov 2015 | 07 Nov 2015 |  |  | 1 | 0 | 0 | 0
A1-102 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 06 Nov 2015 | 07 Nov 2015 | 03 Nov 2015 | 10 Nov 2015 | 1 | 7 | 0 | 3
A1-103 | 0 | No Unit | 09 Nov 2015 | 10 Nov 2015 |  |  | 1 | 0 | 0 | 0
A1-103 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 09 Nov 2015 | 10 Nov 2015 | 03 Nov 2015 | 10 Nov 2015 | 1 | 7 | 0 | 0
A1-104 | 0 | No Unit | 11 Nov 2015 | 12 Nov 2015 |  |  | 1 | 0 | 0 | 0
A1-104 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 11 Nov 2015 | 12 Nov 2015 | 03 Nov 2015 | 10 Nov 2015 | 1 | 7 | 0 | 0
A1-1ST FLOOR LOBBY | 0 | No Unit | 13 Nov 2015 | 13 Nov 2015 |  |  | 0 | 0 | 0 | 0
A1-1st Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 13 Nov 2015 | 13 Nov 2015 | 29 Dec 2015 | 29 Dec 2015 | 0 | 0 | 46 | 46
A1-1ST FLOOR MAIN STAIR | 0 | No Unit | 13 Nov 2015 | 13 Nov 2015 |  |  | 0 | 0 | 0 | 0
A1-1st Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 13 Nov 2015 | 13 Nov 2015 | 29 Dec 2015 | 29 Dec 2015 | 0 | 0 | 46 | 46
A1-1ST FLOOR FIRE STAIR | 0 | No Unit | 13 Nov 2015 | 13 Nov 2015 |  |  | 0 | 0 | 0 | 0
A1-1st Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 13 Nov 2015 | 13 Nov 2015 | 29 Dec 2015 | 29 Dec 2015 | 0 | 0 | 46 | 46
A1-2ND FLOOR | 0 | No Unit | 12 Nov 2015 | 24 Nov 2015 |  |  | 12 | 0 | 0 | 0
A1-201 | 0 | No Unit | 12 Nov 2015 | 13 Nov 2015 |  |  | 1 | 0 | 0 | 0
A1-201 Cement Ghotai Plaster (Skirting) | 176.0874 | Sft. | 12 Nov 2015 | 13 Nov 2015 | 06 Nov 2015 | 10 Nov 2015 | 1 | 4 | 0 | 0
A1-202 | 0 | No Unit | 14 Nov 2015 | 16 Nov 2015 |  |  | 2 | 0 | 0 | 0
A1-202 Cement Ghotai Plaster (Skirting) | 176.0874 | Sft. | 14 Nov 2015 | 16 Nov 2015 | 06 Nov 2015 | 10 Nov 2015 | 2 | 4 | 0 | 0
A1-203 | 0 | No Unit | 17 Nov 2015 | 18 Nov 2015 |  |  | 1 | 0 | 0 | 0
A1-203 Cement Ghotai Plaster (Skirting) | 176.0874 | Sft. | 17 Nov 2015 | 18 Nov 2015 | 06 Nov 2015 | 10 Nov 2015 | 1 | 4 | 0 | 0
A1-204 | 0 | No Unit | 19 Nov 2015 | 20 Nov 2015 |  |  | 1 | 0 | 0 | 0
A1-204 Cement Ghotai Plaster (Skirting) | 176.0874 | Sft. | 19 Nov 2015 | 20 Nov 2015 | 06 Nov 2015 | 10 Nov 2015 | 1 | 4 | 0 | 0
A1-2ND FLOOR LOBBY | 0 | No Unit | 21 Nov 2015 | 21 Nov 2015 |  |  | 0 | 0 | 0 | 0
A1-2nd Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 21 Nov 2015 | 21 Nov 2015 | 29 Dec 2015 | 29 Dec 2015 | 0 | 0 | 38 | 38
A1-2ND FLOOR MAIN STAIR | 0 | No Unit | 23 Nov 2015 | 23 Nov 2015 |  |  | 0 | 0 | 0 | 0
A1-2nd Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 23 Nov 2015 | 23 Nov 2015 | 29 Dec 2015 | 29 Dec 2015 | 0 | 0 | 36 | 36
A1-2ND FLOOR FIRE STAIR | 0 | No Unit | 24 Nov 2015 | 24 Nov 2015 |  |  | 0 | 0 | 0 | 0
A1-2nd Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 24 Nov 2015 | 24 Nov 2015 | 29 Dec 2015 | 29 Dec 2015 | 0 | 0 | 35 | 35
A1-3RD FLOOR | 0 | No Unit | 02 Dec 2015 | 14 Dec 2015 |  |  | 12 | 0 | 0 | 0
A1-301 | 0 | No Unit | 02 Dec 2015 | 03 Dec 2015 |  |  | 1 | 0 | 0 | 0
A1-301 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 02 Dec 2015 | 03 Dec 2015 | 16 Nov 2015 | 09 Dec 2015 | 1 | 23 | 0 | 6
A1-302 | 0 | No Unit | 04 Dec 2015 | 05 Dec 2015 |  |  | 1 | 0 | 0 | 0
A1-302 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 04 Dec 2015 | 05 Dec 2015 | 16 Nov 2015 | 09 Dec 2015 | 1 | 23 | 0 | 4
A1-303 | 0 | No Unit | 07 Dec 2015 | 08 Dec 2015 |  |  | 1 | 0 | 0 | 0
A1-303 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 07 Dec 2015 | 08 Dec 2015 | 16 Nov 2015 | 09 Dec 2015 | 1 | 23 | 0 | 1
A1-304 | 0 | No Unit | 09 Dec 2015 | 10 Dec 2015 |  |  | 1 | 0 | 0 | 0
A1-304 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 09 Dec 2015 | 10 Dec 2015 | 16 Nov 2015 | 29 Dec 2015 | 1 | 43 | 0 | 19
A1-3RD FLOOR LOBBY | 0 | No Unit | 11 Dec 2015 | 11 Dec 2015 |  |  | 0 | 0 | 0 | 0
A1-3rd Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 11 Dec 2015 | 11 Dec 2015 | 29 Dec 2015 | 29 Dec 2015 | 0 | 0 | 18 | 18
A1-3RD FLOOR MAIN STAIR | 0 | No Unit | 12 Dec 2015 | 12 Dec 2015 |  |  | 0 | 0 | 0 | 0
A1-3rd Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 12 Dec 2015 | 12 Dec 2015 | 29 Dec 2015 | 29 Dec 2015 | 0 | 0 | 17 | 17
A1-3RD FLOOR FIRE STAIR | 0 | No Unit | 14 Dec 2015 | 14 Dec 2015 |  |  | 0 | 0 | 0 | 0
A1-3rd Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 14 Dec 2015 | 14 Dec 2015 | 29 Dec 2015 | 29 Dec 2015 | 0 | 0 | 15 | 15
A1-4TH FLOOR | 0 | No Unit | 23 Dec 2015 | 05 Jan 2016 |  |  | 13 | 0 | 0 | 0
A1-401 | 0 | No Unit | 23 Dec 2015 | 24 Dec 2015 |  |  | 1 | 0 | 0 | 0
A1-401 Cement Ghotai Plaster (Skirting) | 176.0874 | Sft. | 23 Dec 2015 | 24 Dec 2015 | 19 Dec 2015 | 30 Dec 2015 | 1 | 11 | 0 | 6
A1-402 | 0 | No Unit | 25 Dec 2015 | 26 Dec 2015 |  |  | 1 | 0 | 0 | 0
A1-402 Cement Ghotai Plaster (Skirting) | 176.0874 | Sft. | 25 Dec 2015 | 26 Dec 2015 | 19 Dec 2015 | 30 Dec 2015 | 1 | 11 | 0 | 4
A1-403 | 0 | No Unit | 28 Dec 2015 | 29 Dec 2015 |  |  | 1 | 0 | 0 | 0
A1-403 Cement Ghotai Plaster (Skirting) | 176.0874 | Sft. | 28 Dec 2015 | 29 Dec 2015 | 19 Dec 2015 | 30 Dec 2015 | 1 | 11 | 0 | 1
A1-404 | 0 | No Unit | 30 Dec 2015 | 01 Jan 2016 |  |  | 2 | 0 | 0 | 0
A1-404 Cement Ghotai Plaster (Skirting) | 176.0874 | Sft. | 30 Dec 2015 | 01 Jan 2016 | 19 Dec 2015 | 30 Dec 2015 | 2 | 11 | 0 | 0
A1-4TH FLOOR LOBBY | 0 | No Unit | 02 Jan 2016 | 02 Jan 2016 |  |  | 0 | 0 | 0 | 0
A1-4th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 02 Jan 2016 | 02 Jan 2016 | 19 Dec 2015 | 17 Jan 2016 | 0 | 29 | 0 | 15
A1-4TH FLOOR MAIN STAIR | 0 | No Unit | 04 Jan 2016 | 04 Jan 2016 |  |  | 0 | 0 | 0 | 0
A1-4th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 04 Jan 2016 | 04 Jan 2016 | 04 Jan 2016 | 17 Jan 2016 | 0 | 13 | 0 | 13
A1-4TH FLOOR FIRE STAIR | 0 | No Unit | 05 Jan 2016 | 05 Jan 2016 |  |  | 0 | 0 | 0 | 0
A1-4th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 05 Jan 2016 | 05 Jan 2016 | 04 Jan 2016 | 17 Jan 2016 | 0 | 13 | 0 | 12
A1-5TH FLOOR | 0 | No Unit | 15 Jan 2016 | 28 Jan 2016 |  |  | 13 | 0 | 0 | 0
A1-501 | 0 | No Unit | 15 Jan 2016 | 16 Jan 2016 |  |  | 1 | 0 | 0 | 0
A1-501 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 15 Jan 2016 | 16 Jan 2016 | 04 Jan 2016 | 17 Jan 2016 | 1 | 13 | 0 | 1
A1-502 | 0 | No Unit | 18 Jan 2016 | 19 Jan 2016 |  |  | 1 | 0 | 0 | 0
A1-502 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 18 Jan 2016 | 19 Jan 2016 | 04 Jan 2016 | 17 Jan 2016 | 1 | 13 | 0 | 0
A1-503 | 0 | No Unit | 20 Jan 2016 | 21 Jan 2016 |  |  | 1 | 0 | 0 | 0
A1-503 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 20 Jan 2016 | 21 Jan 2016 | 04 Jan 2016 | 17 Jan 2016 | 1 | 13 | 0 | 0
A1-504 | 0 | No Unit | 22 Jan 2016 | 23 Jan 2016 |  |  | 1 | 0 | 0 | 0
A1-504 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 22 Jan 2016 | 23 Jan 2016 | 04 Jan 2016 | 17 Jan 2016 | 1 | 13 | 0 | 0
A1-5TH FLOOR LOBBY | 0 | No Unit | 25 Jan 2016 | 25 Jan 2016 |  |  | 0 | 0 | 0 | 0
A1-5th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 25 Jan 2016 | 25 Jan 2016 | 04 Jan 2016 | 17 Jan 2016 | 0 | 13 | 0 | 0
A1-5TH FLOOR MAIN STAIR | 0 | No Unit | 27 Jan 2016 | 27 Jan 2016 |  |  | 0 | 0 | 0 | 0
A1-5th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 27 Jan 2016 | 27 Jan 2016 | 04 Jan 2016 | 17 Jan 2016 | 0 | 13 | 0 | 0
A1-5TH FLOOR FIRE STAIR | 0 | No Unit | 28 Jan 2016 | 28 Jan 2016 |  |  | 0 | 0 | 0 | 0
A1-5th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 28 Jan 2016 | 28 Jan 2016 | 04 Jan 2016 | 17 Jan 2016 | 0 | 13 | 0 | 0
A1-6TH FLOOR | 0 | No Unit | 06 Feb 2016 | 18 Feb 2016 |  |  | 12 | 0 | 0 | 0
A1-601 | 0 | No Unit | 06 Feb 2016 | 08 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1-601 Cement Ghotai Plaster (Skirting) | 176.0874 | Sft. | 06 Feb 2016 | 08 Feb 2016 | 11 Jan 2016 | 17 Jan 2016 | 2 | 6 | 0 | 0
A1-602 | 0 | No Unit | 09 Feb 2016 | 10 Feb 2016 |  |  | 1 | 0 | 0 | 0
A1-602 Cement Ghotai Plaster (Skirting) | 176.0874 | Sft. | 09 Feb 2016 | 10 Feb 2016 | 11 Jan 2016 | 17 Jan 2016 | 1 | 6 | 0 | 0
A1-603 | 0 | No Unit | 11 Feb 2016 | 12 Feb 2016 |  |  | 1 | 0 | 0 | 0
A1-603 Cement Ghotai Plaster (Skirting) | 176.0874 | Sft. | 11 Feb 2016 | 12 Feb 2016 | 11 Jan 2016 | 17 Jan 2016 | 1 | 6 | 0 | 0
A1-604 | 0 | No Unit | 13 Feb 2016 | 15 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1-604 Cement Ghotai Plaster (Skirting) | 176.0874 | Sft. | 13 Feb 2016 | 15 Feb 2016 | 11 Jan 2016 | 17 Jan 2016 | 2 | 6 | 0 | 0
A1-6TH FLOOR LOBBY | 0 | No Unit | 16 Feb 2016 | 16 Feb 2016 |  |  | 0 | 0 | 0 | 0
A1-6th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 16 Feb 2016 | 16 Feb 2016 | 04 Jan 2016 | 17 Jan 2016 | 0 | 13 | 0 | 0
A1-6TH FLOOR MAIN STAIR | 0 | No Unit | 17 Feb 2016 | 17 Feb 2016 |  |  | 0 | 0 | 0 | 0
A1-6th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 17 Feb 2016 | 17 Feb 2016 | 04 Jan 2016 | 17 Jan 2016 | 0 | 13 | 0 | 0
A1-6TH FLOOR FIRE STAIR | 0 | No Unit | 18 Feb 2016 | 18 Feb 2016 |  |  | 0 | 0 | 0 | 0
A1-6th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 18 Feb 2016 | 18 Feb 2016 | 04 Jan 2016 | 17 Jan 2016 | 0 | 13 | 0 | 0
A1-7TH FLOOR | 0 | No Unit | 23 Feb 2016 | 05 Mar 2016 |  |  | 11 | 0 | 0 | 0
A1-701 | 0 | No Unit | 23 Feb 2016 | 24 Feb 2016 |  |  | 1 | 0 | 0 | 0
A1-701 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 23 Feb 2016 | 24 Feb 2016 | 18 Jan 2016 | 12 Feb 2016 | 1 | 25 | 0 | 0
A1-702 | 0 | No Unit | 25 Feb 2016 | 26 Feb 2016 |  |  | 1 | 0 | 0 | 0
A1-702 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 25 Feb 2016 | 26 Feb 2016 | 18 Jan 2016 | 12 Feb 2016 | 1 | 25 | 0 | 0
A1-703 | 0 | No Unit | 27 Feb 2016 | 29 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1-703 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 27 Feb 2016 | 29 Feb 2016 | 18 Jan 2016 | 12 Feb 2016 | 2 | 25 | 0 | 0
A1-704 | 0 | No Unit | 01 Mar 2016 | 02 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-704 Cement Ghotai Plaster (Skirting) | 177.54 | Sft. | 01 Mar 2016 | 02 Mar 2016 | 18 Jan 2016 | 12 Feb 2016 | 1 | 25 | 0 | 0
A1-7TH FLOOR LOBBY | 0 | No Unit | 03 Mar 2016 | 03 Mar 2016 |  |  | 0 | 0 | 0 | 0
A1-7th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 03 Mar 2016 | 03 Mar 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 42 | 50
A1-7TH FLOOR MAIN STAIR | 0 | No Unit | 04 Mar 2016 | 04 Mar 2016 |  |  | 0 | 0 | 0 | 0
A1-7th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 04 Mar 2016 | 04 Mar 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 41 | 49
A1-7TH FLOOR FIRE STAIR | 0 | No Unit | 05 Mar 2016 | 05 Mar 2016 |  |  | 0 | 0 | 0 | 0
A1-7th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 05 Mar 2016 | 05 Mar 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 40 | 48
A1-8TH FLOOR | 0 | No Unit | 11 Mar 2016 | 24 Mar 2016 |  |  | 13 | 0 | 0 | 0
A1-REFUGE 804 | 0 | No Unit | 11 Mar 2016 | 12 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-Refuge 804 Cement Ghotai Plaster (Skirting) | 0 | Sft. | 11 Mar 2016 | 12 Mar 2016 | 08 Feb 2016 | 30 Jun 2016 | 1 | 143 | 0 | 110
A1-802 | 0 | No Unit | 14 Mar 2016 | 15 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-802 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 14 Mar 2016 | 15 Mar 2016 | 08 Feb 2016 | 27 Feb 2016 | 1 | 19 | 0 | 0
A1-803 | 0 | No Unit | 16 Mar 2016 | 17 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-803 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 16 Mar 2016 | 17 Mar 2016 | 08 Feb 2016 | 27 Feb 2016 | 1 | 19 | 0 | 0
A1-801 | 0 | No Unit | 18 Mar 2016 | 19 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-801 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 18 Mar 2016 | 19 Mar 2016 | 08 Feb 2016 | 27 Feb 2016 | 1 | 19 | 0 | 0
A1-8TH FLOOR LOBBY | 0 | No Unit | 21 Mar 2016 | 22 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-8th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 21 Mar 2016 | 22 Mar 2016 | 14 Apr 2016 | 22 Apr 2016 | 1 | 8 | 24 | 31
A1-8TH FLOOR MAIN STAIR | 0 | No Unit | 23 Mar 2016 | 23 Mar 2016 |  |  | 0 | 0 | 0 | 0
A1-8th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 23 Mar 2016 | 23 Mar 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 22 | 30
A1-8TH FLOOR FIRE STAIR | 0 | No Unit | 24 Mar 2016 | 24 Mar 2016 |  |  | 0 | 0 | 0 | 0
A1-8th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 24 Mar 2016 | 24 Mar 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 21 | 29
A1-9TH FLOOR | 0 | No Unit | 01 Apr 2016 | 12 Apr 2016 |  |  | 11 | 0 | 0 | 0
A1-901 | 0 | No Unit | 01 Apr 2016 | 02 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1-901 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 01 Apr 2016 | 02 Apr 2016 | 14 Apr 2016 | 20 Apr 2016 | 1 | 6 | 13 | 18
A1-902 | 0 | No Unit | 04 Apr 2016 | 05 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1-902 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 04 Apr 2016 | 05 Apr 2016 | 14 Apr 2016 | 20 Apr 2016 | 1 | 6 | 10 | 15
A1-903 | 0 | No Unit | 06 Apr 2016 | 07 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1-903 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 06 Apr 2016 | 07 Apr 2016 | 14 Apr 2016 | 20 Apr 2016 | 1 | 6 | 8 | 13
A1-904 | 0 | No Unit | 08 Apr 2016 | 09 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1-904 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 08 Apr 2016 | 09 Apr 2016 | 14 Apr 2016 | 20 Apr 2016 | 1 | 6 | 6 | 11
A1-9TH FLOOR LOBBY | 0 | No Unit | 11 Apr 2016 | 11 Apr 2016 |  |  | 0 | 0 | 0 | 0
A1-9th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 11 Apr 2016 | 11 Apr 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 3 | 11
A1-9TH FLOOR MAIN STAIR | 0 | No Unit | 12 Apr 2016 | 12 Apr 2016 |  |  | 0 | 0 | 0 | 0
A1-9th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 12 Apr 2016 | 12 Apr 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 2 | 10
A1-9TH FLOOR FIRE STAIR | 0 | No Unit | 12 Apr 2016 | 12 Apr 2016 |  |  | 0 | 0 | 0 | 0
A1-9th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 12 Apr 2016 | 12 Apr 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 2 | 10
A1-10TH FLOOR | 0 | No Unit | 13 Apr 2016 | 23 Apr 2016 |  |  | 10 | 0 | 0 | 0
A1-1001 | 0 | No Unit | 13 Apr 2016 | 14 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1-1001 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 13 Apr 2016 | 14 Apr 2016 | 14 Apr 2016 | 20 Apr 2016 | 1 | 6 | 1 | 6
A1-1002 | 0 | No Unit | 15 Apr 2016 | 16 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1-1002 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 15 Apr 2016 | 16 Apr 2016 | 14 Apr 2016 | 20 Apr 2016 | 1 | 6 | 0 | 4
A1-1003 | 0 | No Unit | 18 Apr 2016 | 19 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1-1003 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 18 Apr 2016 | 19 Apr 2016 | 14 Apr 2016 | 20 Apr 2016 | 1 | 6 | 0 | 1
A1-1004 | 0 | No Unit | 20 Apr 2016 | 21 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1-1004 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 20 Apr 2016 | 21 Apr 2016 | 14 Apr 2016 | 20 Apr 2016 | 1 | 6 | 0 | 0
A1-10TH FLOOR LOBBY | 0 | No Unit | 22 Apr 2016 | 22 Apr 2016 |  |  | 0 | 0 | 0 | 0
A1-10th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 22 Apr 2016 | 22 Apr 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 0 | 0
A1-10TH FLOOR MAIN STAIR | 0 | No Unit | 23 Apr 2016 | 23 Apr 2016 |  |  | 0 | 0 | 0 | 0
A1-10th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 23 Apr 2016 | 23 Apr 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 0 | 0
A1-10TH FLOOR FIRE STAIR | 0 | No Unit | 23 Apr 2016 | 23 Apr 2016 |  |  | 0 | 0 | 0 | 0
A1-10th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 23 Apr 2016 | 23 Apr 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 0 | 0
A1-11TH FLOOR | 0 | No Unit | 28 Apr 2016 | 09 May 2016 |  |  | 11 | 0 | 0 | 0
A1-1101 | 0 | No Unit | 28 Apr 2016 | 29 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1-1101 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 28 Apr 2016 | 29 Apr 2016 | 14 Apr 2016 | 22 Apr 2016 | 1 | 8 | 0 | 0
A1-1102 | 0 | No Unit | 30 Apr 2016 | 02 May 2016 |  |  | 2 | 0 | 0 | 0
A1-1102 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 30 Apr 2016 | 02 May 2016 | 14 Apr 2016 | 22 Apr 2016 | 2 | 8 | 0 | 0
A1-1103 | 0 | No Unit | 03 May 2016 | 04 May 2016 |  |  | 1 | 0 | 0 | 0
A1-1103 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 03 May 2016 | 04 May 2016 | 14 Apr 2016 | 22 Apr 2016 | 1 | 8 | 0 | 0
A1-1104 | 0 | No Unit | 05 May 2016 | 06 May 2016 |  |  | 1 | 0 | 0 | 0
A1-1104 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 05 May 2016 | 06 May 2016 | 14 Apr 2016 | 22 Apr 2016 | 1 | 8 | 0 | 0
A1-11TH FLOOR LOBBY | 0 | No Unit | 07 May 2016 | 07 May 2016 |  |  | 0 | 0 | 0 | 0
A1-11th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 07 May 2016 | 07 May 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 0 | 0
A1-11TH FLOOR MAIN STAIR | 0 | No Unit | 09 May 2016 | 09 May 2016 |  |  | 0 | 0 | 0 | 0
A1-11th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 09 May 2016 | 09 May 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 0 | 0
A1-11TH FLOOR FIRE STAIR | 0 | No Unit | 09 May 2016 | 09 May 2016 |  |  | 0 | 0 | 0 | 0
A1-11th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 09 May 2016 | 09 May 2016 | 14 Apr 2016 | 22 Apr 2016 | 0 | 8 | 0 | 0
A1-12TH FLOOR | 0 | No Unit | 09 May 2016 | 19 May 2016 |  |  | 10 | 0 | 0 | 0
A1-1201 | 0 | No Unit | 09 May 2016 | 10 May 2016 |  |  | 1 | 0 | 0 | 0
A1-1201 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 09 May 2016 | 10 May 2016 | 08 Jul 2016 | 20 Jul 2016 | 1 | 12 | 60 | 71
A1-1202 | 0 | No Unit | 11 May 2016 | 12 May 2016 |  |  | 1 | 0 | 0 | 0
A1-1202 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 11 May 2016 | 12 May 2016 | 08 Jul 2016 | 20 Jul 2016 | 1 | 12 | 58 | 69
A1-1203 | 0 | No Unit | 13 May 2016 | 14 May 2016 |  |  | 1 | 0 | 0 | 0
A1-1203 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 13 May 2016 | 14 May 2016 | 08 Jul 2016 | 20 Jul 2016 | 1 | 12 | 56 | 67
A1-1204 | 0 | No Unit | 16 May 2016 | 17 May 2016 |  |  | 1 | 0 | 0 | 0
A1-1204 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 16 May 2016 | 17 May 2016 | 08 Jul 2016 | 20 Jul 2016 | 1 | 12 | 53 | 64
A1-12TH FLOOR LOBBY | 0 | No Unit | 18 May 2016 | 18 May 2016 |  |  | 0 | 0 | 0 | 0
A1-12th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 18 May 2016 | 18 May 2016 | 08 Jul 2016 | 21 Jul 2016 | 0 | 13 | 51 | 64
A1-12TH FLOOR MAIN STAIR | 0 | No Unit | 19 May 2016 | 19 May 2016 |  |  | 0 | 0 | 0 | 0
A1-12th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 19 May 2016 | 19 May 2016 | 08 Jul 2016 | 20 Jul 2016 | 0 | 12 | 50 | 62
A1-12TH FLOOR FIRE STAIR | 0 | No Unit | 19 May 2016 | 19 May 2016 |  |  | 0 | 0 | 0 | 0
A1-12th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 19 May 2016 | 19 May 2016 | 08 Jul 2016 | 20 Jul 2016 | 0 | 12 | 50 | 62
A1-13TH FLOOR | 0 | No Unit | 24 Jun 2016 | 05 Jul 2016 |  |  | 11 | 0 | 0 | 0
A1-REFUGE 1304 | 0 | No Unit | 24 Jun 2016 | 25 Jun 2016 |  |  | 1 | 0 | 0 | 0
A1-Refuge 1304 Cement Ghotai Plaster (Skirting) | 0 | Sft. | 24 Jun 2016 | 25 Jun 2016 | 11 Dec 2016 | 11 Dec 2016 | 1 | 0 | 170 | 169
A1-1302 | 0 | No Unit | 27 Jun 2016 | 28 Jun 2016 |  |  | 1 | 0 | 0 | 0
A1-1302 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 27 Jun 2016 | 28 Jun 2016 | 07 Oct 2016 | 11 Dec 2016 | 1 | 65 | 102 | 166
A1-1303 | 0 | No Unit | 29 Jun 2016 | 30 Jun 2016 |  |  | 1 | 0 | 0 | 0
A1-1303 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 29 Jun 2016 | 30 Jun 2016 | 07 Oct 2016 | 11 Dec 2016 | 1 | 65 | 100 | 164
A1-1301 | 0 | No Unit | 01 Jul 2016 | 02 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1-1301 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 01 Jul 2016 | 02 Jul 2016 | 07 Oct 2016 | 11 Dec 2016 | 1 | 65 | 98 | 162
A1-13TH FLOOR LOBBY | 0 | No Unit | 04 Jul 2016 | 04 Jul 2016 |  |  | 0 | 0 | 0 | 0
A1-13th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 04 Jul 2016 | 04 Jul 2016 | 20 Jul 2016 | 21 Jul 2016 | 0 | 1 | 16 | 17
A1-13TH FLOOR MAIN STAIR | 0 | No Unit | 05 Jul 2016 | 05 Jul 2016 |  |  | 0 | 0 | 0 | 0
A1-13th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 05 Jul 2016 | 05 Jul 2016 | 20 Jul 2016 | 21 Jul 2016 | 0 | 1 | 15 | 16
A1-13TH FLOOR FIRE STAIR | 0 | No Unit | 05 Jul 2016 | 05 Jul 2016 |  |  | 0 | 0 | 0 | 0
A1-13th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 05 Jul 2016 | 05 Jul 2016 | 20 Jul 2016 | 21 Jul 2016 | 0 | 1 | 15 | 16
A1-14TH FLOOR | 0 | No Unit | 11 Jul 2016 | 21 Jul 2016 |  |  | 10 | 0 | 0 | 0
A1-1401 | 0 | No Unit | 11 Jul 2016 | 12 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1-1401 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 11 Jul 2016 | 12 Jul 2016 | 11 Dec 2016 | 30 Dec 2016 | 1 | 19 | 153 | 171
A1-1402 | 0 | No Unit | 13 Jul 2016 | 14 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1-1402 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 13 Jul 2016 | 14 Jul 2016 | 11 Dec 2016 | 30 Dec 2016 | 1 | 19 | 151 | 169
A1-1403 | 0 | No Unit | 15 Jul 2016 | 16 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1-1403 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 15 Jul 2016 | 16 Jul 2016 | 11 Dec 2016 | 30 Dec 2016 | 1 | 19 | 149 | 167
A1-1404 | 0 | No Unit | 18 Jul 2016 | 19 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1-1404 Cement Ghotai Plaster (Skirting) | 140 | Sft. | 18 Jul 2016 | 19 Jul 2016 | 11 Dec 2016 | 30 Dec 2016 | 1 | 19 | 146 | 164
A1-14TH FLOOR LOBBY | 0 | No Unit | 20 Jul 2016 | 20 Jul 2016 |  |  | 0 | 0 | 0 | 0
A1-14th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.43 | Sft. | 20 Jul 2016 | 20 Jul 2016 | 20 Jul 2016 | 21 Jul 2016 | 0 | 1 | 0 | 1
A1-14TH FLOOR MAIN STAIR | 0 | No Unit | 21 Jul 2016 | 21 Jul 2016 |  |  | 0 | 0 | 0 | 0
A1-14th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.92 | Sft. | 21 Jul 2016 | 21 Jul 2016 | 20 Jul 2016 | 21 Jul 2016 | 0 | 1 | 0 | 0
A1-14TH FLOOR FIRE STAIR | 0 | No Unit | 21 Jul 2016 | 21 Jul 2016 |  |  | 0 | 0 | 0 | 0
A1-14th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 49.94 | Sft. | 21 Jul 2016 | 21 Jul 2016 | 20 Jul 2016 | 21 Jul 2016 | 0 | 1 | 0 | 0
A1- ABOVE TERRACE | 0 | No Unit | 30 Jul 2016 | 05 Aug 2016 |  |  | 6 | 0 | 0 | 0
A1- ABOVE TERRACE LOBBY | 0 | No Unit | 30 Jul 2016 | 01 Aug 2016 |  |  | 2 | 0 | 0 | 0
A1- Above Terrace Lobby Cement Ghotai Plaster (Skirting) | 0 | Sft. | 30 Jul 2016 | 01 Aug 2016 | 12 Jan 2017 | 12 Jan 2017 | 2 | 0 | 166 | 164
A1- ABOVE TERRACE FIRE STAIR | 0 | No Unit | 02 Aug 2016 | 03 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- Above Terrace Fire Stair Cement Ghotai Plaster (Skirting | 0 | Sft. | 02 Aug 2016 | 03 Aug 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 163 | 162
A1 - LMR | 0 | No Unit | 04 Aug 2016 | 05 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1 - LMR Cement Ghotai Plaster (Skirting) | 0 | Sft. | 04 Aug 2016 | 05 Aug 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 161 | 160
A1-SANLA PLASTER | 0 | No Unit | 12 Dec 2015 | 16 Aug 2016 |  |  | 248 | 0 | 0 | 0
A1-PARKING FLOOR | 509.03 | No Unit | 29 Jul 2016 | 02 Aug 2016 |  |  | 4 | 0 | 0 | 0
A1-PARKING FL MAIN STAIR | 0 | No Unit | 29 Jul 2016 | 30 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1-Parking Fl Main Stair Sanla Plaster | 501.58 | Sft. | 29 Jul 2016 | 30 Jul 2016 | 08 Dec 2015 | 26 Dec 2015 | 1 | 18 | 0 | 0
A1-PARKING FL FIRE STAIR | 0 | No Unit | 29 Jul 2016 | 30 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1-Parking Fl Fire Stair Sanla Plaster | 750.7 | Sft. | 29 Jul 2016 | 30 Jul 2016 | 30 Dec 2015 | 17 Jan 2016 | 1 | 18 | 0 | 0
A1-PARKING FL LOBBY | 0 | No Unit | 01 Aug 2016 | 02 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1-Parking Fl Lobby Sanla Plaster | 0 | Sft. | 01 Aug 2016 | 02 Aug 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 164 | 163
A1-1ST FLOOR | 0 | No Unit | 12 Dec 2015 | 19 Feb 2016 |  |  | 69 | 0 | 0 | 0
A1- FLAT 101 | 0 | No Unit | 12 Dec 2015 | 14 Dec 2015 |  |  | 2 | 0 | 0 | 0
A1- Flat 101 Sanla Plaster | 81.43 | Sft. | 12 Dec 2015 | 14 Dec 2015 | 27 Nov 2015 | 09 Dec 2015 | 2 | 12 | 0 | 0
A1- FLAT 102 | 0 | No Unit | 17 Dec 2015 | 18 Dec 2015 |  |  | 1 | 0 | 0 | 0
A1- Flat 102 Sanla Plaster | 81.43 | Sft. | 17 Dec 2015 | 18 Dec 2015 | 27 Nov 2015 | 13 Dec 2015 | 1 | 16 | 0 | 0
A1- FLAT 103 | 0 | No Unit | 22 Dec 2015 | 23 Dec 2015 |  |  | 1 | 0 | 0 | 0
A1- Flat 103 Sanla Plaster | 81.43 | Sft. | 22 Dec 2015 | 23 Dec 2015 | 27 Nov 2015 | 13 Dec 2015 | 1 | 16 | 0 | 0
A1- FLAT 104 | 0 | No Unit | 26 Dec 2015 | 28 Dec 2015 |  |  | 2 | 0 | 0 | 0
A1- Flat 104 Sanla Plaster | 81.43 | Sft. | 26 Dec 2015 | 28 Dec 2015 | 27 Nov 2015 | 13 Dec 2015 | 2 | 16 | 0 | 0
A1-1ST FL ELECTRICAL DUCT | 0 | No Unit | 29 Dec 2015 | 29 Dec 2015 |  |  | 0 | 0 | 0 | 0
A1-1st Fl Electrical Duct Sanla Plaster | 215.98 | Sft. | 29 Dec 2015 | 29 Dec 2015 | 14 Jan 2016 | 17 Jan 2016 | 0 | 3 | 16 | 19
A1-1ST FL MAIN STAIR | 0 | No Unit | 13 Feb 2016 | 16 Feb 2016 |  |  | 3 | 0 | 0 | 0
A1-1st Fl Main Stair Sanla Plaster | 501.58 | Sft. | 13 Feb 2016 | 16 Feb 2016 | 10 Dec 2015 | 26 Dec 2015 | 3 | 16 | 0 | 0
A1-1ST FL FIRE STAIR | 0 | No Unit | 17 Feb 2016 | 19 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1-1st Fl Fire Stair Sanla Plaster | 750.7 | Sft. | 17 Feb 2016 | 19 Feb 2016 | 30 Dec 2015 | 17 Jan 2016 | 2 | 18 | 0 | 0
A1-2ND FLOOR | 0 | No Unit | 21 Dec 2015 | 26 Feb 2016 |  |  | 67 | 0 | 0 | 0
A1- FLAT 201 | 0 | No Unit | 21 Dec 2015 | 22 Dec 2015 |  |  | 1 | 0 | 0 | 0
A1- Flat 201 Sanla Plaster | 81.43 | Sft. | 21 Dec 2015 | 22 Dec 2015 | 03 Dec 2015 | 13 Dec 2015 | 1 | 10 | 0 | 0
A1- FLAT 202 | 0 | No Unit | 25 Dec 2015 | 26 Dec 2015 |  |  | 1 | 0 | 0 | 0
A1- Flat 202 Sanla Plaster | 81.43 | Sft. | 25 Dec 2015 | 26 Dec 2015 | 03 Dec 2015 | 13 Dec 2015 | 1 | 10 | 0 | 0
A1- FLAT 203 | 0 | No Unit | 30 Dec 2015 | 01 Jan 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 203 Sanla Plaster | 81.43 | Sft. | 30 Dec 2015 | 01 Jan 2016 | 03 Dec 2015 | 13 Dec 2015 | 2 | 10 | 0 | 0
A1- FLAT 204 | 0 | No Unit | 05 Jan 2016 | 06 Jan 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 204 Sanla Plaster | 81.43 | Sft. | 05 Jan 2016 | 06 Jan 2016 | 03 Dec 2015 | 13 Dec 2015 | 1 | 10 | 0 | 0
A1-2ND FL ELECTRICAL DUCT | 0 | No Unit | 07 Jan 2016 | 07 Jan 2016 |  |  | 0 | 0 | 0 | 0
A1-2nd Fl Electrical Duct Sanla Plaster | 215.98 | Sft. | 07 Jan 2016 | 07 Jan 2016 | 15 Jan 2016 | 17 Jan 2016 | 0 | 2 | 8 | 10
A1-2ND FL MAIN STAIR | 0 | No Unit | 20 Feb 2016 | 23 Feb 2016 |  |  | 3 | 0 | 0 | 0
A1-2nd Fl Main Stair Sanla Plaster | 501.58 | Sft. | 20 Feb 2016 | 23 Feb 2016 | 11 Dec 2015 | 26 Dec 2015 | 3 | 15 | 0 | 0
A1-2NDFL FIRE STAIR | 0 | No Unit | 24 Feb 2016 | 26 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1-2ndFl Fire Stair Sanla Plaster | 750.7 | Sft. | 24 Feb 2016 | 26 Feb 2016 | 04 Jan 2016 | 17 Jan 2016 | 2 | 13 | 0 | 0
A1-3RD FLOOR | 0 | No Unit | 11 Jan 2016 | 04 Mar 2016 |  |  | 53 | 0 | 0 | 0
A1- FLAT 301 | 0 | No Unit | 11 Jan 2016 | 12 Jan 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 301 Sanla Plaster | 81.43 | Sft. | 11 Jan 2016 | 12 Jan 2016 | 18 Dec 2015 | 29 Dec 2015 | 1 | 11 | 0 | 0
A1- FLAT 302 | 0 | No Unit | 15 Jan 2016 | 16 Jan 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 302 Sanla Plaster | 81.43 | Sft. | 15 Jan 2016 | 16 Jan 2016 | 18 Dec 2015 | 29 Dec 2015 | 1 | 11 | 0 | 0
A1- FLAT 303 | 0 | No Unit | 20 Jan 2016 | 21 Jan 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 303 Sanla Plaster | 81.43 | Sft. | 20 Jan 2016 | 21 Jan 2016 | 18 Dec 2015 | 29 Dec 2015 | 1 | 11 | 0 | 0
A1- FLAT 304 | 0 | No Unit | 25 Jan 2016 | 27 Jan 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 304 Sanla Plaster | 81.43 | Sft. | 25 Jan 2016 | 27 Jan 2016 | 18 Dec 2015 | 29 Dec 2015 | 2 | 11 | 0 | 0
A1-3RD FL ELECTRICAL DUCT | 0 | No Unit | 28 Jan 2016 | 28 Jan 2016 |  |  | 0 | 0 | 0 | 0
A1-3rd Fl Electrical Duct Sanla Plaster | 215.98 | Sft. | 28 Jan 2016 | 28 Jan 2016 | 15 Jan 2016 | 12 Feb 2016 | 0 | 28 | 0 | 15
A1-3RD FL MAIN STAIR | 0 | No Unit | 27 Feb 2016 | 01 Mar 2016 |  |  | 3 | 0 | 0 | 0
A1-3rd Fl Main Stair Sanla Plaster | 501.58 | Sft. | 27 Feb 2016 | 01 Mar 2016 | 12 Dec 2015 | 29 Dec 2015 | 3 | 17 | 0 | 0
A1-3RD FL FIRE STAIR | 0 | No Unit | 02 Mar 2016 | 04 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1-3rd Fl Fire Stair Sanla Plaster | 750.7 | Sft. | 02 Mar 2016 | 04 Mar 2016 | 04 Jan 2016 | 17 Jan 2016 | 2 | 13 | 0 | 0
A1-4TH FLOOR | 0 | No Unit | 02 Feb 2016 | 12 Mar 2016 |  |  | 39 | 0 | 0 | 0
A1- FLAT 401 | 0 | No Unit | 02 Feb 2016 | 03 Feb 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 401 Sanla Plaster | 81.43 | Sft. | 02 Feb 2016 | 03 Feb 2016 | 07 Jan 2016 | 18 Jan 2016 | 1 | 11 | 0 | 0
A1- FLAT 402 | 0 | No Unit | 06 Feb 2016 | 08 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 402 Sanla Plaster | 81.43 | Sft. | 06 Feb 2016 | 08 Feb 2016 | 07 Jan 2016 | 18 Jan 2016 | 2 | 11 | 0 | 0
A1- FLAT 403 | 0 | No Unit | 11 Feb 2016 | 12 Feb 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 403 Sanla Plaster | 81.43 | Sft. | 11 Feb 2016 | 12 Feb 2016 | 07 Jan 2016 | 18 Jan 2016 | 1 | 11 | 0 | 0
A1- FLAT 404 | 0 | No Unit | 16 Feb 2016 | 17 Feb 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 404 Sanla Plaster | 81.43 | Sft. | 16 Feb 2016 | 17 Feb 2016 | 07 Jan 2016 | 18 Jan 2016 | 1 | 11 | 0 | 0
A1-4TH FL ELECTRICAL DUCT | 0 | No Unit | 18 Feb 2016 | 18 Feb 2016 |  |  | 0 | 0 | 0 | 0
A1-4th Fl Electrical Duct Sanla Plaster | 215.98 | Sft. | 18 Feb 2016 | 18 Feb 2016 | 06 Jan 2016 | 04 May 2016 | 0 | 119 | 0 | 76
A1-4TH FL MAIN STAIR | 0 | No Unit | 05 Mar 2016 | 09 Mar 2016 |  |  | 4 | 0 | 0 | 0
A1-4th Fl Main Stair Sanla Plaster | 501.58 | Sft. | 05 Mar 2016 | 09 Mar 2016 | 29 Dec 2015 | 17 Jan 2016 | 4 | 19 | 0 | 0
A1-4TH FL FIRE STAIR | 0 | No Unit | 10 Mar 2016 | 12 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1-4th Fl Fire Stair Sanla Plaster | 750.7 | Sft. | 10 Mar 2016 | 12 Mar 2016 | 04 Jan 2016 | 04 May 2016 | 2 | 121 | 0 | 53
A1-5TH FLOOR | 0 | No Unit | 24 Feb 2016 | 19 Mar 2016 |  |  | 24 | 0 | 0 | 0
A1- FLAT 501 | 0 | No Unit | 24 Feb 2016 | 25 Feb 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 501 Sanla Plaster | 81.43 | Sft. | 24 Feb 2016 | 25 Feb 2016 | 08 Jan 2016 | 18 Jan 2016 | 1 | 10 | 0 | 0
A1- FLAT 502 | 0 | No Unit | 29 Feb 2016 | 01 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 502 Sanla Plaster | 81.43 | Sft. | 29 Feb 2016 | 01 Mar 2016 | 08 Jan 2016 | 18 Jan 2016 | 1 | 10 | 0 | 0
A1- FLAT 503 | 0 | No Unit | 04 Mar 2016 | 05 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 503 Sanla Plaster | 81.43 | Sft. | 04 Mar 2016 | 05 Mar 2016 | 08 Jan 2016 | 18 Jan 2016 | 1 | 10 | 0 | 0
A1- FLAT 504 | 0 | No Unit | 10 Mar 2016 | 11 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 504 Sanla Plaster | 81.43 | Sft. | 10 Mar 2016 | 11 Mar 2016 | 08 Jan 2016 | 18 Jan 2016 | 1 | 10 | 0 | 0
A1-5TH FL ELECTRICAL DUCT | 0 | No Unit | 12 Mar 2016 | 12 Mar 2016 |  |  | 0 | 0 | 0 | 0
A1-5th Fl Electrical Duct Sanla Plaster | 215.98 | Sft. | 12 Mar 2016 | 12 Mar 2016 | 06 Jan 2016 | 12 Feb 2016 | 0 | 37 | 0 | 0
A1-5TH FL MAIN STAIR | 0 | No Unit | 14 Mar 2016 | 16 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1-5th Fl Main Stair Sanla Plaster | 501.58 | Sft. | 14 Mar 2016 | 16 Mar 2016 | 04 Jan 2016 | 17 Jan 2016 | 2 | 13 | 0 | 0
A1-5TH FL FIRE STAIR | 0 | No Unit | 17 Mar 2016 | 19 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1-5th Fl Fire Stair Sanla Plaster | 750.7 | Sft. | 17 Mar 2016 | 19 Mar 2016 | 06 Jan 2016 | 12 Feb 2016 | 2 | 37 | 0 | 0
A1-6TH FLOOR | 0 | No Unit | 17 Mar 2016 | 02 Apr 2016 |  |  | 16 | 0 | 0 | 0
A1- FLAT 601 | 0 | No Unit | 17 Mar 2016 | 18 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 601 Sanla Plaster | 81.43 | Sft. | 17 Mar 2016 | 18 Mar 2016 | 13 Jan 2016 | 18 Jan 2016 | 1 | 5 | 0 | 0
A1- FLAT 602 | 0 | No Unit | 22 Mar 2016 | 23 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 602 Sanla Plaster | 81.43 | Sft. | 22 Mar 2016 | 23 Mar 2016 | 13 Jan 2016 | 18 Jan 2016 | 1 | 5 | 0 | 0
A1- FLAT 603 | 0 | No Unit | 26 Mar 2016 | 28 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 603 Sanla Plaster | 81.43 | Sft. | 26 Mar 2016 | 28 Mar 2016 | 13 Jan 2016 | 18 Jan 2016 | 2 | 5 | 0 | 0
A1- FLAT 604 | 0 | No Unit | 31 Mar 2016 | 01 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 604 Sanla Plaster | 81.43 | Sft. | 31 Mar 2016 | 01 Apr 2016 | 13 Jan 2016 | 18 Jan 2016 | 1 | 5 | 0 | 0
A1-6TH FL ELECTRICAL DUCT | 0 | No Unit | 02 Apr 2016 | 02 Apr 2016 |  |  | 0 | 0 | 0 | 0
A1-6th Fl Electrical Duct Sanla Plaster | 215.98 | Sft. | 02 Apr 2016 | 02 Apr 2016 | 06 Jan 2016 | 12 Feb 2016 | 0 | 37 | 0 | 0
A1-6TH FL MAIN STAIR | 0 | No Unit | 21 Mar 2016 | 23 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1-6th Fl Main Stair Sanla Plaster | 501.58 | Sft. | 21 Mar 2016 | 23 Mar 2016 | 06 Jan 2016 | 04 May 2016 | 2 | 119 | 0 | 42
A1-6TH FL FIRE STAIR | 0 | No Unit | 24 Mar 2016 | 26 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1-6th Fl Fire Stair Sanla Plaster | 750.7 | Sft. | 24 Mar 2016 | 26 Mar 2016 | 06 Jan 2016 | 12 Feb 2016 | 2 | 37 | 0 | 0
A1-7TH FLOOR | 0 | No Unit | 14 Mar 2016 | 02 Apr 2016 |  |  | 19 | 0 | 0 | 0
A1- FLAT 701 | 0 | No Unit | 14 Mar 2016 | 15 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 701 Sanla Plaster | 30 | Sft. | 14 Mar 2016 | 15 Mar 2016 | 18 Feb 2016 | 04 May 2016 | 1 | 76 | 0 | 50
A1- FLAT 702 | 0 | No Unit | 18 Mar 2016 | 19 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 702 Sanla Plaster | 30 | Sft. | 18 Mar 2016 | 19 Mar 2016 | 18 Feb 2016 | 04 May 2016 | 1 | 76 | 0 | 46
A1- FLAT 703 | 0 | No Unit | 23 Mar 2016 | 24 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 703 Sanla Plaster | 30 | Sft. | 23 Mar 2016 | 24 Mar 2016 | 18 Feb 2016 | 04 May 2016 | 1 | 76 | 0 | 41
A1- FLAT 704 | 0 | No Unit | 28 Mar 2016 | 29 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 704 Sanla Plaster | 30 | Sft. | 28 Mar 2016 | 29 Mar 2016 | 18 Feb 2016 | 04 May 2016 | 1 | 76 | 0 | 36
A1-7TH FL ELECTRICAL DUCT | 0 | No Unit | 30 Mar 2016 | 30 Mar 2016 |  |  | 0 | 0 | 0 | 0
A1-7th Fl Electrical Duct Sanla Plaster | 200 | Sft. | 30 Mar 2016 | 30 Mar 2016 | 23 Mar 2016 | 04 May 2016 | 0 | 42 | 0 | 35
A1-7TH FL MAIN STAIR | 0 | No Unit | 28 Mar 2016 | 30 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1-7th Fl Main Stair Sanla Plaster | 400 | Sft. | 28 Mar 2016 | 30 Mar 2016 | 23 Feb 2016 | 04 May 2016 | 2 | 71 | 0 | 35
A1- 7TH FL FIRE STAIR | 0 | No Unit | 31 Mar 2016 | 02 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1- 7th Fl Fire Stair Sanla Plaster | 500 | Sft. | 31 Mar 2016 | 02 Apr 2016 | 25 Feb 2016 | 04 May 2016 | 2 | 69 | 0 | 32
A1-8TH FLOOR | 0 | No Unit | 24 Mar 2016 | 09 Apr 2016 |  |  | 16 | 0 | 0 | 0
A1- FLAT 801 | 0 | No Unit | 24 Mar 2016 | 25 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 801 Sanla Plaster | 30 | Sft. | 24 Mar 2016 | 25 Mar 2016 | 26 Feb 2016 | 04 May 2016 | 1 | 68 | 0 | 40
A1- FLAT 802 | 0 | No Unit | 29 Mar 2016 | 30 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 802 Sanla Plaster | 30 | Sft. | 29 Mar 2016 | 30 Mar 2016 | 26 Feb 2016 | 04 May 2016 | 1 | 68 | 0 | 35
A1- FLAT 803 | 0 | No Unit | 02 Apr 2016 | 04 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 803 Sanla Plaster | 30 | Sft. | 02 Apr 2016 | 04 Apr 2016 | 26 Feb 2016 | 04 May 2016 | 2 | 68 | 0 | 30
A1- REFUGE FLAT 804 | 0 | No Unit | 07 Apr 2016 | 08 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1- Refuge Flat 804 Sanla Plaster | 0 | Sft. | 07 Apr 2016 | 08 Apr 2016 | 26 Feb 2016 | 12 Jan 2017 | 1 | 321 | 0 | 279
A1-8TH FL ELECTRICAL DUCT | 0 | No Unit | 09 Apr 2016 | 09 Apr 2016 |  |  | 0 | 0 | 0 | 0
A1-8th Fl Electrical Duct Sanla Plaster | 200 | Sft. | 09 Apr 2016 | 09 Apr 2016 | 11 Jun 2016 | 21 Jul 2016 | 0 | 40 | 63 | 103
A1-8TH FL MAIN STAIR | 0 | No Unit | 04 Apr 2016 | 06 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1-8th Fl Main Stair Sanla Plaster | 400 | Sft. | 04 Apr 2016 | 06 Apr 2016 | 23 Feb 2016 | 04 May 2016 | 2 | 71 | 0 | 28
A1-8TH FL FIRE STAIR | 0 | No Unit | 07 Apr 2016 | 09 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1-8th Fl Fire Stair Sanla Plaster | 500 | Sft. | 07 Apr 2016 | 09 Apr 2016 | 26 Feb 2016 | 04 May 2016 | 2 | 68 | 0 | 25
A1-9TH FLOOR | 0 | No Unit | 31 Mar 2016 | 16 Apr 2016 |  |  | 16 | 0 | 0 | 0
A1- FLAT 901 | 0 | No Unit | 31 Mar 2016 | 01 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 901 Sanla Plaster | 30 | Sft. | 31 Mar 2016 | 01 Apr 2016 | 01 Mar 2016 | 04 May 2016 | 1 | 64 | 0 | 33
A1- FLAT 902 | 0 | No Unit | 05 Apr 2016 | 06 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 902 Sanla Plaster | 30 | Sft. | 05 Apr 2016 | 06 Apr 2016 | 01 Mar 2016 | 04 May 2016 | 1 | 64 | 0 | 28
A1- FLAT 903 | 0 | No Unit | 09 Apr 2016 | 11 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 903 Sanla Plaster | 30 | Sft. | 09 Apr 2016 | 11 Apr 2016 | 01 Mar 2016 | 04 May 2016 | 2 | 64 | 0 | 23
A1- FLAT 904 | 0 | No Unit | 14 Apr 2016 | 15 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 904 Sanla Plaster | 30 | Sft. | 14 Apr 2016 | 15 Apr 2016 | 01 Mar 2016 | 04 May 2016 | 1 | 64 | 0 | 19
A1-9THFL ELECTRICAL DUCT | 0 | No Unit | 16 Apr 2016 | 16 Apr 2016 |  |  | 0 | 0 | 0 | 0
A1-9thFl Electrical Duct Sanla Plaster | 200 | Sft. | 16 Apr 2016 | 16 Apr 2016 | 11 Jun 2016 | 21 Jul 2016 | 0 | 40 | 56 | 96
A1-9TH FL MAIN STAIR | 215.98 | No Unit | 11 Apr 2016 | 13 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1-9th Fl Main Stair Sanla Plaster | 400 | Sft. | 11 Apr 2016 | 13 Apr 2016 | 27 Feb 2016 | 04 May 2016 | 2 | 67 | 0 | 21
A1-9TH FL FIRE STAIR | 0 | No Unit | 14 Apr 2016 | 16 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1-9th Fl Fire Stair Sanla Plaster | 500 | Sft. | 14 Apr 2016 | 16 Apr 2016 | 27 Feb 2016 | 04 May 2016 | 2 | 67 | 0 | 18
A1-10TH FLOOR | 0 | No Unit | 07 Apr 2016 | 23 Apr 2016 |  |  | 16 | 0 | 0 | 0
A1- FLAT 1001 | 0 | No Unit | 07 Apr 2016 | 08 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1001 Sanla Plaster | 30 | Sft. | 07 Apr 2016 | 08 Apr 2016 | 16 Mar 2016 | 08 Jul 2016 | 1 | 114 | 0 | 91
A1- FLAT 1002 | 0 | No Unit | 12 Apr 2016 | 13 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1002 Sanla Plaster | 30 | Sft. | 12 Apr 2016 | 13 Apr 2016 | 16 Mar 2016 | 08 Jul 2016 | 1 | 114 | 0 | 86
A1- FLAT 1003 | 0 | No Unit | 16 Apr 2016 | 18 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1003 Sanla Plaster | 30 | Sft. | 16 Apr 2016 | 18 Apr 2016 | 16 Mar 2016 | 08 Jul 2016 | 2 | 114 | 0 | 81
A1- FLAT 1004 | 0 | No Unit | 21 Apr 2016 | 22 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1004 Sanla Plaster | 30 | Sft. | 21 Apr 2016 | 22 Apr 2016 | 16 Mar 2016 | 08 Jul 2016 | 1 | 114 | 0 | 77
A1-10THFL ELECTRICAL DUCT | 0 | No Unit | 23 Apr 2016 | 23 Apr 2016 |  |  | 0 | 0 | 0 | 0
A1-10thFl Electrical Duct Sanla Plaster | 200 | Sft. | 23 Apr 2016 | 23 Apr 2016 | 11 Jun 2016 | 21 Jul 2016 | 0 | 40 | 49 | 89
A1-10TH FL MAIN STAIR | 0 | No Unit | 18 Apr 2016 | 20 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1-10th Fl Main Stair Sanla Plaster | 400 | Sft. | 18 Apr 2016 | 20 Apr 2016 | 20 Mar 2016 | 21 Jul 2016 | 2 | 123 | 0 | 92
A1-10TH FL FIRE STAIR | 0 | No Unit | 21 Apr 2016 | 23 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1-10th Fl Fire Stair Sanla Plaster | 500 | Sft. | 21 Apr 2016 | 23 Apr 2016 | 30 Mar 2016 | 21 Jul 2016 | 2 | 113 | 0 | 89
A1-11TH FLOOR | 0 | No Unit | 07 Apr 2016 | 30 Apr 2016 |  |  | 23 | 0 | 0 | 0
A1- FLAT 1101 | 0 | No Unit | 07 Apr 2016 | 08 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1101 Sanla Plaster | 30 | Sft. | 07 Apr 2016 | 08 Apr 2016 | 04 May 2016 | 08 Jul 2016 | 1 | 65 | 27 | 91
A1- FLAT 1102 | 0 | No Unit | 12 Apr 2016 | 13 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1102 Sanla Plaster | 30 | Sft. | 12 Apr 2016 | 13 Apr 2016 | 04 May 2016 | 08 Jul 2016 | 1 | 65 | 22 | 86
A1- FLAT 1103 | 0 | No Unit | 16 Apr 2016 | 18 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1- Flat 1103 Sanla Plaster | 30 | Sft. | 16 Apr 2016 | 18 Apr 2016 | 04 May 2016 | 08 Jul 2016 | 2 | 65 | 18 | 81
A1- FLAT 1104 | 0 | No Unit | 21 Apr 2016 | 22 Apr 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1104 Sanla Plaster | 30 | Sft. | 21 Apr 2016 | 22 Apr 2016 | 04 May 2016 | 08 Jul 2016 | 1 | 65 | 13 | 77
A1-11TH FL ELECTRICAL DUCT | 0 | No Unit | 23 Apr 2016 | 23 Apr 2016 |  |  | 0 | 0 | 0 | 0
A1-11th Fl Electrical Duct Sanla Plaster | 200 | Sft. | 23 Apr 2016 | 23 Apr 2016 | 08 Jul 2016 | 21 Jul 2016 | 0 | 13 | 76 | 89
A1-11TH FL MAIN STAIR | 0 | No Unit | 25 Apr 2016 | 27 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1-11th Fl Main Stair Sanla Plaster | 400 | Sft. | 25 Apr 2016 | 27 Apr 2016 | 31 Mar 2016 | 21 Jul 2016 | 2 | 112 | 0 | 85
A1-11TH FL FIRE STAIR | 0 | No Unit | 28 Apr 2016 | 30 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1-11th Fl Fire Stair Sanla Plaster | 500 | Sft. | 28 Apr 2016 | 30 Apr 2016 | 31 Mar 2016 | 21 Jul 2016 | 2 | 112 | 0 | 82
A1-12TH FLOOR | 0 | No Unit | 02 May 2016 | 04 Jul 2016 |  |  | 63 | 0 | 0 | 0
A1- FLAT 1201 | 0 | No Unit | 17 Jun 2016 | 18 Jun 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1201 Sanla Plaster | 30 | Sft. | 17 Jun 2016 | 18 Jun 2016 | 08 Jul 2016 | 21 Jul 2016 | 1 | 13 | 21 | 33
A1- FLAT 1202 | 0 | No Unit | 22 Jun 2016 | 23 Jun 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1202 Sanla Plaster | 30 | Sft. | 22 Jun 2016 | 23 Jun 2016 | 08 Jul 2016 | 21 Jul 2016 | 1 | 13 | 16 | 28
A1- FLAT 1203 | 0 | No Unit | 27 Jun 2016 | 28 Jun 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1203 Sanla Plaster | 30 | Sft. | 27 Jun 2016 | 28 Jun 2016 | 08 Jul 2016 | 21 Jul 2016 | 1 | 13 | 11 | 23
A1- FLAT 1204 | 0 | No Unit | 01 Jul 2016 | 02 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1204 Sanla Plaster | 30 | Sft. | 01 Jul 2016 | 02 Jul 2016 | 08 Jul 2016 | 21 Jul 2016 | 1 | 13 | 7 | 19
A1-12TH FL ELECTRICAL DUCT | 0 | No Unit | 04 Jul 2016 | 04 Jul 2016 |  |  | 0 | 0 | 0 | 0
A1-12th Fl Electrical Duct Sanla Plaster | 200 | Sft. | 04 Jul 2016 | 04 Jul 2016 | 08 Jul 2016 | 21 Jul 2016 | 0 | 13 | 4 | 17
A1-12TH FL MAIN STAIR | 0 | No Unit | 02 May 2016 | 04 May 2016 |  |  | 2 | 0 | 0 | 0
A1-12th Fl Main Stair Sanla Plaster | 400 | Sft. | 02 May 2016 | 04 May 2016 | 16 Jun 2016 | 21 Jul 2016 | 2 | 35 | 45 | 78
A1-12TH FL FIRE STAIR | 0 | No Unit | 05 May 2016 | 07 May 2016 |  |  | 2 | 0 | 0 | 0
A1-12th Fl Fire Stair Sanla Plaster | 500 | Sft. | 05 May 2016 | 07 May 2016 | 16 Jun 2016 | 21 Jul 2016 | 2 | 35 | 42 | 75
A1-13TH FLOOR | 0 | No Unit | 09 May 2016 | 30 Jul 2016 |  |  | 82 | 0 | 0 | 0
A1- FLAT 1301 | 0 | No Unit | 13 Jul 2016 | 14 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1301 Sanla Plaster | 30 | Sft. | 13 Jul 2016 | 14 Jul 2016 | 07 Oct 2016 | 30 Dec 2016 | 1 | 84 | 86 | 169
A1- FLAT 1302 | 0 | No Unit | 18 Jul 2016 | 19 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1302 Sanla Plaster | 30 | Sft. | 18 Jul 2016 | 19 Jul 2016 | 07 Oct 2016 | 30 Dec 2016 | 1 | 84 | 81 | 164
A1- FLAT 1303 | 0 | No Unit | 22 Jul 2016 | 23 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1303 Sanla Plaster | 30 | Sft. | 22 Jul 2016 | 23 Jul 2016 | 07 Oct 2016 | 30 Dec 2016 | 1 | 84 | 77 | 160
A1- REFUGE FLAT 1304 | 0 | No Unit | 27 Jul 2016 | 28 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1- Refuge Flat 1304 Sanla Plaster | 0 | Sft. | 27 Jul 2016 | 28 Jul 2016 | 11 Dec 2016 | 11 Dec 2016 | 1 | 0 | 137 | 136
A1-13TH FL ELECTRICAL DUCT | 0 | No Unit | 29 Jul 2016 | 30 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1-13th Fl Electrical Duct Sanla Plaster | 200 | Sft. | 29 Jul 2016 | 30 Jul 2016 | 20 Jul 2016 | 21 Jul 2016 | 1 | 1 | 0 | 0
A1-13TH FL MAIN STAIR | 0 | No Unit | 09 May 2016 | 11 May 2016 |  |  | 2 | 0 | 0 | 0
A1-13th Fl Main Stair Sanla Plaster | 400 | Sft. | 09 May 2016 | 11 May 2016 | 06 Jul 2016 | 21 Jul 2016 | 2 | 15 | 58 | 71
A1-13TH FL FIRE STAIR | 0 | No Unit | 12 May 2016 | 14 May 2016 |  |  | 2 | 0 | 0 | 0
A1-13th Fl Fire Stair Sanla Plaster | 500 | Sft. | 12 May 2016 | 14 May 2016 | 20 Jun 2016 | 21 Jul 2016 | 2 | 31 | 39 | 68
A1-14TH FLOOR | 0 | No Unit | 16 May 2016 | 16 Aug 2016 |  |  | 92 | 0 | 0 | 0
A1- FLAT 1401 | 751 | No Unit | 29 Jul 2016 | 30 Jul 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1401 Sanla Plaster | 30 | Sft. | 29 Jul 2016 | 30 Jul 2016 | 11 Dec 2016 | 30 Dec 2016 | 1 | 19 | 135 | 153
A1- FLAT 1402 | 0 | No Unit | 03 Aug 2016 | 04 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1402 Sanla Plaster | 30 | Sft. | 03 Aug 2016 | 04 Aug 2016 | 11 Dec 2016 | 30 Dec 2016 | 1 | 19 | 130 | 148
A1- FLAT 1403 | 0 | No Unit | 08 Aug 2016 | 09 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1403 Sanla Plaster | 30 | Sft. | 08 Aug 2016 | 09 Aug 2016 | 11 Dec 2016 | 30 Dec 2016 | 1 | 19 | 125 | 143
A1- FLAT 1404 | 0 | No Unit | 12 Aug 2016 | 13 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- Flat 1404 Sanla Plaster | 30 | Sft. | 12 Aug 2016 | 13 Aug 2016 | 11 Dec 2016 | 30 Dec 2016 | 1 | 19 | 121 | 139
A1-14TH FL ELECTRICAL DUCT | 0 | No Unit | 16 Aug 2016 | 16 Aug 2016 |  |  | 0 | 0 | 0 | 0
A1-14th Fl Electrical Duct Sanla Plaster | 200 | Sft. | 16 Aug 2016 | 16 Aug 2016 | 20 Jul 2016 | 21 Jul 2016 | 0 | 1 | 0 | 0
A1-14TH FL MAIN STAIR | 751 | No Unit | 16 May 2016 | 18 May 2016 |  |  | 2 | 0 | 0 | 0
A1-14th Fl Main Stair Sanla Plaster | 400 | Sft. | 16 May 2016 | 18 May 2016 | 21 Jul 2016 | 21 Jul 2016 | 2 | 0 | 66 | 64
A1-14TH FL FIRE STAIR | 0 | No Unit | 19 May 2016 | 21 May 2016 |  |  | 2 | 0 | 0 | 0
A1-14th Fl Fire Stair Sanla Plaster | 500 | Sft. | 19 May 2016 | 21 May 2016 | 20 Jun 2016 | 21 Jul 2016 | 2 | 31 | 32 | 61
A1- ABOVE TERRACE | 0 | No Unit | 23 May 2016 | 04 Jun 2016 |  |  | 12 | 0 | 0 | 0
A1- AB. TERRACE FL MAIN STAIR | 0 | No Unit | 23 May 2016 | 25 May 2016 |  |  | 2 | 0 | 0 | 0
A1- Ab. Terrace Fl Main Stair Sanla Plaster | 0 | Sft. | 23 May 2016 | 25 May 2016 | 21 Jul 2016 | 12 Jan 2017 | 2 | 175 | 59 | 232
A1- AB. TERRACE FL FIRE STAIR | 0 | No Unit | 26 May 2016 | 28 May 2016 |  |  | 2 | 0 | 0 | 0
A1- Ab. Terrace Fl Fire Stair Sanla Plaster | 500 | Sft. | 26 May 2016 | 28 May 2016 | 21 Jul 2016 | 12 Jan 2017 | 2 | 175 | 56 | 229
A1-TOP TERRACE ELECTRICAL DUCT | 509.03 | No Unit | 30 May 2016 | 01 Jun 2016 |  |  | 2 | 0 | 0 | 0
A1-Top Terrace Electrical Duct Sanla Plaster | 509.03 | Sft. | 30 May 2016 | 01 Jun 2016 | 21 Jul 2016 | 12 Jan 2017 | 2 | 175 | 52 | 225
A1- LMR | 0 | No Unit | 02 Jun 2016 | 04 Jun 2016 |  |  | 2 | 0 | 0 | 0
A1- LMR Sanla Plaster | 370 | Sft. | 02 Jun 2016 | 04 Jun 2016 | 12 Jan 2017 | 12 Jan 2017 | 2 | 0 | 224 | 222
A1-TEXTURE | 0 | No Unit | 29 Jun 2016 | 07 Sep 2016 |  |  | 70 | 0 | 0 | 0
A1-Texture Texture for Entrance Lobby (M+L) | 500 | Sft. | 29 Jun 2016 | 02 Aug 2016 | 12 Jan 2017 | 12 Jan 2017 | 34 | 0 | 197 | 163
A1-Texture Texture for Bldg. Elevation (M+L) | 500 | Sft. | 29 Jun 2016 | 07 Sep 2016 | 12 Jan 2017 | 12 Jan 2017 | 70 | 0 | 197 | 127
A1-EXTERNAL PLASTER | 0 | No Unit | 20 Oct 2015 | 17 Aug 2016 |  |  | 302 | 0 | 0 | 0
A1-PARKING | 7162.1 | No Unit | 20 Oct 2015 | 06 Aug 2016 |  |  | 291 | 0 | 0 | 0
A1-Parking Sand Faced Plaster 2 Coat | 7793.53 | Sft. | 20 Oct 2015 | 28 Oct 2015 | 27 Oct 2015 | 27 Jul 2016 | 8 | 274 | 7 | 273
A1-METER ROOM & LIFT FRONT WALL INSIDE FACE | 0 | No Unit | 03 Aug 2016 | 06 Aug 2016 |  |  | 3 | 0 | 0 | 0
A1-Meter Room & Lift front wall Inside Face Sand Faced Plast | 1521.78 | Sft. | 03 Aug 2016 | 06 Aug 2016 | 03 Feb 2016 | 25 Jan 2017 | 3 | 357 | 0 | 172
A1-Parking Misc. | 1 | Job | 03 Aug 2016 | 04 Aug 2016 | 16 Nov 2016 | 25 Jan 2017 | 1 | 70 | 105 | 174
A1-FRONT SIDE | 0 | No Unit | 10 Dec 2015 | 02 Aug 2016 |  |  | 236 | 0 | 0 | 0
A1-Front Side Sand Faced Plaster 2 Coat | 18515 | Sft. | 10 Dec 2015 | 02 Aug 2016 | 09 Dec 2015 | 25 Jan 2017 | 236 | 413 | 0 | 176
A1-REAR SIDE | 0 | No Unit | 10 Dec 2015 | 02 Aug 2016 |  |  | 236 | 0 | 0 | 0
A1-Rear Side Sand Faced Plaster 2 Coat | 19998 | Sft. | 10 Dec 2015 | 02 Aug 2016 | 11 Jan 2016 | 25 Jan 2017 | 236 | 380 | 32 | 176
A1-RIGHT SIDE | 0 | No Unit | 10 Dec 2015 | 02 Aug 2016 |  |  | 236 | 0 | 0 | 0
A1-Right Side Sand Faced Plaster 2 Coat | 0 | Sft. | 10 Dec 2015 | 02 Aug 2016 | 09 May 2016 | 25 Jan 2017 | 236 | 261 | 151 | 176
A1-RIGHT SIDE DUCT | 7763.1 | No Unit | 10 Dec 2015 | 02 Aug 2016 |  |  | 236 | 0 | 0 | 0
A1-Right Side Duct Sand Faced Plaster 2 Coat | 5452 | Sft. | 10 Dec 2015 | 02 Aug 2016 | 12 Jan 2016 | 25 Jan 2017 | 236 | 379 | 33 | 176
A1-LEFT SIDE | 0 | No Unit | 10 Dec 2015 | 02 Aug 2016 |  |  | 236 | 0 | 0 | 0
A1-Left Side Sand Faced Plaster 2 Coat | 7308 | Sft. | 10 Dec 2015 | 02 Aug 2016 | 12 Feb 2016 | 25 Jan 2017 | 236 | 348 | 64 | 176
A1-LEFT SIDE DUCT | 0 | No Unit | 10 Dec 2015 | 02 Aug 2016 |  |  | 236 | 0 | 0 | 0
A1-Left Side Duct Sand Faced Plaster 2 Coat | 7767 | Sft. | 10 Dec 2015 | 02 Aug 2016 | 13 Jan 2016 | 25 Jan 2017 | 236 | 378 | 34 | 176
A1-CENTRAL DUCT | 0 | No Unit | 10 Dec 2015 | 02 Aug 2016 |  |  | 236 | 0 | 0 | 0
A1-Central Duct Sand Faced Plaster 2 Coat | 0 | Sft. | 10 Dec 2015 | 02 Aug 2016 | 09 May 2016 | 25 Jan 2017 | 236 | 261 | 151 | 176
A1-LOBBY DUCT | 0 | No Unit | 10 Dec 2015 | 02 Aug 2016 |  |  | 236 | 0 | 0 | 0
A1-Lobby Duct Sand Faced Plaster 2 Coat | 4585 | Sft. | 10 Dec 2015 | 02 Aug 2016 | 29 Feb 2016 | 25 Jan 2017 | 236 | 331 | 81 | 176
A1-ELECTRICAL DUCT | 0 | No Unit | 10 Dec 2015 | 02 Aug 2016 |  |  | 236 | 0 | 0 | 0
A1-Electrical Duct Sand Faced Plaster 2 Coat | 0 | Sft. | 10 Dec 2015 | 02 Aug 2016 | 06 Feb 2016 | 25 Jan 2017 | 236 | 354 | 58 | 176
A1-F.F. DUCT | 0 | No Unit | 10 Dec 2015 | 02 Aug 2016 |  |  | 236 | 0 | 0 | 0
A1-F.F. Duct Sand Faced Plaster 2 Coat | 3000 | Sft. | 10 Dec 2015 | 02 Aug 2016 | 09 May 2016 | 25 Jan 2017 | 236 | 261 | 151 | 176
A1-ABOVE TERRACE | 0 | No Unit | 03 Aug 2016 | 11 Aug 2016 |  |  | 8 | 0 | 0 | 0
A1-Above Terrace Sand Faced Plaster 2 Coat | 7587 | Sft. | 03 Aug 2016 | 11 Aug 2016 | 28 Jul 2016 | 25 Jan 2017 | 8 | 181 | 0 | 167
A1-CHIKEN MESH | 0 | No Unit | 10 Dec 2015 | 02 Aug 2016 |  |  | 236 | 0 | 0 | 0
A1-Chiken Mesh Misc.M & P | 1 | Job | 10 Dec 2015 | 02 Aug 2016 | 27 Oct 2015 | 25 Jan 2017 | 236 | 456 | 0 | 176
A1-PLUMBING GABADI/FINISH | 0 | No Unit | 03 Aug 2016 | 17 Aug 2016 |  |  | 14 | 0 | 0 | 0
A1-Plumbing gabadi/finish Plumbing gabadi/finish | 1200 | Sft. | 03 Aug 2016 | 17 Aug 2016 | 22 Aug 2016 | 25 Jan 2017 | 14 | 156 | 19 | 161
A1-WATERPROOFING | 0 | No Unit | 21 Dec 2015 | 01 Sep 2016 |  |  | 255 | 0 | 0 | 0
A1-PARKING FLOOR WATERPROOFING | 54.6 | No Unit | 02 Aug 2016 | 10 Aug 2016 |  |  | 8 | 0 | 0 | 0
A1-Parking Floor Waterproofing Brick Bat W/P (Toilet) | 40 | Sft. | 02 Aug 2016 | 10 Aug 2016 | 14 Apr 2016 | 27 Jun 2016 | 8 | 74 | 0 | 0
A1-1ST FL W/P | 0 | No Unit | 21 Dec 2015 | 18 Mar 2016 |  |  | 88 | 0 | 0 | 0
A1-1st Fl W/P Brick Bat W/P (Toilet) | 344.2 | Sft. | 21 Dec 2015 | 01 Jan 2016 | 10 Dec 2015 | 19 Feb 2016 | 11 | 71 | 0 | 49
A1-1st Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 10 Mar 2016 | 18 Mar 2016 | 26 Mar 2016 | 26 Mar 2016 | 8 | 0 | 16 | 8
A1-1st Fl W/P Brick Bat W/P entrance lobby | 120.66 | Sft. | 10 Mar 2016 | 18 Mar 2016 | 09 May 2016 | 09 Aug 2016 | 8 | 92 | 60 | 144
A1-1st Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 21 Dec 2015 | 01 Jan 2016 | 26 Mar 2016 | 26 Mar 2016 | 11 | 0 | 96 | 85
A1-1st Fl W/P Screed + Chemical W/P (Ter.) | 250.12 | Sft. | 10 Mar 2016 | 18 Mar 2016 | 29 Jan 2016 | 09 May 2016 | 8 | 101 | 0 | 52
A1-2ND FL W/P | 0 | No Unit | 29 Dec 2015 | 28 Mar 2016 |  |  | 90 | 0 | 0 | 0
A1-2nd Fl W/P Brick Bat W/P (Toilet) | 344.2 | Sft. | 29 Dec 2015 | 09 Jan 2016 | 10 Dec 2015 | 19 Feb 2016 | 11 | 71 | 0 | 41
A1-2nd Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 19 Mar 2016 | 28 Mar 2016 | 26 Mar 2016 | 26 Mar 2016 | 9 | 0 | 7 | 0
A1-2nd Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 29 Dec 2015 | 09 Jan 2016 | 26 Mar 2016 | 26 Mar 2016 | 11 | 0 | 88 | 77
A1-2nd Fl W/P Screed + Chemical W/P (Ter.) | 370.14 | Sft. | 19 Mar 2016 | 28 Mar 2016 | 29 Jan 2016 | 09 May 2016 | 9 | 101 | 0 | 42
A1-3RD FL W/P | 0 | No Unit | 19 Jan 2016 | 06 Apr 2016 |  |  | 78 | 0 | 0 | 0
A1-3rd Fl W/P Brick Bat W/P (Toilet) | 344.2 | Sft. | 19 Jan 2016 | 30 Jan 2016 | 26 Dec 2015 | 19 Feb 2016 | 11 | 55 | 0 | 20
A1-3rd Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 29 Mar 2016 | 06 Apr 2016 | 26 Mar 2016 | 26 Mar 2016 | 8 | 0 | 0 | 0
A1-3rd Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 19 Jan 2016 | 30 Jan 2016 | 26 Mar 2016 | 26 Mar 2016 | 11 | 0 | 67 | 56
A1-3rd Fl W/P Screed + Chemical W/P (Ter.) | 250.12 | Sft. | 29 Mar 2016 | 06 Apr 2016 | 13 Feb 2016 | 09 May 2016 | 8 | 86 | 0 | 33
A1-4TH FL W/P | 0 | No Unit | 10 Feb 2016 | 15 Apr 2016 |  |  | 65 | 0 | 0 | 0
A1-4th Fl W/P Brick Bat W/P (Toilet) | 344.2 | Sft. | 10 Feb 2016 | 20 Feb 2016 | 07 Jan 2016 | 19 Feb 2016 | 10 | 43 | 0 | 0
A1-4th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 07 Apr 2016 | 15 Apr 2016 | 26 Mar 2016 | 26 Mar 2016 | 8 | 0 | 0 | 0
A1-4th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 10 Feb 2016 | 20 Feb 2016 | 26 Mar 2016 | 26 Mar 2016 | 10 | 0 | 45 | 35
A1-4th Fl W/P Screed + Chemical W/P (Ter.) | 370.14 | Sft. | 07 Apr 2016 | 15 Apr 2016 | 13 Feb 2016 | 09 May 2016 | 8 | 86 | 0 | 24
A1-5TH FL W/P | 0 | No Unit | 03 Mar 2016 | 25 Apr 2016 |  |  | 53 | 0 | 0 | 0
A1-5th Fl W/P Brick Bat W/P (Toilet) | 344.2 | Sft. | 03 Mar 2016 | 15 Mar 2016 | 08 Jan 2016 | 19 Feb 2016 | 12 | 42 | 0 | 0
A1-5th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 16 Apr 2016 | 25 Apr 2016 | 26 Mar 2016 | 26 Mar 2016 | 9 | 0 | 0 | 0
A1-5th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 03 Mar 2016 | 15 Mar 2016 | 26 Mar 2016 | 26 Mar 2016 | 12 | 0 | 23 | 11
A1-5th Fl W/P Screed + Chemical W/P (Ter.) | 250.12 | Sft. | 16 Apr 2016 | 25 Apr 2016 | 22 Feb 2016 | 09 May 2016 | 9 | 77 | 0 | 14
A1-6TH FL W/P | 90.41 | No Unit | 25 Mar 2016 | 04 May 2016 |  |  | 40 | 0 | 0 | 0
A1-6th Fl W/P Brick Bat W/P (Toilet) | 304.2 | Sft. | 25 Mar 2016 | 05 Apr 2016 | 03 Feb 2016 | 23 Apr 2016 | 11 | 80 | 0 | 18
A1-6th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 26 Apr 2016 | 04 May 2016 | 26 Mar 2016 | 26 Mar 2016 | 8 | 0 | 0 | 0
A1-6th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 25 Mar 2016 | 05 Apr 2016 | 26 Mar 2016 | 26 Mar 2016 | 11 | 0 | 1 | 0
A1-6th Fl W/P Screed + Chemical W/P (Ter.) | 370.14 | Sft. | 26 Apr 2016 | 04 May 2016 | 21 Mar 2016 | 18 Jun 2016 | 8 | 89 | 0 | 45
A1-7TH FL W/P | 0 | No Unit | 22 Mar 2016 | 13 May 2016 |  |  | 52 | 0 | 0 | 0
A1-7th Fl W/P Brick Bat W/P (Toilet) | 304.2 | Sft. | 22 Mar 2016 | 30 Mar 2016 | 23 Feb 2016 | 23 Apr 2016 | 8 | 60 | 0 | 24
A1-7th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 05 May 2016 | 13 May 2016 | 09 May 2016 | 09 May 2016 | 8 | 0 | 4 | 0
A1-7th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 22 Mar 2016 | 01 Apr 2016 | 09 May 2016 | 09 May 2016 | 10 | 0 | 48 | 38
A1-7th Fl W/P Screed + Chemical W/P (Ter.) | 250.12 | Sft. | 05 May 2016 | 13 May 2016 | 22 Mar 2016 | 09 May 2016 | 8 | 48 | 0 | 0
A1-8TH FL W/P | 716.1935 | No Unit | 22 Mar 2016 | 25 May 2016 |  |  | 64 | 0 | 0 | 0
A1-8th Fl W/P Brick Bat W/P (Toilet) | 258.15 | Sft. | 22 Mar 2016 | 30 Mar 2016 | 02 Mar 2016 | 23 Apr 2016 | 8 | 52 | 0 | 24
A1-8th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 14 May 2016 | 23 May 2016 | 09 May 2016 | 09 May 2016 | 9 | 0 | 0 | 0
A1-8th Fl W/P Screed + Chemical W/P (Refuge) | 716.19 | Sft. | 14 May 2016 | 23 May 2016 | 06 May 2016 | 25 Jan 2017 | 9 | 264 | 0 | 247
A1-8th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 22 Mar 2016 | 30 Mar 2016 | 09 May 2016 | 09 May 2016 | 8 | 0 | 48 | 40
A1-8th Fl W/P Screed + Chemical W/P (Ter.) | 370.14 | Sft. | 14 May 2016 | 25 May 2016 | 15 Apr 2016 | 09 May 2016 | 11 | 24 | 0 | 0
A1-9TH FL W/P | 343.01 | No Unit | 22 Mar 2016 | 01 Jun 2016 |  |  | 71 | 0 | 0 | 0
A1-9th Fl W/P Brick Bat W/P (Toilet) | 304.2 | Sft. | 22 Mar 2016 | 30 Mar 2016 | 14 Mar 2016 | 23 Apr 2016 | 8 | 40 | 0 | 24
A1-9th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 24 May 2016 | 01 Jun 2016 | 09 May 2016 | 18 Jun 2016 | 8 | 40 | 0 | 17
A1-9th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 22 Mar 2016 | 01 Apr 2016 | 09 May 2016 | 18 Jun 2016 | 10 | 40 | 48 | 78
A1-9th Fl W/P Screed + Chemical W/P (Ter.) | 250.12 | Sft. | 24 May 2016 | 01 Jun 2016 | 03 May 2016 | 18 Jun 2016 | 8 | 46 | 0 | 17
A1-10TH FL W/P | 0 | No Unit | 22 Mar 2016 | 15 Jun 2016 |  |  | 85 | 0 | 0 | 0
A1-10th Fl W/P Brick Bat W/P (Toilet) | 304.2 | Sft. | 25 Apr 2016 | 14 May 2016 | 18 Mar 2016 | 23 Apr 2016 | 19 | 36 | 0 | 0
A1-10th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 02 Jun 2016 | 15 Jun 2016 | 09 May 2016 | 18 Jun 2016 | 13 | 40 | 0 | 3
A1-10th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 22 Mar 2016 | 11 Apr 2016 | 09 May 2016 | 18 Jun 2016 | 20 | 40 | 48 | 68
A1-10th Fl W/P Screed + Chemical W/P (Ter.) | 370.14 | Sft. | 02 Jun 2016 | 15 Jun 2016 | 09 May 2016 | 18 Jun 2016 | 13 | 40 | 0 | 3
A1-11TH FL W/P | 0 | No Unit | 25 Apr 2016 | 29 Jun 2016 |  |  | 65 | 0 | 0 | 0
A1-11th Fl W/P Brick Bat W/P (Toilet) | 304.2 | Sft. | 25 Apr 2016 | 14 May 2016 | 13 Apr 2016 | 23 Apr 2016 | 19 | 10 | 0 | 0
A1-11th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 16 Jun 2016 | 29 Jun 2016 | 18 Jun 2016 | 18 Jun 2016 | 13 | 0 | 2 | 0
A1-11th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 25 Apr 2016 | 14 May 2016 | 18 Jun 2016 | 18 Jun 2016 | 19 | 0 | 54 | 35
A1-11th Fl W/P Screed + Chemical W/P (Ter.) | 250.12 | Sft. | 16 Jun 2016 | 29 Jun 2016 | 08 Jun 2016 | 11 Jul 2016 | 13 | 33 | 0 | 12
A1-12TH FL W/P | 0 | No Unit | 30 Jun 2016 | 25 Jul 2016 |  |  | 25 | 0 | 0 | 0
A1-12th Fl W/P Brick Bat W/P (Toilet) | 304.2 | Sft. | 05 Jul 2016 | 25 Jul 2016 | 08 Jun 2016 | 11 Jul 2016 | 20 | 33 | 0 | 0
A1-12th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 30 Jun 2016 | 13 Jul 2016 | 18 Jun 2016 | 18 Jun 2016 | 13 | 0 | 0 | 0
A1-12th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 05 Jul 2016 | 25 Jul 2016 | 18 Jun 2016 | 18 Jun 2016 | 20 | 0 | 0 | 0
A1-12th Fl W/P Screed + Chemical W/P (Ter.) | 370.14 | Sft. | 30 Jun 2016 | 13 Jul 2016 | 08 Jun 2016 | 09 Aug 2016 | 13 | 62 | 0 | 27
A1-13TH FL W/P | 380.2814 | No Unit | 14 Jul 2016 | 08 Aug 2016 |  |  | 25 | 0 | 0 | 0
A1-13th Fl W/P Brick Bat W/P (Toilet) | 258.15 | Sft. | 21 Jul 2016 | 08 Aug 2016 | 20 Sep 2016 | 12 Nov 2016 | 18 | 53 | 61 | 96
A1-13th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 14 Jul 2016 | 22 Jul 2016 | 12 Nov 2016 | 12 Nov 2016 | 8 | 0 | 121 | 113
A1-13th Fl W/P Screed + Chemical W/P (Refuge) | 716.19 | Sft. | 14 Jul 2016 | 22 Jul 2016 | 12 Nov 2016 | 25 Jan 2017 | 8 | 74 | 121 | 187
A1-13th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 21 Jul 2016 | 08 Aug 2016 | 12 Nov 2016 | 12 Nov 2016 | 18 | 0 | 114 | 96
A1-13th Fl W/P Screed + Chemical W/P (Ter.) | 250.12 | Sft. | 14 Jul 2016 | 22 Jul 2016 | 11 Aug 2016 | 12 Nov 2016 | 8 | 93 | 28 | 113
A1-14TH FL W/P | 0 | No Unit | 23 Jul 2016 | 29 Aug 2016 |  |  | 37 | 0 | 0 | 0
A1-14th Fl W/P Brick Bat W/P (Toilet) | 0 | Sft. | 10 Aug 2016 | 29 Aug 2016 | 12 Nov 2016 | 12 Nov 2016 | 19 | 0 | 94 | 75
A1-14th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 23 Jul 2016 | 01 Aug 2016 | 12 Nov 2016 | 12 Nov 2016 | 9 | 0 | 112 | 103
A1-14th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 10 Aug 2016 | 29 Aug 2016 | 12 Nov 2016 | 12 Nov 2016 | 19 | 0 | 94 | 75
A1-14th Fl W/P Screed + Chemical W/P (Ter.) | 0 | Sft. | 23 Jul 2016 | 01 Aug 2016 | 12 Nov 2016 | 12 Nov 2016 | 9 | 0 | 112 | 103
A1-TOP TERRACE W/P | 0 | No Unit | 05 Aug 2016 | 23 Aug 2016 |  |  | 18 | 0 | 0 | 0
A1-Top Terrace W/P Brick Bat W/P (Terrace) | 3639.58 | Sft. | 05 Aug 2016 | 23 Aug 2016 | 13 Sep 2016 | 29 Nov 2016 | 18 | 77 | 39 | 98
A1-LMR WATERPROOFING | 0 | No Unit | 24 Aug 2016 | 01 Sep 2016 |  |  | 8 | 0 | 0 | 0
A1-LMR Waterproofing Brick Bat W/P (Terrace) | 0 | Sft. | 24 Aug 2016 | 01 Sep 2016 | 15 Jul 2016 | 12 Nov 2016 | 8 | 120 | 0 | 72
A1-OHWT WATERPROOFING | 0 | No Unit | 24 Aug 2016 | 01 Sep 2016 |  |  | 8 | 0 | 0 | 0
A1-OHWT Waterproofing Brick Bat W/P (Terrace) | 458.73 | Sft. | 24 Aug 2016 | 01 Sep 2016 | 07 Sep 2016 | 12 Nov 2016 | 8 | 66 | 14 | 72
A1-OHWT Waterproofing W/P Plaster | 826.82 | Sft. | 24 Aug 2016 | 01 Sep 2016 | 07 Sep 2016 | 12 Nov 2016 | 8 | 66 | 14 | 72
A1-TILLING | 0 | No Unit | 07 Dec 2015 | 19 Dec 2016 |  |  | 378 | 0 | 0 | 0
A1-FLOORING | 323.92 | No Unit | 20 Jan 2016 | 03 Dec 2016 |  |  | 318 | 0 | 0 | 0
A1-PARKING | 56695 | No Unit | 14 Oct 2016 | 03 Dec 2016 |  |  | 50 | 0 | 0 | 0
A1-PARKING ENTRACE LOBBY | 3 | No Unit | 14 Oct 2016 | 27 Oct 2016 |  |  | 13 | 0 | 0 | 0
A1-Parking Entrace Lobby Floor Lobby Flooring | 374.1252 | Sft. | 14 Oct 2016 | 22 Oct 2016 | 16 Apr 2016 | 13 Jan 2017 | 8 | 272 | 0 | 83
A1-Parking Entrace Lobby Floor Lobby Skirting | 0 | Rft | 26 Oct 2016 | 27 Oct 2016 | 16 Apr 2016 | 13 Jan 2017 | 1 | 272 | 0 | 78
A1-Parking Entrace Lobby Entracnce Lobby (Lab) | 56695 | Sft. | 14 Oct 2016 | 22 Oct 2016 | 16 Apr 2016 | 28 Jan 2017 | 8 | 287 | 0 | 98
A1-Parking Entrace Lobby Entrance Lobby | 1 | Job | 14 Oct 2016 | 22 Oct 2016 | 16 Apr 2016 |  | 8 | 0 | 0 | 0
A1-Parking Entrace Lobby Misc. Material (White Cement) | 1 | NO | 14 Oct 2016 | 22 Oct 2016 | 16 Apr 2016 | 25 Jan 2017 | 8 | 284 | 0 | 95
A1-MAIN STAIRCASE | 0 | No Unit | 14 Oct 2016 | 17 Oct 2016 |  |  | 3 | 0 | 0 | 0
A1-Main Staircase Main Staircase Flooring | 32 | Sft. | 14 Oct 2016 | 17 Oct 2016 | 28 Apr 2016 | 13 Jan 2017 | 3 | 260 | 0 | 88
A1-Main Staircase Main Staircase Riser | 76 | Rft | 14 Oct 2016 | 17 Oct 2016 | 28 Apr 2016 | 13 Jan 2017 | 3 | 260 | 0 | 88
A1-Main Staircase Main Staircase Skirting | 62.25 | Rft | 14 Oct 2016 | 17 Oct 2016 | 28 Apr 2016 | 13 Jan 2017 | 3 | 260 | 0 | 88
A1-Main Staircase Main Staircase Tread | 76 | Sft. | 14 Oct 2016 | 17 Oct 2016 | 28 Apr 2016 | 13 Jan 2017 | 3 | 260 | 0 | 88
A1-Main Staircase Main Staircase (Lab) | 56695 | Sft. | 14 Oct 2016 | 17 Oct 2016 | 28 Apr 2016 | 28 Jan 2017 | 3 | 275 | 0 | 103
A1-FIRE STAIRCASE | 69.4 | No Unit | 14 Oct 2016 | 17 Oct 2016 |  |  | 3 | 0 | 0 | 0
A1-Fire Staircase Fire Staircase Flooring | 63 | Sft. | 14 Oct 2016 | 17 Oct 2016 | 28 Jan 2017 | 28 Jan 2017 | 3 | 0 | 106 | 103
A1-Fire Staircase Fire Staircase Riser | 95 | Rft | 14 Oct 2016 | 17 Oct 2016 | 28 Jan 2017 | 28 Jan 2017 | 3 | 0 | 106 | 103
A1-Fire Staircase Fire Staircase Skirting | 93 | Rft | 14 Oct 2016 | 17 Oct 2016 | 28 Jan 2017 | 28 Jan 2017 | 3 | 0 | 106 | 103
A1-Fire Staircase Fire Staircase Tread | 95 | Sft. | 14 Oct 2016 | 17 Oct 2016 | 28 Jan 2017 | 28 Jan 2017 | 3 | 0 | 106 | 103
A1-Fire Staircase Fire Staircase (Lab) | 56695 | Sft. | 14 Oct 2016 | 17 Oct 2016 | 28 Jan 2017 | 28 Jan 2017 | 3 | 0 | 106 | 103
A1-LIFT CLADDING | 140.32 | No Unit | 14 Oct 2016 | 19 Oct 2016 |  |  | 5 | 0 | 0 | 0
A1-Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 14 Oct 2016 | 19 Oct 2016 | 25 Jul 2016 |  | 5 | 0 | 0 | 0
A1-Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 14 Oct 2016 | 19 Oct 2016 | 25 Jul 2016 |  | 5 | 0 | 0 | 0
A1-Lift Cladding Misc. Material (White Cement) | 2 | NO | 14 Oct 2016 | 19 Oct 2016 | 25 Jul 2016 |  | 5 | 0 | 0 | 0
A1-PARKING CHUQUERD TILE FLOORING | 0 | No Unit | 28 Oct 2016 | 03 Nov 2016 |  |  | 6 | 0 | 0 | 0
A1-Parking Chuquerd Tile Flooring Chquered Tile Flooring | 3100.93 | Sft. | 28 Oct 2016 | 03 Nov 2016 | 06 Sep 2016 | 28 Jan 2017 | 6 | 144 | 0 | 86
A1-Parking Chuquerd Tile Flooring Chequred/Paving Flooring(L | 56695 | Sft. | 28 Oct 2016 | 03 Nov 2016 | 06 Sep 2016 | 28 Jan 2017 | 6 | 144 | 0 | 86
A1-PARKING TOILET | 343.15 | No Unit | 14 Oct 2016 | 17 Oct 2016 |  |  | 3 | 0 | 0 | 0
A1-Parking Toilet Common Toilet Flooring | 37.47 | Sft. | 14 Oct 2016 | 17 Oct 2016 | 24 Jun 2016 | 28 Jan 2017 | 3 | 218 | 0 | 103
A1-Parking Toilet Common Toilet Dado | 100 | Sft. | 14 Oct 2016 | 17 Oct 2016 | 24 Jun 2016 | 28 Jan 2017 | 3 | 218 | 0 | 103
A1-PARKING CENTRAL DUCT FLOORING | 1091.06 | No Unit | 28 Oct 2016 | 29 Oct 2016 |  |  | 1 | 0 | 0 | 0
A1-Parking Central Duct Flooring Rough Kotta Flooring | 0 | Sft. | 28 Oct 2016 | 29 Oct 2016 | 15 Feb 2017 |  | 1 | 0 | 110 | 0
A1-Parking Central Duct Flooring Cement Ghotai | 429 | Sft. | 23 May 2015 |  | 15 Feb 2017 |  | 0 | 0 | 634 | 0
A1-Parking Central Duct Flooring RMC M10 Outsource | 4 | Cum. | 23 May 2015 |  | 22 Dec 2016 | 28 Jan 2017 | 0 | 37 | 579 | 42761
A1-PARKING METER ROOM(RUBBER MAT) | 0 | No Unit | 02 Dec 2016 | 03 Dec 2016 |  |  | 1 | 0 | 0 | 0
A1-Parking Meter Room(Rubber Mat) Misc. Item (Meter Room) | 1 | No. | 02 Dec 2016 | 03 Dec 2016 | 09 Feb 2016 |  | 1 | 0 | 0 | 0
A1-Parking 9" wide cudappa/Granite boarder in Parki | 0 | Rft | 02 Dec 2016 | 03 Dec 2016 | 13 Jan 2017 |  | 1 | 0 | 42 | 0
A1-Parking Flooring | 0 | Sft. | 23 May 2015 |  | 13 Jan 2017 |  | 0 | 0 | 601 | 0
A1-1ST FLOOR | 0 | No Unit | 20 Jan 2016 | 31 Mar 2016 |  |  | 71 | 0 | 0 | 0
A1-FLAT-101 | 0 | No Unit | 20 Jan 2016 | 28 Mar 2016 |  |  | 68 | 0 | 0 | 0
A1-Flat-101 Common Toilet Dado | 172.56 | Sft. | 20 Jan 2016 | 21 Jan 2016 | 08 Jan 2016 | 24 Mar 2016 | 1 | 76 | 0 | 63
A1-Flat-101 Master Toilet Dado | 164.5 | Sft. | 20 Jan 2016 | 21 Jan 2016 | 30 Dec 2015 | 24 Mar 2016 | 1 | 85 | 0 | 63
A1-Flat-101 Kit. Dado Above | 63.39 | Sft. | 20 Jan 2016 | 21 Jan 2016 | 08 Jan 2016 | 24 Mar 2016 | 1 | 76 | 0 | 63
A1-Flat-101 Flat Flooring | 635.83 | Sft. | 28 Jan 2016 | 01 Feb 2016 | 10 Feb 2016 | 24 Mar 2016 | 4 | 43 | 13 | 52
A1-Flat-101 Flat Skirting | 204.04 | Rft | 04 Feb 2016 | 05 Feb 2016 | 10 Feb 2016 | 24 Mar 2016 | 1 | 43 | 6 | 48
A1-Flat-101 Common Toilet Flooring | 37.47 | Sft. | 22 Jan 2016 | 23 Jan 2016 | 08 Jan 2016 | 24 Mar 2016 | 1 | 76 | 0 | 61
A1-Flat-101 Master Toilet Flooring | 39.92 | Sft. | 22 Jan 2016 | 23 Jan 2016 | 04 Jan 2016 | 24 Mar 2016 | 1 | 80 | 0 | 61
A1-Flat-101 Sitout/Terrace Flooring | 48.62 | Sft. | 30 Jan 2016 | 01 Feb 2016 | 15 Feb 2016 | 24 Mar 2016 | 2 | 38 | 16 | 52
A1-Flat-101 Sitout/Terrace Skirting | 23 | Rft | 04 Feb 2016 | 04 Feb 2016 | 15 Feb 2016 | 24 Mar 2016 | 0 | 38 | 11 | 49
A1-Flat-101 Window Box Flooring | 14.53 | Sft. | 02 Feb 2016 | 02 Feb 2016 | 15 Feb 2016 | 27 Mar 2016 | 0 | 41 | 13 | 54
A1-Flat-101 Umara Patti | 0 | Rft | 28 Mar 2016 | 28 Mar 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 78 | 102
A1-Flat-101 Flat Tiling (Lab) | 56695 | Sft. | 20 Jan 2016 | 05 Feb 2016 | 12 Feb 2016 | 13 Jul 2016 | 16 | 152 | 23 | 159
A1-FLAT-102 | 0 | No Unit | 22 Jan 2016 | 29 Mar 2016 |  |  | 67 | 0 | 0 | 0
A1-Flat-102 Common Toilet Dado | 172.56 | Sft. | 22 Jan 2016 | 23 Jan 2016 | 09 Jan 2016 | 30 Mar 2016 | 1 | 81 | 0 | 67
A1-Flat-102 Master Toilet Dado | 164.5 | Sft. | 22 Jan 2016 | 23 Jan 2016 | 06 Jan 2016 | 30 Mar 2016 | 1 | 84 | 0 | 67
A1-Flat-102 Kit. Dado Above | 68.5 | Sft. | 22 Jan 2016 | 23 Jan 2016 | 09 Jan 2016 | 30 Mar 2016 | 1 | 81 | 0 | 67
A1-Flat-102 Flat Flooring | 629.31 | Sft. | 30 Jan 2016 | 03 Feb 2016 | 03 Mar 2016 | 30 Mar 2016 | 4 | 27 | 33 | 56
A1-Flat-102 Flat Skirting | 201.77 | Rft | 06 Feb 2016 | 08 Feb 2016 | 03 Mar 2016 | 30 Mar 2016 | 2 | 27 | 26 | 51
A1-Flat-102 Common Toilet Flooring | 37.47 | Sft. | 25 Jan 2016 | 27 Jan 2016 | 09 Jan 2016 | 30 Mar 2016 | 2 | 81 | 0 | 63
A1-Flat-102 Master Toilet Flooring | 39.92 | Sft. | 25 Jan 2016 | 27 Jan 2016 | 06 Jan 2016 | 30 Mar 2016 | 2 | 84 | 0 | 63
A1-Flat-102 Sitout/Terrace Flooring | 48.62 | Sft. | 02 Feb 2016 | 03 Feb 2016 | 10 Mar 2016 | 17 Jun 2016 | 1 | 99 | 37 | 135
A1-Flat-102 Sitout/Terrace Skirting | 23 | Rft | 06 Feb 2016 | 06 Feb 2016 | 10 Mar 2016 | 30 Mar 2016 | 0 | 20 | 33 | 53
A1-Flat-102 Window Box Flooring | 14.53 | Sft. | 04 Feb 2016 | 04 Feb 2016 | 19 Mar 2016 | 30 Mar 2016 | 0 | 11 | 44 | 55
A1-Flat-102 Umara Patti | 0 | Rft | 29 Mar 2016 | 29 Mar 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 77 | 101
A1-Flat-102 Flat Tiling (Lab) | 56695 | Sft. | 22 Jan 2016 | 05 Feb 2016 | 12 Feb 2016 | 13 Jul 2016 | 14 | 152 | 21 | 159
A1-FLAT-103 | 23 | No Unit | 25 Jan 2016 | 30 Mar 2016 |  |  | 65 | 0 | 0 | 0
A1-Flat-103 Common Toilet Dado | 172.56 | Sft. | 25 Jan 2016 | 27 Jan 2016 | 09 Jan 2016 | 30 Mar 2016 | 2 | 81 | 0 | 63
A1-Flat-103 Master Toilet Dado | 164.5 | Sft. | 25 Jan 2016 | 27 Jan 2016 | 06 Jan 2016 | 30 Mar 2016 | 2 | 84 | 0 | 63
A1-Flat-103 Kit. Dado Above | 68.5 | Sft. | 25 Jan 2016 | 27 Jan 2016 | 09 Jan 2016 | 30 Mar 2016 | 2 | 81 | 0 | 63
A1-Flat-103 Flat Flooring | 629.31 | Sft. | 02 Feb 2016 | 05 Feb 2016 | 23 Mar 2016 | 30 Mar 2016 | 3 | 7 | 50 | 54
A1-Flat-103 Flat Skirting | 201.77 | Rft | 09 Feb 2016 | 10 Feb 2016 | 23 Mar 2016 | 30 Mar 2016 | 1 | 7 | 43 | 49
A1-Flat-103 Common Toilet Flooring | 37.47 | Sft. | 28 Jan 2016 | 29 Jan 2016 | 09 Jan 2016 | 30 Mar 2016 | 1 | 81 | 0 | 61
A1-Flat-103 Master Toilet Flooring | 39.92 | Sft. | 28 Jan 2016 | 29 Jan 2016 | 06 Jan 2016 | 30 Mar 2016 | 1 | 84 | 0 | 61
A1-Flat-103 Sitout/Terrace Flooring | 76.33 | Sft. | 04 Feb 2016 | 05 Feb 2016 | 29 Mar 2016 | 17 Jun 2016 | 1 | 80 | 54 | 133
A1-Flat-103 Sitout/Terrace Skirting | 31 | Rft | 09 Feb 2016 | 09 Feb 2016 | 29 Mar 2016 | 17 Jun 2016 | 0 | 80 | 49 | 129
A1-Flat-103 Window Box Flooring | 14.53 | Sft. | 06 Feb 2016 | 06 Feb 2016 | 09 May 2016 | 17 Jun 2016 | 0 | 39 | 93 | 132
A1-Flat-103 Umara Patti | 0 | Rft | 30 Mar 2016 | 30 Mar 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 76 | 100
A1-Flat-103 Flat Tiling (Lab) | 56695 | Sft. | 25 Jan 2016 | 05 Feb 2016 | 12 Feb 2016 | 13 Jul 2016 | 11 | 152 | 18 | 159
A1-FLAT-104 | 0 | No Unit | 28 Jan 2016 | 31 Mar 2016 |  |  | 63 | 0 | 0 | 0
A1-Flat-104 Common Toilet Dado | 172.56 | Sft. | 28 Jan 2016 | 29 Jan 2016 | 08 Jan 2016 | 24 Mar 2016 | 1 | 76 | 0 | 55
A1-Flat-104 Master Toilet Dado | 164.5 | Sft. | 28 Jan 2016 | 29 Jan 2016 | 29 Dec 2015 | 24 Mar 2016 | 1 | 86 | 0 | 55
A1-Flat-104 Kit. Dado Above | 68.5 | Sft. | 28 Jan 2016 | 29 Jan 2016 | 09 Jan 2016 | 24 Mar 2016 | 1 | 75 | 0 | 55
A1-Flat-104 Flat Flooring | 629.31 | Sft. | 04 Feb 2016 | 08 Feb 2016 | 12 Feb 2016 | 24 Mar 2016 | 4 | 41 | 8 | 45
A1-Flat-104 Flat Skirting | 201.77 | Rft | 11 Feb 2016 | 12 Feb 2016 | 12 Feb 2016 | 24 Mar 2016 | 1 | 41 | 1 | 41
A1-Flat-104 Common Toilet Flooring | 37.47 | Sft. | 30 Jan 2016 | 01 Feb 2016 | 08 Jan 2016 | 24 Mar 2016 | 2 | 76 | 0 | 52
A1-Flat-104 Master Toilet Flooring | 39.92 | Sft. | 30 Jan 2016 | 01 Feb 2016 | 04 Jan 2016 | 24 Mar 2016 | 2 | 80 | 0 | 52
A1-Flat-104 Sitout/Terrace Flooring | 76.33 | Sft. | 06 Feb 2016 | 08 Feb 2016 | 15 Feb 2016 | 27 Mar 2016 | 2 | 41 | 9 | 48
A1-Flat-104 Sitout/Terrace Skirting | 31 | Rft | 11 Feb 2016 | 11 Feb 2016 | 15 Feb 2016 | 24 Mar 2016 | 0 | 38 | 4 | 42
A1-Flat-104 Window Box Flooring | 14.53 | Sft. | 09 Feb 2016 | 09 Feb 2016 | 15 Feb 2016 | 27 Mar 2016 | 0 | 41 | 6 | 47
A1-Flat-104 Umara Patti | 0 | Rft | 31 Mar 2016 | 31 Mar 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 75 | 99
A1-Flat-104 Flat Tiling (Lab) | 56695 | Sft. | 28 Jan 2016 | 12 Feb 2016 | 12 Feb 2016 | 13 Jul 2016 | 15 | 152 | 15 | 152
A1-1ST FL.LOBBY | 0 | No Unit | 15 Feb 2016 | 17 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1-1st Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 15 Feb 2016 | 17 Feb 2016 | 28 Mar 2016 | 17 Jun 2016 | 2 | 81 | 42 | 121
A1-1st Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Feb 2016 | 17 Feb 2016 | 17 Apr 2016 | 17 Jun 2016 | 2 | 61 | 62 | 121
A1-1st Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 15 Feb 2016 | 17 Feb 2016 | 17 Apr 2016 | 27 Dec 2016 | 2 | 254 | 62 | 314
A1-1st Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Feb 2016 | 17 Feb 2016 | 17 Apr 2016 | 17 Jun 2016 | 2 | 61 | 62 | 121
A1-1ST FL MAIN STAIR | 343.15 | No Unit | 18 Feb 2016 | 19 Feb 2016 |  |  | 1 | 0 | 0 | 0
A1-1st Fl Main Stair Main Staircase Flooring | 32 | Sft. | 18 Feb 2016 | 19 Feb 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 44 | 120
A1-1st Fl Main Stair Main Staircase Riser | 76 | Rft | 18 Feb 2016 | 19 Feb 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 44 | 120
A1-1st Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 18 Feb 2016 | 19 Feb 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 44 | 120
A1-1st Fl Main Stair Main Staircase Tread | 76 | Sft. | 18 Feb 2016 | 19 Feb 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 44 | 120
A1-1st Fl Main Stair Main Staircase (Lab) | 56695 | Sft. | 18 Feb 2016 | 19 Feb 2016 | 02 Apr 2016 | 30 Dec 2016 | 1 | 272 | 44 | 315
A1-1ST FL FIRE STAIR | 343.15 | No Unit | 18 Feb 2016 | 19 Feb 2016 |  |  | 1 | 0 | 0 | 0
A1-1st Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 18 Feb 2016 | 19 Feb 2016 | 29 Mar 2016 | 18 Jun 2016 | 1 | 81 | 40 | 120
A1-1st Fl Fire Stair Fire Staircase Riser | 95 | Rft | 18 Feb 2016 | 19 Feb 2016 | 29 Mar 2016 | 18 Jun 2016 | 1 | 81 | 40 | 120
A1-1st Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 18 Feb 2016 | 19 Feb 2016 | 29 Mar 2016 | 18 Jun 2016 | 1 | 81 | 40 | 120
A1-1st Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 18 Feb 2016 | 19 Feb 2016 | 29 Mar 2016 | 18 Jun 2016 | 1 | 81 | 40 | 120
A1-1st Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 18 Feb 2016 | 19 Feb 2016 | 29 Mar 2016 | 30 Dec 2016 | 1 | 276 | 40 | 315
A1-1ST FL LIFT CLADDING | 343.15 | No Unit | 20 Feb 2016 | 24 Feb 2016 |  |  | 4 | 0 | 0 | 0
A1-1st Fl Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 20 Feb 2016 | 24 Feb 2016 | 05 Jul 2016 | 30 Dec 2016 | 4 | 178 | 136 | 310
A1-1st Fl Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 20 Feb 2016 | 24 Feb 2016 | 21 Jul 2016 | 30 Dec 2016 | 4 | 162 | 152 | 310
A1-1st Fl Lift Cladding Misc. Material (White Cement) | 2 | NO | 20 Feb 2016 | 24 Feb 2016 | 05 Jul 2016 | 08 Aug 2016 | 4 | 34 | 136 | 166
A1-1st Floor 1st fl. duct over entran. lobby flooring | 120.66 | Sft. | 20 Feb 2016 | 24 Feb 2016 | 03 Aug 2016 | 30 Dec 2016 | 4 | 149 | 165 | 310
A1-1st Floor 1st fl. duct over entran. lobby Skirting | 0 | Rft | 20 Feb 2016 | 24 Feb 2016 | 03 Aug 2016 | 30 Dec 2016 | 4 | 149 | 165 | 310
A1-2ND FLOOR | 0 | No Unit | 30 Jan 2016 | 05 Apr 2016 |  |  | 66 | 0 | 0 | 0
A1-FLAT-201 | 0 | No Unit | 30 Jan 2016 | 01 Apr 2016 |  |  | 62 | 0 | 0 | 0
A1-Flat-201 Common Toilet Dado | 172.56 | Sft. | 30 Jan 2016 | 01 Feb 2016 | 18 Jan 2016 | 25 Mar 2016 | 2 | 67 | 0 | 53
A1-Flat-201 Master Toilet Dado | 164.5 | Sft. | 30 Jan 2016 | 01 Feb 2016 | 13 Jan 2016 | 25 Mar 2016 | 2 | 72 | 0 | 53
A1-Flat-201 Kit. Dado Above | 63.39 | Sft. | 30 Jan 2016 | 01 Feb 2016 | 11 Jan 2016 | 25 Mar 2016 | 2 | 74 | 0 | 53
A1-Flat-201 Flat Flooring | 630.02 | Sft. | 06 Feb 2016 | 10 Feb 2016 | 15 Feb 2016 | 25 Mar 2016 | 4 | 39 | 9 | 44
A1-Flat-201 Flat Skirting | 199.06 | Rft | 13 Feb 2016 | 15 Feb 2016 | 15 Feb 2016 | 25 Mar 2016 | 2 | 39 | 2 | 39
A1-Flat-201 Common Toilet Flooring | 37.47 | Sft. | 02 Feb 2016 | 03 Feb 2016 | 18 Jan 2016 | 25 Mar 2016 | 1 | 67 | 0 | 51
A1-Flat-201 Master Toilet Flooring | 39.92 | Sft. | 02 Feb 2016 | 03 Feb 2016 | 18 Jan 2016 | 25 Mar 2016 | 1 | 67 | 0 | 51
A1-Flat-201 Sitout/Terrace Flooring | 125.06 | Sft. | 09 Feb 2016 | 10 Feb 2016 | 17 Feb 2016 | 27 Mar 2016 | 1 | 39 | 8 | 46
A1-Flat-201 Sitout/Terrace Skirting | 59 | Rft | 13 Feb 2016 | 13 Feb 2016 | 17 Feb 2016 | 27 Mar 2016 | 0 | 39 | 4 | 43
A1-Flat-201 Window Box Flooring | 7.27 | Sft. | 11 Feb 2016 | 11 Feb 2016 | 27 Feb 2016 | 27 Mar 2016 | 0 | 29 | 16 | 45
A1-Flat-201 Umara Patti | 0 | Rft | 01 Apr 2016 | 01 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 74 | 98
A1-Flat-201 Flat Tiling (Lab) | 56695 | Sft. | 30 Jan 2016 | 15 Feb 2016 | 12 Feb 2016 | 13 Jul 2016 | 16 | 152 | 13 | 149
A1-FLAT-202 | 0 | No Unit | 02 Feb 2016 | 02 Apr 2016 |  |  | 60 | 0 | 0 | 0
A1-Flat-202 Common Toilet Dado | 172.56 | Sft. | 02 Feb 2016 | 03 Feb 2016 | 29 Jan 2016 | 30 Mar 2016 | 1 | 61 | 0 | 56
A1-Flat-202 Master Toilet Dado | 164.5 | Sft. | 02 Feb 2016 | 03 Feb 2016 | 29 Jan 2016 | 30 Mar 2016 | 1 | 61 | 0 | 56
A1-Flat-202 Kit. Dado Above | 68.5 | Sft. | 02 Feb 2016 | 03 Feb 2016 | 11 Jan 2016 | 30 Mar 2016 | 1 | 79 | 0 | 56
A1-Flat-202 Flat Flooring | 623.45 | Sft. | 09 Feb 2016 | 12 Feb 2016 | 03 Mar 2016 | 30 Mar 2016 | 3 | 27 | 23 | 47
A1-Flat-202 Flat Skirting | 196.8 | Rft | 16 Feb 2016 | 17 Feb 2016 | 03 Mar 2016 | 30 Mar 2016 | 1 | 27 | 16 | 42
A1-Flat-202 Common Toilet Flooring | 37.47 | Sft. | 04 Feb 2016 | 05 Feb 2016 | 03 Feb 2016 | 30 Mar 2016 | 1 | 56 | 0 | 54
A1-Flat-202 Master Toilet Flooring | 39.92 | Sft. | 04 Feb 2016 | 05 Feb 2016 | 03 Feb 2016 | 30 Mar 2016 | 1 | 56 | 0 | 54
A1-Flat-202 Sitout/Terrace Flooring | 125.06 | Sft. | 11 Feb 2016 | 12 Feb 2016 | 12 Mar 2016 | 17 Jun 2016 | 1 | 97 | 30 | 126
A1-Flat-202 Sitout/Terrace Skirting | 59 | Rft | 16 Feb 2016 | 16 Feb 2016 | 12 Mar 2016 | 30 Mar 2016 | 0 | 18 | 25 | 43
A1-Flat-202 Window Box Flooring | 7.27 | Sft. | 13 Feb 2016 | 13 Feb 2016 | 19 Mar 2016 | 30 Mar 2016 | 0 | 11 | 35 | 46
A1-Flat-202 Umara Patti | 0 | Rft | 02 Apr 2016 | 02 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 73 | 97
A1-Flat-202 Flat Tiling (Lab) | 56695 | Sft. | 02 Feb 2016 | 17 Feb 2016 | 12 Feb 2016 | 13 Jul 2016 | 15 | 152 | 10 | 147
A1-FLAT-203 | 0 | No Unit | 04 Feb 2016 | 04 Apr 2016 |  |  | 60 | 0 | 0 | 0
A1-Flat-203 Common Toilet Dado | 172.56 | Sft. | 04 Feb 2016 | 05 Feb 2016 | 29 Jan 2016 | 30 Mar 2016 | 1 | 61 | 0 | 54
A1-Flat-203 Master Toilet Dado | 164.5 | Sft. | 04 Feb 2016 | 05 Feb 2016 | 29 Jan 2016 | 30 Mar 2016 | 1 | 61 | 0 | 54
A1-Flat-203 Kit. Dado Above | 68.5 | Sft. | 04 Feb 2016 | 05 Feb 2016 | 11 Jan 2016 | 30 Mar 2016 | 1 | 79 | 0 | 54
A1-Flat-203 Flat Flooring | 623.45 | Sft. | 11 Feb 2016 | 15 Feb 2016 | 22 Mar 2016 | 30 Mar 2016 | 4 | 8 | 40 | 44
A1-Flat-203 Flat Skirting | 196.8 | Rft | 18 Feb 2016 | 19 Feb 2016 | 22 Mar 2016 | 30 Mar 2016 | 1 | 8 | 33 | 40
A1-Flat-203 Common Toilet Flooring | 37.47 | Sft. | 06 Feb 2016 | 08 Feb 2016 | 03 Feb 2016 | 30 Mar 2016 | 2 | 56 | 0 | 51
A1-Flat-203 Master Toilet Flooring | 39.92 | Sft. | 06 Feb 2016 | 08 Feb 2016 | 03 Feb 2016 | 30 Mar 2016 | 2 | 56 | 0 | 51
A1-Flat-203 Sitout/Terrace Flooring | 62.26 | Sft. | 13 Feb 2016 | 15 Feb 2016 | 19 Feb 2016 | 17 Jun 2016 | 2 | 119 | 6 | 123
A1-Flat-203 Sitout/Terrace Skirting | 30 | Rft | 18 Feb 2016 | 18 Feb 2016 | 19 Feb 2016 | 17 Jun 2016 | 0 | 119 | 1 | 120
A1-Flat-203 Window Box Flooring | 7.27 | Sft. | 16 Feb 2016 | 16 Feb 2016 | 21 Mar 2016 | 30 Mar 2016 | 0 | 9 | 34 | 43
A1-Flat-203 Umara Patti | 0 | Rft | 04 Apr 2016 | 04 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 71 | 95
A1-Flat-203 Flat Tiling (Lab) | 56695 | Sft. | 04 Feb 2016 | 19 Feb 2016 | 12 Feb 2016 | 13 Jul 2016 | 15 | 152 | 8 | 145
A1-FLAT-204 | 0 | No Unit | 06 Feb 2016 | 05 Apr 2016 |  |  | 59 | 0 | 0 | 0
A1-Flat-204 Common Toilet Dado | 172.56 | Sft. | 06 Feb 2016 | 08 Feb 2016 | 18 Jan 2016 | 25 Mar 2016 | 2 | 67 | 0 | 46
A1-Flat-204 Master Toilet Dado | 164.5 | Sft. | 06 Feb 2016 | 08 Feb 2016 | 18 Jan 2016 | 25 Mar 2016 | 2 | 67 | 0 | 46
A1-Flat-204 Kit. Dado Above | 68.5 | Sft. | 06 Feb 2016 | 08 Feb 2016 | 11 Jan 2016 | 25 Mar 2016 | 2 | 74 | 0 | 46
A1-Flat-204 Flat Flooring | 623.45 | Sft. | 13 Feb 2016 | 17 Feb 2016 | 15 Feb 2016 | 27 Mar 2016 | 4 | 41 | 2 | 39
A1-Flat-204 Flat Skirting | 196.8 | Rft | 20 Feb 2016 | 22 Feb 2016 | 15 Feb 2016 | 25 Mar 2016 | 2 | 39 | 0 | 32
A1-Flat-204 Common Toilet Flooring | 37.47 | Sft. | 09 Feb 2016 | 10 Feb 2016 | 18 Jan 2016 | 25 Mar 2016 | 1 | 67 | 0 | 44
A1-Flat-204 Master Toilet Flooring | 39.92 | Sft. | 09 Feb 2016 | 10 Feb 2016 | 18 Jan 2016 | 25 Mar 2016 | 1 | 67 | 0 | 44
A1-Flat-204 Sitout/Terrace Flooring | 62.26 | Sft. | 16 Feb 2016 | 17 Feb 2016 | 17 Feb 2016 | 27 Mar 2016 | 1 | 39 | 1 | 39
A1-Flat-204 Sitout/Terrace Skirting | 30 | Rft | 20 Feb 2016 | 20 Feb 2016 | 17 Feb 2016 | 27 Mar 2016 | 0 | 39 | 0 | 36
A1-Flat-204 Window Box Flooring | 7.27 | Sft. | 18 Feb 2016 | 18 Feb 2016 | 27 Feb 2016 | 25 Mar 2016 | 0 | 27 | 9 | 36
A1-Flat-204 Umara Patti | 0 | Rft | 05 Apr 2016 | 05 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 70 | 94
A1-Flat-204 Flat Tiling (Lab) | 56695 | Sft. | 06 Feb 2016 | 22 Feb 2016 | 12 Feb 2016 | 13 Jul 2016 | 16 | 152 | 6 | 142
A1-2ND FL.LOBBY | 0 | No Unit | 25 Feb 2016 | 27 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1-2nd Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 25 Feb 2016 | 27 Feb 2016 | 17 Apr 2016 | 17 Jun 2016 | 2 | 61 | 52 | 111
A1-2nd Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 25 Feb 2016 | 27 Feb 2016 | 17 Apr 2016 | 17 Jun 2016 | 2 | 61 | 52 | 111
A1-2nd Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 25 Feb 2016 | 27 Feb 2016 | 17 Apr 2016 | 27 Dec 2016 | 2 | 254 | 52 | 304
A1-2nd Fl.Lobby Misc. Material (White Cement) | 1 | NO | 25 Feb 2016 | 27 Feb 2016 | 17 Apr 2016 | 17 Jun 2016 | 2 | 61 | 52 | 111
A1-2ND FL MAIN STAIR | 343.15 | No Unit | 29 Feb 2016 | 01 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-2nd Fl Main Stair Main Staircase Flooring | 32 | Sft. | 29 Feb 2016 | 01 Mar 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 33 | 109
A1-2nd Fl Main Stair Main Staircase Riser | 76 | Rft | 29 Feb 2016 | 01 Mar 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 33 | 109
A1-2nd Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 29 Feb 2016 | 01 Mar 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 33 | 109
A1-2nd Fl Main Stair Main Staircase Tread | 76 | Sft. | 29 Feb 2016 | 01 Mar 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 33 | 109
A1-2nd Fl Main Stair Main Staircase (Lab) | 56695 | Sft. | 29 Feb 2016 | 01 Mar 2016 | 02 Apr 2016 | 30 Dec 2016 | 1 | 272 | 33 | 304
A1-2ND FL FIRE STAIR | 343.15 | No Unit | 29 Feb 2016 | 01 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-2nd Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 29 Feb 2016 | 01 Mar 2016 | 06 Apr 2016 | 18 Jun 2016 | 1 | 73 | 37 | 109
A1-2nd Fl Fire Stair Fire Staircase Riser | 95 | Rft | 29 Feb 2016 | 01 Mar 2016 | 06 Apr 2016 | 18 Jun 2016 | 1 | 73 | 37 | 109
A1-2nd Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 29 Feb 2016 | 01 Mar 2016 | 06 Apr 2016 | 18 Jun 2016 | 1 | 73 | 37 | 109
A1-2nd Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 29 Feb 2016 | 01 Mar 2016 | 06 Apr 2016 | 18 Jun 2016 | 1 | 73 | 37 | 109
A1-2nd Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 29 Feb 2016 | 01 Mar 2016 | 06 Apr 2016 | 30 Dec 2016 | 1 | 268 | 37 | 304
A1-2ND FL.LIFT CLADDING | 343.15 | No Unit | 02 Mar 2016 | 05 Mar 2016 |  |  | 3 | 0 | 0 | 0
A1-2nd Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 02 Mar 2016 | 05 Mar 2016 | 05 Jul 2016 | 30 Dec 2016 | 3 | 178 | 125 | 300
A1-2nd Fl.Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 02 Mar 2016 | 05 Mar 2016 | 21 Jul 2016 | 30 Dec 2016 | 3 | 162 | 141 | 300
A1-2nd Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 02 Mar 2016 | 05 Mar 2016 | 05 Jul 2016 | 08 Aug 2016 | 3 | 34 | 125 | 156
A1-3RD FLOOR | 0 | No Unit | 09 Feb 2016 | 09 Apr 2016 |  |  | 60 | 0 | 0 | 0
A1-FLAT-301 | 0 | No Unit | 09 Feb 2016 | 06 Apr 2016 |  |  | 57 | 0 | 0 | 0
A1-Flat-301 Common Toilet Dado | 172.56 | Sft. | 09 Feb 2016 | 10 Feb 2016 | 19 Jan 2016 | 25 Mar 2016 | 1 | 66 | 0 | 44
A1-Flat-301 Master Toilet Dado | 164.5 | Sft. | 09 Feb 2016 | 10 Feb 2016 | 19 Jan 2016 | 25 Mar 2016 | 1 | 66 | 0 | 44
A1-Flat-301 Kit. Dado Above | 63.39 | Sft. | 09 Feb 2016 | 10 Feb 2016 | 19 Jan 2016 | 25 Mar 2016 | 1 | 66 | 0 | 44
A1-Flat-301 Flat Flooring | 635.83 | Sft. | 16 Feb 2016 | 19 Feb 2016 | 17 Feb 2016 | 27 Mar 2016 | 3 | 39 | 1 | 37
A1-Flat-301 Flat Skirting | 204.04 | Rft | 23 Feb 2016 | 24 Feb 2016 | 17 Feb 2016 | 25 Mar 2016 | 1 | 37 | 0 | 30
A1-Flat-301 Common Toilet Flooring | 37.47 | Sft. | 11 Feb 2016 | 12 Feb 2016 | 21 Jan 2016 | 27 Mar 2016 | 1 | 66 | 0 | 44
A1-Flat-301 Master Toilet Flooring | 39.92 | Sft. | 11 Feb 2016 | 12 Feb 2016 | 21 Jan 2016 | 27 Mar 2016 | 1 | 66 | 0 | 44
A1-Flat-301 Sitout/Terrace Flooring | 48.62 | Sft. | 18 Feb 2016 | 19 Feb 2016 | 19 Feb 2016 | 27 Mar 2016 | 1 | 37 | 1 | 37
A1-Flat-301 Sitout/Terrace Skirting | 23 | Rft | 23 Feb 2016 | 23 Feb 2016 | 19 Feb 2016 | 27 Mar 2016 | 0 | 37 | 0 | 33
A1-Flat-301 Window Box Flooring | 14.53 | Sft. | 20 Feb 2016 | 20 Feb 2016 | 27 Feb 2016 | 27 Mar 2016 | 0 | 29 | 7 | 36
A1-Flat-301 Umara Patti | 0 | Rft | 06 Apr 2016 | 06 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 69 | 93
A1-Flat-301 Flat Tiling (Lab) | 56695 | Sft. | 09 Feb 2016 | 24 Feb 2016 | 12 Feb 2016 | 13 Jul 2016 | 15 | 152 | 3 | 140
A1-FLAT-302 | 0 | No Unit | 11 Feb 2016 | 07 Apr 2016 |  |  | 56 | 0 | 0 | 0
A1-Flat-302 Common Toilet Dado | 172.56 | Sft. | 11 Feb 2016 | 12 Feb 2016 | 02 Feb 2016 | 30 Mar 2016 | 1 | 57 | 0 | 47
A1-Flat-302 Master Toilet Dado | 164.5 | Sft. | 11 Feb 2016 | 12 Feb 2016 | 02 Feb 2016 | 30 Mar 2016 | 1 | 57 | 0 | 47
A1-Flat-302 Kit. Dado Above | 68.5 | Sft. | 11 Feb 2016 | 12 Feb 2016 | 19 Jan 2016 | 30 Mar 2016 | 1 | 71 | 0 | 47
A1-Flat-302 Flat Flooring | 629.31 | Sft. | 19 Feb 2016 | 23 Feb 2016 | 09 Mar 2016 | 17 Jun 2016 | 4 | 100 | 19 | 115
A1-Flat-302 Flat Skirting | 201.77 | Rft | 26 Feb 2016 | 27 Feb 2016 | 09 Mar 2016 | 17 Jun 2016 | 1 | 100 | 12 | 111
A1-Flat-302 Common Toilet Flooring | 37.47 | Sft. | 13 Feb 2016 | 15 Feb 2016 | 03 Feb 2016 | 30 Mar 2016 | 2 | 56 | 0 | 44
A1-Flat-302 Master Toilet Flooring | 39.92 | Sft. | 13 Feb 2016 | 15 Feb 2016 | 03 Feb 2016 | 30 Mar 2016 | 2 | 56 | 0 | 44
A1-Flat-302 Sitout/Terrace Flooring | 48.62 | Sft. | 22 Feb 2016 | 23 Feb 2016 | 14 Mar 2016 | 17 Jun 2016 | 1 | 95 | 21 | 115
A1-Flat-302 Sitout/Terrace Skirting | 23 | Rft | 26 Feb 2016 | 26 Feb 2016 | 14 Mar 2016 | 17 Jun 2016 | 0 | 95 | 17 | 112
A1-Flat-302 Window Box Flooring | 14.53 | Sft. | 24 Feb 2016 | 24 Feb 2016 | 09 May 2016 | 17 Jun 2016 | 0 | 39 | 75 | 114
A1-Flat-302 Umara Patti | 0 | Rft | 07 Apr 2016 | 07 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 68 | 92
A1-Flat-302 Flat Tiling (Lab) | 56695 | Sft. | 11 Feb 2016 | 26 Feb 2016 | 12 Feb 2016 | 13 Jul 2016 | 15 | 152 | 1 | 138
A1-FLAT-303 | 23 | No Unit | 13 Feb 2016 | 08 Apr 2016 |  |  | 55 | 0 | 0 | 0
A1-Flat-303 Common Toilet Dado | 172.56 | Sft. | 13 Feb 2016 | 15 Feb 2016 | 02 Feb 2016 | 30 Mar 2016 | 2 | 57 | 0 | 44
A1-Flat-303 Master Toilet Dado | 164.5 | Sft. | 13 Feb 2016 | 15 Feb 2016 | 02 Feb 2016 | 30 Mar 2016 | 2 | 57 | 0 | 44
A1-Flat-303 Kit. Dado Above | 68.5 | Sft. | 13 Feb 2016 | 15 Feb 2016 | 19 Jan 2016 | 30 Mar 2016 | 2 | 71 | 0 | 44
A1-Flat-303 Flat Flooring | 629.31 | Sft. | 22 Feb 2016 | 25 Feb 2016 | 18 Mar 2016 | 30 Mar 2016 | 3 | 12 | 25 | 34
A1-Flat-303 Flat Skirting | 201.77 | Rft | 29 Feb 2016 | 01 Mar 2016 | 18 Mar 2016 | 30 Mar 2016 | 1 | 12 | 18 | 29
A1-Flat-303 Common Toilet Flooring | 37.47 | Sft. | 16 Feb 2016 | 17 Feb 2016 | 03 Feb 2016 | 30 Mar 2016 | 1 | 56 | 0 | 42
A1-Flat-303 Master Toilet Flooring | 39.92 | Sft. | 16 Feb 2016 | 17 Feb 2016 | 03 Feb 2016 | 30 Mar 2016 | 1 | 56 | 0 | 42
A1-Flat-303 Sitout/Terrace Flooring | 76.33 | Sft. | 24 Feb 2016 | 25 Feb 2016 | 21 Mar 2016 | 17 Jun 2016 | 1 | 88 | 26 | 113
A1-Flat-303 Sitout/Terrace Skirting | 31 | Rft | 29 Feb 2016 | 29 Feb 2016 | 21 Mar 2016 | 30 Mar 2016 | 0 | 9 | 21 | 30
A1-Flat-303 Window Box Flooring | 14.53 | Sft. | 26 Feb 2016 | 26 Feb 2016 | 21 Mar 2016 | 30 Mar 2016 | 0 | 9 | 24 | 33
A1-Flat-303 Umara Patti | 0 | Rft | 08 Apr 2016 | 08 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 67 | 91
A1-Flat-303 Flat Tiling (Lab) | 56695 | Sft. | 13 Feb 2016 | 12 Mar 2016 | 12 Feb 2016 | 13 Jul 2016 | 28 | 152 | 0 | 123
A1-FLAT-304 | 0 | No Unit | 16 Feb 2016 | 09 Apr 2016 |  |  | 53 | 0 | 0 | 0
A1-Flat-304 Common Toilet Dado | 172.56 | Sft. | 16 Feb 2016 | 17 Feb 2016 | 19 Jan 2016 | 25 Mar 2016 | 1 | 66 | 0 | 37
A1-Flat-304 Master Toilet Dado | 164.5 | Sft. | 16 Feb 2016 | 17 Feb 2016 | 19 Jan 2016 | 27 Mar 2016 | 1 | 68 | 0 | 39
A1-Flat-304 Kit. Dado Above | 68.5 | Sft. | 16 Feb 2016 | 17 Feb 2016 | 19 Jan 2016 | 25 Mar 2016 | 1 | 66 | 0 | 37
A1-Flat-304 Flat Flooring | 629.31 | Sft. | 24 Feb 2016 | 29 Feb 2016 | 17 Feb 2016 | 25 Mar 2016 | 5 | 37 | 0 | 25
A1-Flat-304 Flat Skirting | 201.77 | Rft | 03 Mar 2016 | 04 Mar 2016 | 17 Feb 2016 | 27 Mar 2016 | 1 | 39 | 0 | 23
A1-Flat-304 Common Toilet Flooring | 37.47 | Sft. | 18 Feb 2016 | 19 Feb 2016 | 21 Jan 2016 | 27 Mar 2016 | 1 | 66 | 0 | 37
A1-Flat-304 Master Toilet Flooring | 39.92 | Sft. | 18 Feb 2016 | 19 Feb 2016 | 21 Jan 2016 | 27 Mar 2016 | 1 | 66 | 0 | 37
A1-Flat-304 Sitout/Terrace Flooring | 76.33 | Sft. | 26 Feb 2016 | 27 Feb 2016 | 19 Feb 2016 | 27 Mar 2016 | 1 | 37 | 0 | 29
A1-Flat-304 Sitout/Terrace Skirting | 31 | Rft | 03 Mar 2016 | 03 Mar 2016 | 19 Feb 2016 | 27 Mar 2016 | 0 | 37 | 0 | 24
A1-Flat-304 Window Box Flooring | 14.53 | Sft. | 01 Mar 2016 | 01 Mar 2016 | 27 Feb 2016 | 25 Mar 2016 | 0 | 27 | 0 | 24
A1-Flat-304 Umara Patti | 0 | Rft | 09 Apr 2016 | 09 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 66 | 90
A1-Flat-304 Flat Tiling (Lab) | 56695 | Sft. | 16 Feb 2016 | 15 Mar 2016 | 12 Feb 2016 | 13 Jul 2016 | 28 | 152 | 0 | 120
A1-3RD FL.LOBBY | 0 | No Unit | 08 Mar 2016 | 10 Mar 2016 |  |  | 2 | 0 | 0 | 0
A1-3rd Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 08 Mar 2016 | 10 Mar 2016 | 22 Apr 2016 | 17 Jun 2016 | 2 | 56 | 45 | 99
A1-3rd Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 08 Mar 2016 | 10 Mar 2016 | 22 Apr 2016 | 17 Jun 2016 | 2 | 56 | 45 | 99
A1-3rd Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 08 Mar 2016 | 10 Mar 2016 | 22 Apr 2016 | 27 Dec 2016 | 2 | 249 | 45 | 292
A1-3rd Fl.Lobby Misc. Material (White Cement) | 1 | NO | 08 Mar 2016 | 10 Mar 2016 | 22 Apr 2016 | 17 Jun 2016 | 2 | 56 | 45 | 99
A1-3RD FL MAIN STAIR | 343.15 | No Unit | 11 Mar 2016 | 12 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-3rd Fl Main Stair Main Staircase Flooring | 32 | Sft. | 11 Mar 2016 | 12 Mar 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 22 | 98
A1-3rd Fl Main Stair Main Staircase Riser | 76 | Rft | 11 Mar 2016 | 12 Mar 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 22 | 98
A1-3rd Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 11 Mar 2016 | 12 Mar 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 22 | 98
A1-3rd Fl Main Stair Main Staircase Tread | 76 | Sft. | 11 Mar 2016 | 12 Mar 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 22 | 98
A1-3rd Fl Main Stair Main Staircase (Lab) | 56695 | Sft. | 11 Mar 2016 | 12 Mar 2016 | 02 Apr 2016 | 30 Dec 2016 | 1 | 272 | 22 | 293
A1-3RD FL FIRE STAIR | 343.15 | No Unit | 11 Mar 2016 | 12 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-3rd Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 11 Mar 2016 | 12 Mar 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 22 | 98
A1-3rd Fl Fire Stair Fire Staircase Riser | 95 | Rft | 11 Mar 2016 | 12 Mar 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 22 | 98
A1-3rd Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 11 Mar 2016 | 12 Mar 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 22 | 98
A1-3rd Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 11 Mar 2016 | 12 Mar 2016 | 02 Apr 2016 | 18 Jun 2016 | 1 | 77 | 22 | 98
A1-3rd Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 11 Mar 2016 | 12 Mar 2016 | 02 Apr 2016 | 30 Dec 2016 | 1 | 272 | 22 | 293
A1-3RD FL.LIFT CLADDING | 343.15 | No Unit | 14 Mar 2016 | 18 Mar 2016 |  |  | 4 | 0 | 0 | 0
A1-3rd Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 14 Mar 2016 | 18 Mar 2016 | 14 Jul 2016 | 30 Dec 2016 | 4 | 169 | 122 | 287
A1-3rd Fl.Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 14 Mar 2016 | 18 Mar 2016 | 21 Jul 2016 | 30 Dec 2016 | 4 | 162 | 129 | 287
A1-3rd Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 14 Mar 2016 | 18 Mar 2016 | 14 Jul 2016 | 08 Aug 2016 | 4 | 25 | 122 | 143
A1-4TH FLOOR | 0 | No Unit | 18 Feb 2016 | 14 Apr 2016 |  |  | 56 | 0 | 0 | 0
A1-FLAT-401 | 0 | No Unit | 18 Feb 2016 | 11 Apr 2016 |  |  | 53 | 0 | 0 | 0
A1-Flat-401 Common Toilet Dado | 172.56 | Sft. | 18 Feb 2016 | 19 Feb 2016 | 22 Jan 2016 | 27 Mar 2016 | 1 | 65 | 0 | 37
A1-Flat-401 Master Toilet Dado | 164.5 | Sft. | 18 Feb 2016 | 19 Feb 2016 | 22 Jan 2016 | 27 Mar 2016 | 1 | 65 | 0 | 37
A1-Flat-401 Kit. Dado Above | 63.39 | Sft. | 18 Feb 2016 | 19 Feb 2016 | 25 Jan 2016 | 27 Mar 2016 | 1 | 62 | 0 | 37
A1-Flat-401 Flat Flooring | 630.02 | Sft. | 26 Feb 2016 | 02 Mar 2016 | 22 Feb 2016 | 27 Mar 2016 | 5 | 34 | 0 | 25
A1-Flat-401 Flat Skirting | 199.06 | Rft | 05 Mar 2016 | 08 Mar 2016 | 22 Feb 2016 | 27 Mar 2016 | 3 | 34 | 0 | 19
A1-Flat-401 Common Toilet Flooring | 37.47 | Sft. | 20 Feb 2016 | 22 Feb 2016 | 28 Jan 2016 | 27 Mar 2016 | 2 | 59 | 0 | 34
A1-Flat-401 Master Toilet Flooring | 39.92 | Sft. | 20 Feb 2016 | 22 Feb 2016 | 28 Jan 2016 | 27 Mar 2016 | 2 | 59 | 0 | 34
A1-Flat-401 Sitout/Terrace Flooring | 125.06 | Sft. | 01 Mar 2016 | 02 Mar 2016 | 27 Feb 2016 | 27 Mar 2016 | 1 | 29 | 0 | 25
A1-Flat-401 Sitout/Terrace Skirting | 59 | Rft | 05 Mar 2016 | 05 Mar 2016 | 27 Feb 2016 | 27 Mar 2016 | 0 | 29 | 0 | 22
A1-Flat-401 Window Box Flooring | 7.27 | Sft. | 03 Mar 2016 | 03 Mar 2016 | 03 Mar 2016 | 17 Jun 2016 | 0 | 106 | 0 | 106
A1-Flat-401 Umara Patti | 0 | Rft | 11 Apr 2016 | 11 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 64 | 88
A1-Flat-401 Flat Tiling (Lab) | 56695 | Sft. | 18 Feb 2016 | 17 Mar 2016 | 12 Feb 2016 | 13 Jul 2016 | 28 | 152 | 0 | 118
A1-FLAT-402 | 0 | No Unit | 23 Feb 2016 | 12 Apr 2016 |  |  | 49 | 0 | 0 | 0
A1-Flat-402 Common Toilet Dado | 172.56 | Sft. | 23 Feb 2016 | 24 Feb 2016 | 04 Feb 2016 | 30 Mar 2016 | 1 | 55 | 0 | 35
A1-Flat-402 Master Toilet Dado | 164.5 | Sft. | 25 Feb 2016 | 26 Feb 2016 | 04 Feb 2016 | 30 Mar 2016 | 1 | 55 | 0 | 33
A1-Flat-402 Kit. Dado Above | 68.5 | Sft. | 27 Feb 2016 | 29 Feb 2016 | 25 Jan 2016 | 30 Mar 2016 | 2 | 65 | 0 | 30
A1-Flat-402 Flat Flooring | 623.45 | Sft. | 09 Mar 2016 | 14 Mar 2016 | 11 Mar 2016 | 30 Mar 2016 | 5 | 19 | 2 | 16
A1-Flat-402 Flat Skirting | 196.8 | Rft | 18 Mar 2016 | 19 Mar 2016 | 11 Mar 2016 | 30 Mar 2016 | 1 | 19 | 0 | 11
A1-Flat-402 Common Toilet Flooring | 37.47 | Sft. | 25 Feb 2016 | 26 Feb 2016 | 06 Feb 2016 | 30 Mar 2016 | 1 | 53 | 0 | 33
A1-Flat-402 Master Toilet Flooring | 39.92 | Sft. | 27 Feb 2016 | 29 Feb 2016 | 06 Feb 2016 | 30 Mar 2016 | 2 | 53 | 0 | 30
A1-Flat-402 Sitout/Terrace Flooring | 125.06 | Sft. | 12 Mar 2016 | 14 Mar 2016 | 16 Mar 2016 | 17 Jun 2016 | 2 | 93 | 4 | 95
A1-Flat-402 Sitout/Terrace Skirting | 59 | Rft | 18 Mar 2016 | 18 Mar 2016 | 16 Mar 2016 | 30 Mar 2016 | 0 | 14 | 0 | 12
A1-Flat-402 Window Box Flooring | 7.27 | Sft. | 15 Mar 2016 | 15 Mar 2016 | 09 May 2016 | 17 Jun 2016 | 0 | 39 | 55 | 94
A1-Flat-402 Umara Patti | 0 | Rft | 12 Apr 2016 | 12 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 63 | 87
A1-Flat-402 Flat Tiling (Lab) | 56695 | Sft. | 23 Feb 2016 | 22 Mar 2016 | 12 Feb 2016 | 13 Jul 2016 | 28 | 152 | 0 | 113
A1-FLAT-403 | 0 | No Unit | 01 Mar 2016 | 13 Apr 2016 |  |  | 43 | 0 | 0 | 0
A1-Flat-403 Common Toilet Dado | 172.56 | Sft. | 01 Mar 2016 | 02 Mar 2016 | 04 Feb 2016 | 30 Mar 2016 | 1 | 55 | 0 | 28
A1-Flat-403 Master Toilet Dado | 164.5 | Sft. | 03 Mar 2016 | 04 Mar 2016 | 04 Feb 2016 | 30 Mar 2016 | 1 | 55 | 0 | 26
A1-Flat-403 Kit. Dado Above | 68.5 | Sft. | 05 Mar 2016 | 08 Mar 2016 | 25 Jan 2016 | 30 Mar 2016 | 3 | 65 | 0 | 22
A1-Flat-403 Flat Flooring | 623.45 | Sft. | 16 Mar 2016 | 21 Mar 2016 | 21 Mar 2016 | 30 Mar 2016 | 5 | 9 | 5 | 9
A1-Flat-403 Flat Skirting | 196.8 | Rft | 25 Mar 2016 | 26 Mar 2016 | 21 Mar 2016 | 30 Mar 2016 | 1 | 9 | 0 | 4
A1-Flat-403 Common Toilet Flooring | 37.47 | Sft. | 03 Mar 2016 | 04 Mar 2016 | 06 Feb 2016 | 30 Mar 2016 | 1 | 53 | 0 | 26
A1-Flat-403 Master Toilet Flooring | 39.92 | Sft. | 05 Mar 2016 | 08 Mar 2016 | 06 Feb 2016 | 30 Mar 2016 | 3 | 53 | 0 | 22
A1-Flat-403 Sitout/Terrace Flooring | 62.26 | Sft. | 19 Mar 2016 | 21 Mar 2016 | 29 Mar 2016 | 17 Jun 2016 | 2 | 80 | 10 | 88
A1-Flat-403 Sitout/Terrace Skirting | 30 | Rft | 25 Mar 2016 | 25 Mar 2016 | 29 Mar 2016 | 17 Jun 2016 | 0 | 80 | 4 | 84
A1-Flat-403 Window Box Flooring | 7.27 | Sft. | 22 Mar 2016 | 22 Mar 2016 | 09 May 2016 | 17 Jun 2016 | 0 | 39 | 48 | 87
A1-Flat-403 Umara Patti | 0 | Rft | 13 Apr 2016 | 13 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 62 | 86
A1-Flat-403 Flat Tiling (Lab) | 56695 | Sft. | 01 Mar 2016 | 29 Mar 2016 | 12 Feb 2016 | 13 Jul 2016 | 28 | 152 | 0 | 106
A1-FLAT-404 | 0 | No Unit | 09 Mar 2016 | 14 Apr 2016 |  |  | 36 | 0 | 0 | 0
A1-Flat-404 Common Toilet Dado | 172.56 | Sft. | 09 Mar 2016 | 10 Mar 2016 | 22 Jan 2016 | 27 Mar 2016 | 1 | 65 | 0 | 17
A1-Flat-404 Master Toilet Dado | 164.5 | Sft. | 11 Mar 2016 | 12 Mar 2016 | 22 Jan 2016 | 27 Mar 2016 | 1 | 65 | 0 | 15
A1-Flat-404 Kit. Dado Above | 68.5 | Sft. | 14 Mar 2016 | 15 Mar 2016 | 25 Jan 2016 | 25 Mar 2016 | 1 | 60 | 0 | 10
A1-Flat-404 Flat Flooring | 623.45 | Sft. | 23 Mar 2016 | 28 Mar 2016 | 22 Feb 2016 | 27 Mar 2016 | 5 | 34 | 0 | 0
A1-Flat-404 Flat Skirting | 196.8 | Rft | 01 Apr 2016 | 02 Apr 2016 | 22 Feb 2016 | 27 Mar 2016 | 1 | 34 | 0 | 0
A1-Flat-404 Common Toilet Flooring | 37.47 | Sft. | 11 Mar 2016 | 12 Mar 2016 | 28 Jan 2016 | 27 Mar 2016 | 1 | 59 | 0 | 15
A1-Flat-404 Master Toilet Flooring | 39.92 | Sft. | 14 Mar 2016 | 15 Mar 2016 | 28 Jan 2016 | 27 Mar 2016 | 1 | 59 | 0 | 12
A1-Flat-404 Sitout/Terrace Flooring | 62.26 | Sft. | 26 Mar 2016 | 28 Mar 2016 | 29 Feb 2016 | 27 Mar 2016 | 2 | 27 | 0 | 0
A1-Flat-404 Sitout/Terrace Skirting | 30 | Rft | 01 Apr 2016 | 01 Apr 2016 | 29 Feb 2016 | 27 Mar 2016 | 0 | 27 | 0 | 0
A1-Flat-404 Window Box Flooring | 7.27 | Sft. | 29 Mar 2016 | 29 Mar 2016 | 03 Mar 2016 | 25 Mar 2016 | 0 | 22 | 0 | 0
A1-Flat-404 Umara Patti | 0 | Rft | 14 Apr 2016 | 14 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 61 | 85
A1-Flat-404 Flat Tiling (Lab) | 56695 | Sft. | 09 Mar 2016 | 05 Apr 2016 | 12 Feb 2016 | 13 Jul 2016 | 27 | 152 | 0 | 99
A1-4TH FL.LOBBY | 0 | No Unit | 19 Mar 2016 | 22 Mar 2016 |  |  | 3 | 0 | 0 | 0
A1-4th Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 19 Mar 2016 | 22 Mar 2016 | 22 Apr 2016 | 17 Jun 2016 | 3 | 56 | 34 | 87
A1-4th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 19 Mar 2016 | 22 Mar 2016 | 22 Apr 2016 | 17 Jun 2016 | 3 | 56 | 34 | 87
A1-4th Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 19 Mar 2016 | 22 Mar 2016 | 22 Apr 2016 | 27 Dec 2016 | 3 | 249 | 34 | 280
A1-4th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 19 Mar 2016 | 22 Mar 2016 | 22 Apr 2016 | 17 Jun 2016 | 3 | 56 | 34 | 87
A1-4TH FL MAIN STAIR | 343.15 | No Unit | 23 Mar 2016 | 24 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-4th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 23 Mar 2016 | 24 Mar 2016 | 09 Apr 2016 | 18 Jun 2016 | 1 | 70 | 17 | 86
A1-4th Fl Main Stair Main Staircase Riser | 76 | Rft | 23 Mar 2016 | 24 Mar 2016 | 09 Apr 2016 | 18 Jun 2016 | 1 | 70 | 17 | 86
A1-4th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 23 Mar 2016 | 24 Mar 2016 | 09 Apr 2016 | 18 Jun 2016 | 1 | 70 | 17 | 86
A1-4th Fl Main Stair Main Staircase Tread | 76 | Sft. | 23 Mar 2016 | 24 Mar 2016 | 09 Apr 2016 | 18 Jun 2016 | 1 | 70 | 17 | 86
A1-4th Fl Main Stair Main Staircase (Lab) | 56695 | Sft. | 23 Mar 2016 | 24 Mar 2016 | 09 Apr 2016 | 30 Dec 2016 | 1 | 265 | 17 | 281
A1-4TH FL FIRE STAIR | 343.15 | No Unit | 23 Mar 2016 | 24 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-4th Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 23 Mar 2016 | 24 Mar 2016 | 09 Apr 2016 | 18 Jun 2016 | 1 | 70 | 17 | 86
A1-4th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 23 Mar 2016 | 24 Mar 2016 | 09 Apr 2016 | 18 Jun 2016 | 1 | 70 | 17 | 86
A1-4th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 23 Mar 2016 | 24 Mar 2016 | 09 Apr 2016 | 18 Jun 2016 | 1 | 70 | 17 | 86
A1-4th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 23 Mar 2016 | 24 Mar 2016 | 09 Apr 2016 | 18 Jun 2016 | 1 | 70 | 17 | 86
A1-4th Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 23 Mar 2016 | 24 Mar 2016 | 09 Apr 2016 | 30 Dec 2016 | 1 | 265 | 17 | 281
A1-4TH FL.LIFT CLADDING | 343.15 | No Unit | 25 Mar 2016 | 29 Mar 2016 |  |  | 4 | 0 | 0 | 0
A1-4th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 25 Mar 2016 | 29 Mar 2016 | 14 Jul 2016 | 30 Dec 2016 | 4 | 169 | 111 | 276
A1-4th Fl.Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 25 Mar 2016 | 29 Mar 2016 | 21 Jul 2016 | 30 Dec 2016 | 4 | 162 | 118 | 276
A1-4th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 25 Mar 2016 | 29 Mar 2016 | 14 Jul 2016 | 08 Aug 2016 | 4 | 25 | 111 | 132
A1-5TH FLOOR | 0 | No Unit | 16 Mar 2016 | 03 May 2016 |  |  | 48 | 0 | 0 | 0
A1-FLAT-501 | 0 | No Unit | 16 Mar 2016 | 15 Apr 2016 |  |  | 30 | 0 | 0 | 0
A1-Flat-501 Common Toilet Dado | 172.56 | Sft. | 16 Mar 2016 | 17 Mar 2016 | 25 Jan 2016 | 30 Mar 2016 | 1 | 65 | 0 | 13
A1-Flat-501 Master Toilet Dado | 164.5 | Sft. | 18 Mar 2016 | 19 Mar 2016 | 25 Jan 2016 | 30 Mar 2016 | 1 | 65 | 0 | 11
A1-Flat-501 Kit. Dado Above | 63.39 | Sft. | 21 Mar 2016 | 22 Mar 2016 | 28 Jan 2016 | 30 Mar 2016 | 1 | 62 | 0 | 8
A1-Flat-501 Flat Flooring | 635.83 | Sft. | 30 Mar 2016 | 04 Apr 2016 | 26 Feb 2016 | 30 Mar 2016 | 5 | 33 | 0 | 0
A1-Flat-501 Flat Skirting | 204.04 | Rft | 08 Apr 2016 | 09 Apr 2016 | 26 Feb 2016 | 30 Mar 2016 | 1 | 33 | 0 | 0
A1-Flat-501 Common Toilet Flooring | 37.47 | Sft. | 18 Mar 2016 | 19 Mar 2016 | 01 Feb 2016 | 30 Mar 2016 | 1 | 58 | 0 | 11
A1-Flat-501 Master Toilet Flooring | 39.92 | Sft. | 21 Mar 2016 | 22 Mar 2016 | 01 Feb 2016 | 30 Mar 2016 | 1 | 58 | 0 | 8
A1-Flat-501 Sitout/Terrace Flooring | 48.62 | Sft. | 02 Apr 2016 | 04 Apr 2016 | 03 Mar 2016 | 17 Jun 2016 | 2 | 106 | 0 | 74
A1-Flat-501 Sitout/Terrace Skirting | 23 | Rft | 08 Apr 2016 | 08 Apr 2016 | 03 Mar 2016 | 30 Mar 2016 | 0 | 27 | 0 | 0
A1-Flat-501 Window Box Flooring | 14.53 | Sft. | 05 Apr 2016 | 05 Apr 2016 | 16 Mar 2016 | 30 Mar 2016 | 0 | 14 | 0 | 0
A1-Flat-501 Umara Patti | 0 | Rft | 15 Apr 2016 | 15 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 60 | 84
A1-Flat-501 Flat Tiling (Lab) | 56695 | Sft. | 16 Mar 2016 | 12 Apr 2016 | 30 Mar 2016 | 13 Jul 2016 | 27 | 105 | 14 | 92
A1-FLAT-502 | 0 | No Unit | 23 Mar 2016 | 03 May 2016 |  |  | 41 | 0 | 0 | 0
A1-Flat-502 Common Toilet Dado | 172.56 | Sft. | 23 Mar 2016 | 24 Mar 2016 | 30 Jan 2016 | 30 Mar 2016 | 1 | 60 | 0 | 6
A1-Flat-502 Master Toilet Dado | 164.5 | Sft. | 25 Mar 2016 | 26 Mar 2016 | 30 Jan 2016 | 30 Mar 2016 | 1 | 60 | 0 | 4
A1-Flat-502 Kit. Dado Above | 68.5 | Sft. | 28 Mar 2016 | 29 Mar 2016 | 28 Jan 2016 | 30 Mar 2016 | 1 | 62 | 0 | 1
A1-Flat-502 Flat Flooring | 629.31 | Sft. | 06 Apr 2016 | 11 Apr 2016 | 14 Mar 2016 | 30 Mar 2016 | 5 | 16 | 0 | 0
A1-Flat-502 Flat Skirting | 201.77 | Rft | 15 Apr 2016 | 16 Apr 2016 | 14 Mar 2016 | 30 Mar 2016 | 1 | 16 | 0 | 0
A1-Flat-502 Common Toilet Flooring | 37.47 | Sft. | 25 Mar 2016 | 26 Mar 2016 | 30 Jan 2016 | 30 Mar 2016 | 1 | 60 | 0 | 4
A1-Flat-502 Master Toilet Flooring | 39.92 | Sft. | 28 Mar 2016 | 29 Mar 2016 | 30 Jan 2016 | 30 Mar 2016 | 1 | 60 | 0 | 1
A1-Flat-502 Sitout/Terrace Flooring | 48.62 | Sft. | 09 Apr 2016 | 11 Apr 2016 | 18 Mar 2016 | 17 Jun 2016 | 2 | 91 | 0 | 67
A1-Flat-502 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2016 | 15 Apr 2016 | 18 Mar 2016 | 30 Mar 2016 | 0 | 12 | 0 | 0
A1-Flat-502 Window Box Flooring | 14.53 | Sft. | 12 Apr 2016 | 12 Apr 2016 | 21 Mar 2016 | 17 Jun 2016 | 0 | 88 | 0 | 66
A1-Flat-502 Umara Patti | 0 | Rft | 16 Apr 2016 | 16 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 59 | 83
A1-Flat-502 Flat Tiling (Lab) | 56695 | Sft. | 06 Apr 2016 | 03 May 2016 | 30 Mar 2016 | 13 Jul 2016 | 27 | 105 | 0 | 71
A1-FLAT-503 | 23 | No Unit | 30 Mar 2016 | 26 Apr 2016 |  |  | 27 | 0 | 0 | 0
A1-Flat-503 Common Toilet Dado | 172.56 | Sft. | 30 Mar 2016 | 31 Mar 2016 | 30 Jan 2016 | 30 Mar 2016 | 1 | 60 | 0 | 0
A1-Flat-503 Master Toilet Dado | 164.5 | Sft. | 01 Apr 2016 | 02 Apr 2016 | 30 Jan 2016 | 30 Mar 2016 | 1 | 60 | 0 | 0
A1-Flat-503 Kit. Dado Above | 68.5 | Sft. | 04 Apr 2016 | 05 Apr 2016 | 28 Jan 2016 | 30 Mar 2016 | 1 | 62 | 0 | 0
A1-Flat-503 Flat Flooring | 629.31 | Sft. | 13 Apr 2016 | 18 Apr 2016 | 28 Mar 2016 | 17 Jun 2016 | 5 | 81 | 0 | 60
A1-Flat-503 Flat Skirting | 201.77 | Rft | 22 Apr 2016 | 23 Apr 2016 | 28 Mar 2016 | 17 Jun 2016 | 1 | 81 | 0 | 55
A1-Flat-503 Common Toilet Flooring | 37.47 | Sft. | 01 Apr 2016 | 02 Apr 2016 | 30 Jan 2016 | 30 Mar 2016 | 1 | 60 | 0 | 0
A1-Flat-503 Master Toilet Flooring | 39.92 | Sft. | 04 Apr 2016 | 05 Apr 2016 | 30 Jan 2016 | 30 Mar 2016 | 1 | 60 | 0 | 0
A1-Flat-503 Sitout/Terrace Flooring | 76.33 | Sft. | 16 Apr 2016 | 18 Apr 2016 | 30 Mar 2016 | 17 Jun 2016 | 2 | 79 | 0 | 60
A1-Flat-503 Sitout/Terrace Skirting | 31 | Rft | 22 Apr 2016 | 22 Apr 2016 | 30 Mar 2016 | 17 Jun 2016 | 0 | 79 | 0 | 56
A1-Flat-503 Window Box Flooring | 14.53 | Sft. | 19 Apr 2016 | 19 Apr 2016 | 30 Mar 2016 | 17 Jun 2016 | 0 | 79 | 0 | 59
A1-Flat-503 Umara Patti | 0 | Rft | 18 Apr 2016 | 18 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 57 | 81
A1-Flat-503 Flat Tiling (Lab) | 56695 | Sft. | 30 Mar 2016 | 26 Apr 2016 | 30 Mar 2016 | 13 Jul 2016 | 27 | 105 | 0 | 78
A1-FLAT-504 | 0 | No Unit | 06 Apr 2016 | 03 May 2016 |  |  | 27 | 0 | 0 | 0
A1-Flat-504 Common Toilet Dado | 172.56 | Sft. | 06 Apr 2016 | 07 Apr 2016 | 25 Jan 2016 | 30 Mar 2016 | 1 | 65 | 0 | 0
A1-Flat-504 Master Toilet Dado | 164.5 | Sft. | 08 Apr 2016 | 09 Apr 2016 | 25 Jan 2016 | 30 Mar 2016 | 1 | 65 | 0 | 0
A1-Flat-504 Kit. Dado Above | 68.5 | Sft. | 11 Apr 2016 | 12 Apr 2016 | 28 Jan 2016 | 30 Mar 2016 | 1 | 62 | 0 | 0
A1-Flat-504 Flat Flooring | 629.31 | Sft. | 20 Apr 2016 | 25 Apr 2016 | 26 Feb 2016 | 30 Mar 2016 | 5 | 33 | 0 | 0
A1-Flat-504 Flat Skirting | 201.77 | Rft | 29 Apr 2016 | 30 Apr 2016 | 26 Feb 2016 | 30 Mar 2016 | 1 | 33 | 0 | 0
A1-Flat-504 Common Toilet Flooring | 37.47 | Sft. | 08 Apr 2016 | 09 Apr 2016 | 01 Feb 2016 | 30 Mar 2016 | 1 | 58 | 0 | 0
A1-Flat-504 Master Toilet Flooring | 39.92 | Sft. | 11 Apr 2016 | 12 Apr 2016 | 01 Feb 2016 | 30 Mar 2016 | 1 | 58 | 0 | 0
A1-Flat-504 Sitout/Terrace Flooring | 76.33 | Sft. | 23 Apr 2016 | 25 Apr 2016 | 03 Mar 2016 | 30 Mar 2016 | 2 | 27 | 0 | 0
A1-Flat-504 Sitout/Terrace Skirting | 31 | Rft | 29 Apr 2016 | 29 Apr 2016 | 03 Mar 2016 | 17 Jun 2016 | 0 | 106 | 0 | 49
A1-Flat-504 Window Box Flooring | 14.53 | Sft. | 26 Apr 2016 | 26 Apr 2016 | 16 Mar 2016 | 30 Mar 2016 | 0 | 14 | 0 | 0
A1-Flat-504 Umara Patti | 0 | Rft | 19 Apr 2016 | 19 Apr 2016 | 14 Jun 2016 | 08 Jul 2016 | 0 | 24 | 56 | 80
A1-Flat-504 Flat Tiling (Lab) | 56695 | Sft. | 06 Apr 2016 | 03 May 2016 | 30 Mar 2016 | 13 Jul 2016 | 27 | 105 | 0 | 71
A1-5TH FL.LOBBY | 0 | No Unit | 30 Mar 2016 | 01 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1-5th Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 30 Mar 2016 | 01 Apr 2016 | 27 Apr 2016 | 17 Jun 2016 | 2 | 51 | 28 | 77
A1-5th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 30 Mar 2016 | 01 Apr 2016 | 27 Apr 2016 | 17 Jun 2016 | 2 | 51 | 28 | 77
A1-5th Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 30 Mar 2016 | 01 Apr 2016 | 27 Apr 2016 | 27 Dec 2016 | 2 | 244 | 28 | 270
A1-5th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 30 Mar 2016 | 01 Apr 2016 | 27 Apr 2016 | 17 Jun 2016 | 2 | 51 | 28 | 77
A1-5TH FL MAIN STAIR | 343.15 | No Unit | 02 Apr 2016 | 04 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1-5th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 02 Apr 2016 | 04 Apr 2016 | 09 Apr 2016 | 18 Jun 2016 | 2 | 70 | 7 | 75