## Task Details637397344604532297_
Task Details
Project Name : A SAMPLE PROJECT 3
Task Name : CONSTRUCTION
Total Records: 13876 Records 2001 to 4000
Page 2 of 7
Task (1) | Qty (2) | Unit (3) | Planned Start (4) | Planned Finish (5) | Actual Start (6) | Actual Finish (7) | Planned Duration (8)=(4)-(5) Days | Actual Duration (9)=(6)-(7) Days | Start Variance (10)=(4)-(6) Days | Finish Variance (11)=(4)-(5) Days | Remark
A1-5th Fl Main Stair Main Staircase Riser | 76 | Rft | 02 Apr 2016 | 04 Apr 2016 | 09 Apr 2016 | 18 Jun 2016 | 2 | 70 | 7 | 75
A1-5th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 02 Apr 2016 | 04 Apr 2016 | 09 Apr 2016 | 18 Jun 2016 | 2 | 70 | 7 | 75
A1-5th Fl Main Stair Main Staircase Tread | 76 | Sft. | 02 Apr 2016 | 04 Apr 2016 | 09 Apr 2016 | 18 Jun 2016 | 2 | 70 | 7 | 75
A1-5th Fl Main Stair Main Staircase (Lab) | 56695 | Sft. | 02 Apr 2016 | 04 Apr 2016 | 09 Apr 2016 | 30 Dec 2016 | 2 | 265 | 7 | 270
A1-5TH FL FIRE STAIR | 343.15 | No Unit | 02 Apr 2016 | 04 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1-5th Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 02 Apr 2016 | 04 Apr 2016 | 09 Apr 2016 | 18 Jun 2016 | 2 | 70 | 7 | 75
A1-5th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 02 Apr 2016 | 04 Apr 2016 | 09 Apr 2016 | 18 Jun 2016 | 2 | 70 | 7 | 75
A1-5th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 02 Apr 2016 | 04 Apr 2016 | 09 Apr 2016 | 18 Jun 2016 | 2 | 70 | 7 | 75
A1-5th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 02 Apr 2016 | 04 Apr 2016 | 09 Apr 2016 | 18 Jun 2016 | 2 | 70 | 7 | 75
A1-5th Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 02 Apr 2016 | 04 Apr 2016 | 09 Apr 2016 | 30 Dec 2016 | 2 | 265 | 7 | 270
A1-5TH FL.LIFT CLADDING | 343.15 | No Unit | 05 Apr 2016 | 08 Apr 2016 |  |  | 3 | 0 | 0 | 0
A1-5th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 05 Apr 2016 | 08 Apr 2016 | 19 Jul 2016 | 30 Dec 2016 | 3 | 164 | 105 | 266
A1-5th Fl.Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 05 Apr 2016 | 08 Apr 2016 | 21 Jul 2016 | 30 Dec 2016 | 3 | 162 | 107 | 266
A1-5th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 05 Apr 2016 | 08 Apr 2016 | 19 Jul 2016 | 08 Aug 2016 | 3 | 20 | 105 | 122
A1-6TH FLOOR | 44 | No Unit | 11 Apr 2016 | 07 May 2016 |  |  | 26 | 0 | 0 | 0
A1-FLAT-601 | 0 | No Unit | 11 Apr 2016 | 07 May 2016 |  |  | 26 | 0 | 0 | 0
A1-Flat-601 Common Toilet Dado | 172.56 | Sft. | 11 Apr 2016 | 12 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 115 | 114
A1-Flat-601 Master Toilet Dado | 164.5 | Sft. | 11 Apr 2016 | 12 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 115 | 114
A1-Flat-601 Kit. Dado Above | 63.39 | Sft. | 11 Apr 2016 | 12 Apr 2016 | 12 Feb 2016 | 17 Jun 2016 | 1 | 126 | 0 | 66
A1-Flat-601 Flat Flooring | 630.02 | Sft. | 19 Apr 2016 | 23 Apr 2016 | 11 Apr 2016 | 17 Jun 2016 | 4 | 67 | 0 | 55
A1-Flat-601 Flat Skirting | 199.06 | Rft | 28 Apr 2016 | 29 Apr 2016 | 11 Apr 2016 | 17 Jun 2016 | 1 | 67 | 0 | 49
A1-Flat-601 Common Toilet Flooring | 37.47 | Sft. | 13 Apr 2016 | 14 Apr 2016 | 02 Apr 2016 | 17 Jun 2016 | 1 | 76 | 0 | 64
A1-Flat-601 Master Toilet Flooring | 39.92 | Sft. | 13 Apr 2016 | 14 Apr 2016 | 02 Apr 2016 | 17 Jun 2016 | 1 | 76 | 0 | 64
A1-Flat-601 Sitout/Terrace Flooring | 125.06 | Sft. | 21 Apr 2016 | 22 Apr 2016 | 19 Apr 2016 | 17 Jun 2016 | 1 | 59 | 0 | 56
A1-Flat-601 Sitout/Terrace Skirting | 59 | Rft | 28 Apr 2016 | 28 Apr 2016 | 19 Apr 2016 | 17 Jun 2016 | 0 | 59 | 0 | 50
A1-Flat-601 Window Box Flooring | 7.27 | Sft. | 25 Apr 2016 | 25 Apr 2016 | 26 Apr 2016 | 17 Jun 2016 | 0 | 52 | 1 | 53
A1-Flat-601 Umara Patti | 0 | Rft | 20 Apr 2016 | 20 Apr 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 111 | 218
A1-Flat-601 Flat Tiling (Lab) | 56695 | Sft. | 11 Apr 2016 | 07 May 2016 | 10 May 2016 | 24 Nov 2016 | 26 | 198 | 29 | 201
A1-FLAT-602 | 0 | No Unit | 13 Apr 2016 | 30 Apr 2016 |  |  | 17 | 0 | 0 | 0
A1-Flat-602 Common Toilet Dado | 172.56 | Sft. | 13 Apr 2016 | 14 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 113 | 112
A1-Flat-602 Master Toilet Dado | 164.5 | Sft. | 13 Apr 2016 | 14 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 113 | 112
A1-Flat-602 Kit. Dado Above | 68.5 | Sft. | 13 Apr 2016 | 14 Apr 2016 | 12 Feb 2016 | 17 Jun 2016 | 1 | 126 | 0 | 64
A1-Flat-602 Flat Flooring | 623.45 | Sft. | 21 Apr 2016 | 26 Apr 2016 | 11 Jun 2016 | 17 Jun 2016 | 5 | 6 | 51 | 52
A1-Flat-602 Flat Skirting | 196.8 | Rft | 29 Apr 2016 | 30 Apr 2016 | 11 Jun 2016 | 17 Jun 2016 | 1 | 6 | 43 | 48
A1-Flat-602 Common Toilet Flooring | 37.47 | Sft. | 15 Apr 2016 | 16 Apr 2016 | 07 May 2016 | 17 Jun 2016 | 1 | 41 | 22 | 62
A1-Flat-602 Master Toilet Flooring | 39.92 | Sft. | 15 Apr 2016 | 16 Apr 2016 | 07 May 2016 | 17 Jun 2016 | 1 | 41 | 22 | 62
A1-Flat-602 Sitout/Terrace Flooring | 125.06 | Sft. | 25 Apr 2016 | 26 Apr 2016 | 13 Jun 2016 | 17 Jun 2016 | 1 | 4 | 49 | 52
A1-Flat-602 Sitout/Terrace Skirting | 59 | Rft | 29 Apr 2016 | 29 Apr 2016 | 13 Jun 2016 | 17 Jun 2016 | 0 | 4 | 45 | 49
A1-Flat-602 Window Box Flooring | 7.27 | Sft. | 27 Apr 2016 | 27 Apr 2016 | 11 Jun 2016 | 17 Jun 2016 | 0 | 6 | 45 | 51
A1-Flat-602 Umara Patti | 0 | Rft | 21 Apr 2016 | 21 Apr 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 110 | 217
A1-Flat-602 Flat Tiling (Lab) | 56695 | Sft. | 13 Apr 2016 | 30 Apr 2016 | 10 May 2016 | 24 Nov 2016 | 17 | 198 | 27 | 208
A1-FLAT-603 | 0 | No Unit | 15 Apr 2016 | 03 May 2016 |  |  | 18 | 0 | 0 | 0
A1-Flat-603 Common Toilet Dado | 172.56 | Sft. | 15 Apr 2016 | 16 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 111 | 110
A1-Flat-603 Master Toilet Dado | 164.5 | Sft. | 15 Apr 2016 | 16 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 111 | 110
A1-Flat-603 Kit. Dado Above | 68.5 | Sft. | 15 Apr 2016 | 16 Apr 2016 | 12 Feb 2016 | 17 Jun 2016 | 1 | 126 | 0 | 62
A1-Flat-603 Flat Flooring | 623.45 | Sft. | 23 Apr 2016 | 28 Apr 2016 | 08 Jun 2016 | 17 Jun 2016 | 5 | 9 | 46 | 50
A1-Flat-603 Flat Skirting | 196.8 | Rft | 02 May 2016 | 03 May 2016 | 08 Jun 2016 | 17 Jun 2016 | 1 | 9 | 37 | 45
A1-Flat-603 Common Toilet Flooring | 37.47 | Sft. | 18 Apr 2016 | 19 Apr 2016 | 10 May 2016 | 17 Jun 2016 | 1 | 38 | 22 | 59
A1-Flat-603 Master Toilet Flooring | 39.92 | Sft. | 18 Apr 2016 | 19 Apr 2016 | 07 May 2016 | 17 Jun 2016 | 1 | 41 | 19 | 59
A1-Flat-603 Sitout/Terrace Flooring | 62.26 | Sft. | 26 Apr 2016 | 27 Apr 2016 | 07 May 2016 | 17 Jun 2016 | 1 | 41 | 11 | 51
A1-Flat-603 Sitout/Terrace Skirting | 30 | Rft | 02 May 2016 | 02 May 2016 | 08 Jun 2016 | 17 Jun 2016 | 0 | 9 | 37 | 46
A1-Flat-603 Window Box Flooring | 7.27 | Sft. | 29 Apr 2016 | 29 Apr 2016 | 11 Jun 2016 | 17 Jun 2016 | 0 | 6 | 43 | 49
A1-Flat-603 Umara Patti | 0 | Rft | 22 Apr 2016 | 22 Apr 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 109 | 216
A1-Flat-603 Flat Tiling (Lab) | 56695 | Sft. | 15 Apr 2016 | 30 Apr 2016 | 08 Jun 2016 | 24 Nov 2016 | 15 | 169 | 54 | 208
A1-FLAT-604 | 0 | No Unit | 18 Apr 2016 | 05 May 2016 |  |  | 17 | 0 | 0 | 0
A1-Flat-604 Common Toilet Dado | 172.56 | Sft. | 18 Apr 2016 | 19 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 108 | 107
A1-Flat-604 Master Toilet Dado | 164.5 | Sft. | 18 Apr 2016 | 19 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 108 | 107
A1-Flat-604 Kit. Dado Above | 68.5 | Sft. | 18 Apr 2016 | 19 Apr 2016 | 12 Feb 2016 | 17 Jun 2016 | 1 | 126 | 0 | 59
A1-Flat-604 Flat Flooring | 623.45 | Sft. | 26 Apr 2016 | 30 Apr 2016 | 11 Apr 2016 | 17 Jun 2016 | 4 | 67 | 0 | 48
A1-Flat-604 Flat Skirting | 196.8 | Rft | 04 May 2016 | 05 May 2016 | 11 Apr 2016 | 17 Jun 2016 | 1 | 67 | 0 | 43
A1-Flat-604 Common Toilet Flooring | 37.47 | Sft. | 20 Apr 2016 | 21 Apr 2016 | 02 Apr 2016 | 17 Jun 2016 | 1 | 76 | 0 | 57
A1-Flat-604 Master Toilet Flooring | 39.92 | Sft. | 20 Apr 2016 | 21 Apr 2016 | 02 Apr 2016 | 17 Jun 2016 | 1 | 76 | 0 | 57
A1-Flat-604 Sitout/Terrace Flooring | 62.26 | Sft. | 29 Apr 2016 | 30 Apr 2016 | 19 Apr 2016 | 17 Jun 2016 | 1 | 59 | 0 | 48
A1-Flat-604 Sitout/Terrace Skirting | 30 | Rft | 04 May 2016 | 04 May 2016 | 19 Apr 2016 | 17 Jun 2016 | 0 | 59 | 0 | 44
A1-Flat-604 Window Box Flooring | 7.27 | Sft. | 02 May 2016 | 02 May 2016 | 26 Apr 2016 | 17 Jun 2016 | 0 | 52 | 0 | 46
A1-Flat-604 Umara Patti | 0 | Rft | 23 Apr 2016 | 23 Apr 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 108 | 215
A1-Flat-604 Flat Tiling (Lab) | 56695 | Sft. | 18 Apr 2016 | 03 May 2016 | 10 May 2016 | 24 Nov 2016 | 15 | 198 | 22 | 205
A1-6TH FL.LOBBY | 0 | No Unit | 27 Apr 2016 | 29 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1-6th Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 27 Apr 2016 | 29 Apr 2016 | 27 Apr 2016 | 17 Jun 2016 | 2 | 51 | 0 | 49
A1-6th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 27 Apr 2016 | 29 Apr 2016 | 27 Apr 2016 | 17 Jun 2016 | 2 | 51 | 0 | 49
A1-6th Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 27 Apr 2016 | 29 Apr 2016 | 27 Apr 2016 | 27 Dec 2016 | 2 | 244 | 0 | 242
A1-6th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 27 Apr 2016 | 29 Apr 2016 | 27 Apr 2016 | 17 Jun 2016 | 2 | 51 | 0 | 49
A1-6TH FL MAIN STAIR | 343.15 | No Unit | 30 Apr 2016 | 02 May 2016 |  |  | 2 | 0 | 0 | 0
A1-6th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 30 Apr 2016 | 02 May 2016 | 22 Apr 2016 | 18 Jun 2016 | 2 | 57 | 0 | 47
A1-6th Fl Main Stair Main Staircase Riser | 76 | Rft | 30 Apr 2016 | 02 May 2016 | 22 Apr 2016 | 18 Jun 2016 | 2 | 57 | 0 | 47
A1-6th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 30 Apr 2016 | 02 May 2016 | 22 Apr 2016 | 18 Jun 2016 | 2 | 57 | 0 | 47
A1-6th Fl Main Stair Main Staircase Tread | 76 | Sft. | 30 Apr 2016 | 02 May 2016 | 22 Apr 2016 | 18 Jun 2016 | 2 | 57 | 0 | 47
A1-6th Fl Main Stair Main Staircase (Lab) | 56695 | Sft. | 30 Apr 2016 | 02 May 2016 | 22 Apr 2016 | 30 Dec 2016 | 2 | 252 | 0 | 242
A1-6TH FL FIRE STAIR | 343.15 | No Unit | 30 Apr 2016 | 02 May 2016 |  |  | 2 | 0 | 0 | 0
A1-6th Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 30 Apr 2016 | 02 May 2016 | 27 Apr 2016 | 18 Jun 2016 | 2 | 52 | 0 | 47
A1-6th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 30 Apr 2016 | 02 May 2016 | 27 Apr 2016 | 18 Jun 2016 | 2 | 52 | 0 | 47
A1-6th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 30 Apr 2016 | 02 May 2016 | 27 Apr 2016 | 18 Jun 2016 | 2 | 52 | 0 | 47
A1-6th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 30 Apr 2016 | 02 May 2016 | 27 Apr 2016 | 18 Jun 2016 | 2 | 52 | 0 | 47
A1-6th Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 30 Apr 2016 | 02 May 2016 | 27 Apr 2016 | 30 Dec 2016 | 2 | 247 | 0 | 242
A1-6TH FL.LIFT CLADDING | 343.15 | No Unit | 03 May 2016 | 06 May 2016 |  |  | 3 | 0 | 0 | 0
A1-6th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 03 May 2016 | 06 May 2016 | 20 Jul 2016 | 30 Dec 2016 | 3 | 163 | 78 | 238
A1-6th Fl.Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 03 May 2016 | 06 May 2016 | 21 Jul 2016 | 30 Dec 2016 | 3 | 162 | 79 | 238
A1-6th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 03 May 2016 | 06 May 2016 | 20 Jul 2016 | 08 Aug 2016 | 3 | 19 | 78 | 94
A1-7TH FLOOR | 0 | No Unit | 20 Apr 2016 | 28 May 2016 |  |  | 38 | 0 | 0 | 0
A1-FLAT-701 | 0 | No Unit | 20 Apr 2016 | 17 May 2016 |  |  | 27 | 0 | 0 | 0
A1-Flat-701 Common Toilet Dado | 172.56 | Sft. | 20 Apr 2016 | 21 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 106 | 105
A1-Flat-701 Master Toilet Dado | 164.5 | Sft. | 20 Apr 2016 | 21 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 106 | 105
A1-Flat-701 Kit. Dado Above | 63.39 | Sft. | 20 Apr 2016 | 21 Apr 2016 | 25 Apr 2016 | 17 Jun 2016 | 1 | 53 | 5 | 57
A1-Flat-701 Flat Flooring | 637.89 | Sft. | 28 Apr 2016 | 03 May 2016 | 18 Apr 2016 | 17 Jun 2016 | 5 | 60 | 0 | 45
A1-Flat-701 Flat Skirting | 204.04 | Rft | 06 May 2016 | 07 May 2016 | 18 Apr 2016 | 17 Jun 2016 | 1 | 60 | 0 | 41
A1-Flat-701 Common Toilet Flooring | 37.47 | Sft. | 22 Apr 2016 | 23 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 104 | 103
A1-Flat-701 Master Toilet Flooring | 39.92 | Sft. | 22 Apr 2016 | 23 Apr 2016 | 02 Apr 2016 | 17 Jun 2016 | 1 | 76 | 0 | 55
A1-Flat-701 Sitout/Terrace Flooring | 48.62 | Sft. | 30 Apr 2016 | 02 May 2016 | 25 Apr 2016 | 17 Jun 2016 | 2 | 53 | 0 | 46
A1-Flat-701 Sitout/Terrace Skirting | 23 | Rft | 06 May 2016 | 06 May 2016 | 25 Apr 2016 | 17 Jun 2016 | 0 | 53 | 0 | 42
A1-Flat-701 Window Box Flooring | 14.53 | Sft. | 04 May 2016 | 04 May 2016 | 10 May 2016 | 17 Jun 2016 | 0 | 38 | 6 | 44
A1-Flat-701 Umara Patti | 0 | Rft | 25 Apr 2016 | 25 Apr 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 106 | 213
A1-Flat-701 Flat Tiling (Lab) | 56695 | Sft. | 20 Apr 2016 | 17 May 2016 | 10 May 2016 | 24 Nov 2016 | 27 | 198 | 20 | 191
A1-FLAT-702 | 0 | No Unit | 22 Apr 2016 | 19 May 2016 |  |  | 27 | 0 | 0 | 0
A1-Flat-702 Common Toilet Dado | 172.56 | Sft. | 22 Apr 2016 | 23 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 104 | 103
A1-Flat-702 Master Toilet Dado | 164.5 | Sft. | 22 Apr 2016 | 23 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 104 | 103
A1-Flat-702 Kit. Dado Above | 68.5 | Sft. | 22 Apr 2016 | 23 Apr 2016 | 25 Apr 2016 | 17 Jun 2016 | 1 | 53 | 3 | 55
A1-Flat-702 Flat Flooring | 629.31 | Sft. | 30 Apr 2016 | 05 May 2016 | 11 Jun 2016 | 17 Jun 2016 | 5 | 6 | 42 | 43
A1-Flat-702 Flat Skirting | 201.77 | Rft | 09 May 2016 | 10 May 2016 | 11 Jun 2016 | 17 Jun 2016 | 1 | 6 | 33 | 38
A1-Flat-702 Common Toilet Flooring | 37.47 | Sft. | 25 Apr 2016 | 26 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 101 | 100
A1-Flat-702 Master Toilet Flooring | 39.92 | Sft. | 25 Apr 2016 | 26 Apr 2016 | 07 May 2016 | 17 Jun 2016 | 1 | 41 | 12 | 52
A1-Flat-702 Sitout/Terrace Flooring | 48.62 | Sft. | 03 May 2016 | 04 May 2016 | 13 Jun 2016 | 17 Jun 2016 | 1 | 4 | 41 | 44
A1-Flat-702 Sitout/Terrace Skirting | 23 | Rft | 09 May 2016 | 09 May 2016 | 13 Jun 2016 | 17 Jun 2016 | 0 | 4 | 35 | 39
A1-Flat-702 Window Box Flooring | 14.53 | Sft. | 06 May 2016 | 06 May 2016 | 11 Jun 2016 | 17 Jun 2016 | 0 | 6 | 36 | 42
A1-Flat-702 Umara Patti | 0 | Rft | 26 Apr 2016 | 26 Apr 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 105 | 212
A1-Flat-702 Flat Tiling (Lab) | 56695 | Sft. | 22 Apr 2016 | 19 May 2016 | 13 Jun 2016 | 24 Nov 2016 | 27 | 164 | 52 | 189
A1-FLAT-703 | 23 | No Unit | 25 Apr 2016 | 21 May 2016 |  |  | 26 | 0 | 0 | 0
A1-Flat-703 Common Toilet Dado | 172.56 | Sft. | 25 Apr 2016 | 26 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 101 | 100
A1-Flat-703 Master Toilet Dado | 164.5 | Sft. | 25 Apr 2016 | 26 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 101 | 100
A1-Flat-703 Kit. Dado Above | 68.5 | Sft. | 27 Apr 2016 | 28 Apr 2016 | 25 Apr 2016 | 17 Jun 2016 | 1 | 53 | 0 | 50
A1-Flat-703 Flat Flooring | 629.31 | Sft. | 03 May 2016 | 07 May 2016 | 11 Jun 2016 | 17 Jun 2016 | 4 | 6 | 39 | 41
A1-Flat-703 Flat Skirting | 201.77 | Rft | 12 May 2016 | 13 May 2016 | 11 Jun 2016 | 17 Jun 2016 | 1 | 6 | 30 | 35
A1-Flat-703 Common Toilet Flooring | 37.47 | Sft. | 27 Apr 2016 | 28 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 99 | 98
A1-Flat-703 Master Toilet Flooring | 39.92 | Sft. | 27 Apr 2016 | 28 Apr 2016 | 07 May 2016 | 17 Jun 2016 | 1 | 41 | 10 | 50
A1-Flat-703 Sitout/Terrace Flooring | 76.33 | Sft. | 06 May 2016 | 07 May 2016 | 13 Jun 2016 | 17 Jun 2016 | 1 | 4 | 38 | 41
A1-Flat-703 Sitout/Terrace Skirting | 31 | Rft | 12 May 2016 | 12 May 2016 | 13 Jun 2016 | 17 Jun 2016 | 0 | 4 | 32 | 36
A1-Flat-703 Window Box Flooring | 14.53 | Sft. | 09 May 2016 | 09 May 2016 | 11 Jun 2016 | 17 Jun 2016 | 0 | 6 | 33 | 39
A1-Flat-703 Umara Patti | 0 | Rft | 27 Apr 2016 | 27 Apr 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 104 | 211
A1-Flat-703 Flat Tiling (Lab) | 56695 | Sft. | 25 Apr 2016 | 21 May 2016 | 13 Jun 2016 | 24 Nov 2016 | 26 | 164 | 49 | 187
A1-FLAT-704 | 0 | No Unit | 27 Apr 2016 | 24 May 2016 |  |  | 27 | 0 | 0 | 0
A1-Flat-704 Common Toilet Dado | 172.56 | Sft. | 27 Apr 2016 | 28 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 99 | 98
A1-Flat-704 Master Toilet Dado | 164.5 | Sft. | 29 Apr 2016 | 30 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 97 | 96
A1-Flat-704 Kit. Dado Above | 68.5 | Sft. | 02 May 2016 | 03 May 2016 | 25 Apr 2016 | 17 Jun 2016 | 1 | 53 | 0 | 45
A1-Flat-704 Flat Flooring | 629.31 | Sft. | 05 May 2016 | 10 May 2016 | 13 Apr 2016 | 17 Jun 2016 | 5 | 65 | 0 | 38
A1-Flat-704 Flat Skirting | 201.77 | Rft | 13 May 2016 | 14 May 2016 | 13 Apr 2016 | 17 Jun 2016 | 1 | 65 | 0 | 34
A1-Flat-704 Common Toilet Flooring | 37.47 | Sft. | 29 Apr 2016 | 30 Apr 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 97 | 96
A1-Flat-704 Master Toilet Flooring | 39.92 | Sft. | 02 May 2016 | 03 May 2016 | 02 Apr 2016 | 17 Jun 2016 | 1 | 76 | 0 | 45
A1-Flat-704 Sitout/Terrace Flooring | 76.33 | Sft. | 07 May 2016 | 09 May 2016 | 25 Apr 2016 | 17 Jun 2016 | 2 | 53 | 0 | 39
A1-Flat-704 Sitout/Terrace Skirting | 31 | Rft | 13 May 2016 | 13 May 2016 | 25 Apr 2016 | 17 Jun 2016 | 0 | 53 | 0 | 35
A1-Flat-704 Window Box Flooring | 14.53 | Sft. | 11 May 2016 | 11 May 2016 | 10 May 2016 | 17 Jun 2016 | 0 | 38 | 0 | 37
A1-Flat-704 Umara Patti | 0 | Rft | 28 Apr 2016 | 28 Apr 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 103 | 210
A1-Flat-704 Flat Tiling (Lab) | 56695 | Sft. | 27 Apr 2016 | 24 May 2016 | 10 May 2016 | 24 Nov 2016 | 27 | 198 | 13 | 184
A1-7TH FL.LOBBY | 0 | No Unit | 19 May 2016 | 21 May 2016 |  |  | 2 | 0 | 0 | 0
A1-7th Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 19 May 2016 | 21 May 2016 | 30 Apr 2016 | 17 Jun 2016 | 2 | 48 | 0 | 27
A1-7th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 19 May 2016 | 21 May 2016 | 30 Apr 2016 | 17 Jun 2016 | 2 | 48 | 0 | 27
A1-7th Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 19 May 2016 | 21 May 2016 | 30 Apr 2016 | 27 Dec 2016 | 2 | 241 | 0 | 220
A1-7th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 19 May 2016 | 21 May 2016 | 30 Apr 2016 | 17 Jun 2016 | 2 | 48 | 0 | 27
A1-7THFL MAIN STAIR | 343.15 | No Unit | 23 May 2016 | 24 May 2016 |  |  | 1 | 0 | 0 | 0
A1-7thFl Main Stair Main Staircase Flooring | 32 | Sft. | 23 May 2016 | 24 May 2016 | 22 Apr 2016 | 18 Jun 2016 | 1 | 57 | 0 | 25
A1-7thFl Main Stair Main Staircase Riser | 76 | Rft | 23 May 2016 | 24 May 2016 | 22 Apr 2016 | 18 Jun 2016 | 1 | 57 | 0 | 25
A1-7thFl Main Stair Main Staircase Skirting | 62.25 | Rft | 23 May 2016 | 24 May 2016 | 22 Apr 2016 | 18 Jun 2016 | 1 | 57 | 0 | 25
A1-7thFl Main Stair Main Staircase Tread | 76 | Sft. | 23 May 2016 | 24 May 2016 | 22 Apr 2016 | 18 Jun 2016 | 1 | 57 | 0 | 25
A1-7thFl Main Stair Main Staircase (Lab) | 56695 | Sft. | 23 May 2016 | 24 May 2016 | 22 Apr 2016 | 30 Dec 2016 | 1 | 252 | 0 | 220
A1-7TH FL FIRE STAIR | 343.15 | No Unit | 23 May 2016 | 24 May 2016 |  |  | 1 | 0 | 0 | 0
A1-7th Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 23 May 2016 | 24 May 2016 | 27 Apr 2016 | 18 Jun 2016 | 1 | 52 | 0 | 25
A1-7th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 23 May 2016 | 24 May 2016 | 27 Apr 2016 | 18 Jun 2016 | 1 | 52 | 0 | 25
A1-7th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 23 May 2016 | 24 May 2016 | 27 Apr 2016 | 18 Jun 2016 | 1 | 52 | 0 | 25
A1-7th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 23 May 2016 | 24 May 2016 | 27 Apr 2016 | 18 Jun 2016 | 1 | 52 | 0 | 25
A1-7th Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 23 May 2016 | 24 May 2016 | 27 Apr 2016 | 30 Dec 2016 | 1 | 247 | 0 | 220
A1-7TH FL.LIFT CLADDING | 343.15 | No Unit | 25 May 2016 | 28 May 2016 |  |  | 3 | 0 | 0 | 0
A1-7th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 25 May 2016 | 28 May 2016 | 20 Jul 2016 | 30 Dec 2016 | 3 | 163 | 56 | 216
A1-7th Fl.Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 25 May 2016 | 28 May 2016 | 21 Jul 2016 | 30 Dec 2016 | 3 | 162 | 57 | 216
A1-7th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 25 May 2016 | 28 May 2016 | 20 Jul 2016 | 08 Aug 2016 | 3 | 19 | 56 | 72
A1-8TH FLOOR | 44 | No Unit | 29 Apr 2016 | 20 Jun 2016 |  |  | 52 | 0 | 0 | 0
A1-REFUGE FLAT-804 | 0 | No Unit | 04 May 2016 | 09 May 2016 |  |  | 5 | 0 | 0 | 0
A1-Refuge Flat-804 Flat Tiling (Lab) | 56695 | Sft. | 04 May 2016 | 09 May 2016 | 22 Nov 2016 | 30 Dec 2016 | 5 | 38 | 202 | 235
A1-Refuge Flat-804 Refuge Ceramic Flooring | 0 | Sft. | 04 May 2016 | 09 May 2016 | 22 Nov 2016 | 30 Dec 2016 | 5 | 38 | 202 | 235
A1-Refuge Flat-804 Refuge Ceramic Skirting | 0 | Rft | 04 May 2016 | 09 May 2016 | 22 Nov 2016 | 30 Dec 2016 | 5 | 38 | 202 | 235
A1-FLAT-802 | 0 | No Unit | 29 Apr 2016 | 06 Jun 2016 |  |  | 38 | 0 | 0 | 0
A1-Flat-802 Common Toilet Dado | 172.56 | Sft. | 10 May 2016 | 11 May 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 86 | 85
A1-Flat-802 Master Toilet Dado | 164.5 | Sft. | 10 May 2016 | 11 May 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 86 | 85
A1-Flat-802 Kit. Dado Above | 68.5 | Sft. | 10 May 2016 | 11 May 2016 | 25 Apr 2016 | 17 Jun 2016 | 1 | 53 | 0 | 37
A1-Flat-802 Flat Flooring | 623.45 | Sft. | 17 May 2016 | 21 May 2016 | 13 Jun 2016 | 17 Jun 2016 | 4 | 4 | 27 | 27
A1-Flat-802 Flat Skirting | 196.8 | Rft | 25 May 2016 | 26 May 2016 | 13 Jun 2016 | 17 Jun 2016 | 1 | 4 | 19 | 22
A1-Flat-802 Common Toilet Flooring | 37.47 | Sft. | 12 May 2016 | 13 May 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 84 | 83
A1-Flat-802 Master Toilet Flooring | 39.92 | Sft. | 12 May 2016 | 13 May 2016 | 12 Apr 2016 | 17 Jun 2016 | 1 | 66 | 0 | 35
A1-Flat-802 Sitout/Terrace Flooring | 125.06 | Sft. | 19 May 2016 | 20 May 2016 | 13 Jun 2016 | 17 Jun 2016 | 1 | 4 | 25 | 28
A1-Flat-802 Sitout/Terrace Skirting | 59 | Rft | 25 May 2016 | 25 May 2016 | 13 Jun 2016 | 17 Jun 2016 | 0 | 4 | 19 | 23
A1-Flat-802 Window Box Flooring | 7.27 | Sft. | 23 May 2016 | 23 May 2016 | 07 Jun 2016 | 17 Jun 2016 | 0 | 10 | 15 | 25
A1-Flat-802 Umara Patti | 0 | Rft | 29 Apr 2016 | 29 Apr 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 102 | 209
A1-Flat-802 Flat Tiling (Lab) | 56695 | Sft. | 10 May 2016 | 06 Jun 2016 | 14 Jun 2016 | 24 Nov 2016 | 27 | 163 | 35 | 171
A1-FLAT-803 | 68.5 | No Unit | 30 Apr 2016 | 09 Jun 2016 |  |  | 40 | 0 | 0 | 0
A1-Flat-803 Common Toilet Dado | 172.56 | Sft. | 14 May 2016 | 16 May 2016 | 04 Aug 2016 | 04 Aug 2016 | 2 | 0 | 82 | 80
A1-Flat-803 Master Toilet Dado | 164.5 | Sft. | 14 May 2016 | 16 May 2016 | 04 Aug 2016 | 04 Aug 2016 | 2 | 0 | 82 | 80
A1-Flat-803 Kit. Dado Above | 68.5 | Sft. | 14 May 2016 | 16 May 2016 | 25 Apr 2016 | 17 Jun 2016 | 2 | 53 | 0 | 32
A1-Flat-803 Flat Flooring | 623.45 | Sft. | 21 May 2016 | 26 May 2016 | 29 Apr 2016 | 17 Jun 2016 | 5 | 49 | 0 | 22
A1-Flat-803 Flat Skirting | 196.8 | Rft | 30 May 2016 | 31 May 2016 | 29 Apr 2016 | 17 Jun 2016 | 1 | 49 | 0 | 17
A1-Flat-803 Common Toilet Flooring | 37.47 | Sft. | 17 May 2016 | 18 May 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 79 | 78
A1-Flat-803 Master Toilet Flooring | 39.92 | Sft. | 17 May 2016 | 18 May 2016 | 07 May 2016 | 17 Jun 2016 | 1 | 41 | 0 | 30
A1-Flat-803 Sitout/Terrace Flooring | 62.26 | Sft. | 24 May 2016 | 25 May 2016 | 13 Jun 2016 | 17 Jun 2016 | 1 | 4 | 20 | 23
A1-Flat-803 Sitout/Terrace Skirting | 30 | Rft | 30 May 2016 | 30 May 2016 | 13 Jun 2016 | 17 Jun 2016 | 0 | 4 | 14 | 18
A1-Flat-803 Window Box Flooring | 7.27 | Sft. | 27 May 2016 | 27 May 2016 | 07 Jun 2016 | 17 Jun 2016 | 0 | 10 | 11 | 21
A1-Flat-803 Umara Patti | 0 | Rft | 30 Apr 2016 | 30 Apr 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 101 | 208
A1-Flat-803 Flat Tiling (Lab) | 56695 | Sft. | 14 May 2016 | 09 Jun 2016 | 14 Jun 2016 | 24 Nov 2016 | 26 | 163 | 31 | 168
A1-FLAT-801 | 0 | No Unit | 02 May 2016 | 14 Jun 2016 |  |  | 43 | 0 | 0 | 0
A1-Flat-801 Common Toilet Dado | 172.56 | Sft. | 19 May 2016 | 20 May 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 77 | 76
A1-Flat-801 Master Toilet Dado | 164.5 | Sft. | 19 May 2016 | 20 May 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 77 | 76
A1-Flat-801 Kit. Dado Above | 63.39 | Sft. | 19 May 2016 | 20 May 2016 | 25 Apr 2016 | 17 Jun 2016 | 1 | 53 | 0 | 28
A1-Flat-801 Flat Flooring | 630.02 | Sft. | 26 May 2016 | 31 May 2016 | 21 Apr 2016 | 17 Jun 2016 | 5 | 57 | 0 | 17
A1-Flat-801 Flat Skirting | 199.06 | Rft | 03 Jun 2016 | 04 Jun 2016 | 21 Apr 2016 | 17 Jun 2016 | 1 | 57 | 0 | 13
A1-Flat-801 Common Toilet Flooring | 37.47 | Sft. | 21 May 2016 | 23 May 2016 | 04 Aug 2016 | 04 Aug 2016 | 2 | 0 | 75 | 73
A1-Flat-801 Master Toilet Flooring | 39.92 | Sft. | 21 May 2016 | 23 May 2016 | 12 Apr 2016 | 17 Jun 2016 | 2 | 66 | 0 | 25
A1-Flat-801 Sitout/Terrace Flooring | 125.06 | Sft. | 28 May 2016 | 30 May 2016 | 05 May 2016 | 17 Jun 2016 | 2 | 43 | 0 | 18
A1-Flat-801 Sitout/Terrace Skirting | 59.09 | Rft | 03 Jun 2016 | 03 Jun 2016 | 05 May 2016 | 17 Jun 2016 | 0 | 43 | 0 | 14
A1-Flat-801 Window Box Flooring | 7.27 | Sft. | 01 Jun 2016 | 01 Jun 2016 | 10 May 2016 | 17 Jun 2016 | 0 | 38 | 0 | 16
A1-Flat-801 Umara Patti | 0 | Rft | 02 May 2016 | 02 May 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 99 | 206
A1-Flat-801 Flat Tiling (Lab) | 56695 | Sft. | 19 May 2016 | 14 Jun 2016 | 10 May 2016 | 24 Nov 2016 | 26 | 198 | 0 | 163
A1-8TH FL.LOBBY | 0 | No Unit | 10 Jun 2016 | 13 Jun 2016 |  |  | 3 | 0 | 0 | 0
A1-8th Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 10 Jun 2016 | 13 Jun 2016 | 30 Apr 2016 | 30 Dec 2016 | 3 | 244 | 0 | 200
A1-8th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 10 Jun 2016 | 13 Jun 2016 | 30 Apr 2016 | 30 Dec 2016 | 3 | 244 | 0 | 200
A1-8th Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 10 Jun 2016 | 13 Jun 2016 | 30 Apr 2016 | 27 Dec 2016 | 3 | 241 | 0 | 197
A1-8th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 10 Jun 2016 | 13 Jun 2016 | 30 Apr 2016 | 30 Dec 2016 | 3 | 244 | 0 | 200
A1-8TH FL MAIN STAIR | 343.15 | No Unit | 14 Jun 2016 | 15 Jun 2016 |  |  | 1 | 0 | 0 | 0
A1-8th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 14 Jun 2016 | 15 Jun 2016 | 22 Apr 2016 | 18 Jun 2016 | 1 | 57 | 0 | 3
A1-8th Fl Main Stair Main Staircase Riser | 76 | Rft | 14 Jun 2016 | 15 Jun 2016 | 22 Apr 2016 | 18 Jun 2016 | 1 | 57 | 0 | 3
A1-8th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 14 Jun 2016 | 15 Jun 2016 | 22 Apr 2016 | 18 Jun 2016 | 1 | 57 | 0 | 3
A1-8th Fl Main Stair Main Staircase Tread | 76 | Sft. | 14 Jun 2016 | 15 Jun 2016 | 22 Apr 2016 | 18 Jun 2016 | 1 | 57 | 0 | 3
A1-8th Fl Main Stair Main Staircase (Lab) | 56695 | Sft. | 14 Jun 2016 | 15 Jun 2016 | 22 Apr 2016 | 30 Dec 2016 | 1 | 252 | 0 | 198
A1-8TH FL FIRE STAIR | 343.15 | No Unit | 14 Jun 2016 | 15 Jun 2016 |  |  | 1 | 0 | 0 | 0
A1-8th Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 14 Jun 2016 | 15 Jun 2016 | 27 Apr 2016 | 18 Jun 2016 | 1 | 52 | 0 | 3
A1-8th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 14 Jun 2016 | 15 Jun 2016 | 27 Apr 2016 | 18 Jun 2016 | 1 | 52 | 0 | 3
A1-8th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 14 Jun 2016 | 15 Jun 2016 | 27 Apr 2016 | 18 Jun 2016 | 1 | 52 | 0 | 3
A1-8th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 14 Jun 2016 | 15 Jun 2016 | 27 Apr 2016 | 18 Jun 2016 | 1 | 52 | 0 | 3
A1-8th Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 14 Jun 2016 | 15 Jun 2016 | 27 Apr 2016 | 30 Dec 2016 | 1 | 247 | 0 | 198
A1-8TH FL.LIFT CLADDING | 343.15 | No Unit | 16 Jun 2016 | 20 Jun 2016 |  |  | 4 | 0 | 0 | 0
A1-8th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 16 Jun 2016 | 20 Jun 2016 | 20 Jul 2016 | 30 Dec 2016 | 4 | 163 | 34 | 193
A1-8th Fl.Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 16 Jun 2016 | 20 Jun 2016 | 21 Jul 2016 | 30 Dec 2016 | 4 | 162 | 35 | 193
A1-8th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 16 Jun 2016 | 20 Jun 2016 | 20 Jul 2016 | 08 Aug 2016 | 4 | 19 | 34 | 49
A1-9TH FLOOR | 0 | No Unit | 03 May 2016 | 16 Jul 2016 |  |  | 74 | 0 | 0 | 0
A1-FLAT-901 | 0 | No Unit | 03 May 2016 | 18 Jun 2016 |  |  | 46 | 0 | 0 | 0
A1-Flat-901 Common Toilet Dado | 172.56 | Sft. | 24 May 2016 | 25 May 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 72 | 71
A1-Flat-901 Master Toilet Dado | 164.5 | Sft. | 26 May 2016 | 27 May 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 70 | 69
A1-Flat-901 Kit. Dado Above | 63.39 | Sft. | 28 May 2016 | 30 May 2016 | 25 Apr 2016 | 17 Jun 2016 | 2 | 53 | 0 | 18
A1-Flat-901 Flat Flooring | 637.89 | Sft. | 01 Jun 2016 | 06 Jun 2016 | 29 Apr 2016 | 17 Jun 2016 | 5 | 49 | 0 | 11
A1-Flat-901 Flat Skirting | 204.04 | Rft | 09 Jun 2016 | 10 Jun 2016 | 29 Apr 2016 | 17 Jun 2016 | 1 | 49 | 0 | 7
A1-Flat-901 Common Toilet Flooring | 37.47 | Sft. | 26 May 2016 | 27 May 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 70 | 69
A1-Flat-901 Master Toilet Flooring | 39.92 | Sft. | 28 May 2016 | 30 May 2016 | 30 Apr 2016 | 17 Jun 2016 | 2 | 48 | 0 | 18
A1-Flat-901 Sitout/Terrace Flooring | 48.62 | Sft. | 03 Jun 2016 | 04 Jun 2016 | 10 May 2016 | 17 Jun 2016 | 1 | 38 | 0 | 13
A1-Flat-901 Sitout/Terrace Skirting | 23 | Rft | 03 Jun 2016 | 03 Jun 2016 | 10 May 2016 | 17 Jun 2016 | 0 | 38 | 0 | 14
A1-Flat-901 Window Box Flooring | 14.53 | Sft. | 07 Jun 2016 | 07 Jun 2016 | 10 May 2016 | 17 Jun 2016 | 0 | 38 | 0 | 10
A1-Flat-901 Umara Patti | 0 | Rft | 03 May 2016 | 03 May 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 98 | 205
A1-Flat-901 Flat Tiling (Lab) | 56695 | Sft. | 24 May 2016 | 18 Jun 2016 | 10 May 2016 | 24 Nov 2016 | 25 | 198 | 0 | 159
A1-FLAT-902 | 0 | No Unit | 04 May 2016 | 25 Jun 2016 |  |  | 52 | 0 | 0 | 0
A1-Flat-902 Common Toilet Dado | 172.56 | Sft. | 31 May 2016 | 01 Jun 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 65 | 64
A1-Flat-902 Master Toilet Dado | 164.5 | Sft. | 02 Jun 2016 | 03 Jun 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 63 | 62
A1-Flat-902 Kit. Dado Above | 68.5 | Sft. | 04 Jun 2016 | 06 Jun 2016 | 25 Apr 2016 | 17 Jun 2016 | 2 | 53 | 0 | 11
A1-Flat-902 Flat Flooring | 629.31 | Sft. | 08 Jun 2016 | 13 Jun 2016 | 03 May 2016 | 17 Jun 2016 | 5 | 45 | 0 | 4
A1-Flat-902 Flat Skirting | 201.77 | Rft | 16 Jun 2016 | 17 Jun 2016 | 03 May 2016 | 17 Jun 2016 | 1 | 45 | 0 | 0
A1-Flat-902 Common Toilet Flooring | 37.47 | Sft. | 02 Jun 2016 | 03 Jun 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 63 | 62
A1-Flat-902 Master Toilet Flooring | 39.92 | Sft. | 04 Jun 2016 | 06 Jun 2016 | 03 May 2016 | 17 Jun 2016 | 2 | 45 | 0 | 11
A1-Flat-902 Sitout/Terrace Flooring | 48.62 | Sft. | 10 Jun 2016 | 11 Jun 2016 | 09 Jun 2016 | 17 Jun 2016 | 1 | 8 | 0 | 6
A1-Flat-902 Sitout/Terrace Skirting | 23 | Rft | 16 Jun 2016 | 16 Jun 2016 | 09 Jun 2016 | 17 Jun 2016 | 0 | 8 | 0 | 1
A1-Flat-902 Window Box Flooring | 14.53 | Sft. | 14 Jun 2016 | 14 Jun 2016 | 07 Jun 2016 | 17 Jun 2016 | 0 | 10 | 0 | 3
A1-Flat-902 Umara Patti | 0 | Rft | 04 May 2016 | 04 May 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 97 | 204
A1-Flat-902 Flat Tiling (Lab) | 56695 | Sft. | 31 May 2016 | 25 Jun 2016 | 03 May 2016 | 24 Nov 2016 | 25 | 205 | 0 | 152
A1-FLAT-903 | 23 | No Unit | 05 May 2016 | 02 Jul 2016 |  |  | 58 | 0 | 0 | 0
A1-Flat-903 Common Toilet Dado | 172.56 | Sft. | 07 Jun 2016 | 08 Jun 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 58 | 57
A1-Flat-903 Master Toilet Dado | 164.5 | Sft. | 14 Jun 2016 | 15 Jun 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 51 | 50
A1-Flat-903 Kit. Dado Above | 68.5 | Sft. | 16 Jun 2016 | 17 Jun 2016 | 25 Apr 2016 | 17 Jun 2016 | 1 | 53 | 0 | 0
A1-Flat-903 Flat Flooring | 629.31 | Sft. | 15 Jun 2016 | 20 Jun 2016 | 03 May 2016 | 17 Jun 2016 | 5 | 45 | 0 | 0
A1-Flat-903 Flat Skirting | 201.77 | Rft | 23 Jun 2016 | 24 Jun 2016 | 03 May 2016 | 17 Jun 2016 | 1 | 45 | 0 | 0
A1-Flat-903 Common Toilet Flooring | 37.47 | Sft. | 09 Jun 2016 | 10 Jun 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 56 | 55
A1-Flat-903 Master Toilet Flooring | 39.92 | Sft. | 16 Jun 2016 | 17 Jun 2016 | 03 May 2016 | 17 Jun 2016 | 1 | 45 | 0 | 0
A1-Flat-903 Sitout/Terrace Flooring | 76.33 | Sft. | 17 Jun 2016 | 18 Jun 2016 | 09 Jun 2016 | 17 Jun 2016 | 1 | 8 | 0 | 0
A1-Flat-903 Sitout/Terrace Skirting | 31 | Rft | 23 Jun 2016 | 23 Jun 2016 | 09 Jun 2016 | 17 Jun 2016 | 0 | 8 | 0 | 0
A1-Flat-903 Window Box Flooring | 14.53 | Sft. | 21 Jun 2016 | 21 Jun 2016 | 07 Jun 2016 | 17 Jun 2016 | 0 | 10 | 0 | 0
A1-Flat-903 Umara Patti | 0 | Rft | 05 May 2016 | 05 May 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 96 | 203
A1-Flat-903 Flat Tiling (Lab) | 56695 | Sft. | 07 Jun 2016 | 02 Jul 2016 | 03 May 2016 | 24 Nov 2016 | 25 | 205 | 0 | 145
A1-FLAT-904 | 0 | No Unit | 06 May 2016 | 14 Jul 2016 |  |  | 69 | 0 | 0 | 0
A1-Flat-904 Common Toilet Dado | 172.56 | Sft. | 18 Jun 2016 | 21 Jun 2016 | 04 Aug 2016 | 04 Aug 2016 | 3 | 0 | 47 | 44
A1-Flat-904 Master Toilet Dado | 164.5 | Sft. | 22 Jun 2016 | 24 Jun 2016 | 04 Aug 2016 | 04 Aug 2016 | 2 | 0 | 43 | 41
A1-Flat-904 Kit. Dado Above | 68.5 | Sft. | 25 Jun 2016 | 27 Jun 2016 | 25 Apr 2016 | 17 Jun 2016 | 2 | 53 | 0 | 0
A1-Flat-904 Flat Flooring | 629.31 | Sft. | 04 Jul 2016 | 08 Jul 2016 | 29 Apr 2016 | 17 Jun 2016 | 4 | 49 | 0 | 0
A1-Flat-904 Flat Skirting | 201.77 | Rft | 12 Jul 2016 | 13 Jul 2016 | 29 Apr 2016 | 17 Jun 2016 | 1 | 49 | 0 | 0
A1-Flat-904 Common Toilet Flooring | 37.47 | Sft. | 22 Jun 2016 | 23 Jun 2016 | 04 Aug 2016 | 04 Aug 2016 | 1 | 0 | 43 | 42
A1-Flat-904 Master Toilet Flooring | 39.92 | Sft. | 25 Jun 2016 | 27 Jun 2016 | 21 Apr 2016 | 17 Jun 2016 | 2 | 57 | 0 | 0
A1-Flat-904 Sitout/Terrace Flooring | 76.33 | Sft. | 07 Jul 2016 | 08 Jul 2016 | 10 May 2016 | 17 Jun 2016 | 1 | 38 | 0 | 0
A1-Flat-904 Sitout/Terrace Skirting | 31 | Rft | 12 Jul 2016 | 12 Jul 2016 | 10 May 2016 | 17 Jun 2016 | 0 | 38 | 0 | 0
A1-Flat-904 Window Box Flooring | 14.53 | Sft. | 09 Jul 2016 | 09 Jul 2016 | 10 May 2016 | 17 Jun 2016 | 0 | 38 | 0 | 0
A1-Flat-904 Umara Patti | 0 | Rft | 06 May 2016 | 06 May 2016 | 09 Aug 2016 | 24 Nov 2016 | 0 | 107 | 95 | 202
A1-Flat-904 Flat Tiling (Lab) | 56695 | Sft. | 18 Jun 2016 | 14 Jul 2016 | 10 May 2016 | 24 Nov 2016 | 26 | 198 | 0 | 133
A1-9TH FL.LOBBY | 0 | No Unit | 08 Jul 2016 | 12 Jul 2016 |  |  | 4 | 0 | 0 | 0
A1-9th Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 08 Jul 2016 | 12 Jul 2016 | 30 Apr 2016 | 30 Dec 2016 | 4 | 244 | 0 | 171
A1-9th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 08 Jul 2016 | 12 Jul 2016 | 30 Apr 2016 | 30 Dec 2016 | 4 | 244 | 0 | 171
A1-9th Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 08 Jul 2016 | 12 Jul 2016 | 30 Apr 2016 | 27 Dec 2016 | 4 | 241 | 0 | 168
A1-9th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 08 Jul 2016 | 12 Jul 2016 | 30 Apr 2016 | 30 Dec 2016 | 4 | 244 | 0 | 171
A1-9TH FL MAIN STAIR | 343.15 | No Unit | 08 Jul 2016 | 11 Jul 2016 |  |  | 3 | 0 | 0 | 0
A1-9th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 08 Jul 2016 | 11 Jul 2016 | 22 Apr 2016 | 18 Jun 2016 | 3 | 57 | 0 | 0
A1-9th Fl Main Stair Main Staircase Riser | 76 | Rft | 08 Jul 2016 | 11 Jul 2016 | 22 Apr 2016 | 18 Jun 2016 | 3 | 57 | 0 | 0
A1-9th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 08 Jul 2016 | 11 Jul 2016 | 22 Apr 2016 | 18 Jun 2016 | 3 | 57 | 0 | 0
A1-9th Fl Main Stair Main Staircase Tread | 76 | Sft. | 08 Jul 2016 | 11 Jul 2016 | 22 Apr 2016 | 18 Jun 2016 | 3 | 57 | 0 | 0
A1-9th Fl Main Stair Main Staircase (Lab) | 56695 | Sft. | 08 Jul 2016 | 11 Jul 2016 | 22 Apr 2016 | 30 Dec 2016 | 3 | 252 | 0 | 172
A1-9TH FL FIRE STAIR | 343.15 | No Unit | 08 Jul 2016 | 11 Jul 2016 |  |  | 3 | 0 | 0 | 0
A1-9th Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 08 Jul 2016 | 11 Jul 2016 | 27 Apr 2016 | 18 Jun 2016 | 3 | 52 | 0 | 0
A1-9th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 08 Jul 2016 | 11 Jul 2016 | 27 Apr 2016 | 18 Jun 2016 | 3 | 52 | 0 | 0
A1-9th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 08 Jul 2016 | 11 Jul 2016 | 27 Apr 2016 | 18 Jun 2016 | 3 | 52 | 0 | 0
A1-9th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 08 Jul 2016 | 11 Jul 2016 | 27 Apr 2016 | 18 Jun 2016 | 3 | 52 | 0 | 0
A1-9th Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 08 Jul 2016 | 11 Jul 2016 | 27 Apr 2016 | 30 Dec 2016 | 3 | 247 | 0 | 172
A1-9TH FL.LIFT CLADDING | 343.15 | No Unit | 12 Jul 2016 | 16 Jul 2016 |  |  | 4 | 0 | 0 | 0
A1-9th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 12 Jul 2016 | 16 Jul 2016 | 23 Jul 2016 | 30 Dec 2016 | 4 | 160 | 11 | 167
A1-9th Fl.Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 12 Jul 2016 | 16 Jul 2016 | 23 Jul 2016 | 30 Dec 2016 | 4 | 160 | 11 | 167
A1-9th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 12 Jul 2016 | 16 Jul 2016 | 23 Jul 2016 | 08 Aug 2016 | 4 | 16 | 11 | 23
A1-10TH FLOOR | 44 | No Unit | 07 May 2016 | 24 Aug 2016 |  |  | 109 | 0 | 0 | 0
A1-FLAT-1001 | 0 | No Unit | 07 May 2016 | 23 Jul 2016 |  |  | 77 | 0 | 0 | 0
A1-Flat-1001 Common Toilet Dado | 172.56 | Sft. | 28 Jun 2016 | 29 Jun 2016 | 25 Apr 2016 | 24 Nov 2016 | 1 | 213 | 0 | 148
A1-Flat-1001 Master Toilet Dado | 164.5 | Sft. | 30 Jun 2016 | 01 Jul 2016 | 25 Apr 2016 | 24 Nov 2016 | 1 | 213 | 0 | 146
A1-Flat-1001 Kit. Dado Above | 63.39 | Sft. | 02 Jul 2016 | 04 Jul 2016 | 25 Apr 2016 | 24 Nov 2016 | 2 | 213 | 0 | 143
A1-Flat-1001 Flat Flooring | 630.02 | Sft. | 06 Jul 2016 | 11 Jul 2016 | 09 Jun 2016 | 24 Nov 2016 | 5 | 168 | 0 | 136
A1-Flat-1001 Flat Skirting | 199.06 | Rft | 14 Jul 2016 | 15 Jul 2016 | 09 Jun 2016 | 24 Nov 2016 | 1 | 168 | 0 | 132
A1-Flat-1001 Common Toilet Flooring | 37.47 | Sft. | 30 Jun 2016 | 01 Jul 2016 | 30 Apr 2016 | 24 Nov 2016 | 1 | 208 | 0 | 146
A1-Flat-1001 Master Toilet Flooring | 39.92 | Sft. | 02 Jul 2016 | 04 Jul 2016 | 30 Apr 2016 | 24 Nov 2016 | 2 | 208 | 0 | 143
A1-Flat-1001 Sitout/Terrace Flooring | 125.06 | Sft. | 08 Jul 2016 | 09 Jul 2016 | 09 Jun 2016 | 24 Nov 2016 | 1 | 168 | 0 | 138
A1-Flat-1001 Sitout/Terrace Skirting | 59 | Rft | 14 Jul 2016 | 14 Jul 2016 | 09 Jun 2016 | 24 Nov 2016 | 0 | 168 | 0 | 133
A1-Flat-1001 Window Box Flooring | 7.27 | Sft. | 12 Jul 2016 | 12 Jul 2016 | 07 Jun 2016 | 24 Nov 2016 | 0 | 170 | 0 | 135
A1-Flat-1001 Umara Patti | 0 | Rft | 07 May 2016 | 07 May 2016 | 09 Aug 2016 | 21 Dec 2016 | 0 | 134 | 94 | 228
A1-Flat-1001 Flat Tiling (Lab) | 56695 | Sft. | 28 Jun 2016 | 23 Jul 2016 | 09 Jun 2016 | 21 Dec 2016 | 25 | 195 | 0 | 151
A1-FLAT-1002 | 0 | No Unit | 09 May 2016 | 30 Jul 2016 |  |  | 82 | 0 | 0 | 0
A1-Flat-1002 Common Toilet Dado | 172.56 | Sft. | 05 Jul 2016 | 06 Jul 2016 | 06 Jun 2016 | 24 Nov 2016 | 1 | 171 | 0 | 141
A1-Flat-1002 Master Toilet Dado | 164.5 | Sft. | 07 Jul 2016 | 08 Jul 2016 | 06 Jun 2016 | 24 Nov 2016 | 1 | 171 | 0 | 139
A1-Flat-1002 Kit. Dado Above | 68.5 | Sft. | 09 Jul 2016 | 11 Jul 2016 | 25 Apr 2016 | 24 Nov 2016 | 2 | 213 | 0 | 136
A1-Flat-1002 Flat Flooring | 623.45 | Sft. | 13 Jul 2016 | 18 Jul 2016 | 08 Jun 2016 | 24 Nov 2016 | 5 | 169 | 0 | 129
A1-Flat-1002 Flat Skirting | 196.8 | Rft | 21 Jul 2016 | 22 Jul 2016 | 08 Jun 2016 | 24 Nov 2016 | 1 | 169 | 0 | 125
A1-Flat-1002 Common Toilet Flooring | 37.47 | Sft. | 07 Jul 2016 | 08 Jul 2016 | 06 Jun 2016 | 24 Nov 2016 | 1 | 171 | 0 | 139
A1-Flat-1002 Master Toilet Flooring | 39.92 | Sft. | 09 Jul 2016 | 11 Jul 2016 | 06 Jun 2016 | 24 Nov 2016 | 2 | 171 | 0 | 136
A1-Flat-1002 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Jul 2016 | 16 Jul 2016 | 09 Jun 2016 | 24 Nov 2016 | 1 | 168 | 0 | 131
A1-Flat-1002 Sitout/Terrace Skirting | 59 | Rft | 21 Jul 2016 | 21 Jul 2016 | 09 Jun 2016 | 24 Nov 2016 | 0 | 168 | 0 | 126
A1-Flat-1002 Window Box Flooring | 7.27 | Sft. | 19 Jul 2016 | 19 Jul 2016 | 07 Jun 2016 | 24 Nov 2016 | 0 | 170 | 0 | 128
A1-Flat-1002 Umara Patti | 0 | Rft | 09 May 2016 | 09 May 2016 | 09 Aug 2016 | 21 Dec 2016 | 0 | 134 | 92 | 226
A1-Flat-1002 Flat Tiling (Lab) | 56695 | Sft. | 05 Jul 2016 | 30 Jul 2016 | 09 Jun 2016 | 21 Dec 2016 | 25 | 195 | 0 | 144
A1-FLAT-1003 | 0 | No Unit | 10 May 2016 | 06 Aug 2016 |  |  | 88 | 0 | 0 | 0
A1-Flat-1003 Common Toilet Dado | 172.56 | Sft. | 12 Jul 2016 | 13 Jul 2016 | 06 Jun 2016 | 24 Nov 2016 | 1 | 171 | 0 | 134
A1-Flat-1003 Master Toilet Dado | 164.5 | Sft. | 14 Jul 2016 | 16 Jul 2016 | 06 Jun 2016 | 24 Nov 2016 | 2 | 171 | 0 | 131
A1-Flat-1003 Kit. Dado Above | 68.5 | Sft. | 18 Jul 2016 | 19 Jul 2016 | 25 Apr 2016 | 24 Nov 2016 | 1 | 213 | 0 | 128
A1-Flat-1003 Flat Flooring | 623.45 | Sft. | 20 Jul 2016 | 25 Jul 2016 | 07 Jun 2016 | 24 Nov 2016 | 5 | 170 | 0 | 122
A1-Flat-1003 Flat Skirting | 196.8 | Rft | 28 Jul 2016 | 29 Jul 2016 | 07 Jun 2016 | 24 Nov 2016 | 1 | 170 | 0 | 118
A1-Flat-1003 Common Toilet Flooring | 37.47 | Sft. | 14 Jul 2016 | 15 Jul 2016 | 06 Jun 2016 | 24 Nov 2016 | 1 | 171 | 0 | 132
A1-Flat-1003 Master Toilet Flooring | 39.92 | Sft. | 18 Jul 2016 | 19 Jul 2016 | 06 Jun 2016 | 24 Nov 2016 | 1 | 171 | 0 | 128
A1-Flat-1003 Sitout/Terrace Flooring | 62.26 | Sft. | 22 Jul 2016 | 23 Jul 2016 | 09 Jun 2016 | 24 Nov 2016 | 1 | 168 | 0 | 124
A1-Flat-1003 Sitout/Terrace Skirting | 30 | Rft | 28 Jul 2016 | 28 Jul 2016 | 09 Jun 2016 | 24 Nov 2016 | 0 | 168 | 0 | 119
A1-Flat-1003 Window Box Flooring | 7.27 | Sft. | 26 Jul 2016 | 26 Jul 2016 | 07 Jun 2016 | 24 Nov 2016 | 0 | 170 | 0 | 121
A1-Flat-1003 Umara Patti | 0 | Rft | 10 May 2016 | 10 May 2016 | 09 Aug 2016 | 21 Dec 2016 | 0 | 134 | 91 | 225
A1-Flat-1003 Flat Tiling (Lab) | 56695 | Sft. | 12 Jul 2016 | 06 Aug 2016 | 09 Jun 2016 | 21 Dec 2016 | 25 | 195 | 0 | 137
A1-FLAT-1004 | 0 | No Unit | 11 May 2016 | 16 Aug 2016 |  |  | 97 | 0 | 0 | 0
A1-Flat-1004 Common Toilet Dado | 172.56 | Sft. | 20 Jul 2016 | 21 Jul 2016 | 25 Apr 2016 | 24 Nov 2016 | 1 | 213 | 0 | 126
A1-Flat-1004 Master Toilet Dado | 164.5 | Sft. | 22 Jul 2016 | 23 Jul 2016 | 25 Apr 2016 | 24 Nov 2016 | 1 | 213 | 0 | 124
A1-Flat-1004 Kit. Dado Above | 68.5 | Sft. | 25 Jul 2016 | 26 Jul 2016 | 25 Apr 2016 | 24 Nov 2016 | 1 | 213 | 0 | 121
A1-Flat-1004 Flat Flooring | 623.45 | Sft. | 03 Aug 2016 | 08 Aug 2016 | 07 Jun 2016 | 24 Nov 2016 | 5 | 170 | 0 | 108
A1-Flat-1004 Flat Skirting | 196.8 | Rft | 11 Aug 2016 | 12 Aug 2016 | 07 Jun 2016 | 24 Nov 2016 | 1 | 170 | 0 | 104
A1-Flat-1004 Common Toilet Flooring | 37.47 | Sft. | 22 Jul 2016 | 23 Jul 2016 | 30 Apr 2016 | 24 Nov 2016 | 1 | 208 | 0 | 124
A1-Flat-1004 Master Toilet Flooring | 39.92 | Sft. | 25 Jul 2016 | 26 Jul 2016 | 30 Apr 2016 | 24 Nov 2016 | 1 | 208 | 0 | 121
A1-Flat-1004 Sitout/Terrace Flooring | 62.26 | Sft. | 06 Aug 2016 | 08 Aug 2016 | 09 Jun 2016 | 24 Nov 2016 | 2 | 168 | 0 | 108
A1-Flat-1004 Sitout/Terrace Skirting | 30 | Rft | 11 Aug 2016 | 11 Aug 2016 | 09 Jun 2016 | 24 Nov 2016 | 0 | 168 | 0 | 105
A1-Flat-1004 Window Box Flooring | 7.27 | Sft. | 09 Aug 2016 | 09 Aug 2016 | 07 Jun 2016 | 24 Nov 2016 | 0 | 170 | 0 | 107
A1-Flat-1004 Umara Patti | 0 | Rft | 11 May 2016 | 11 May 2016 | 09 Aug 2016 | 21 Dec 2016 | 0 | 134 | 90 | 224
A1-Flat-1004 Flat Tiling (Lab) | 56695 | Sft. | 20 Jul 2016 | 16 Aug 2016 | 09 Jun 2016 | 21 Dec 2016 | 27 | 195 | 0 | 127
A1-10TH FL.LOBBY | 0 | No Unit | 10 Aug 2016 | 13 Aug 2016 |  |  | 3 | 0 | 0 | 0
A1-10th Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 10 Aug 2016 | 13 Aug 2016 | 30 Apr 2016 | 30 Dec 2016 | 3 | 244 | 0 | 139
A1-10th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 10 Aug 2016 | 13 Aug 2016 | 30 Apr 2016 | 30 Dec 2016 | 3 | 244 | 0 | 139
A1-10th Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 10 Aug 2016 | 13 Aug 2016 | 30 Apr 2016 | 27 Dec 2016 | 3 | 241 | 0 | 136
A1-10th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 10 Aug 2016 | 13 Aug 2016 | 30 Apr 2016 | 30 Dec 2016 | 3 | 244 | 0 | 139
A1-10TH FL MAIN STAIR | 343.15 | No Unit | 16 Aug 2016 | 18 Aug 2016 |  |  | 2 | 0 | 0 | 0
A1-10th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 16 Aug 2016 | 18 Aug 2016 | 22 Apr 2016 | 30 Dec 2016 | 2 | 252 | 0 | 134
A1-10th Fl Main Stair Main Staircase Riser | 76 | Rft | 16 Aug 2016 | 18 Aug 2016 | 22 Apr 2016 | 30 Dec 2016 | 2 | 252 | 0 | 134
A1-10th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 16 Aug 2016 | 18 Aug 2016 | 22 Apr 2016 | 30 Dec 2016 | 2 | 252 | 0 | 134
A1-10th Fl Main Stair Main Staircase Tread | 90 | Sft. | 16 Aug 2016 | 18 Aug 2016 | 22 Apr 2016 | 30 Dec 2016 | 2 | 252 | 0 | 134
A1-10th Fl Main Stair Main Staircase (Lab) | 56695 | Sft. | 16 Aug 2016 | 18 Aug 2016 | 22 Apr 2016 | 30 Dec 2016 | 2 | 252 | 0 | 134
A1-10TH FL FIRE STAIR | 343.15 | No Unit | 16 Aug 2016 | 18 Aug 2016 |  |  | 2 | 0 | 0 | 0
A1-10th Fl Fire Stair Fire Staircase Flooring | 309 | Sft. | 16 Aug 2016 | 18 Aug 2016 | 27 Apr 2016 | 30 Dec 2016 | 2 | 247 | 0 | 134
A1-10th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 16 Aug 2016 | 18 Aug 2016 | 27 Apr 2016 | 30 Dec 2016 | 2 | 247 | 0 | 134
A1-10th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 16 Aug 2016 | 18 Aug 2016 | 27 Apr 2016 | 30 Dec 2016 | 2 | 247 | 0 | 134
A1-10th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 16 Aug 2016 | 18 Aug 2016 | 27 Apr 2016 | 30 Dec 2016 | 2 | 247 | 0 | 134
A1-10th Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 16 Aug 2016 | 18 Aug 2016 | 27 Apr 2016 | 30 Dec 2016 | 2 | 247 | 0 | 134
A1-10TH FL.LIFT CLADDING | 343.15 | No Unit | 19 Aug 2016 | 24 Aug 2016 |  |  | 5 | 0 | 0 | 0
A1-10th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 19 Aug 2016 | 24 Aug 2016 | 29 Jul 2016 | 30 Dec 2016 | 5 | 154 | 0 | 128
A1-10th Fl.Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 19 Aug 2016 | 24 Aug 2016 | 29 Jul 2016 | 30 Dec 2016 | 5 | 154 | 0 | 128
A1-10th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 19 Aug 2016 | 24 Aug 2016 | 29 Jul 2016 | 08 Aug 2016 | 5 | 10 | 0 | 0
A1-11TH FLOOR | 0 | No Unit | 12 May 2016 | 17 Sep 2016 |  |  | 128 | 0 | 0 | 0
A1-FLAT-1101 | 0 | No Unit | 12 May 2016 | 23 Aug 2016 |  |  | 103 | 0 | 0 | 0
A1-Flat-1101 Common Toilet Dado | 172.56 | Sft. | 27 Jul 2016 | 28 Jul 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 151
A1-Flat-1101 Master Toilet Dado | 164.5 | Sft. | 29 Jul 2016 | 30 Jul 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 149
A1-Flat-1101 Kit. Dado Above | 63.39 | Sft. | 01 Aug 2016 | 02 Aug 2016 | 10 May 2016 | 26 Dec 2016 | 1 | 230 | 0 | 146
A1-Flat-1101 Flat Flooring | 637.89 | Sft. | 04 Aug 2016 | 09 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 5 | 192 | 0 | 139
A1-Flat-1101 Flat Skirting | 204.04 | Rft | 12 Aug 2016 | 13 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 135
A1-Flat-1101 Common Toilet Flooring | 37.47 | Sft. | 29 Jul 2016 | 30 Jul 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 149
A1-Flat-1101 Master Toilet Flooring | 39.92 | Sft. | 01 Aug 2016 | 02 Aug 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 146
A1-Flat-1101 Sitout/Terrace Flooring | 48.62 | Sft. | 06 Aug 2016 | 08 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 2 | 192 | 0 | 140
A1-Flat-1101 Sitout/Terrace Skirting | 23 | Rft | 12 Aug 2016 | 12 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 136
A1-Flat-1101 Window Box Flooring | 14.53 | Sft. | 10 Aug 2016 | 10 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 138
A1-Flat-1101 Umara Patti | 0 | Rft | 12 May 2016 | 12 May 2016 | 22 Nov 2016 | 26 Dec 2016 | 0 | 34 | 194 | 228
A1-Flat-1101 Flat Tiling (Lab) | 56695 | Sft. | 27 Jul 2016 | 23 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 27 | 192 | 0 | 125
A1-FLAT1102 | 0 | No Unit | 13 May 2016 | 30 Aug 2016 |  |  | 109 | 0 | 0 | 0
A1-Flat1102 Common Toilet Dado | 172.56 | Sft. | 03 Aug 2016 | 04 Aug 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 144
A1-Flat1102 Master Toilet Dado | 164.5 | Sft. | 05 Aug 2016 | 06 Aug 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 142
A1-Flat1102 Kit. Dado Above | 68.5 | Sft. | 08 Aug 2016 | 09 Aug 2016 | 10 May 2016 | 26 Dec 2016 | 1 | 230 | 0 | 139
A1-Flat1102 Flat Flooring | 629.31 | Sft. | 18 Aug 2016 | 23 Aug 2016 | 08 Jun 2016 | 26 Dec 2016 | 5 | 201 | 0 | 125
A1-Flat1102 Flat Skirting | 201.77 | Rft | 26 Aug 2016 | 27 Aug 2016 | 08 Jun 2016 | 26 Dec 2016 | 1 | 201 | 0 | 121
A1-Flat1102 Common Toilet Flooring | 37.47 | Sft. | 05 Aug 2016 | 06 Aug 2016 | 09 Jun 2016 | 26 Dec 2016 | 1 | 200 | 0 | 142
A1-Flat1102 Master Toilet Flooring | 39.92 | Sft. | 08 Aug 2016 | 09 Aug 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 139
A1-Flat1102 Sitout/Terrace Flooring | 48.62 | Sft. | 22 Aug 2016 | 23 Aug 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 125
A1-Flat1102 Sitout/Terrace Skirting | 23 | Rft | 26 Aug 2016 | 26 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 122
A1-Flat1102 Window Box Flooring | 14.53 | Sft. | 24 Aug 2016 | 24 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 124
A1-Flat1102 Umara Patti | 0 | Rft | 13 May 2016 | 13 May 2016 | 22 Nov 2016 | 26 Dec 2016 | 0 | 34 | 193 | 227
A1-Flat1102 Flat Tiling (Lab) | 56695 | Sft. | 03 Aug 2016 | 30 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 27 | 192 | 0 | 118
A1-FLAT-1103 | 23 | No Unit | 14 May 2016 | 06 Sep 2016 |  |  | 115 | 0 | 0 | 0
A1-Flat-1103 Common Toilet Dado | 172.56 | Sft. | 10 Aug 2016 | 11 Aug 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 137
A1-Flat-1103 Master Toilet Dado | 164.5 | Sft. | 12 Aug 2016 | 13 Aug 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 135
A1-Flat-1103 Kit. Dado Above | 68.5 | Sft. | 16 Aug 2016 | 17 Aug 2016 | 10 May 2016 | 26 Dec 2016 | 1 | 230 | 0 | 131
A1-Flat-1103 Flat Flooring | 629.31 | Sft. | 25 Aug 2016 | 30 Aug 2016 | 08 Jun 2016 | 26 Dec 2016 | 5 | 201 | 0 | 118
A1-Flat-1103 Flat Skirting | 201.77 | Rft | 02 Sep 2016 | 03 Sep 2016 | 08 Jun 2016 | 26 Dec 2016 | 1 | 201 | 0 | 114
A1-Flat-1103 Common Toilet Flooring | 37.47 | Sft. | 12 Aug 2016 | 13 Aug 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 135
A1-Flat-1103 Master Toilet Flooring | 39.92 | Sft. | 16 Aug 2016 | 17 Aug 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 131
A1-Flat-1103 Sitout/Terrace Flooring | 76.33 | Sft. | 29 Aug 2016 | 30 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 118
A1-Flat-1103 Sitout/Terrace Skirting | 31 | Rft | 02 Sep 2016 | 02 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 115
A1-Flat-1103 Window Box Flooring | 14.53 | Sft. | 31 Aug 2016 | 31 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 117
A1-Flat-1103 Umara Patti | 0 | Rft | 14 May 2016 | 14 May 2016 | 22 Nov 2016 | 26 Dec 2016 | 0 | 34 | 192 | 226
A1-Flat-1103 Flat Tiling (Lab) | 56695 | Sft. | 10 Aug 2016 | 06 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 27 | 192 | 0 | 111
A1-FLAT-1104 | 0 | No Unit | 16 May 2016 | 13 Sep 2016 |  |  | 120 | 0 | 0 | 0
A1-Flat-1104 Common Toilet Dado | 172.56 | Sft. | 18 Aug 2016 | 19 Aug 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 129
A1-Flat-1104 Master Toilet Dado | 164.5 | Sft. | 20 Aug 2016 | 22 Aug 2016 | 07 Jun 2016 | 26 Dec 2016 | 2 | 202 | 0 | 126
A1-Flat-1104 Kit. Dado Above | 68.5 | Sft. | 23 Aug 2016 | 24 Aug 2016 | 10 May 2016 | 26 Dec 2016 | 1 | 230 | 0 | 124
A1-Flat-1104 Flat Flooring | 629.31 | Sft. | 01 Sep 2016 | 06 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 5 | 192 | 0 | 111
A1-Flat-1104 Flat Skirting | 201.77 | Rft | 09 Sep 2016 | 10 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 107
A1-Flat-1104 Common Toilet Flooring | 37.47 | Sft. | 20 Aug 2016 | 22 Aug 2016 | 07 Jun 2016 | 26 Dec 2016 | 2 | 202 | 0 | 126
A1-Flat-1104 Master Toilet Flooring | 39.92 | Sft. | 23 Aug 2016 | 24 Aug 2016 | 07 Jun 2016 | 26 Dec 2016 | 1 | 202 | 0 | 124
A1-Flat-1104 Sitout/Terrace Flooring | 76.33 | Sft. | 05 Sep 2016 | 06 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 111
A1-Flat-1104 Sitout/Terrace Skirting | 31 | Rft | 05 Sep 2016 | 05 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 112
A1-Flat-1104 Window Box Flooring | 14.53 | Sft. | 07 Sep 2016 | 07 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 110
A1-Flat-1104 Umara Patti | 0 | Rft | 16 May 2016 | 16 May 2016 | 22 Nov 2016 | 26 Dec 2016 | 0 | 34 | 190 | 224
A1-Flat-1104 Flat Tiling (Lab) | 56695 | Sft. | 18 Aug 2016 | 13 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 26 | 192 | 0 | 104
A1-11TH FL.LOBBY | 0 | No Unit | 05 Sep 2016 | 08 Sep 2016 |  |  | 3 | 0 | 0 | 0
A1-11th Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 05 Sep 2016 | 08 Sep 2016 | 17 Jun 2016 | 12 Jan 2017 | 3 | 209 | 0 | 126
A1-11th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 05 Sep 2016 | 08 Sep 2016 | 17 Jun 2016 | 12 Jan 2017 | 3 | 209 | 0 | 126
A1-11th Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 05 Sep 2016 | 08 Sep 2016 | 13 Jul 2016 | 27 Dec 2016 | 3 | 167 | 0 | 110
A1-11th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 05 Sep 2016 | 08 Sep 2016 | 17 Jun 2016 | 12 Jan 2017 | 3 | 209 | 0 | 126
A1-11TH FL MAIN STAIR | 343.15 | No Unit | 09 Sep 2016 | 12 Sep 2016 |  |  | 3 | 0 | 0 | 0
A1-11th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 09 Sep 2016 | 12 Sep 2016 | 14 Jun 2016 | 12 Jan 2017 | 3 | 212 | 0 | 122
A1-11th Fl Main Stair Main Staircase Riser | 76 | Rft | 09 Sep 2016 | 12 Sep 2016 | 14 Jun 2016 | 12 Jan 2017 | 3 | 212 | 0 | 122
A1-11th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 09 Sep 2016 | 12 Sep 2016 | 14 Jun 2016 | 12 Jan 2017 | 3 | 212 | 0 | 122
A1-11th Fl Main Stair Main Staircase Tread | 90 | Sft. | 09 Sep 2016 | 12 Sep 2016 | 14 Jun 2016 | 12 Jan 2017 | 3 | 212 | 0 | 122
A1-11th Fl Main Stair Main Staircase (Lab) | 56695 | Sft. | 09 Sep 2016 | 12 Sep 2016 | 14 Jun 2016 | 30 Dec 2016 | 3 | 199 | 0 | 109
A1-11TH FL FIRE STAIR | 343.15 | No Unit | 09 Sep 2016 | 12 Sep 2016 |  |  | 3 | 0 | 0 | 0
A1-11th Fl Fire Stair Fire Staircase Flooring | 309 | Sft. | 09 Sep 2016 | 12 Sep 2016 | 17 Jun 2016 | 12 Jan 2017 | 3 | 209 | 0 | 122
A1-11th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 09 Sep 2016 | 12 Sep 2016 | 17 Jun 2016 | 12 Jan 2017 | 3 | 209 | 0 | 122
A1-11th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 09 Sep 2016 | 12 Sep 2016 | 17 Jun 2016 | 12 Jan 2017 | 3 | 209 | 0 | 122
A1-11th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 09 Sep 2016 | 12 Sep 2016 | 17 Jun 2016 | 12 Jan 2017 | 3 | 209 | 0 | 122
A1-11th Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 09 Sep 2016 | 12 Sep 2016 | 13 Jul 2016 | 30 Dec 2016 | 3 | 170 | 0 | 109
A1-11THFL.LIFT CLADDING | 0 | No Unit | 13 Sep 2016 | 17 Sep 2016 |  |  | 4 | 0 | 0 | 0
A1-11thFl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 13 Sep 2016 | 17 Sep 2016 | 29 Jul 2016 | 12 Jan 2017 | 4 | 167 | 0 | 117
A1-11thFl.Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 13 Sep 2016 | 17 Sep 2016 | 29 Jul 2016 | 30 Dec 2016 | 4 | 154 | 0 | 104
A1-11thFl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 13 Sep 2016 | 17 Sep 2016 | 29 Jul 2016 | 08 Aug 2016 | 4 | 10 | 0 | 0
A1-12TH FLOOR | 44 | No Unit | 17 May 2016 | 21 Oct 2016 |  |  | 157 | 0 | 0 | 0
A1-FLAT-1201 | 0 | No Unit | 17 May 2016 | 20 Sep 2016 |  |  | 126 | 0 | 0 | 0
A1-Flat-1201 Common Toilet Dado | 172.56 | Sft. | 25 Aug 2016 | 26 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 122
A1-Flat-1201 Master Toilet Dado | 164.5 | Sft. | 27 Aug 2016 | 29 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 2 | 192 | 0 | 119
A1-Flat-1201 Kit. Dado Above | 63.39 | Sft. | 30 Aug 2016 | 31 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 117
A1-Flat-1201 Flat Flooring | 630.02 | Sft. | 08 Sep 2016 | 13 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 5 | 192 | 0 | 104
A1-Flat-1201 Flat Skirting | 199.06 | Rft | 16 Sep 2016 | 17 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 100
A1-Flat-1201 Common Toilet Flooring | 37.47 | Sft. | 27 Aug 2016 | 29 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 2 | 192 | 0 | 119
A1-Flat-1201 Master Toilet Flooring | 39.92 | Sft. | 30 Aug 2016 | 31 Aug 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 117
A1-Flat-1201 Sitout/Terrace Flooring | 125.06 | Sft. | 12 Sep 2016 | 13 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 104
A1-Flat-1201 Sitout/Terrace Skirting | 59 | Rft | 16 Sep 2016 | 16 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 101
A1-Flat-1201 Window Box Flooring | 7.27 | Sft. | 14 Sep 2016 | 14 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 103
A1-Flat-1201 Umara Patti | 0 | Rft | 17 May 2016 | 17 May 2016 | 22 Nov 2016 | 26 Dec 2016 | 0 | 34 | 189 | 223
A1-Flat-1201 Flat Tiling (Lab) | 56695 | Sft. | 25 Aug 2016 | 20 Sep 2016 | 26 Jul 2016 | 26 Dec 2016 | 26 | 153 | 0 | 97
A1-FLAT-1202 | 0 | No Unit | 18 May 2016 | 27 Sep 2016 |  |  | 132 | 0 | 0 | 0
A1-Flat-1202 Common Toilet Dado | 172.56 | Sft. | 01 Sep 2016 | 02 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 115
A1-Flat-1202 Master Toilet Dado | 164.5 | Sft. | 03 Sep 2016 | 05 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 2 | 192 | 0 | 112
A1-Flat-1202 Kit. Dado Above | 68.5 | Sft. | 06 Sep 2016 | 07 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 110
A1-Flat-1202 Flat Flooring | 623.45 | Sft. | 15 Sep 2016 | 20 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 5 | 192 | 0 | 97
A1-Flat-1202 Flat Skirting | 196.8 | Rft | 23 Sep 2016 | 24 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 93
A1-Flat-1202 Common Toilet Flooring | 37.47 | Sft. | 03 Sep 2016 | 05 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 2 | 192 | 0 | 112
A1-Flat-1202 Master Toilet Flooring | 39.92 | Sft. | 06 Sep 2016 | 07 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 110
A1-Flat-1202 Sitout/Terrace Flooring | 125.06 | Sft. | 19 Sep 2016 | 20 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 97
A1-Flat-1202 Sitout/Terrace Skirting | 59 | Rft | 23 Sep 2016 | 23 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 94
A1-Flat-1202 Window Box Flooring | 7.27 | Sft. | 21 Sep 2016 | 21 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 96
A1-Flat-1202 Umara Patti | 0 | Rft | 18 May 2016 | 18 May 2016 | 22 Nov 2016 | 26 Dec 2016 | 0 | 34 | 188 | 222
A1-Flat-1202 Flat Tiling (Lab) | 56695 | Sft. | 01 Sep 2016 | 27 Sep 2016 | 09 Aug 2016 | 26 Dec 2016 | 26 | 139 | 0 | 90
A1-FLAT-1203 | 0 | No Unit | 19 May 2016 | 04 Oct 2016 |  |  | 138 | 0 | 0 | 0
A1-Flat-1203 Common Toilet Dado | 172.56 | Sft. | 08 Sep 2016 | 09 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 108
A1-Flat-1203 Master Toilet Dado | 164.5 | Sft. | 10 Sep 2016 | 12 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 2 | 192 | 0 | 105
A1-Flat-1203 Kit. Dado Above | 68.5 | Sft. | 13 Sep 2016 | 14 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 103
A1-Flat-1203 Flat Flooring | 623.45 | Sft. | 22 Sep 2016 | 27 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 5 | 192 | 0 | 90
A1-Flat-1203 Flat Skirting | 196.8 | Rft | 30 Sep 2016 | 01 Oct 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 86
A1-Flat-1203 Common Toilet Flooring | 37.47 | Sft. | 10 Sep 2016 | 12 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 2 | 192 | 0 | 105
A1-Flat-1203 Master Toilet Flooring | 39.92 | Sft. | 13 Sep 2016 | 14 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 103
A1-Flat-1203 Sitout/Terrace Flooring | 62.26 | Sft. | 26 Sep 2016 | 27 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 90
A1-Flat-1203 Sitout/Terrace Skirting | 30 | Rft | 30 Sep 2016 | 30 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 87
A1-Flat-1203 Window Box Flooring | 7.27 | Sft. | 28 Sep 2016 | 28 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 89
A1-Flat-1203 Umara Patti | 0 | Rft | 19 May 2016 | 19 May 2016 | 22 Nov 2016 | 26 Dec 2016 | 0 | 34 | 187 | 221
A1-Flat-1203 Flat Tiling (Lab) | 56695 | Sft. | 08 Sep 2016 | 04 Oct 2016 | 09 Aug 2016 | 26 Dec 2016 | 26 | 139 | 0 | 83
A1-FLAT-1204 | 0 | No Unit | 20 May 2016 | 11 Oct 2016 |  |  | 144 | 0 | 0 | 0
A1-Flat-1204 Common Toilet Dado | 172.56 | Sft. | 15 Sep 2016 | 16 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 101
A1-Flat-1204 Master Toilet Dado | 164.5 | Sft. | 17 Sep 2016 | 19 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 2 | 192 | 0 | 98
A1-Flat-1204 Kit. Dado Above | 68.5 | Sft. | 20 Sep 2016 | 21 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 96
A1-Flat-1204 Flat Flooring | 623.45 | Sft. | 29 Sep 2016 | 04 Oct 2016 | 17 Jun 2016 | 26 Dec 2016 | 5 | 192 | 0 | 83
A1-Flat-1204 Flat Skirting | 196.8 | Rft | 07 Oct 2016 | 08 Oct 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 79
A1-Flat-1204 Common Toilet Flooring | 37.47 | Sft. | 17 Sep 2016 | 19 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 2 | 192 | 0 | 98
A1-Flat-1204 Master Toilet Flooring | 39.92 | Sft. | 20 Sep 2016 | 21 Sep 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 96
A1-Flat-1204 Sitout/Terrace Flooring | 62.26 | Sft. | 03 Oct 2016 | 04 Oct 2016 | 17 Jun 2016 | 26 Dec 2016 | 1 | 192 | 0 | 83
A1-Flat-1204 Sitout/Terrace Skirting | 30 | Rft | 07 Oct 2016 | 07 Oct 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 80
A1-Flat-1204 Window Box Flooring | 7.27 | Sft. | 05 Oct 2016 | 05 Oct 2016 | 17 Jun 2016 | 26 Dec 2016 | 0 | 192 | 0 | 82
A1-Flat-1204 Umara Patti | 0 | Rft | 20 May 2016 | 20 May 2016 | 22 Nov 2016 | 26 Dec 2016 | 0 | 34 | 186 | 220
A1-Flat-1204 Flat Tiling (Lab) | 56695 | Sft. | 15 Sep 2016 | 11 Oct 2016 | 09 Aug 2016 | 26 Dec 2016 | 26 | 139 | 0 | 76
A1-12TH FL.LOBBY | 0 | No Unit | 08 Oct 2016 | 12 Oct 2016 |  |  | 4 | 0 | 0 | 0
A1-12th Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 08 Oct 2016 | 12 Oct 2016 | 17 Jun 2016 | 12 Jan 2017 | 4 | 209 | 0 | 92
A1-12th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 08 Oct 2016 | 12 Oct 2016 | 17 Jun 2016 | 12 Jan 2017 | 4 | 209 | 0 | 92
A1-12th Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 08 Oct 2016 | 12 Oct 2016 | 17 Jun 2016 | 27 Dec 2016 | 4 | 193 | 0 | 76
A1-12th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 08 Oct 2016 | 12 Oct 2016 | 17 Jun 2016 | 12 Jan 2017 | 4 | 209 | 0 | 92
A1-12TH FL MAIN STAIR | 343.15 | No Unit | 13 Oct 2016 | 15 Oct 2016 |  |  | 2 | 0 | 0 | 0
A1-12th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 13 Oct 2016 | 15 Oct 2016 | 16 Jun 2016 | 12 Jan 2017 | 2 | 210 | 0 | 89
A1-12th Fl Main Stair Main Staircase Riser | 76 | Rft | 13 Oct 2016 | 15 Oct 2016 | 16 Jun 2016 | 12 Jan 2017 | 2 | 210 | 0 | 89
A1-12th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 13 Oct 2016 | 15 Oct 2016 | 16 Jun 2016 | 12 Jan 2017 | 2 | 210 | 0 | 89
A1-12th Fl Main Stair Main Staircase Tread | 90 | Sft. | 13 Oct 2016 | 15 Oct 2016 | 16 Jun 2016 | 12 Jan 2017 | 2 | 210 | 0 | 89
A1-12th Fl Main Stair Main Staircase (Lab) | 56695 | Sft. | 13 Oct 2016 | 15 Oct 2016 | 16 Jun 2016 | 30 Dec 2016 | 2 | 197 | 0 | 76
A1-12TH FL FIRE STAIR | 343.15 | No Unit | 13 Oct 2016 | 15 Oct 2016 |  |  | 2 | 0 | 0 | 0
A1-12th Fl Fire Stair Fire Staircase Flooring | 309 | Sft. | 13 Oct 2016 | 15 Oct 2016 | 17 Jun 2016 | 12 Jan 2017 | 2 | 209 | 0 | 89
A1-12th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 13 Oct 2016 | 15 Oct 2016 | 17 Jun 2016 | 12 Jan 2017 | 2 | 209 | 0 | 89
A1-12th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 13 Oct 2016 | 15 Oct 2016 | 17 Jun 2016 | 12 Jan 2017 | 2 | 209 | 0 | 89
A1-12th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 13 Oct 2016 | 15 Oct 2016 | 17 Jun 2016 | 12 Jan 2017 | 2 | 209 | 0 | 89
A1-12th Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 13 Oct 2016 | 15 Oct 2016 | 13 Jul 2016 | 30 Dec 2016 | 2 | 170 | 0 | 76
A1-12TH FL.LIFT CLADDING | 343.15 | No Unit | 17 Oct 2016 | 21 Oct 2016 |  |  | 4 | 0 | 0 | 0
A1-12th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 17 Oct 2016 | 21 Oct 2016 | 29 Jul 2016 | 12 Jan 2017 | 4 | 167 | 0 | 83
A1-12th Fl.Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 17 Oct 2016 | 21 Oct 2016 | 29 Jul 2016 | 30 Dec 2016 | 4 | 154 | 0 | 70
A1-12th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 17 Oct 2016 | 21 Oct 2016 | 29 Jul 2016 | 08 Aug 2016 | 4 | 10 | 0 | 0
A1-13TH FLOOR | 0 | No Unit | 21 May 2016 | 01 Nov 2016 |  |  | 164 | 0 | 0 | 0
A1-REFUGE FLAT-1304 | 0 | No Unit | 15 Sep 2016 | 20 Sep 2016 |  |  | 5 | 0 | 0 | 0
A1-Refuge Flat-1304 Flat Tiling (Lab) | 56695 | Sft. | 15 Sep 2016 | 20 Sep 2016 | 22 Nov 2016 | 12 Jan 2017 | 5 | 51 | 68 | 114
A1-Refuge Flat-1304 Refuge Ceramic Skirting | 0 | Rft | 15 Sep 2016 | 20 Sep 2016 | 22 Nov 2016 | 12 Jan 2017 | 5 | 51 | 68 | 114
A1-Refuge Flat-1304 Refuge Ceramic Flooring | 0 | Sft. | 15 Sep 2016 | 20 Sep 2016 | 22 Nov 2016 | 12 Jan 2017 | 5 | 51 | 68 | 114
A1-FLAT-1302 | 0 | No Unit | 21 May 2016 | 11 Oct 2016 |  |  | 143 | 0 | 0 | 0
A1-Flat-1302 Common Toilet Dado | 172.56 | Sft. | 15 Sep 2016 | 16 Sep 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 22 | 118
A1-Flat-1302 Master Toilet Dado | 164.5 | Sft. | 17 Sep 2016 | 19 Sep 2016 | 07 Oct 2016 | 12 Jan 2017 | 2 | 97 | 20 | 115
A1-Flat-1302 Kit. Dado Above | 68.5 | Sft. | 20 Sep 2016 | 21 Sep 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 17 | 113
A1-Flat-1302 Flat Flooring | 629.31 | Sft. | 29 Sep 2016 | 04 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 5 | 97 | 8 | 100
A1-Flat-1302 Flat Skirting | 201.77 | Rft | 07 Oct 2016 | 08 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 0 | 96
A1-Flat-1302 Common Toilet Flooring | 37.47 | Sft. | 17 Sep 2016 | 19 Sep 2016 | 07 Oct 2016 | 12 Jan 2017 | 2 | 97 | 20 | 115
A1-Flat-1302 Master Toilet Flooring | 39.92 | Sft. | 20 Sep 2016 | 21 Sep 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 17 | 113
A1-Flat-1302 Sitout/Terrace Flooring | 48.62 | Sft. | 03 Oct 2016 | 04 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 4 | 100
A1-Flat-1302 Sitout/Terrace Skirting | 23 | Rft | 07 Oct 2016 | 07 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 0 | 97 | 0 | 97
A1-Flat-1302 Window Box Flooring | 14.53 | Sft. | 05 Oct 2016 | 05 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 0 | 97 | 2 | 99
A1-Flat-1302 Umara Patti | 0 | Rft | 21 May 2016 | 21 May 2016 | 07 Oct 2016 | 12 Jan 2017 | 0 | 97 | 139 | 236
A1-Flat-1302 Flat Tiling (Lab) | 56695 | Sft. | 15 Sep 2016 | 11 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 26 | 97 | 22 | 93
A1-FLAT-1303 | 23 | No Unit | 23 May 2016 | 13 Oct 2016 |  |  | 143 | 0 | 0 | 0
A1-Flat-1303 Common Toilet Dado | 172.56 | Sft. | 17 Sep 2016 | 19 Sep 2016 | 07 Oct 2016 | 12 Jan 2017 | 2 | 97 | 20 | 115
A1-Flat-1303 Master Toilet Dado | 164.5 | Sft. | 20 Sep 2016 | 21 Sep 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 17 | 113
A1-Flat-1303 Kit. Dado Above | 68.5 | Sft. | 22 Sep 2016 | 23 Sep 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 15 | 111
A1-Flat-1303 Flat Flooring | 629.31 | Sft. | 01 Oct 2016 | 06 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 5 | 97 | 6 | 98
A1-Flat-1303 Flat Skirting | 201.77 | Rft | 10 Oct 2016 | 11 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 0 | 93
A1-Flat-1303 Common Toilet Flooring | 37.47 | Sft. | 20 Sep 2016 | 21 Sep 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 17 | 113
A1-Flat-1303 Master Toilet Flooring | 39.92 | Sft. | 22 Sep 2016 | 23 Sep 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 15 | 111
A1-Flat-1303 Sitout/Terrace Flooring | 76.33 | Sft. | 05 Oct 2016 | 06 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 2 | 98
A1-Flat-1303 Sitout/Terrace Skirting | 31 | Rft | 10 Oct 2016 | 10 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 0 | 97 | 0 | 94
A1-Flat-1303 Window Box Flooring | 14.53 | Sft. | 07 Oct 2016 | 07 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 0 | 97 | 0 | 97
A1-Flat-1303 Umara Patti | 0 | Rft | 23 May 2016 | 23 May 2016 | 07 Oct 2016 | 12 Jan 2017 | 0 | 97 | 137 | 234
A1-Flat-1303 Flat Tiling (Lab) | 56695 | Sft. | 17 Sep 2016 | 13 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 26 | 97 | 20 | 91
A1-FLAT-1301 | 56693 | No Unit | 24 May 2016 | 13 Oct 2016 |  |  | 142 | 0 | 0 | 0
A1-Flat-1301 Common Toilet Dado | 172.56 | Sft. | 17 Sep 2016 | 19 Sep 2016 | 26 Sep 2016 | 12 Jan 2017 | 2 | 108 | 9 | 115
A1-Flat-1301 Master Toilet Dado | 164.5 | Sft. | 20 Sep 2016 | 21 Sep 2016 | 26 Sep 2016 | 12 Jan 2017 | 1 | 108 | 6 | 113
A1-Flat-1301 Kit. Dado Above | 63.39 | Sft. | 22 Sep 2016 | 23 Sep 2016 | 26 Sep 2016 | 12 Jan 2017 | 1 | 108 | 4 | 111
A1-Flat-1301 Flat Flooring | 637.89 | Sft. | 01 Oct 2016 | 06 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 5 | 97 | 6 | 98
A1-Flat-1301 Flat Skirting | 204.04 | Rft | 10 Oct 2016 | 11 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 0 | 93
A1-Flat-1301 Common Toilet Flooring | 37.47 | Sft. | 20 Sep 2016 | 21 Sep 2016 | 26 Sep 2016 | 12 Jan 2017 | 1 | 108 | 6 | 113
A1-Flat-1301 Master Toilet Flooring | 39.92 | Sft. | 22 Sep 2016 | 23 Sep 2016 | 26 Sep 2016 | 12 Jan 2017 | 1 | 108 | 4 | 111
A1-Flat-1301 Sitout/Terrace Flooring | 48.62 | Sft. | 05 Oct 2016 | 06 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 2 | 98
A1-Flat-1301 Sitout/Terrace Skirting | 23.09 | Rft | 10 Oct 2016 | 10 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 0 | 97 | 0 | 94
A1-Flat-1301 Window Box Flooring | 14.53 | Sft. | 07 Oct 2016 | 07 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 0 | 97 | 0 | 97
A1-Flat-1301 Umara Patti | 0 | Rft | 24 May 2016 | 24 May 2016 | 07 Oct 2016 | 12 Jan 2017 | 0 | 97 | 136 | 233
A1-Flat-1301 Flat Tiling (Lab) | 56695 | Sft. | 17 Sep 2016 | 13 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 26 | 97 | 20 | 91
A1-13TH FL.LOBBY | 0 | No Unit | 22 Oct 2016 | 26 Oct 2016 |  |  | 4 | 0 | 0 | 0
A1-13th Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 22 Oct 2016 | 26 Oct 2016 | 13 Jul 2016 | 13 Jan 2017 | 4 | 184 | 0 | 79
A1-13th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 22 Oct 2016 | 26 Oct 2016 | 13 Jul 2016 | 13 Jan 2017 | 4 | 184 | 0 | 79
A1-13th Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 22 Oct 2016 | 26 Oct 2016 | 13 Jul 2016 | 13 Jan 2017 | 4 | 184 | 0 | 79
A1-13th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 22 Oct 2016 | 26 Oct 2016 | 13 Jul 2016 | 13 Jan 2017 | 4 | 184 | 0 | 79
A1-13TH FL MAIN STAIR | 343.15 | No Unit | 27 Oct 2016 | 29 Oct 2016 |  |  | 2 | 0 | 0 | 0
A1-13th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 27 Oct 2016 | 29 Oct 2016 | 17 Jun 2016 | 13 Jan 2017 | 2 | 210 | 0 | 76
A1-13th Fl Main Stair Main Staircase Riser | 76 | Rft | 27 Oct 2016 | 29 Oct 2016 | 17 Jun 2016 | 13 Jan 2017 | 2 | 210 | 0 | 76
A1-13th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 27 Oct 2016 | 29 Oct 2016 | 17 Jun 2016 | 13 Jan 2017 | 2 | 210 | 0 | 76
A1-13th Fl Main Stair Main Staircase Tread | 90 | Sft. | 27 Oct 2016 | 29 Oct 2016 | 17 Jun 2016 | 13 Jan 2017 | 2 | 210 | 0 | 76
A1-13th Fl Main Stair Main Staircase (Lab) | 56695 | Sft. | 27 Oct 2016 | 29 Oct 2016 | 13 Jul 2016 | 13 Jan 2017 | 2 | 184 | 0 | 76
A1-13TH FL FIRE STAIR | 343.15 | No Unit | 27 Oct 2016 | 29 Oct 2016 |  |  | 2 | 0 | 0 | 0
A1-13th Fl Fire Stair Fire Staircase Flooring | 309 | Sft. | 27 Oct 2016 | 29 Oct 2016 | 17 Jun 2016 | 13 Jan 2017 | 2 | 210 | 0 | 76
A1-13th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 27 Oct 2016 | 29 Oct 2016 | 17 Jun 2016 | 13 Jan 2017 | 2 | 210 | 0 | 76
A1-13th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 27 Oct 2016 | 29 Oct 2016 | 17 Jun 2016 | 13 Jan 2017 | 2 | 210 | 0 | 76
A1-13th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 27 Oct 2016 | 29 Oct 2016 | 17 Jun 2016 | 13 Jan 2017 | 2 | 210 | 0 | 76
A1-13th Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 27 Oct 2016 | 29 Oct 2016 | 13 Jul 2016 | 13 Jan 2017 | 2 | 184 | 0 | 76
A1-13TH FL.LIFT CLADDING | 343.15 | No Unit | 27 Oct 2016 | 01 Nov 2016 |  |  | 5 | 0 | 0 | 0
A1-13th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 27 Oct 2016 | 01 Nov 2016 | 29 Jul 2016 | 13 Jan 2017 | 5 | 168 | 0 | 73
A1-13th Fl.Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 27 Oct 2016 | 01 Nov 2016 | 29 Jul 2016 | 13 Jan 2017 | 5 | 168 | 0 | 73
A1-13th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 27 Oct 2016 | 01 Nov 2016 | 29 Jul 2016 | 08 Aug 2016 | 5 | 10 | 0 | 0
A1-14TH FLOOR | 44 | No Unit | 25 May 2016 | 12 Nov 2016 |  |  | 171 | 0 | 0 | 0
A1-FLAT-1401 | 0 | No Unit | 25 May 2016 | 13 Oct 2016 |  |  | 141 | 0 | 0 | 0
A1-Flat-1401 Common Toilet Dado | 172.56 | Sft. | 17 Sep 2016 | 19 Sep 2016 | 12 Jan 2017 | 12 Jan 2017 | 2 | 0 | 117 | 115
A1-Flat-1401 Master Toilet Dado | 164.5 | Sft. | 20 Sep 2016 | 21 Sep 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 114 | 113
A1-Flat-1401 Kit. Dado Above | 68.5 | Sft. | 22 Sep 2016 | 23 Sep 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 112 | 111
A1-Flat-1401 Flat Flooring | 630.02 | Sft. | 01 Oct 2016 | 06 Oct 2016 | 12 Jan 2017 | 12 Jan 2017 | 5 | 0 | 103 | 98
A1-Flat-1401 Flat Skirting | 199.06 | Rft | 10 Oct 2016 | 11 Oct 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 94 | 93
A1-Flat-1401 Common Toilet Flooring | 37.47 | Sft. | 20 Sep 2016 | 21 Sep 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 114 | 113
A1-Flat-1401 Master Toilet Flooring | 39.92 | Sft. | 22 Sep 2016 | 23 Sep 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 112 | 111
A1-Flat-1401 Sitout/Terrace Flooring | 125.06 | Sft. | 05 Oct 2016 | 06 Oct 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 99 | 98
A1-Flat-1401 Sitout/Terrace Skirting | 59 | Rft | 10 Oct 2016 | 10 Oct 2016 | 12 Jan 2017 | 12 Jan 2017 | 0 | 0 | 94 | 94
A1-Flat-1401 Window Box Flooring | 7.27 | Sft. | 07 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 12 Jan 2017 | 0 | 0 | 97 | 97
A1-Flat-1401 Umara Patti | 0 | Rft | 25 May 2016 | 25 May 2016 | 12 Jan 2017 | 12 Jan 2017 | 0 | 0 | 232 | 232
A1-Flat-1401 Flat Tiling (Lab) | 56695 | Sft. | 17 Sep 2016 | 13 Oct 2016 | 12 Jan 2017 | 12 Jan 2017 | 26 | 0 | 117 | 91
A1-FLAT-1402 | 0 | No Unit | 26 May 2016 | 29 Oct 2016 |  |  | 156 | 0 | 0 | 0
A1-Flat-1402 Common Toilet Dado | 172.56 | Sft. | 20 Sep 2016 | 21 Sep 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 114 | 113
A1-Flat-1402 Master Toilet Dado | 164.5 | Sft. | 22 Sep 2016 | 23 Sep 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 112 | 111
A1-Flat-1402 Kit. Dado Above | 68.5 | Sft. | 24 Sep 2016 | 26 Sep 2016 | 12 Jan 2017 | 12 Jan 2017 | 2 | 0 | 110 | 108
A1-Flat-1402 Flat Flooring | 623.45 | Sft. | 04 Oct 2016 | 08 Oct 2016 | 12 Jan 2017 | 12 Jan 2017 | 4 | 0 | 100 | 96
A1-Flat-1402 Flat Skirting | 196.8 | Rft | 12 Oct 2016 | 13 Oct 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 92 | 91
A1-Flat-1402 Common Toilet Flooring | 37.47 | Sft. | 22 Sep 2016 | 23 Sep 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 112 | 111
A1-Flat-1402 Master Toilet Flooring | 39.92 | Sft. | 24 Sep 2016 | 26 Sep 2016 | 12 Jan 2017 | 12 Jan 2017 | 2 | 0 | 110 | 108
A1-Flat-1402 Sitout/Terrace Flooring | 125.06 | Sft. | 07 Oct 2016 | 08 Oct 2016 | 12 Jan 2017 | 12 Jan 2017 | 1 | 0 | 97 | 96
A1-Flat-1402 Sitout/Terrace Skirting | 59 | Rft | 12 Oct 2016 | 12 Oct 2016 | 12 Jan 2017 | 12 Jan 2017 | 0 | 0 | 92 | 92
A1-Flat-1402 Window Box Flooring | 7.27 | Sft. | 10 Oct 2016 | 10 Oct 2016 | 12 Jan 2017 | 12 Jan 2017 | 0 | 0 | 94 | 94
A1-Flat-1402 Umara Patti | 0 | Rft | 26 May 2016 | 26 May 2016 | 12 Jan 2017 | 12 Jan 2017 | 0 | 0 | 231 | 231
A1-Flat-1402 Flat Tiling (Lab) | 56695 | Sft. | 04 Oct 2016 | 29 Oct 2016 | 12 Jan 2017 | 12 Jan 2017 | 25 | 0 | 100 | 75
A1-FLAT-1403 | 0 | No Unit | 27 May 2016 | 15 Oct 2016 |  |  | 141 | 0 | 0 | 0
A1-Flat-1403 Common Toilet Dado | 172.56 | Sft. | 22 Sep 2016 | 23 Sep 2016 | 10 May 2016 | 26 Dec 2016 | 1 | 230 | 0 | 94
A1-Flat-1403 Master Toilet Dado | 164.5 | Sft. | 24 Sep 2016 | 26 Sep 2016 | 10 May 2016 | 26 Dec 2016 | 2 | 230 | 0 | 91
A1-Flat-1403 Kit. Dado Above | 68.5 | Sft. | 27 Sep 2016 | 28 Sep 2016 | 10 May 2016 | 26 Dec 2016 | 1 | 230 | 0 | 89
A1-Flat-1403 Flat Flooring | 623.45 | Sft. | 06 Oct 2016 | 11 Oct 2016 | 10 May 2016 | 26 Dec 2016 | 5 | 230 | 0 | 76
A1-Flat-1403 Flat Skirting | 196.8 | Rft | 14 Oct 2016 | 15 Oct 2016 | 10 May 2016 | 26 Dec 2016 | 1 | 230 | 0 | 72
A1-Flat-1403 Common Toilet Flooring | 37.47 | Sft. | 24 Sep 2016 | 26 Sep 2016 | 10 May 2016 | 26 Dec 2016 | 2 | 230 | 0 | 91
A1-Flat-1403 Master Toilet Flooring | 39.92 | Sft. | 27 Sep 2016 | 28 Sep 2016 | 10 May 2016 | 26 Dec 2016 | 1 | 230 | 0 | 89
A1-Flat-1403 Sitout/Terrace Flooring | 62.26 | Sft. | 10 Oct 2016 | 11 Oct 2016 | 05 May 2016 | 26 Dec 2016 | 1 | 235 | 0 | 76
A1-Flat-1403 Sitout/Terrace Skirting | 30 | Rft | 14 Oct 2016 | 14 Oct 2016 | 05 May 2016 | 26 Dec 2016 | 0 | 235 | 0 | 73
A1-Flat-1403 Window Box Flooring | 7.27 | Sft. | 24 Sep 2016 | 24 Sep 2016 | 10 May 2016 | 26 Dec 2016 | 0 | 230 | 0 | 93
A1-Flat-1403 Umara Patti | 0 | Rft | 27 May 2016 | 27 May 2016 | 26 Dec 2016 | 12 Jan 2017 | 0 | 17 | 213 | 230
A1-Flat-1403 Flat Tiling (Lab) | 56695 | Sft. | 22 Sep 2016 | 22 Sep 2016 | 10 May 2016 | 26 Dec 2016 | 0 | 230 | 0 | 95
A1-FLAT-1404 | 0 | No Unit | 28 May 2016 | 18 Oct 2016 |  |  | 143 | 0 | 0 | 0
A1-Flat-1404 Common Toilet Dado | 172.56 | Sft. | 24 Sep 2016 | 26 Sep 2016 | 26 Sep 2016 | 12 Jan 2017 | 2 | 108 | 2 | 108
A1-Flat-1404 Master Toilet Dado | 164.5 | Sft. | 27 Sep 2016 | 28 Sep 2016 | 26 Sep 2016 | 12 Jan 2017 | 1 | 108 | 0 | 106
A1-Flat-1404 Kit. Dado Above | 68.5 | Sft. | 29 Sep 2016 | 30 Sep 2016 | 10 May 2016 | 12 Jan 2017 | 1 | 247 | 0 | 104
A1-Flat-1404 Flat Flooring | 623.45 | Sft. | 08 Oct 2016 | 13 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 5 | 97 | 0 | 91
A1-Flat-1404 Flat Skirting | 196.8 | Rft | 17 Oct 2016 | 18 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 0 | 86
A1-Flat-1404 Common Toilet Flooring | 37.47 | Sft. | 27 Sep 2016 | 28 Sep 2016 | 26 Sep 2016 | 12 Jan 2017 | 1 | 108 | 0 | 106
A1-Flat-1404 Master Toilet Flooring | 39.92 | Sft. | 29 Sep 2016 | 30 Sep 2016 | 26 Sep 2016 | 12 Jan 2017 | 1 | 108 | 0 | 104
A1-Flat-1404 Sitout/Terrace Flooring | 62.26 | Sft. | 12 Oct 2016 | 13 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 1 | 97 | 0 | 91
A1-Flat-1404 Sitout/Terrace Skirting | 30 | Rft | 17 Oct 2016 | 17 Oct 2016 | 07 Oct 2016 | 12 Jan 2017 | 0 | 97 | 0 | 87
A1-Flat-1404 Window Box Flooring | 7.27 | Sft. | 14 Oct 2016 | 14 Oct 2016 | 10 May 2016 | 12 Jan 2017 | 0 | 247 | 0 | 90
A1-Flat-1404 Umara Patti | 0 | Rft | 28 May 2016 | 28 May 2016 | 07 Oct 2016 | 12 Jan 2017 | 0 | 97 | 132 | 229
A1-Flat-1404 Flat Tiling (Lab) | 56695 | Sft. | 24 Sep 2016 | 24 Sep 2016 | 07 Oct 2016 | 12 Jan 2017 | 0 | 97 | 13 | 110
A1-14TH FL.LOBBY | 0 | No Unit | 31 Oct 2016 | 03 Nov 2016 |  |  | 3 | 0 | 0 | 0
A1-14th Fl.Lobby Floor Lobby Flooring | 258.32 | Sft. | 31 Oct 2016 | 03 Nov 2016 | 29 Jul 2016 | 28 Jan 2017 | 3 | 183 | 0 | 86
A1-14th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 31 Oct 2016 | 03 Nov 2016 | 29 Jul 2016 | 28 Jan 2017 | 3 | 183 | 0 | 86
A1-14th Fl.Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 31 Oct 2016 | 03 Nov 2016 | 29 Jul 2016 | 13 Jan 2017 | 3 | 168 | 0 | 71
A1-14th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 31 Oct 2016 | 03 Nov 2016 | 29 Jul 2016 | 28 Jan 2017 | 3 | 183 | 0 | 86
A1-14TH FL MAIN STAIR | 343.15 | No Unit | 04 Nov 2016 | 07 Nov 2016 |  |  | 3 | 0 | 0 | 0
A1-14th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 04 Nov 2016 | 07 Nov 2016 | 17 Jun 2016 | 28 Jan 2017 | 3 | 225 | 0 | 82
A1-14th Fl Main Stair Main Staircase Riser | 76 | Rft | 04 Nov 2016 | 07 Nov 2016 | 17 Jun 2016 | 28 Jan 2017 | 3 | 225 | 0 | 82
A1-14th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 04 Nov 2016 | 07 Nov 2016 | 17 Jun 2016 | 28 Jan 2017 | 3 | 225 | 0 | 82
A1-14th Fl Main Stair Main Staircase Tread | 90 | Sft. | 04 Nov 2016 | 07 Nov 2016 | 17 Jun 2016 | 28 Jan 2017 | 3 | 225 | 0 | 82
A1-14th Fl Main Stair Main Staircase (Lab) | 56695 | Sft. | 04 Nov 2016 | 07 Nov 2016 | 20 Jul 2016 | 13 Jan 2017 | 3 | 177 | 0 | 67
A1-14TH FL FIRE STAIR | 343.15 | No Unit | 04 Nov 2016 | 07 Nov 2016 |  |  | 3 | 0 | 0 | 0
A1-14th Fl Fire Stair Fire Staircase Flooring | 309 | Sft. | 04 Nov 2016 | 07 Nov 2016 | 17 Jun 2016 | 28 Jan 2017 | 3 | 225 | 0 | 82
A1-14th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 04 Nov 2016 | 07 Nov 2016 | 17 Jun 2016 | 28 Jan 2017 | 3 | 225 | 0 | 82
A1-14th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 04 Nov 2016 | 07 Nov 2016 | 17 Jun 2016 | 28 Jan 2017 | 3 | 225 | 0 | 82
A1-14th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 04 Nov 2016 | 07 Nov 2016 | 17 Jun 2016 | 28 Jan 2017 | 3 | 225 | 0 | 82
A1-14th Fl Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 04 Nov 2016 | 07 Nov 2016 | 20 Jul 2016 | 13 Jan 2017 | 3 | 177 | 0 | 67
A1-14TH FL.LIFT CLADDING | 343.15 | No Unit | 08 Nov 2016 | 12 Nov 2016 |  |  | 4 | 0 | 0 | 0
A1-14th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 08 Nov 2016 | 12 Nov 2016 | 29 Jul 2016 | 28 Jan 2017 | 4 | 183 | 0 | 77
A1-14th Fl.Lift Cladding Lift Cladding (lab) | 56695 | Sft. | 08 Nov 2016 | 12 Nov 2016 | 29 Jul 2016 | 13 Jan 2017 | 4 | 168 | 0 | 62
A1-14th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 08 Nov 2016 | 12 Nov 2016 | 29 Jul 2016 | 28 Jan 2017 | 4 | 183 | 0 | 77
A1-TOP TERRACE | 0 | No Unit | 16 Aug 2016 | 10 Nov 2016 |  |  | 86 | 0 | 0 | 0
A1-TERRACE LOBBY | 0 | No Unit | 08 Nov 2016 | 10 Nov 2016 |  |  | 2 | 0 | 0 | 0
A1-Terrace Lobby Floor lobby Tiling (Lab) | 56695 | Sft. | 08 Nov 2016 | 10 Nov 2016 | 20 Sep 2016 | 13 Jan 2017 | 2 | 115 | 0 | 64
A1-Terrace Lobby Floor Lobby Flooring | 0 | Sft. | 08 Nov 2016 | 10 Nov 2016 | 20 Sep 2016 | 13 Jan 2017 | 2 | 115 | 0 | 64
A1-Terrace Lobby Floor Lobby Skirting | 0 | Rft | 08 Nov 2016 | 10 Nov 2016 | 20 Sep 2016 | 13 Jan 2017 | 2 | 115 | 0 | 64
A1-TERRACE FIRE STAIR | 56693 | No Unit | 08 Nov 2016 | 10 Nov 2016 |  |  | 2 | 0 | 0 | 0
A1-Terrace Fire Stair Fire Staircase Flooring | 0 | Sft. | 08 Nov 2016 | 10 Nov 2016 | 20 Jul 2016 | 13 Jan 2017 | 2 | 177 | 0 | 64
A1-Terrace Fire Stair Fire Staircase Riser | 0 | Rft | 08 Nov 2016 | 10 Nov 2016 | 20 Jul 2016 | 13 Jan 2017 | 2 | 177 | 0 | 64
A1-Terrace Fire Stair Fire Staircase Skirting | 0 | Rft | 08 Nov 2016 | 10 Nov 2016 | 20 Jul 2016 | 13 Jan 2017 | 2 | 177 | 0 | 64
A1-Terrace Fire Stair Fire Staircase Tread | 0 | Sft. | 08 Nov 2016 | 10 Nov 2016 | 20 Jul 2016 | 13 Jan 2017 | 2 | 177 | 0 | 64
A1-Terrace Fire Stair Fire Staircase (Lab) | 56695 | Sft. | 08 Nov 2016 | 10 Nov 2016 | 20 Jul 2016 | 13 Jan 2017 | 2 | 177 | 0 | 64
A1-TERRACE MACHINE ROOM | 0 | No Unit | 16 Aug 2016 | 20 Aug 2016 |  |  | 4 | 0 | 0 | 0
A1-Terrace Machine Room IPS Finish | 0 | Sft. | 16 Aug 2016 | 20 Aug 2016 | 13 Jan 2017 | 13 Jan 2017 | 4 | 0 | 150 | 146
A1-MAINTENANACE | 323.92 | No Unit | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-MAINT.ALL FLATS | 0 | No Unit | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-Maint.All Flats Common Toilet Dado | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 | 12 Aug 2016 |  | 34 | 0 | 0 | 0
A1-Maint.All Flats Master Toilet Dado | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 | 12 Aug 2016 |  | 34 | 0 | 0 | 0
A1-Maint.All Flats Kit. Dado Above | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 | 12 Aug 2016 |  | 34 | 0 | 0 | 0
A1-Maint.All Flats Flat Flooring | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 | 01 Aug 2016 |  | 34 | 0 | 0 | 0
A1-Maint.All Flats Flat Skirting | 0 | Rft | 04 Oct 2016 | 07 Nov 2016 | 12 Aug 2016 |  | 34 | 0 | 0 | 0
A1-Maint.All Flats Common Toilet Flooring | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 | 12 Aug 2016 |  | 34 | 0 | 0 | 0
A1-Maint.All Flats Master Toilet Flooring | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 | 12 Aug 2016 |  | 34 | 0 | 0 | 0
A1-Maint.All Flats Sitout/Terrace Flooring | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 | 12 Aug 2016 |  | 34 | 0 | 0 | 0
A1-Maint.All Flats Sitout/Terrace Skirting | 0 | Rft | 04 Oct 2016 | 07 Nov 2016 | 12 Aug 2016 |  | 34 | 0 | 0 | 0
A1-Maint.All Flats Window Box Flooring | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 | 12 Aug 2016 |  | 34 | 0 | 0 | 0
A1-Maint.All Flats Umara Patti | 0 | Rft | 04 Oct 2016 | 07 Nov 2016 | 12 Aug 2016 |  | 34 | 0 | 0 | 0
A1-MAINT.ALL COMMON AREA | 0 | No Unit | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-MAINT.ALL LOBBY | 0 | No Unit | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-Maint.All Lobby Floor Lobby Flooring | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-Maint.All Lobby Floor Lobby Skirting | 0 | Rft | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-Maint.All Lobby Misc. Material (White Cement) | 0 | NO | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-MAINT.ALL MAIN STAIR | 0 | No Unit | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-Maint.All Main Stair Main Staircase Flooring | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 | 26 Sep 2016 |  | 34 | 0 | 0 | 0
A1-Maint.All Main Stair Main Staircase Riser | 0 | Rft | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-Maint.All Main Stair Main Staircase Skirting | 0 | Rft | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-Maint.All Main Stair Main Staircase Tread | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-MAINT.ALL FIRE STAIR | 343.15 | No Unit | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-Maint.All Fire Stair Fire Staircase Flooring | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 | 25 Nov 2016 |  | 34 | 0 | 52 | 0
A1-Maint.All Fire Stair Fire Staircase Riser | 0 | Rft | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-Maint.All Fire Stair Fire Staircase Skirting | 0 | Rft | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-Maint.All Fire Stair Fire Staircase Tread | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-MAINT.ALL LIFT CLADDING | 0 | No Unit | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-Maint.All Lift Cladding Lift Cladding-1 | 0 | Sft. | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-Maint.All Lift Cladding Misc. Material (White Cement) | 0 | NO | 04 Oct 2016 | 07 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-SHIFTING OF RABIT | 0 | No Unit | 20 Sep 2016 | 24 Oct 2016 |  |  | 34 | 0 | 0 | 0
A1-Shifting of Rabit Shifting of Rabit by tractor (Morter Wa | 0 | Cft | 20 Sep 2016 | 24 Oct 2016 | 09 May 2016 |  | 34 | 0 | 0 | 0
A1-MISC. | 0 | No Unit | 20 Apr 2016 | 28 Nov 2016 |  |  | 222 | 0 | 0 | 0
A1-Misc. HCL Acid | 500 | lit | 20 Apr 2016 | 28 Nov 2016 | 13 Jan 2016 |  | 222 | 0 | 0 | 0
A1-TILING (M+L) | 0 | No Unit | 07 Dec 2015 | 19 Dec 2016 |  |  | 378 | 0 | 0 | 0
A1-PARKING TILE | 1 | No Unit | 14 Oct 2016 | 17 Oct 2016 |  |  | 3 | 0 | 0 | 0
A1-Parking Tile Granite Door Frame (M+L) | 0 | No. | 14 Oct 2016 | 17 Oct 2016 | 13 Jan 2017 | 13 Jan 2017 | 3 | 0 | 91 | 88
A1-Parking Tile Granite Window Jambs (M+L) | 0 | NO | 14 Oct 2016 | 17 Oct 2016 | 13 Jan 2017 | 13 Jan 2017 | 3 | 0 | 91 | 88
A1-Parking Tile Granite Ledge wall (M+L) | 0 | Rft. | 14 Oct 2016 | 17 Oct 2016 | 13 Jan 2017 | 13 Jan 2017 | 3 | 0 | 91 | 88
A1-PARKING FL FIRE STAIR | 0 | No Unit | 14 Oct 2016 | 15 Oct 2016 |  |  | 1 | 0 | 0 | 0
A1-Parking Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 14 Oct 2016 | 15 Oct 2016 | 13 Jan 2017 | 13 Jan 2017 | 1 | 0 | 91 | 90
A1-1ST FLOOR | 0 | No Unit | 07 Dec 2015 | 24 Aug 2016 |  |  | 261 | 0 | 0 | 0
A1-FLAT 101 TILE (M+L) | 0 | No Unit | 07 Dec 2015 | 17 Aug 2016 |  |  | 254 | 0 | 0 | 0
A1-Flat 101 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 07 Dec 2015 | 10 Dec 2015 | 19 Dec 2015 | 27 Jul 2016 | 3 | 221 | 12 | 230
A1-Flat 101 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 21 Jan 2016 | 23 Jan 2016 | 11 Jan 2016 | 22 Jun 2016 | 2 | 163 | 0 | 151
A1-Flat 101 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 22 Jan 2016 | 23 Jan 2016 | 11 Feb 2016 | 13 Jul 2016 | 1 | 153 | 20 | 172
A1-Flat 101 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 16 Aug 2016 | 17 Aug 2016 | 29 Feb 2016 | 25 Jul 2016 | 1 | 147 | 0 | 0
A1-Flat 101 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 22 Jan 2016 | 22 Jan 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 68 | 155
A1-Flat 101 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 02 Feb 2016 | 03 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 57 | 143
A1-Flat 101 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 02 Feb 2016 | 03 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 57 | 143
A1-FLAT 102 TILE (M+L) | 0 | No Unit | 11 Dec 2015 | 19 Aug 2016 |  |  | 252 | 0 | 0 | 0
A1-Flat 102 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 11 Dec 2015 | 15 Dec 2015 | 19 Dec 2015 | 27 Jul 2016 | 4 | 221 | 8 | 225
A1-Flat 102 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 23 Jan 2016 | 27 Jan 2016 | 11 Jan 2016 | 22 Jun 2016 | 4 | 163 | 0 | 147
A1-Flat 102 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 25 Jan 2016 | 27 Jan 2016 | 11 Feb 2016 | 13 Jul 2016 | 2 | 153 | 17 | 168
A1-Flat 102 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 18 Aug 2016 | 19 Aug 2016 | 29 Feb 2016 | 25 Jul 2016 | 1 | 147 | 0 | 0
A1-Flat 102 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 25 Jan 2016 | 25 Jan 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 65 | 152
A1-Flat 102 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 04 Feb 2016 | 05 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 55 | 141
A1-Flat 102 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 04 Feb 2016 | 05 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 55 | 141
A1-FLAT 103 TILE (M+L) | 0 | No Unit | 16 Dec 2015 | 22 Aug 2016 |  |  | 250 | 0 | 0 | 0
A1-Flat 103 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 16 Dec 2015 | 19 Dec 2015 | 19 Dec 2015 | 27 Jul 2016 | 3 | 221 | 3 | 221
A1-Flat 103 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 27 Jan 2016 | 29 Jan 2016 | 11 Jan 2016 | 22 Jun 2016 | 2 | 163 | 0 | 145
A1-Flat 103 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 28 Jan 2016 | 29 Jan 2016 | 11 Feb 2016 | 13 Jul 2016 | 1 | 153 | 14 | 166
A1-Flat 103 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 20 Aug 2016 | 22 Aug 2016 | 29 Feb 2016 | 25 Jul 2016 | 2 | 147 | 0 | 0
A1-Flat 103 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 30 Jan 2016 | 30 Jan 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 60 | 147
A1-Flat 103 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 06 Feb 2016 | 08 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 2 | 87 | 53 | 138
A1-Flat 103 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | Rft. | 06 Feb 2016 | 08 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 2 | 87 | 53 | 138
A1-FLAT 104 TILE (M+L) | 0 | No Unit | 21 Dec 2015 | 24 Aug 2016 |  |  | 247 | 0 | 0 | 0
A1-Flat 104 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 21 Dec 2015 | 24 Dec 2015 | 19 Dec 2015 | 27 Jul 2016 | 3 | 221 | 0 | 216
A1-Flat 104 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 29 Jan 2016 | 01 Feb 2016 | 11 Jan 2016 | 22 Jun 2016 | 3 | 163 | 0 | 142
A1-Flat 104 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 30 Jan 2016 | 01 Feb 2016 | 11 Feb 2016 | 13 Jul 2016 | 2 | 153 | 12 | 163
A1-Flat 104 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 23 Aug 2016 | 24 Aug 2016 | 29 Feb 2016 | 25 Jul 2016 | 1 | 147 | 0 | 0
A1-Flat 104 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 02 Feb 2016 | 02 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 57 | 144
A1-Flat 104 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 09 Feb 2016 | 10 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 50 | 136
A1-Flat 104 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | Rft. | 09 Feb 2016 | 10 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 50 | 136
A1-1ST FL.LOBBY | 0 | No Unit | 20 Feb 2016 | 22 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1-1st Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 20 Feb 2016 | 22 Feb 2016 | 17 Aug 2016 | 30 Jan 2017 | 2 | 166 | 179 | 343
A1- 1ST FL FIRE STAIR | 0 | No Unit | 20 Feb 2016 | 22 Feb 2016 |  |  | 2 | 0 | 0 | 0
A1- 1st Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 20 Feb 2016 | 22 Feb 2016 | 17 Aug 2016 | 30 Jan 2017 | 2 | 166 | 179 | 343
A1-2ND FLOOR | 0 | No Unit | 15 Dec 2015 | 02 Sep 2016 |  |  | 262 | 0 | 0 | 0
A1-FLAT 201 TILE (M+L) | 11 | No Unit | 15 Dec 2015 | 26 Aug 2016 |  |  | 255 | 0 | 0 | 0
A1-Flat 201 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Dec 2015 | 18 Dec 2015 | 31 Dec 2015 | 27 Jul 2016 | 3 | 209 | 16 | 222
A1-Flat 201 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 01 Feb 2016 | 03 Feb 2016 | 30 Jan 2016 | 22 Jun 2016 | 2 | 144 | 0 | 140
A1-Flat 201 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 02 Feb 2016 | 03 Feb 2016 | 11 Feb 2016 | 13 Jul 2016 | 1 | 153 | 9 | 161
A1-Flat 201 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 25 Aug 2016 | 26 Aug 2016 | 02 Mar 2016 | 25 Jul 2016 | 1 | 145 | 0 | 0
A1-Flat 201 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 04 Feb 2016 | 04 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 55 | 142
A1-Flat 201 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 11 Feb 2016 | 12 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 48 | 134
A1-Flat 201 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 11 Feb 2016 | 12 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 48 | 134
A1-FLAT 202 TILE (M+L) | 0 | No Unit | 19 Dec 2015 | 29 Aug 2016 |  |  | 254 | 0 | 0 | 0
A1-Flat 202 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 19 Dec 2015 | 23 Dec 2015 | 31 Dec 2015 | 27 Jul 2016 | 4 | 209 | 12 | 217
A1-Flat 202 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 03 Feb 2016 | 05 Feb 2016 | 30 Jan 2016 | 22 Jun 2016 | 2 | 144 | 0 | 138
A1-Flat 202 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 04 Feb 2016 | 05 Feb 2016 | 11 Feb 2016 | 13 Jul 2016 | 1 | 153 | 7 | 159
A1-Flat 202 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 27 Aug 2016 | 29 Aug 2016 | 02 Mar 2016 | 25 Jul 2016 | 2 | 145 | 0 | 0
A1-Flat 202 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 06 Feb 2016 | 06 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 53 | 140
A1-Flat 202 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 13 Feb 2016 | 15 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 2 | 87 | 46 | 131
A1-Flat 202 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 13 Feb 2016 | 15 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 2 | 87 | 46 | 131
A1-FLAT 203 TILE (M+L) | 0 | No Unit | 24 Dec 2015 | 31 Aug 2016 |  |  | 251 | 0 | 0 | 0
A1-Flat 203 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 24 Dec 2015 | 28 Dec 2015 | 31 Dec 2015 | 27 Jul 2016 | 4 | 209 | 7 | 212
A1-Flat 203 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 05 Feb 2016 | 08 Feb 2016 | 30 Jan 2016 | 22 Jun 2016 | 3 | 144 | 0 | 135
A1-Flat 203 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 06 Feb 2016 | 08 Feb 2016 | 11 Feb 2016 | 13 Jul 2016 | 2 | 153 | 5 | 156
A1-Flat 203 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 30 Aug 2016 | 31 Aug 2016 | 02 Mar 2016 | 25 Jul 2016 | 1 | 145 | 0 | 0
A1-Flat 203 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 09 Feb 2016 | 09 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 50 | 137
A1-Flat 203 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 16 Feb 2016 | 17 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 43 | 129
A1-Flat 203 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 16 Feb 2016 | 17 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 43 | 129
A1-FLAT 204 TILE (M+L) | 0 | No Unit | 29 Dec 2015 | 02 Sep 2016 |  |  | 248 | 0 | 0 | 0
A1-Flat 204 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 29 Dec 2015 | 02 Jan 2016 | 31 Dec 2015 | 27 Jul 2016 | 4 | 209 | 2 | 207
A1-Flat 204 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 08 Feb 2016 | 10 Feb 2016 | 30 Jan 2016 | 22 Jun 2016 | 2 | 144 | 0 | 133
A1-Flat 204 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 09 Feb 2016 | 10 Feb 2016 | 11 Feb 2016 | 13 Jul 2016 | 1 | 153 | 2 | 154
A1-Flat 204 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 01 Sep 2016 | 02 Sep 2016 | 02 Mar 2016 | 25 Jul 2016 | 1 | 145 | 0 | 0
A1-Flat 204 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 11 Feb 2016 | 11 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 48 | 135
A1-Flat 204 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 18 Feb 2016 | 19 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 41 | 127
A1-Flat 204 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 18 Feb 2016 | 19 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 41 | 127
A1-2ND FL.LOBBY | 0 | No Unit | 29 Feb 2016 | 01 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-2nd Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 29 Feb 2016 | 01 Mar 2016 | 17 Aug 2016 | 30 Jan 2017 | 1 | 166 | 170 | 335
A1-2ND FL FIRE STAIR | 0 | No Unit | 29 Feb 2016 | 01 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-2nd Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 29 Feb 2016 | 01 Mar 2016 | 17 Aug 2016 | 30 Jan 2017 | 1 | 166 | 170 | 335
A1-3RD FLOOR | 0 | No Unit | 05 Jan 2016 | 12 Sep 2016 |  |  | 251 | 0 | 0 | 0
A1-FLAT 301 TILE (M+L) | 11 | No Unit | 05 Jan 2016 | 05 Sep 2016 |  |  | 244 | 0 | 0 | 0
A1-Flat 301 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 05 Jan 2016 | 08 Jan 2016 | 03 Jan 2016 | 27 Jul 2016 | 3 | 206 | 0 | 201
A1-Flat 301 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 10 Feb 2016 | 12 Feb 2016 | 03 Feb 2016 | 22 Jun 2016 | 2 | 140 | 0 | 131
A1-Flat 301 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 11 Feb 2016 | 12 Feb 2016 | 11 Feb 2016 | 13 Jul 2016 | 1 | 153 | 0 | 152
A1-Flat 301 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 03 Sep 2016 | 05 Sep 2016 | 03 Mar 2016 | 25 Jul 2016 | 2 | 144 | 0 | 0
A1-Flat 301 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 13 Feb 2016 | 13 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 46 | 133
A1-Flat 301 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 20 Feb 2016 | 22 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 2 | 87 | 39 | 124
A1-Flat 301 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 20 Feb 2016 | 22 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 2 | 87 | 39 | 124
A1-FLAT 302 TILE (M+L) | 0 | No Unit | 09 Jan 2016 | 07 Sep 2016 |  |  | 242 | 0 | 0 | 0
A1-Flat 302 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 09 Jan 2016 | 13 Jan 2016 | 03 Jan 2016 | 27 Jul 2016 | 4 | 206 | 0 | 196
A1-Flat 302 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 12 Feb 2016 | 15 Feb 2016 | 03 Feb 2016 | 22 Jun 2016 | 3 | 140 | 0 | 128
A1-Flat 302 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 13 Feb 2016 | 15 Feb 2016 | 11 Feb 2016 | 13 Jul 2016 | 2 | 153 | 0 | 149
A1-Flat 302 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 06 Sep 2016 | 07 Sep 2016 | 03 Mar 2016 | 25 Jul 2016 | 1 | 144 | 0 | 0
A1-Flat 302 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 16 Feb 2016 | 16 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 43 | 130
A1-Flat 302 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 24 Feb 2016 | 25 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 35 | 121
A1-Flat 302 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 24 Feb 2016 | 25 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 35 | 121
A1-FLAT 303 TILE (M+L) | 0 | No Unit | 14 Jan 2016 | 09 Sep 2016 |  |  | 239 | 0 | 0 | 0
A1-Flat 303 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 14 Jan 2016 | 18 Jan 2016 | 03 Jan 2016 | 27 Jul 2016 | 4 | 206 | 0 | 191
A1-Flat 303 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Feb 2016 | 17 Feb 2016 | 03 Feb 2016 | 22 Jun 2016 | 2 | 140 | 0 | 126
A1-Flat 303 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 16 Feb 2016 | 17 Feb 2016 | 11 Feb 2016 | 13 Jul 2016 | 1 | 153 | 0 | 147
A1-Flat 303 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 08 Sep 2016 | 09 Sep 2016 | 03 Mar 2016 | 25 Jul 2016 | 1 | 144 | 0 | 0
A1-Flat 303 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 18 Feb 2016 | 18 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 41 | 128
A1-Flat 303 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 26 Feb 2016 | 27 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 33 | 119
A1-Flat 303 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | Rft. | 26 Feb 2016 | 27 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 33 | 119
A1-FLAT 304 TILE (M+L) | 0 | No Unit | 19 Jan 2016 | 12 Sep 2016 |  |  | 237 | 0 | 0 | 0
A1-Flat 304 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 19 Jan 2016 | 22 Jan 2016 | 03 Jan 2016 | 27 Jul 2016 | 3 | 206 | 0 | 187
A1-Flat 304 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 17 Feb 2016 | 19 Feb 2016 | 03 Feb 2016 | 22 Jun 2016 | 2 | 140 | 0 | 124
A1-Flat 304 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 18 Feb 2016 | 19 Feb 2016 | 11 Feb 2016 | 13 Jul 2016 | 1 | 153 | 0 | 145
A1-Flat 304 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 10 Sep 2016 | 12 Sep 2016 | 03 Mar 2016 | 25 Jul 2016 | 2 | 144 | 0 | 0
A1-Flat 304 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 20 Feb 2016 | 20 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 39 | 126
A1-Flat 304 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 01 Mar 2016 | 02 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 29 | 115
A1-Flat 304 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | Rft. | 01 Mar 2016 | 02 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 29 | 115
A1-3RD FL.LOBBY | 0 | No Unit | 11 Mar 2016 | 12 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-3rd Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 11 Mar 2016 | 12 Mar 2016 | 17 Aug 2016 | 30 Jan 2017 | 1 | 166 | 159 | 324
A1-3RD FL FIRE STAIR | 0 | No Unit | 11 Mar 2016 | 12 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-3rd Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 11 Mar 2016 | 12 Mar 2016 | 17 Aug 2016 | 30 Jan 2017 | 1 | 166 | 159 | 324
A1-4TH FLOOR | 0 | No Unit | 27 Jan 2016 | 21 Sep 2016 |  |  | 238 | 0 | 0 | 0
A1-FLAT 401 TILE (M+L) | 11 | No Unit | 27 Jan 2016 | 14 Sep 2016 |  |  | 231 | 0 | 0 | 0
A1-Flat 401 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 27 Jan 2016 | 30 Jan 2016 | 15 Jan 2016 | 27 Jul 2016 | 3 | 194 | 0 | 179
A1-Flat 401 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 19 Feb 2016 | 22 Feb 2016 | 22 Jan 2016 | 22 Jun 2016 | 3 | 152 | 0 | 121
A1-Flat 401 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 20 Feb 2016 | 22 Feb 2016 | 11 Feb 2016 | 25 Jul 2016 | 2 | 165 | 0 | 154
A1-Flat 401 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 13 Sep 2016 | 14 Sep 2016 | 12 Mar 2016 | 25 Jul 2016 | 1 | 135 | 0 | 0
A1-Flat 401 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 23 Feb 2016 | 23 Feb 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 36 | 123
A1-Flat 401 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 03 Mar 2016 | 04 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 27 | 113
A1-Flat 401 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 03 Mar 2016 | 04 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 27 | 113
A1-FLAT 402 TILE (M+L) | 0 | No Unit | 01 Feb 2016 | 16 Sep 2016 |  |  | 228 | 0 | 0 | 0
A1-Flat 402 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 01 Feb 2016 | 04 Feb 2016 | 15 Jan 2016 | 27 Jul 2016 | 3 | 194 | 0 | 174
A1-Flat 402 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 24 Feb 2016 | 26 Feb 2016 | 06 Feb 2016 | 22 Jun 2016 | 2 | 137 | 0 | 117
A1-Flat 402 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 27 Feb 2016 | 29 Feb 2016 | 11 Feb 2016 | 25 Jul 2016 | 2 | 165 | 0 | 147
A1-Flat 402 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Sep 2016 | 16 Sep 2016 | 12 Mar 2016 | 25 Jul 2016 | 1 | 135 | 0 | 0
A1-Flat 402 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 01 Mar 2016 | 01 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 29 | 116
A1-Flat 402 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Mar 2016 | 16 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 15 | 101
A1-Flat 402 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Mar 2016 | 16 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 15 | 101
A1-FLAT 403 TILE (M+L) | 0 | No Unit | 05 Feb 2016 | 19 Sep 2016 |  |  | 227 | 0 | 0 | 0
A1-Flat 403 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 05 Feb 2016 | 09 Feb 2016 | 15 Jan 2016 | 01 Dec 2016 | 4 | 321 | 0 | 296
A1-Flat 403 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 02 Mar 2016 | 04 Mar 2016 | 06 Feb 2016 | 22 Jun 2016 | 2 | 137 | 0 | 110
A1-Flat 403 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 05 Mar 2016 | 08 Mar 2016 | 11 Feb 2016 | 25 Jul 2016 | 3 | 165 | 0 | 139
A1-Flat 403 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 17 Sep 2016 | 19 Sep 2016 | 16 Mar 2016 | 25 Jul 2016 | 2 | 131 | 0 | 0
A1-Flat 403 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 09 Mar 2016 | 09 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 21 | 108
A1-Flat 403 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 22 Mar 2016 | 23 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 8 | 94
A1-Flat 403 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 22 Mar 2016 | 23 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 8 | 94
A1-FLAT 404 TILE (M+L) | 0 | No Unit | 10 Feb 2016 | 21 Sep 2016 |  |  | 224 | 0 | 0 | 0
A1-Flat 404 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 10 Feb 2016 | 13 Feb 2016 | 15 Jan 2016 | 27 Jul 2016 | 3 | 194 | 0 | 165
A1-Flat 404 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 10 Mar 2016 | 12 Mar 2016 | 22 Jan 2016 | 22 Jun 2016 | 2 | 152 | 0 | 102
A1-Flat 404 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 14 Mar 2016 | 15 Mar 2016 | 11 Feb 2016 | 25 Jul 2016 | 1 | 165 | 0 | 132
A1-Flat 404 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 20 Sep 2016 | 21 Sep 2016 | 16 Mar 2016 | 25 Jul 2016 | 1 | 131 | 0 | 0
A1-Flat 404 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 16 Mar 2016 | 16 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 14 | 101
A1-Flat 404 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 29 Mar 2016 | 30 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 1 | 87
A1-Flat 404 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 29 Mar 2016 | 30 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 1 | 87
A1-4TH FL.LOBBY | 0 | No Unit | 23 Mar 2016 | 24 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1-4th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 23 Mar 2016 | 24 Mar 2016 | 17 Aug 2016 | 30 Jan 2017 | 1 | 166 | 147 | 312
A1- 4TH FL FIRE STAIR | 0 | No Unit | 23 Mar 2016 | 24 Mar 2016 |  |  | 1 | 0 | 0 | 0
A1- 4th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 23 Mar 2016 | 24 Mar 2016 | 17 Aug 2016 | 30 Jan 2017 | 1 | 166 | 147 | 312
A1-5TH FLOOR | 0 | No Unit | 18 Feb 2016 | 30 Sep 2016 |  |  | 225 | 0 | 0 | 0
A1-FLAT 501 TILE (M+L) | 11 | No Unit | 18 Feb 2016 | 23 Sep 2016 |  |  | 218 | 0 | 0 | 0
A1-Flat 501 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 18 Feb 2016 | 22 Feb 2016 | 16 Jan 2016 | 27 Jul 2016 | 4 | 193 | 0 | 156
A1-Flat 501 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 17 Mar 2016 | 19 Mar 2016 | 25 Jan 2016 | 22 Jun 2016 | 2 | 149 | 0 | 95
A1-Flat 501 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 21 Mar 2016 | 22 Mar 2016 | 16 Mar 2016 | 13 Jul 2016 | 1 | 119 | 0 | 113
A1-Flat 501 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 22 Sep 2016 | 23 Sep 2016 | 16 Mar 2016 | 25 Jul 2016 | 1 | 131 | 0 | 0
A1-Flat 501 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 23 Mar 2016 | 23 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 7 | 94
A1-Flat 501 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 05 Apr 2016 | 06 Apr 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 0 | 80
A1-Flat 501 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 05 Apr 2016 | 06 Apr 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 0 | 80
A1-FLAT 502 TILE (M+L) | 0 | No Unit | 23 Feb 2016 | 26 Sep 2016 |  |  | 216 | 0 | 0 | 0
A1-Flat 502 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 23 Feb 2016 | 26 Feb 2016 | 16 Jan 2016 | 27 Jul 2016 | 3 | 193 | 0 | 152
A1-Flat 502 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 24 Mar 2016 | 26 Mar 2016 | 06 Feb 2016 | 22 Jun 2016 | 2 | 137 | 0 | 88
A1-Flat 502 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 28 Mar 2016 | 29 Mar 2016 | 16 Mar 2016 | 13 Jul 2016 | 1 | 119 | 0 | 106
A1-Flat 502 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 24 Sep 2016 | 26 Sep 2016 | 16 Mar 2016 | 25 Jul 2016 | 2 | 131 | 0 | 0
A1-Flat 502 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 30 Mar 2016 | 30 Mar 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 0 | 87
A1-Flat 502 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 12 Apr 2016 | 13 Apr 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 0 | 73
A1-Flat 502 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 12 Apr 2016 | 13 Apr 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 0 | 73
A1-FLAT 503 TILE (M+L) | 0 | No Unit | 27 Feb 2016 | 28 Sep 2016 |  |  | 214 | 0 | 0 | 0
A1-Flat 503 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 27 Feb 2016 | 02 Mar 2016 | 16 Jan 2016 | 27 Jul 2016 | 4 | 193 | 0 | 147
A1-Flat 503 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 31 Mar 2016 | 02 Apr 2016 | 06 Feb 2016 | 22 Jun 2016 | 2 | 137 | 0 | 81
A1-Flat 503 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 04 Apr 2016 | 05 Apr 2016 | 30 Mar 2016 | 13 Jul 2016 | 1 | 105 | 0 | 99
A1-Flat 503 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 27 Sep 2016 | 28 Sep 2016 | 27 Mar 2016 | 25 Jul 2016 | 1 | 120 | 0 | 0
A1-Flat 503 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 06 Apr 2016 | 06 Apr 2016 | 30 Mar 2016 | 25 Jun 2016 | 0 | 87 | 0 | 80
A1-Flat 503 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 19 Apr 2016 | 20 Apr 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 0 | 66
A1-Flat 503 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | Rft. | 19 Apr 2016 | 20 Apr 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 0 | 66
A1-FLAT 504 TILE (M+L) | 0 | No Unit | 03 Mar 2016 | 30 Sep 2016 |  |  | 211 | 0 | 0 | 0
A1-Flat 504 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 03 Mar 2016 | 08 Mar 2016 | 16 Jan 2016 | 27 Jul 2016 | 5 | 193 | 0 | 141
A1-Flat 504 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 07 Apr 2016 | 09 Apr 2016 | 25 Jan 2016 | 22 Jun 2016 | 2 | 149 | 0 | 74
A1-Flat 504 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 11 Apr 2016 | 12 Apr 2016 | 30 Mar 2016 | 13 Jul 2016 | 1 | 105 | 0 | 92
A1-Flat 504 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 29 Sep 2016 | 30 Sep 2016 | 27 Mar 2016 | 25 Jul 2016 | 1 | 120 | 0 | 0
A1-Flat 504 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 13 Apr 2016 | 14 Apr 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 0 | 72
A1-Flat 504 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 26 Apr 2016 | 27 Apr 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 0 | 59
A1-Flat 504 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | Rft. | 26 Apr 2016 | 27 Apr 2016 | 30 Mar 2016 | 25 Jun 2016 | 1 | 87 | 0 | 59
A1-5TH FL.LOBBY | 0 | No Unit | 02 Apr 2016 | 04 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1-5th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 02 Apr 2016 | 04 Apr 2016 | 17 Aug 2016 | 30 Jan 2017 | 2 | 166 | 137 | 301
A1- 5TH FL FIRE STAIR | 0 | No Unit | 02 Apr 2016 | 04 Apr 2016 |  |  | 2 | 0 | 0 | 0
A1- 5th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 02 Apr 2016 | 04 Apr 2016 | 17 Aug 2016 | 30 Jan 2017 | 2 | 166 | 137 | 301
A1-6TH FLOOR | 0 | No Unit | 11 Mar 2016 | 10 Oct 2016 |  |  | 213 | 0 | 0 | 0
A1-FLAT 601 TILE (M+L) | 11 | No Unit | 11 Mar 2016 | 03 Oct 2016 |  |  | 206 | 0 | 0 | 0
A1-Flat 601 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 11 Mar 2016 | 15 Mar 2016 | 12 Feb 2016 | 01 Dec 2016 | 4 | 293 | 0 | 261
A1-Flat 601 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 12 Apr 2016 | 14 Apr 2016 | 09 Apr 2016 | 13 Jul 2016 | 2 | 95 | 0 | 90
A1-Flat 601 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 13 Apr 2016 | 14 Apr 2016 | 10 May 2016 | 13 Jul 2016 | 1 | 64 | 27 | 90
A1-Flat 601 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 01 Oct 2016 | 03 Oct 2016 | 08 Jun 2016 | 03 Dec 2016 | 2 | 178 | 0 | 61
A1-Flat 601 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2016 | 15 Apr 2016 | 08 Jun 2016 | 13 Jul 2016 | 0 | 35 | 54 | 89
A1-Flat 601 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 25 Apr 2016 | 26 Apr 2016 | 08 Jun 2016 | 13 Jul 2016 | 1 | 35 | 44 | 78
A1-Flat 601 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 25 Apr 2016 | 26 Apr 2016 | 13 Jul 2016 | 13 Jul 2016 | 1 | 0 | 79 | 78
A1-FLAT 602 TILE (M+L) | 0 | No Unit | 16 Mar 2016 | 05 Oct 2016 |  |  | 203 | 0 | 0 | 0
A1-Flat 602 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 16 Mar 2016 | 19 Mar 2016 | 12 Feb 2016 | 01 Dec 2016 | 3 | 293 | 0 | 257
A1-Flat 602 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 14 Apr 2016 | 16 Apr 2016 | 09 Apr 2016 | 13 Jul 2016 | 2 | 95 | 0 | 88
A1-Flat 602 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2016 | 16 Apr 2016 | 13 Jul 2016 | 13 Jul 2016 | 1 | 0 | 89 | 88
A1-Flat 602 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 04 Oct 2016 | 05 Oct 2016 | 11 Jun 2016 | 03 Dec 2016 | 1 | 175 | 0 | 59
A1-Flat 602 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 18 Apr 2016 | 18 Apr 2016 | 13 Jul 2016 | 13 Jul 2016 | 0 | 0 | 86 | 86
A1-Flat 602 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 27 Apr 2016 | 28 Apr 2016 | 13 Jul 2016 | 13 Jul 2016 | 1 | 0 | 77 | 76
A1-Flat 602 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 27 Apr 2016 | 28 Apr 2016 | 13 Jul 2016 | 13 Jul 2016 | 1 | 0 | 77 | 76
A1-FLAT 603 TILE (M+L) | 0 | No Unit | 21 Mar 2016 | 07 Oct 2016 |  |  | 200 | 0 | 0 | 0
A1-Flat 603 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 21 Mar 2016 | 24 Mar 2016 | 12 Feb 2016 | 01 Dec 2016 | 3 | 293 | 0 | 252
A1-Flat 603 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 16 Apr 2016 | 19 Apr 2016 | 09 Apr 2016 | 13 Jul 2016 | 3 | 95 | 0 | 85
A1-Flat 603 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 18 Apr 2016 | 19 Apr 2016 | 13 Jul 2016 | 13 Jul 2016 | 1 | 0 | 86 | 85
A1-Flat 603 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 06 Oct 2016 | 07 Oct 2016 | 11 Jun 2016 | 03 Dec 2016 | 1 | 175 | 0 | 57
A1-Flat 603 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 20 Apr 2016 | 20 Apr 2016 | 13 Jul 2016 | 13 Jul 2016 | 0 | 0 | 84 | 84
A1-Flat 603 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 29 Apr 2016 | 30 Apr 2016 | 13 Jul 2016 | 13 Jul 2016 | 1 | 0 | 75 | 74
A1-Flat 603 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 29 Apr 2016 | 30 Apr 2016 | 13 Jul 2016 | 13 Jul 2016 | 1 | 0 | 75 | 74
A1-FLAT 604 TILE (M+L) | 0 | No Unit | 25 Mar 2016 | 10 Oct 2016 |  |  | 199 | 0 | 0 | 0
A1-Flat 604 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 25 Mar 2016 | 29 Mar 2016 | 12 Feb 2016 | 01 Dec 2016 | 4 | 293 | 0 | 247
A1-Flat 604 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 19 Apr 2016 | 21 Apr 2016 | 09 Apr 2016 | 13 Jul 2016 | 2 | 95 | 0 | 83
A1-Flat 604 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 20 Apr 2016 | 21 Apr 2016 | 10 May 2016 | 13 Jul 2016 | 1 | 64 | 20 | 83
A1-Flat 604 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 08 Oct 2016 | 10 Oct 2016 | 08 Jun 2016 | 03 Dec 2016 | 2 | 178 | 0 | 54
A1-Flat 604 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 22 Apr 2016 | 22 Apr 2016 | 08 Jun 2016 | 13 Jul 2016 | 0 | 35 | 47 | 82
A1-Flat 604 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 02 May 2016 | 03 May 2016 | 08 Jun 2016 | 13 Jul 2016 | 1 | 35 | 37 | 71
A1-Flat 604 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 02 May 2016 | 03 May 2016 | 08 Jun 2016 | 13 Jul 2016 | 1 | 35 | 37 | 71
A1-6TH FL.LOBBY | 0 | No Unit | 30 Apr 2016 | 02 May 2016 |  |  | 2 | 0 | 0 | 0
A1-6th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 30 Apr 2016 | 02 May 2016 | 22 Nov 2016 | 30 Jan 2017 | 2 | 69 | 206 | 273
A1- 6TH FL FIRE STAIR | 0 | No Unit | 30 Apr 2016 | 02 May 2016 |  |  | 2 | 0 | 0 | 0
A1- 6th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 30 Apr 2016 | 02 May 2016 | 22 Nov 2016 | 30 Jan 2017 | 2 | 69 | 206 | 273
A1-7TH FLOOR | 0 | No Unit | 08 Mar 2016 | 19 Oct 2016 |  |  | 225 | 0 | 0 | 0
A1-FLAT 701 TILE (M+L) | 11 | No Unit | 08 Mar 2016 | 12 Oct 2016 |  |  | 218 | 0 | 0 | 0
A1-Flat 701 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 08 Mar 2016 | 11 Mar 2016 | 31 Mar 2016 | 01 Dec 2016 | 3 | 245 | 23 | 265
A1-Flat 701 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 21 Apr 2016 | 23 Apr 2016 | 09 Apr 2016 | 13 Jul 2016 | 2 | 95 | 0 | 81
A1-Flat 701 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 22 Apr 2016 | 23 Apr 2016 | 10 May 2016 | 13 Jul 2016 | 1 | 64 | 18 | 81
A1-Flat 701 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 11 Oct 2016 | 12 Oct 2016 | 08 Jun 2016 | 03 Dec 2016 | 1 | 178 | 0 | 52
A1-Flat 701 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 25 Apr 2016 | 25 Apr 2016 | 08 Jun 2016 | 13 Jul 2016 | 0 | 35 | 44 | 79
A1-Flat 701 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 04 May 2016 | 05 May 2016 | 08 Jun 2016 | 13 Jul 2016 | 1 | 35 | 35 | 69
A1-Flat 701 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 04 May 2016 | 05 May 2016 | 08 Jun 2016 | 13 Jul 2016 | 1 | 35 | 35 | 69
A1-FLAT 702 TILE (M+L) | 0 | No Unit | 12 Mar 2016 | 14 Oct 2016 |  |  | 216 | 0 | 0 | 0
A1-Flat 702 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 12 Mar 2016 | 16 Mar 2016 | 31 Mar 2016 | 01 Dec 2016 | 4 | 245 | 19 | 260
A1-Flat 702 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 23 Apr 2016 | 26 Apr 2016 | 09 Apr 2016 | 13 Jul 2016 | 3 | 95 | 0 | 78
A1-Flat 702 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 25 Apr 2016 | 26 Apr 2016 | 14 Jun 2016 | 01 Dec 2016 | 1 | 170 | 50 | 219
A1-Flat 702 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 13 Oct 2016 | 14 Oct 2016 | 11 Jun 2016 | 03 Dec 2016 | 1 | 175 | 0 | 50
A1-Flat 702 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 27 Apr 2016 | 27 Apr 2016 | 14 Jun 2016 | 13 Jul 2016 | 0 | 29 | 48 | 77
A1-Flat 702 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 06 May 2016 | 07 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 1 | 29 | 39 | 67
A1-Flat 702 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 06 May 2016 | 07 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 1 | 29 | 39 | 67
A1-FLAT 703 TILE (M+L) | 0 | No Unit | 17 Mar 2016 | 17 Oct 2016 |  |  | 214 | 0 | 0 | 0
A1-Flat 703 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 17 Mar 2016 | 21 Mar 2016 | 31 Mar 2016 | 01 Dec 2016 | 4 | 245 | 14 | 255
A1-Flat 703 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 26 Apr 2016 | 28 Apr 2016 | 09 Apr 2016 | 13 Jul 2016 | 2 | 95 | 0 | 76
A1-Flat 703 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 27 Apr 2016 | 28 Apr 2016 | 14 Jun 2016 | 01 Dec 2016 | 1 | 170 | 48 | 217
A1-Flat 703 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Oct 2016 | 17 Oct 2016 | 11 Jun 2016 | 03 Dec 2016 | 2 | 175 | 0 | 47
A1-Flat 703 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 29 Apr 2016 | 29 Apr 2016 | 14 Jun 2016 | 13 Jul 2016 | 0 | 29 | 46 | 75
A1-Flat 703 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 09 May 2016 | 10 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 1 | 29 | 36 | 64
A1-Flat 703 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | Rft. | 09 May 2016 | 10 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 1 | 29 | 36 | 64
A1-FLAT 704 TILE (M+L) | 0 | No Unit | 22 Mar 2016 | 19 Oct 2016 |  |  | 211 | 0 | 0 | 0
A1-Flat 704 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 22 Mar 2016 | 25 Mar 2016 | 31 Mar 2016 | 01 Dec 2016 | 3 | 245 | 9 | 251
A1-Flat 704 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 28 Apr 2016 | 30 Apr 2016 | 09 Apr 2016 | 13 Jul 2016 | 2 | 95 | 0 | 74
A1-Flat 704 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 02 May 2016 | 03 May 2016 | 10 May 2016 | 13 Jul 2016 | 1 | 64 | 8 | 71
A1-Flat 704 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 18 Oct 2016 | 19 Oct 2016 | 08 Jun 2016 | 03 Dec 2016 | 1 | 178 | 0 | 45
A1-Flat 704 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 04 May 2016 | 04 May 2016 | 08 Jun 2016 | 13 Jul 2016 | 0 | 35 | 35 | 70
A1-Flat 704 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 11 May 2016 | 12 May 2016 | 08 Jun 2016 | 13 Jul 2016 | 1 | 35 | 28 | 62
A1-Flat 704 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | Rft. | 11 May 2016 | 12 May 2016 | 08 Jun 2016 | 13 Jul 2016 | 1 | 35 | 28 | 62
A1-7TH FL.LOBBY | 0 | No Unit | 23 May 2016 | 24 May 2016 |  |  | 1 | 0 | 0 | 0
A1-7th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 23 May 2016 | 24 May 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 183 | 251
A1- 7TH FL FIRE STAIR | 0 | No Unit | 23 May 2016 | 24 May 2016 |  |  | 1 | 0 | 0 | 0
A1- 7th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 23 May 2016 | 24 May 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 183 | 251
A1-8TH FLOOR | 1 | No Unit | 18 Mar 2016 | 28 Oct 2016 |  |  | 224 | 0 | 0 | 0
A1-FLAT 801 TILE (M+L) | 11 | No Unit | 18 Mar 2016 | 21 Oct 2016 |  |  | 217 | 0 | 0 | 0
A1-Flat 801 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 18 Mar 2016 | 22 Mar 2016 | 18 Apr 2016 | 01 Dec 2016 | 4 | 227 | 31 | 254
A1-Flat 801 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 20 May 2016 | 23 May 2016 | 09 Apr 2016 | 13 Jul 2016 | 3 | 95 | 0 | 51
A1-Flat 801 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 21 May 2016 | 23 May 2016 | 10 May 2016 | 01 Dec 2016 | 2 | 205 | 0 | 192
A1-Flat 801 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 20 Oct 2016 | 21 Oct 2016 | 08 Jun 2016 | 03 Dec 2016 | 1 | 178 | 0 | 43
A1-Flat 801 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 24 May 2016 | 24 May 2016 | 08 Jun 2016 | 13 Jul 2016 | 0 | 35 | 15 | 50
A1-Flat 801 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 01 Jun 2016 | 02 Jun 2016 | 08 Jun 2016 | 13 Jul 2016 | 1 | 35 | 7 | 41
A1-Flat 801 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 01 Jun 2016 | 02 Jun 2016 | 08 Jun 2016 | 13 Jul 2016 | 1 | 35 | 7 | 41
A1-FLAT 802 TILE (M+L) | 0 | No Unit | 23 Mar 2016 | 24 Oct 2016 |  |  | 215 | 0 | 0 | 0
A1-Flat 802 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 23 Mar 2016 | 26 Mar 2016 | 18 Apr 2016 | 01 Dec 2016 | 3 | 227 | 26 | 250
A1-Flat 802 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 11 May 2016 | 13 May 2016 | 09 Apr 2016 | 13 Jul 2016 | 2 | 95 | 0 | 61
A1-Flat 802 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 12 May 2016 | 13 May 2016 | 14 Jun 2016 | 01 Dec 2016 | 1 | 170 | 33 | 202
A1-Flat 802 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 22 Oct 2016 | 24 Oct 2016 | 11 Jun 2016 | 03 Dec 2016 | 2 | 175 | 0 | 40
A1-Flat 802 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 14 May 2016 | 14 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 0 | 29 | 31 | 60
A1-Flat 802 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 23 May 2016 | 24 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 1 | 29 | 22 | 50
A1-Flat 802 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 23 May 2016 | 24 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 1 | 29 | 22 | 50
A1-FLAT 803 TILE (M+L) | 0 | No Unit | 28 Mar 2016 | 26 Oct 2016 |  |  | 212 | 0 | 0 | 0
A1-Flat 803 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 28 Mar 2016 | 31 Mar 2016 | 18 Apr 2016 | 01 Dec 2016 | 3 | 227 | 21 | 245
A1-Flat 803 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 16 May 2016 | 18 May 2016 | 09 Apr 2016 | 13 Jul 2016 | 2 | 95 | 0 | 56
A1-Flat 803 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 17 May 2016 | 18 May 2016 | 14 Jun 2016 | 01 Dec 2016 | 1 | 170 | 28 | 197
A1-Flat 803 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 25 Oct 2016 | 26 Oct 2016 | 11 Jun 2016 | 03 Dec 2016 | 1 | 175 | 0 | 38
A1-Flat 803 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 19 May 2016 | 19 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 0 | 29 | 26 | 55
A1-Flat 803 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 27 May 2016 | 28 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 1 | 29 | 18 | 46
A1-Flat 803 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 27 May 2016 | 28 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 1 | 29 | 18 | 46
A1-REFUGE FLAT 804 TILE (M+L) | 0 | No Unit | 01 Apr 2016 | 28 Oct 2016 |  |  | 210 | 0 | 0 | 0
A1-Refuge Flat 804 Tile (M+L) Granite Kitchen Otta (M+L) | 0 | No. | 01 Apr 2016 | 05 Apr 2016 | 14 Jun 2016 | 13 Jul 2016 | 4 | 29 | 74 | 99
A1-Refuge Flat 804 Tile (M+L) Granite Door Frame (M+L) | 0 | No. | 16 May 2016 | 18 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 2 | 29 | 29 | 56
A1-Refuge Flat 804 Tile (M+L) Granite Window Jambs (M+L) | 0 | NO | 17 May 2016 | 18 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 1 | 29 | 28 | 56
A1-Refuge Flat 804 Tile (M+L) Granite WHB Counter (M+L) | 0 | No. | 27 Oct 2016 | 28 Oct 2016 | 14 Jun 2016 | 13 Jul 2016 | 1 | 29 | 0 | 0
A1-Refuge Flat 804 Tile (M+L) Granite Ledge wall (M+L) | 0 | Rft. | 19 May 2016 | 19 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 0 | 29 | 26 | 55
A1-Refuge Flat 804 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+ | 0 | Rft. | 27 May 2016 | 28 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 1 | 29 | 18 | 46
A1-Refuge Flat 804 Tile (M+L) Granite Window Cill upto 3"(M+ | 0 | Rft. | 27 May 2016 | 28 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 1 | 29 | 18 | 46
A1-8TH FL.LOBBY | 0 | No Unit | 14 Jun 2016 | 15 Jun 2016 |  |  | 1 | 0 | 0 | 0
A1-8th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 14 Jun 2016 | 15 Jun 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 161 | 229
A1-8TH FL FIRE STAIR | 0 | No Unit | 14 Jun 2016 | 15 Jun 2016 |  |  | 1 | 0 | 0 | 0
A1-8th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 14 Jun 2016 | 15 Jun 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 161 | 229
A1-9TH FLOOR | 0 | No Unit | 25 Mar 2016 | 04 Nov 2016 |  |  | 224 | 0 | 0 | 0
A1-FLAT 901 TILE (M+L) | 11 | No Unit | 25 Mar 2016 | 28 Oct 2016 |  |  | 217 | 0 | 0 | 0
A1-Flat 901 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 25 Mar 2016 | 29 Mar 2016 | 18 Apr 2016 | 01 Dec 2016 | 4 | 227 | 24 | 247
A1-Flat 901 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 25 May 2016 | 27 May 2016 | 10 May 2016 | 13 Jul 2016 | 2 | 64 | 0 | 47
A1-Flat 901 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 28 May 2016 | 30 May 2016 | 10 May 2016 | 01 Dec 2016 | 2 | 205 | 0 | 185
A1-Flat 901 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 27 Oct 2016 | 28 Oct 2016 | 11 Jun 2016 | 03 Dec 2016 | 1 | 175 | 0 | 36
A1-Flat 901 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 31 May 2016 | 31 May 2016 | 14 Jun 2016 | 13 Jul 2016 | 0 | 29 | 14 | 43
A1-Flat 901 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 07 Jun 2016 | 08 Jun 2016 | 14 Jun 2016 | 03 Dec 2016 | 1 | 172 | 7 | 178
A1-Flat 901 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 07 Jun 2016 | 08 Jun 2016 | 14 Jun 2016 | 04 Dec 2016 | 1 | 173 | 7 | 179
A1-FLAT 902 TILE (M+L) | 0 | No Unit | 30 Mar 2016 | 31 Oct 2016 |  |  | 215 | 0 | 0 | 0
A1-Flat 902 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 30 Mar 2016 | 02 Apr 2016 | 23 Apr 2016 | 01 Dec 2016 | 3 | 222 | 24 | 243
A1-Flat 902 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 01 Jun 2016 | 03 Jun 2016 | 08 Jun 2016 | 13 Jul 2016 | 2 | 35 | 7 | 40
A1-Flat 902 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 04 Jun 2016 | 06 Jun 2016 | 08 Jun 2016 | 01 Dec 2016 | 2 | 176 | 4 | 178
A1-Flat 902 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 29 Oct 2016 | 31 Oct 2016 | 11 Jun 2016 | 03 Dec 2016 | 2 | 175 | 0 | 33
A1-Flat 902 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 07 Jun 2016 | 07 Jun 2016 | 14 Jun 2016 | 13 Jul 2016 | 0 | 29 | 7 | 36
A1-Flat 902 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 14 Jun 2016 | 15 Jun 2016 | 14 Jun 2016 | 03 Dec 2016 | 1 | 172 | 0 | 171
A1-Flat 902 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 14 Jun 2016 | 15 Jun 2016 | 14 Jun 2016 | 04 Dec 2016 | 1 | 173 | 0 | 172
A1-FLAT- 903 TILE (M+L) | 0 | No Unit | 04 Apr 2016 | 02 Nov 2016 |  |  | 212 | 0 | 0 | 0
A1-Flat- 903 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 04 Apr 2016 | 07 Apr 2016 | 23 Apr 2016 | 01 Dec 2016 | 3 | 222 | 19 | 238
A1-Flat- 903 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 08 Jun 2016 | 10 Jun 2016 | 08 Jun 2016 | 13 Jul 2016 | 2 | 35 | 0 | 33
A1-Flat- 903 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 16 Jun 2016 | 17 Jun 2016 | 08 Jun 2016 | 01 Dec 2016 | 1 | 176 | 0 | 167
A1-Flat- 903 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 01 Nov 2016 | 02 Nov 2016 | 11 Jun 2016 | 03 Dec 2016 | 1 | 175 | 0 | 31
A1-Flat- 903 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 18 Jun 2016 | 18 Jun 2016 | 14 Jun 2016 | 13 Jul 2016 | 0 | 29 | 0 | 25
A1-Flat- 903 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 21 Jun 2016 | 22 Jun 2016 | 14 Jun 2016 | 03 Dec 2016 | 1 | 172 | 0 | 164
A1-Flat- 903 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | Rft. | 21 Jun 2016 | 22 Jun 2016 | 14 Jun 2016 | 04 Dec 2016 | 1 | 173 | 0 | 165
A1-FLAT 904 TILE (M+L) | 0 | No Unit | 08 Apr 2016 | 04 Nov 2016 |  |  | 210 | 0 | 0 | 0
A1-Flat 904 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 08 Apr 2016 | 12 Apr 2016 | 23 Apr 2016 | 01 Dec 2016 | 4 | 222 | 15 | 233
A1-Flat 904 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 20 Jun 2016 | 22 Jun 2016 | 10 May 2016 | 13 Jul 2016 | 2 | 64 | 0 | 21
A1-Flat 904 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 25 Jun 2016 | 27 Jun 2016 | 10 May 2016 | 01 Dec 2016 | 2 | 205 | 0 | 157
A1-Flat 904 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 03 Nov 2016 | 04 Nov 2016 | 11 Jun 2016 | 03 Dec 2016 | 1 | 175 | 0 | 29
A1-Flat 904 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 28 Jun 2016 | 28 Jun 2016 | 14 Jun 2016 | 13 Jul 2016 | 0 | 29 | 0 | 15
A1-Flat 904 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 09 Jul 2016 | 11 Jul 2016 | 14 Jun 2016 | 03 Dec 2016 | 2 | 172 | 0 | 145
A1-Flat 904 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | Rft. | 09 Jul 2016 | 11 Jul 2016 | 14 Jun 2016 | 04 Dec 2016 | 2 | 173 | 0 | 146
A1-9TH FL.LOBBY | 0 | No Unit | 16 Jun 2016 | 17 Jun 2016 |  |  | 1 | 0 | 0 | 0
A1-9th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 16 Jun 2016 | 17 Jun 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 159 | 227
A1-9THT FL FIRE STAIR | 0 | No Unit | 16 Jun 2016 | 17 Jun 2016 |  |  | 1 | 0 | 0 | 0
A1-9tht Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 16 Jun 2016 | 17 Jun 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 159 | 227
A1-10TH FLOOR | 0 | No Unit | 01 Apr 2016 | 14 Nov 2016 |  |  | 227 | 0 | 0 | 0
A1-FLAT 1001 TILE (M+L) | 11 | No Unit | 01 Apr 2016 | 07 Nov 2016 |  |  | 220 | 0 | 0 | 0
A1-Flat 1001 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 01 Apr 2016 | 05 Apr 2016 | 26 Apr 2016 | 01 Dec 2016 | 4 | 219 | 25 | 240
A1-Flat 1001 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 29 Jun 2016 | 01 Jul 2016 | 10 May 2016 | 01 Dec 2016 | 2 | 205 | 0 | 153
A1-Flat 1001 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 02 Jul 2016 | 04 Jul 2016 | 10 May 2016 | 01 Dec 2016 | 2 | 205 | 0 | 150
A1-Flat 1001 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 05 Nov 2016 | 07 Nov 2016 | 11 Jun 2016 | 03 Dec 2016 | 2 | 175 | 0 | 26
A1-Flat 1001 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 05 Jul 2016 | 05 Jul 2016 | 13 Jul 2016 | 04 Dec 2016 | 0 | 144 | 8 | 152
A1-Flat 1001 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 12 Jul 2016 | 13 Jul 2016 | 13 Jul 2016 | 03 Dec 2016 | 1 | 143 | 1 | 143
A1-Flat 1001 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 12 Jul 2016 | 13 Jul 2016 | 13 Jul 2016 | 04 Dec 2016 | 1 | 144 | 1 | 144
A1-FLAT 1002 TILE (M+L) | 0 | No Unit | 06 Apr 2016 | 09 Nov 2016 |  |  | 217 | 0 | 0 | 0
A1-Flat 1002 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 06 Apr 2016 | 09 Apr 2016 | 26 Apr 2016 | 01 Dec 2016 | 3 | 219 | 20 | 236
A1-Flat 1002 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 06 Jul 2016 | 08 Jul 2016 | 22 Jun 2016 | 01 Dec 2016 | 2 | 162 | 0 | 146
A1-Flat 1002 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 09 Jul 2016 | 11 Jul 2016 | 13 Jul 2016 | 01 Dec 2016 | 2 | 141 | 4 | 143
A1-Flat 1002 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 08 Nov 2016 | 09 Nov 2016 | 11 Jun 2016 | 03 Dec 2016 | 1 | 175 | 0 | 24
A1-Flat 1002 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 12 Jul 2016 | 12 Jul 2016 | 13 Jul 2016 | 04 Dec 2016 | 0 | 144 | 1 | 145
A1-Flat 1002 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 19 Jul 2016 | 20 Jul 2016 | 13 Jul 2016 | 03 Dec 2016 | 1 | 143 | 0 | 136
A1-Flat 1002 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 19 Jul 2016 | 20 Jul 2016 | 13 Jul 2016 | 04 Dec 2016 | 1 | 144 | 0 | 137
A1-FLAT 1003 TILE (M+L) | 0 | No Unit | 11 Apr 2016 | 11 Nov 2016 |  |  | 214 | 0 | 0 | 0
A1-Flat 1003 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 11 Apr 2016 | 14 Apr 2016 | 26 Apr 2016 | 01 Dec 2016 | 3 | 219 | 15 | 231
A1-Flat 1003 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 13 Jul 2016 | 15 Jul 2016 | 22 Jun 2016 | 01 Dec 2016 | 2 | 162 | 0 | 139
A1-Flat 1003 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 18 Jul 2016 | 19 Jul 2016 | 13 Jul 2016 | 01 Dec 2016 | 1 | 141 | 0 | 135
A1-Flat 1003 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 10 Nov 2016 | 11 Nov 2016 | 11 Jun 2016 | 03 Dec 2016 | 1 | 175 | 0 | 22
A1-Flat 1003 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 20 Jul 2016 | 20 Jul 2016 | 13 Jul 2016 | 04 Dec 2016 | 0 | 144 | 0 | 137
A1-Flat 1003 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 26 Jul 2016 | 27 Jul 2016 | 13 Jul 2016 | 03 Dec 2016 | 1 | 143 | 0 | 129
A1-Flat 1003 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 26 Jul 2016 | 27 Jul 2016 | 13 Jul 2016 | 04 Dec 2016 | 1 | 144 | 0 | 130
A1-FLAT 1004 TILE (M+L) | 0 | No Unit | 15 Apr 2016 | 14 Nov 2016 |  |  | 213 | 0 | 0 | 0
A1-Flat 1004 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2016 | 19 Apr 2016 | 26 Apr 2016 | 01 Dec 2016 | 4 | 219 | 11 | 226
A1-Flat 1004 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 21 Jul 2016 | 23 Jul 2016 | 10 May 2016 | 01 Dec 2016 | 2 | 205 | 0 | 131
A1-Flat 1004 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 25 Jul 2016 | 26 Jul 2016 | 10 May 2016 | 01 Dec 2016 | 1 | 205 | 0 | 128
A1-Flat 1004 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 12 Nov 2016 | 14 Nov 2016 | 11 Jun 2016 | 03 Dec 2016 | 2 | 175 | 0 | 19
A1-Flat 1004 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 27 Jul 2016 | 27 Jul 2016 | 13 Jul 2016 | 04 Dec 2016 | 0 | 144 | 0 | 130
A1-Flat 1004 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 09 Aug 2016 | 10 Aug 2016 | 13 Jul 2016 | 03 Dec 2016 | 1 | 143 | 0 | 115
A1-Flat 1004 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 09 Aug 2016 | 10 Aug 2016 | 13 Jul 2016 | 04 Dec 2016 | 1 | 144 | 0 | 116
A1-10TH FL.LOBBY | 0 | No Unit | 16 Aug 2016 | 17 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1-10th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 16 Aug 2016 | 17 Aug 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 98 | 166
A1- 10TH FL FIRE STAIR | 0 | No Unit | 16 Aug 2016 | 17 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1- 10th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 16 Aug 2016 | 17 Aug 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 98 | 166
A1-11TH FLOOR | 0 | No Unit | 01 Apr 2016 | 23 Nov 2016 |  |  | 236 | 0 | 0 | 0
A1-FLAT 1101 TILE (M+L) | 11 | No Unit | 01 Apr 2016 | 16 Nov 2016 |  |  | 229 | 0 | 0 | 0
A1-Flat 1101 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 01 Apr 2016 | 05 Apr 2016 | 26 Apr 2016 | 26 Dec 2016 | 4 | 244 | 25 | 265
A1-Flat 1101 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 28 Jul 2016 | 30 Jul 2016 | 22 Jun 2016 | 26 Dec 2016 | 2 | 187 | 0 | 149
A1-Flat 1101 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 01 Aug 2016 | 02 Aug 2016 | 13 Jul 2016 | 26 Dec 2016 | 1 | 166 | 0 | 146
A1-Flat 1101 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Nov 2016 | 16 Nov 2016 | 13 Jul 2016 | 26 Dec 2016 | 1 | 166 | 0 | 40
A1-Flat 1101 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 03 Aug 2016 | 03 Aug 2016 | 13 Jul 2016 | 26 Dec 2016 | 0 | 166 | 0 | 145
A1-Flat 1101 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 10 Aug 2016 | 11 Aug 2016 | 13 Jul 2016 | 26 Dec 2016 | 1 | 166 | 0 | 137
A1-Flat 1101 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 10 Aug 2016 | 11 Aug 2016 | 13 Jul 2016 |  | 1 | 0 | 0 | 0
A1-FLAT 1102 TILE (M+L) | 0 | No Unit | 06 Apr 2016 | 18 Nov 2016 |  |  | 226 | 0 | 0 | 0
A1-Flat 1102 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 06 Apr 2016 | 09 Apr 2016 | 03 May 2016 | 26 Dec 2016 | 3 | 237 | 27 | 261
A1-Flat 1102 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 04 Aug 2016 | 06 Aug 2016 | 22 Jun 2016 | 26 Dec 2016 | 2 | 187 | 0 | 142
A1-Flat 1102 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 08 Aug 2016 | 09 Aug 2016 | 13 Jul 2016 | 26 Dec 2016 | 1 | 166 | 0 | 139
A1-Flat 1102 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 17 Nov 2016 | 18 Nov 2016 | 13 Jul 2016 | 26 Dec 2016 | 1 | 166 | 0 | 38
A1-Flat 1102 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 10 Aug 2016 | 10 Aug 2016 | 13 Jul 2016 | 26 Dec 2016 | 0 | 166 | 0 | 138
A1-Flat 1102 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 24 Aug 2016 | 25 Aug 2016 | 13 Jul 2016 | 26 Dec 2016 | 1 | 166 | 0 | 123
A1-Flat 1102 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 24 Aug 2016 | 25 Aug 2016 | 13 Jul 2016 |  | 1 | 0 | 0 | 0
A1-FLAT 1103 TILE (M+L) | 0 | No Unit | 11 Apr 2016 | 21 Nov 2016 |  |  | 224 | 0 | 0 | 0
A1-Flat 1103 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 11 Apr 2016 | 14 Apr 2016 | 03 May 2016 | 26 Dec 2016 | 3 | 237 | 22 | 256
A1-Flat 1103 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 11 Aug 2016 | 13 Aug 2016 | 22 Jun 2016 | 26 Dec 2016 | 2 | 187 | 0 | 135
A1-Flat 1103 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 16 Aug 2016 | 17 Aug 2016 | 13 Jul 2016 | 26 Dec 2016 | 1 | 166 | 0 | 131
A1-Flat 1103 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 19 Nov 2016 | 21 Nov 2016 | 13 Jul 2016 | 26 Dec 2016 | 2 | 166 | 0 | 35
A1-Flat 1103 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 18 Aug 2016 | 18 Aug 2016 | 13 Jul 2016 | 26 Dec 2016 | 0 | 166 | 0 | 130
A1-Flat 1103 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 31 Aug 2016 | 01 Sep 2016 | 13 Jul 2016 | 26 Dec 2016 | 1 | 166 | 0 | 116
A1-Flat 1103 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | Rft. | 31 Aug 2016 | 01 Sep 2016 | 13 Jul 2016 |  | 1 | 0 | 0 | 0
A1-FLAT 1104 TILE (M+L) | 0 | No Unit | 15 Apr 2016 | 23 Nov 2016 |  |  | 222 | 0 | 0 | 0
A1-Flat 1104 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2016 | 19 Apr 2016 | 03 May 2016 | 26 Dec 2016 | 4 | 237 | 18 | 251
A1-Flat 1104 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 19 Aug 2016 | 22 Aug 2016 | 13 Jul 2016 | 26 Dec 2016 | 3 | 166 | 0 | 126
A1-Flat 1104 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 23 Aug 2016 | 24 Aug 2016 | 13 Jul 2016 | 26 Dec 2016 | 1 | 166 | 0 | 124
A1-Flat 1104 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 22 Nov 2016 | 23 Nov 2016 | 13 Jul 2016 | 26 Dec 2016 | 1 | 166 | 0 | 33
A1-Flat 1104 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 25 Aug 2016 | 25 Aug 2016 | 13 Jul 2016 | 26 Dec 2016 | 0 | 166 | 0 | 123
A1-Flat 1104 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 07 Sep 2016 | 08 Sep 2016 | 13 Jul 2016 | 26 Dec 2016 | 1 | 166 | 0 | 109
A1-Flat 1104 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | Rft. | 07 Sep 2016 | 08 Sep 2016 | 13 Jul 2016 |  | 1 | 0 | 0 | 0
A1-11TH FL.LOBBY | 0 | No Unit | 09 Sep 2016 | 10 Sep 2016 |  |  | 1 | 0 | 0 | 0
A1-11th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 09 Sep 2016 | 10 Sep 2016 | 27 Jan 2017 | 30 Jan 2017 | 1 | 3 | 140 | 142
A1- 11TH FL FIRE STAIR | 0 | No Unit | 09 Sep 2016 | 10 Sep 2016 |  |  | 1 | 0 | 0 | 0
A1- 11th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 09 Sep 2016 | 10 Sep 2016 | 30 Jan 2017 | 30 Jan 2017 | 1 | 0 | 143 | 142
A1-12TH FLOOR | 1 | No Unit | 11 Jun 2016 | 02 Dec 2016 |  |  | 174 | 0 | 0 | 0
A1-FLAT 1201 TILE (M+L) | 11 | No Unit | 11 Jun 2016 | 25 Nov 2016 |  |  | 167 | 0 | 0 | 0
A1-Flat 1201 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 11 Jun 2016 | 15 Jun 2016 | 25 Jun 2016 | 26 Dec 2016 | 4 | 184 | 14 | 194
A1-Flat 1201 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 26 Aug 2016 | 29 Aug 2016 | 25 Jun 2016 | 26 Dec 2016 | 3 | 184 | 0 | 119
A1-Flat 1201 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 30 Aug 2016 | 31 Aug 2016 | 25 Jun 2016 | 26 Dec 2016 | 1 | 184 | 0 | 117
A1-Flat 1201 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 24 Nov 2016 | 25 Nov 2016 | 26 Jul 2016 | 26 Dec 2016 | 1 | 153 | 0 | 31
A1-Flat 1201 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 01 Sep 2016 | 01 Sep 2016 | 22 Nov 2016 | 26 Dec 2016 | 0 | 34 | 82 | 116
A1-Flat 1201 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 14 Sep 2016 | 15 Sep 2016 | 22 Nov 2016 | 26 Dec 2016 | 1 | 34 | 69 | 102
A1-Flat 1201 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 14 Sep 2016 | 15 Sep 2016 | 22 Nov 2016 |  | 1 | 0 | 69 | 0
A1-FLAT 1202 TILE (M+L) | 0 | No Unit | 16 Jun 2016 | 28 Nov 2016 |  |  | 165 | 0 | 0 | 0
A1-Flat 1202 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 16 Jun 2016 | 20 Jun 2016 | 25 Jun 2016 | 26 Dec 2016 | 4 | 184 | 9 | 189
A1-Flat 1202 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 02 Sep 2016 | 05 Sep 2016 | 25 Jun 2016 | 26 Dec 2016 | 3 | 184 | 0 | 112
A1-Flat 1202 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 06 Sep 2016 | 07 Sep 2016 | 22 Nov 2016 | 26 Dec 2016 | 1 | 34 | 77 | 110
A1-Flat 1202 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 26 Nov 2016 | 28 Nov 2016 | 26 Jul 2016 | 26 Dec 2016 | 2 | 153 | 0 | 28
A1-Flat 1202 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 08 Sep 2016 | 08 Sep 2016 | 22 Nov 2016 | 26 Dec 2016 | 0 | 34 | 75 | 109
A1-Flat 1202 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 21 Sep 2016 | 22 Sep 2016 | 22 Nov 2016 | 26 Dec 2016 | 1 | 34 | 62 | 95
A1-Flat 1202 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 21 Sep 2016 | 22 Sep 2016 | 22 Nov 2016 |  | 1 | 0 | 62 | 0
A1-FLAT 1203 TILE (M+L) | 0 | No Unit | 21 Jun 2016 | 30 Nov 2016 |  |  | 162 | 0 | 0 | 0
A1-Flat 1203 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 21 Jun 2016 | 24 Jun 2016 | 20 Jul 2016 | 26 Dec 2016 | 3 | 159 | 29 | 185
A1-Flat 1203 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 09 Sep 2016 | 12 Sep 2016 | 16 Aug 2016 | 26 Dec 2016 | 3 | 132 | 0 | 105
A1-Flat 1203 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 13 Sep 2016 | 14 Sep 2016 | 16 Aug 2016 | 26 Dec 2016 | 1 | 132 | 0 | 103
A1-Flat 1203 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 29 Nov 2016 | 30 Nov 2016 | 26 Jul 2016 | 26 Dec 2016 | 1 | 153 | 0 | 26
A1-Flat 1203 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Sep 2016 | 15 Sep 2016 | 16 Aug 2016 | 26 Dec 2016 | 0 | 132 | 0 | 102
A1-Flat 1203 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 28 Sep 2016 | 29 Sep 2016 | 16 Aug 2016 | 26 Dec 2016 | 1 | 132 | 0 | 88
A1-Flat 1203 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 28 Sep 2016 | 29 Sep 2016 | 16 Aug 2016 |  | 1 | 0 | 0 | 0
A1-FLAT 1204 TILE (M+L) | 0 | No Unit | 25 Jun 2016 | 02 Dec 2016 |  |  | 160 | 0 | 0 | 0
A1-Flat 1204 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 25 Jun 2016 | 29 Jun 2016 | 28 Jun 2016 | 26 Dec 2016 | 4 | 181 | 3 | 180
A1-Flat 1204 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 16 Sep 2016 | 19 Sep 2016 | 16 Aug 2016 | 26 Dec 2016 | 3 | 132 | 0 | 98
A1-Flat 1204 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 20 Sep 2016 | 21 Sep 2016 | 16 Aug 2016 | 26 Dec 2016 | 1 | 132 | 0 | 96
A1-Flat 1204 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 01 Dec 2016 | 02 Dec 2016 | 26 Jul 2016 | 26 Dec 2016 | 1 | 153 | 0 | 24
A1-Flat 1204 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 22 Sep 2016 | 22 Sep 2016 | 16 Aug 2016 | 26 Dec 2016 | 0 | 132 | 0 | 95
A1-Flat 1204 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 05 Oct 2016 | 06 Oct 2016 | 16 Aug 2016 | 26 Dec 2016 | 1 | 132 | 0 | 81
A1-Flat 1204 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 05 Oct 2016 | 06 Oct 2016 | 16 Aug 2016 |  | 1 | 0 | 0 | 0
A1-12TH FL.LOBBY | 0 | No Unit | 13 Oct 2016 | 14 Oct 2016 |  |  | 1 | 0 | 0 | 0
A1-12th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 13 Oct 2016 | 14 Oct 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 40 | 108
A1- 12TH FL FIRE STAIR | 0 | No Unit | 13 Oct 2016 | 14 Oct 2016 |  |  | 1 | 0 | 0 | 0
A1- 12th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 13 Oct 2016 | 14 Oct 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 40 | 108
A1-13TH FLOOR | 0 | No Unit | 07 Jul 2016 | 09 Dec 2016 |  |  | 155 | 0 | 0 | 0
A1-FLAT 1301 TILE (M+L) | 11 | No Unit | 07 Jul 2016 | 05 Dec 2016 |  |  | 151 | 0 | 0 | 0
A1-Flat 1301 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 07 Jul 2016 | 11 Jul 2016 | 26 Sep 2016 | 13 Jan 2017 | 4 | 109 | 81 | 186
A1-Flat 1301 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 19 Sep 2016 | 21 Sep 2016 | 19 Sep 2016 | 13 Jan 2017 | 2 | 116 | 0 | 114
A1-Flat 1301 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 22 Sep 2016 | 23 Sep 2016 | 07 Nov 2016 | 05 Jan 2017 | 1 | 59 | 46 | 104
A1-Flat 1301 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 03 Dec 2016 | 05 Dec 2016 | 07 Nov 2016 | 13 Jan 2017 | 2 | 67 | 0 | 39
A1-Flat 1301 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 24 Sep 2016 | 24 Sep 2016 | 07 Nov 2016 | 13 Jan 2017 | 0 | 67 | 44 | 111
A1-Flat 1301 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 07 Oct 2016 | 08 Oct 2016 | 07 Nov 2016 | 13 Jan 2017 | 1 | 67 | 31 | 97
A1-Flat 1301 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 07 Oct 2016 | 08 Oct 2016 | 07 Nov 2016 |  | 1 | 0 | 31 | 0
A1-FLAT 1302 TILE (M+L) | 0 | No Unit | 12 Jul 2016 | 07 Dec 2016 |  |  | 148 | 0 | 0 | 0
A1-Flat 1302 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 12 Jul 2016 | 15 Jul 2016 | 12 Jul 2016 | 13 Jan 2017 | 3 | 185 | 0 | 182
A1-Flat 1302 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 30 Sep 2016 | 03 Oct 2016 | 13 Oct 2016 | 13 Jan 2017 | 3 | 92 | 13 | 102
A1-Flat 1302 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 10 Oct 2016 | 11 Oct 2016 | 07 Nov 2016 | 05 Jan 2017 | 1 | 59 | 28 | 86
A1-Flat 1302 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 06 Dec 2016 | 07 Dec 2016 | 07 Nov 2016 | 13 Jan 2017 | 1 | 67 | 0 | 37
A1-Flat 1302 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 12 Oct 2016 | 12 Oct 2016 | 07 Nov 2016 | 13 Jan 2017 | 0 | 67 | 26 | 93
A1-Flat 1302 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 05 Oct 2016 | 06 Oct 2016 | 07 Nov 2016 | 13 Jan 2017 | 1 | 67 | 33 | 99
A1-Flat 1302 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 05 Oct 2016 | 06 Oct 2016 | 07 Nov 2016 |  | 1 | 0 | 33 | 0
A1-FLAT 1303 TILE (M+L) | 1 | No Unit | 16 Jul 2016 | 09 Dec 2016 |  |  | 146 | 0 | 0 | 0
A1-Flat 1303 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 16 Jul 2016 | 20 Jul 2016 | 15 Oct 2016 | 13 Jan 2017 | 4 | 90 | 91 | 177
A1-Flat 1303 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 19 Sep 2016 | 21 Sep 2016 | 19 Sep 2016 | 13 Jan 2017 | 2 | 116 | 0 | 114
A1-Flat 1303 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 22 Sep 2016 | 23 Sep 2016 | 07 Nov 2016 | 05 Jan 2017 | 1 | 59 | 46 | 104
A1-Flat 1303 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 08 Dec 2016 | 09 Dec 2016 | 07 Nov 2016 | 13 Jan 2017 | 1 | 67 | 0 | 35
A1-Flat 1303 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 24 Sep 2016 | 24 Sep 2016 | 07 Nov 2016 | 13 Jan 2017 | 0 | 67 | 44 | 111
A1-Flat 1303 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 07 Oct 2016 | 08 Oct 2016 | 07 Nov 2016 | 13 Jan 2017 | 1 | 67 | 31 | 97
A1-Flat 1303 Tile (M+L) Granite Window Cill upto 3"(M+L) | 0 | Rft. | 07 Oct 2016 | 08 Oct 2016 | 07 Nov 2016 |  | 1 | 0 | 31 | 0
A1-REFUGE FLAT 1304 TILE (M+L) | 0 | No Unit | 21 Jul 2016 | 09 Dec 2016 |  |  | 141 | 0 | 0 | 0
A1-Refuge Flat 1304 Tile (M+L) Granite Kitchen Otta (M+L) | 0 | No. | 21 Jul 2016 | 25 Jul 2016 | 22 Nov 2016 | 05 Jan 2017 | 4 | 44 | 124 | 164
A1-Refuge Flat 1304 Tile (M+L) Granite Door Frame (M+L) | 0 | No. | 19 Sep 2016 | 21 Sep 2016 | 22 Nov 2016 | 05 Jan 2017 | 2 | 44 | 64 | 106
A1-Refuge Flat 1304 Tile (M+L) Granite Window Jambs (M+L) | 0 | NO | 22 Sep 2016 | 23 Sep 2016 | 22 Nov 2016 | 05 Jan 2017 | 1 | 44 | 61 | 104
A1-Refuge Flat 1304 Tile (M+L) Granite WHB Counter (M+L) | 0 | No. | 08 Dec 2016 | 09 Dec 2016 | 22 Nov 2016 | 05 Jan 2017 | 1 | 44 | 0 | 27
A1-Refuge Flat 1304 Tile (M+L) Granite Ledge wall (M+L) | 0 | Rft. | 24 Sep 2016 | 24 Sep 2016 | 22 Nov 2016 | 05 Jan 2017 | 0 | 44 | 59 | 103
A1-Refuge Flat 1304 Tile (M+L) Granite Wnd Cill- 4" to 6" (M | 0 | Rft. | 07 Oct 2016 | 08 Oct 2016 | 22 Nov 2016 | 05 Jan 2017 | 1 | 44 | 46 | 89
A1-Refuge Flat 1304 Tile (M+L) Granite Window Cill upto 3"(M | 0 | Rft. | 07 Oct 2016 | 08 Oct 2016 | 22 Nov 2016 | 05 Jan 2017 | 1 | 44 | 46 | 89
A1-13TH FL.LOBBY | 0 | No Unit | 27 Oct 2016 | 28 Oct 2016 |  |  | 1 | 0 | 0 | 0
A1-13th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 27 Oct 2016 | 28 Oct 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 26 | 94
A1-13TH FL FIRE STAIR | 0 | No Unit | 27 Oct 2016 | 28 Oct 2016 |  |  | 1 | 0 | 0 | 0
A1-13th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 27 Oct 2016 | 28 Oct 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 26 | 94
A1-14TH FLOOR | 0 | No Unit | 23 Jul 2016 | 19 Dec 2016 |  |  | 149 | 0 | 0 | 0
A1-FLAT 1401 TILE (M+L) | 11 | No Unit | 23 Jul 2016 | 12 Dec 2016 |  |  | 142 | 0 | 0 | 0
A1-Flat 1401 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 23 Jul 2016 | 27 Jul 2016 | 05 Jan 2017 | 05 Jan 2017 | 4 | 0 | 166 | 162
A1-Flat 1401 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 19 Sep 2016 | 21 Sep 2016 | 05 Jan 2017 | 05 Jan 2017 | 2 | 0 | 108 | 106
A1-Flat 1401 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 22 Sep 2016 | 23 Sep 2016 | 05 Jan 2017 | 05 Jan 2017 | 1 | 0 | 105 | 104
A1-Flat 1401 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 10 Dec 2016 | 12 Dec 2016 | 05 Jan 2017 | 05 Jan 2017 | 2 | 0 | 26 | 24
A1-Flat 1401 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 24 Sep 2016 | 24 Sep 2016 | 05 Jan 2017 | 05 Jan 2017 | 0 | 0 | 103 | 103
A1-Flat 1401 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 07 Oct 2016 | 08 Oct 2016 | 05 Jan 2017 | 05 Jan 2017 | 1 | 0 | 90 | 89
A1-Flat 1401 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 07 Oct 2016 | 08 Oct 2016 | 05 Jan 2017 | 05 Jan 2017 | 1 | 0 | 90 | 89
A1-FLAT 1402 TILE (M+L) | 0 | No Unit | 28 Jul 2016 | 14 Dec 2016 |  |  | 139 | 0 | 0 | 0
A1-Flat 1402 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 28 Jul 2016 | 01 Aug 2016 | 05 Jan 2017 | 05 Jan 2017 | 4 | 0 | 161 | 157
A1-Flat 1402 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 21 Sep 2016 | 23 Sep 2016 | 05 Jan 2017 | 05 Jan 2017 | 2 | 0 | 106 | 104
A1-Flat 1402 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 24 Sep 2016 | 26 Sep 2016 | 05 Jan 2017 | 05 Jan 2017 | 2 | 0 | 103 | 101
A1-Flat 1402 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 13 Dec 2016 | 14 Dec 2016 | 05 Jan 2017 | 05 Jan 2017 | 1 | 0 | 23 | 22
A1-Flat 1402 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 27 Sep 2016 | 27 Sep 2016 | 05 Jan 2017 | 05 Jan 2017 | 0 | 0 | 100 | 100
A1-Flat 1402 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 10 Oct 2016 | 11 Oct 2016 | 05 Jan 2017 | 05 Jan 2017 | 1 | 0 | 87 | 86
A1-Flat 1402 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 10 Oct 2016 | 11 Oct 2016 | 05 Jan 2017 | 05 Jan 2017 | 1 | 0 | 87 | 86
A1-FLAT 1403 TILE (M+L) | 0 | No Unit | 02 Aug 2016 | 16 Dec 2016 |  |  | 136 | 0 | 0 | 0
A1-Flat 1403 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 02 Aug 2016 | 05 Aug 2016 | 03 May 2016 | 13 Jan 2017 | 3 | 255 | 0 | 161
A1-Flat 1403 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 23 Sep 2016 | 26 Sep 2016 | 10 May 2016 | 13 Jul 2016 | 3 | 64 | 0 | 0
A1-Flat 1403 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 27 Sep 2016 | 28 Sep 2016 | 10 May 2016 | 05 Jan 2017 | 1 | 240 | 0 | 99
A1-Flat 1403 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Dec 2016 | 16 Dec 2016 | 11 Jun 2016 | 13 Jan 2017 | 1 | 216 | 0 | 28
A1-Flat 1403 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 29 Sep 2016 | 29 Sep 2016 | 13 Jul 2016 | 13 Jan 2017 | 0 | 184 | 0 | 106
A1-Flat 1403 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 12 Oct 2016 | 13 Oct 2016 | 13 Jul 2016 | 13 Jan 2017 | 1 | 184 | 0 | 92
A1-Flat 1403 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 12 Oct 2016 | 13 Oct 2016 | 13 Jul 2016 |  | 1 | 0 | 0 | 0
A1-FLAT 1404 TILE (M+L) | 0 | No Unit | 06 Aug 2016 | 19 Dec 2016 |  |  | 135 | 0 | 0 | 0
A1-Flat 1404 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 06 Aug 2016 | 10 Aug 2016 | 26 Sep 2016 | 13 Jan 2017 | 4 | 109 | 51 | 156
A1-Flat 1404 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 26 Sep 2016 | 28 Sep 2016 | 26 Sep 2016 | 13 Jan 2017 | 2 | 109 | 0 | 107
A1-Flat 1404 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 29 Sep 2016 | 30 Sep 2016 | 07 Nov 2016 | 05 Jan 2017 | 1 | 59 | 39 | 97
A1-Flat 1404 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 17 Dec 2016 | 19 Dec 2016 | 07 Nov 2016 | 13 Jan 2017 | 2 | 67 | 0 | 25
A1-Flat 1404 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 01 Oct 2016 | 01 Oct 2016 | 07 Nov 2016 | 13 Jan 2017 | 0 | 67 | 37 | 104
A1-Flat 1404 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 14 Oct 2016 | 15 Oct 2016 | 07 Nov 2016 | 13 Jan 2017 | 1 | 67 | 24 | 90
A1-Flat 1404 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 14 Oct 2016 | 15 Oct 2016 | 07 Nov 2016 |  | 1 | 0 | 24 | 0
A1-14TH FL.LOBBY | 0 | No Unit | 04 Nov 2016 | 05 Nov 2016 |  |  | 1 | 0 | 0 | 0
A1-14th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 04 Nov 2016 | 05 Nov 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 18 | 86
A1-14TH FL FIRE STAIR | 0 | No Unit | 04 Nov 2016 | 05 Nov 2016 |  |  | 1 | 0 | 0 | 0
A1-14th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 04 Nov 2016 | 05 Nov 2016 | 22 Nov 2016 | 30 Jan 2017 | 1 | 69 | 18 | 86
A1-TERRACE FLOOR | 0 | No Unit | 07 Nov 2016 | 08 Nov 2016 |  |  | 1 | 0 | 0 | 0
A1-Terrace Floor Granite Wnd Cill- 4" to 6" (M+L) | 0 | Rft. | 07 Nov 2016 | 08 Nov 2016 | 13 Jan 2017 | 13 Jan 2017 | 1 | 0 | 67 | 66
A1-TERRACE FL FIRE STAIR | 0 | No Unit | 07 Nov 2016 | 08 Nov 2016 |  |  | 1 | 0 | 0 | 0
A1-Terrace Fl Fire Stair Granite Window Cill upto 3"(M+L) | 0 | Rft. | 07 Nov 2016 | 08 Nov 2016 | 13 Jan 2017 | 13 Jan 2017 | 1 | 0 | 67 | 66
A1- UMARA PATTI (M+L) 1 TO 14TH FLOOR | 0 | No Unit | 23 May 2015 |  |  |  | 0 | 0 | 0 | 0
A1- Umara Patti (M+L) 1 to 14th Floor Umbra Patti (M+L) | 425 | Rft | 23 May 2015 |  | 17 Oct 2016 |  | 0 | 0 | 513 | 0
A1-ELECTRICAL (M+L) | 0 | No Unit | 13 Aug 2015 | 09 Dec 2016 |  |  | 484 | 0 | 0 | 0
A1-PARKING FL | 0 | No Unit | 13 Aug 2015 | 15 Oct 2016 |  |  | 429 | 0 | 0 | 0
A1-Parking Fl Slab conduiting (M+L) | 56695 | Sft. | 13 Aug 2015 | 17 Aug 2015 | 18 Aug 2015 | 01 Oct 2015 | 4 | 44 | 5 | 45
A1-Parking Fl Wall Dropping (M+L) | 56695 | Sft. | 26 Jul 2016 | 27 Jul 2016 | 13 Oct 2016 | 04 Dec 2016 | 1 | 52 | 79 | 130
A1-Parking Fl Wiring (M+L) | 56695 | Sft. | 12 Oct 2016 | 13 Oct 2016 | 13 Oct 2016 | 04 Dec 2016 | 1 | 52 | 1 | 52
A1-Parking Fl Switches,Plates & Acc. (M+L) | 56695 | Sft. | 14 Oct 2016 | 15 Oct 2016 | 13 Oct 2016 |  | 1 | 0 | 0 | 0
A1-1ST FLOOR | 0 | No Unit | 10 Sep 2015 | 12 Jul 2016 |  |  | 306 | 0 | 0 | 0
A1-1st Floor Slab conduiting (M+L) | 56695 | Sft. | 10 Sep 2015 | 12 Sep 2015 | 07 Sep 2015 | 01 Oct 2015 | 2 | 24 | 0 | 19
A1-1st Floor Wall Dropping (M+L) | 56695 | Sft. | 25 Nov 2015 | 08 Dec 2015 | 11 Dec 2015 | 29 Dec 2015 | 13 | 18 | 16 | 21
A1-1st Floor Wiring (M+L) | 56695 | Sft. | 02 May 2016 | 10 May 2016 | 29 Feb 2016 | 18 Jun 2016 | 8 | 110 | 0 | 39
A1-1st Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 29 Jun 2016 | 12 Jul 2016 | 08 Jun 2016 | 18 Jun 2016 | 13 | 10 | 0 | 0
A1-1st Floor MCB-DB (M)- 2BHK 2T | 4 | No. | 29 Jun 2016 | 07 Jul 2016 | 07 May 2016 | 02 Sep 2016 | 8 | 118 | 0 | 57
A1-1st Floor ACCL | 4 | NO | 29 Jun 2016 | 07 Jul 2016 | 01 Sep 2016 | 02 Sep 2016 | 8 | 1 | 64 | 57
A1-2ND FLOOR | 0 | No Unit | 30 Sep 2015 | 19 Jul 2016 |  |  | 293 | 0 | 0 | 0
A1-2nd Floor Slab conduiting (M+L) | 56695 | Sft. | 30 Sep 2015 | 03 Oct 2015 | 15 Sep 2015 | 01 Oct 2015 | 3 | 16 | 0 | 0
A1-2nd Floor Wall Dropping (M+L) | 56695 | Sft. | 03 Dec 2015 | 16 Dec 2015 | 11 Dec 2015 | 29 Dec 2015 | 13 | 18 | 8 | 13
A1-2nd Floor Wiring (M+L) | 56695 | Sft. | 11 May 2016 | 19 May 2016 | 28 Mar 2016 | 18 Jun 2016 | 8 | 82 | 0 | 30
A1-2nd Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 06 Jul 2016 | 19 Jul 2016 | 08 Jun 2016 | 18 Jun 2016 | 13 | 10 | 0 | 0
A1-2nd Floor MCB-DB (M)- 2BHK 2T | 4 | No. | 06 Jul 2016 | 14 Jul 2016 | 07 May 2016 | 02 Sep 2016 | 8 | 118 | 0 | 50
A1-2nd Floor ACCL | 4 | NO | 06 Jul 2016 | 14 Jul 2016 | 01 Sep 2016 | 02 Sep 2016 | 8 | 1 | 57 | 50
A1-3RD FLOOR | 0 | No Unit | 19 Oct 2015 | 28 Jul 2016 |  |  | 283 | 0 | 0 | 0
A1-3rd Floor Slab conduiting (M+L) | 56695 | Sft. | 19 Oct 2015 | 21 Oct 2015 | 26 Sep 2015 | 01 Oct 2015 | 2 | 5 | 0 | 0
A1-3rd Floor Wall Dropping (M+L) | 56695 | Sft. | 23 Dec 2015 | 06 Jan 2016 | 11 Dec 2015 | 29 Dec 2015 | 14 | 18 | 0 | 0
A1-3rd Floor Wiring (M+L) | 56695 | Sft. | 23 May 2016 | 31 May 2016 | 28 Mar 2016 | 18 Jun 2016 | 8 | 82 | 0 | 18
A1-3rd Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 15 Jul 2016 | 28 Jul 2016 | 08 Jun 2016 | 18 Jun 2016 | 13 | 10 | 0 | 0
A1-3rd Floor MCB-DB (M)- 2BHK 2T | 4 | No. | 15 Jul 2016 | 23 Jul 2016 | 07 May 2016 | 02 Sep 2016 | 8 | 118 | 0 | 41
A1-3rd Floor ACCL | 4 | NO | 15 Jul 2016 | 23 Jul 2016 | 01 Sep 2016 | 02 Sep 2016 | 8 | 1 | 48 | 41
A1-4TH FLOOR | 0 | No Unit | 10 Nov 2015 | 08 Aug 2016 |  |  | 272 | 0 | 0 | 0
A1-4th Floor Slab conduiting (M+L) | 56695 | Sft. | 10 Nov 2015 | 12 Nov 2015 | 10 Oct 2015 | 10 Nov 2015 | 2 | 31 | 0 | 0
A1-4th Floor Wall Dropping (M+L) | 56695 | Sft. | 14 Jan 2016 | 28 Jan 2016 | 17 Jan 2016 | 02 Mar 2016 | 14 | 45 | 3 | 34
A1-4th Floor Wiring (M+L) | 56695 | Sft. | 18 Jun 2016 | 27 Jun 2016 | 28 Mar 2016 | 18 Jun 2016 | 9 | 82 | 0 | 0
A1-4th Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 26 Jul 2016 | 08 Aug 2016 | 08 Jun 2016 | 18 Jun 2016 | 13 | 10 | 0 | 0
A1-4th Floor MCB-DB (M)- 2BHK 2T | 4 | No. | 26 Jul 2016 | 03 Aug 2016 | 07 May 2016 | 02 Sep 2016 | 8 | 118 | 0 | 30
A1-4th Floor ACCL | 4 | NO | 26 Jul 2016 | 03 Aug 2016 | 01 Sep 2016 | 02 Sep 2016 | 8 | 1 | 37 | 30
A1-5TH FLOOR | 0 | No Unit | 01 Dec 2015 | 17 Aug 2016 |  |  | 260 | 0 | 0 | 0
A1-5th Floor Slab conduiting (M+L) | 56695 | Sft. | 01 Dec 2015 | 03 Dec 2015 | 09 Nov 2015 | 10 Nov 2015 | 2 | 1 | 0 | 0
A1-5th Floor Wall Dropping (M+L) | 56695 | Sft. | 06 Feb 2016 | 19 Feb 2016 | 17 Jan 2016 | 02 Mar 2016 | 13 | 45 | 0 | 12
A1-5th Floor Wiring (M+L) | 56695 | Sft. | 16 Jul 2016 | 25 Jul 2016 | 28 Mar 2016 | 18 Jun 2016 | 9 | 82 | 0 | 0
A1-5th Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 03 Aug 2016 | 17 Aug 2016 | 18 Jun 2016 | 18 Jun 2016 | 14 | 0 | 0 | 0
A1-5th Floor MCB-DB (M)- 2BHK 2T | 4 | No. | 03 Aug 2016 | 11 Aug 2016 | 07 May 2016 | 02 Sep 2016 | 8 | 118 | 0 | 22
A1-5th Floor ACCL | 4 | NO | 03 Aug 2016 | 11 Aug 2016 | 01 Sep 2016 | 02 Sep 2016 | 8 | 1 | 29 | 22
A1-6TH FLOOR | 0 | No Unit | 21 Dec 2015 | 29 Aug 2016 |  |  | 252 | 0 | 0 | 0
A1-6th Floor Slab conduiting (M+L) | 56695 | Sft. | 21 Dec 2015 | 23 Dec 2015 | 09 Nov 2015 | 10 Nov 2015 | 2 | 1 | 0 | 0
A1-6th Floor Wall Dropping (M+L) | 56695 | Sft. | 27 Feb 2016 | 12 Mar 2016 | 17 Jan 2016 | 02 Mar 2016 | 14 | 45 | 0 | 0
A1-6th Floor Wiring (M+L) | 56695 | Sft. | 22 Jul 2016 | 30 Jul 2016 | 18 Jun 2016 | 18 Jun 2016 | 8 | 0 | 0 | 0
A1-6th Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 16 Aug 2016 | 29 Aug 2016 | 18 Jun 2016 | 20 Jul 2016 | 13 | 32 | 0 | 0
A1-6th Floor MCB-DB (M)- 2BHK 2T | 4 | No. | 16 Aug 2016 | 24 Aug 2016 | 04 Jul 2016 | 02 Sep 2016 | 8 | 60 | 0 | 9
A1-6th Floor ACCL | 4 | NO | 16 Aug 2016 | 24 Aug 2016 | 01 Sep 2016 | 02 Sep 2016 | 8 | 1 | 16 | 9
A1-7TH FLOOR | 0 | No Unit | 14 Jan 2016 | 07 Sep 2016 |  |  | 237 | 0 | 0 | 0
A1-7th Floor Slab conduiting (M+L) | 56695 | Sft. | 14 Jan 2016 | 16 Jan 2016 | 09 Nov 2015 | 09 Jan 2016 | 2 | 61 | 0 | 0
A1-7th Floor Wall Dropping (M+L) | 56695 | Sft. | 20 Feb 2016 | 04 Mar 2016 | 09 Feb 2016 | 02 Mar 2016 | 13 | 22 | 0 | 0
A1-7th Floor Wiring (M+L) | 56695 | Sft. | 01 Aug 2016 | 09 Aug 2016 | 18 Jun 2016 | 18 Jun 2016 | 8 | 0 | 0 | 0
A1-7th Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 25 Aug 2016 | 07 Sep 2016 | 20 Jul 2016 | 20 Jul 2016 | 13 | 0 | 0 | 0
A1-7th Floor MCB-DB (M)- 2BHK 2T | 4 | No. | 25 Aug 2016 | 02 Sep 2016 | 04 Jul 2016 | 02 Sep 2016 | 8 | 60 | 0 | 0
A1-7th Floor ACCL | 4 | NO | 25 Aug 2016 | 02 Sep 2016 | 07 Sep 2016 | 13 Sep 2016 | 8 | 6 | 13 | 11
A1-8TH FLOOR | 0 | No Unit | 01 Feb 2016 | 15 Sep 2016 |  |  | 227 | 0 | 0 | 0
A1-8th Floor Slab conduiting (M+L) | 56695 | Sft. | 01 Feb 2016 | 03 Feb 2016 | 26 Nov 2015 | 09 Jan 2016 | 2 | 44 | 0 | 0
A1-8th Floor Wall Dropping (M+L) | 56695 | Sft. | 01 Apr 2016 | 14 Apr 2016 | 09 Feb 2016 | 18 Jun 2016 | 13 | 130 | 0 | 65
A1-8th Floor Wiring (M+L) | 56695 | Sft. | 27 Aug 2016 | 05 Sep 2016 | 18 Jun 2016 | 18 Jun 2016 | 9 | 0 | 0 | 0
A1-8th Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 02 Sep 2016 | 15 Sep 2016 | 20 Jul 2016 | 20 Jul 2016 | 13 | 0 | 0 | 0
A1-8th Floor MCB-DB (M)- 2BHK 2T | 3 | No. | 02 Sep 2016 | 10 Sep 2016 | 04 Jul 2016 | 02 Sep 2016 | 8 | 60 | 0 | 0
A1-8th Floor ACCL | 4 | NO | 02 Sep 2016 | 10 Sep 2016 | 07 Sep 2016 | 13 Sep 2016 | 8 | 6 | 5 | 3
A1-9TH FLOOR | 0 | No Unit | 17 Feb 2016 | 27 Sep 2016 |  |  | 223 | 0 | 0 | 0
A1-9th Floor Slab conduiting (M+L) | 56695 | Sft. | 17 Feb 2016 | 19 Feb 2016 | 23 Dec 2015 | 09 Jan 2016 | 2 | 17 | 0 | 0
A1-9th Floor Wall Dropping (M+L) | 56695 | Sft. | 23 Apr 2016 | 06 May 2016 | 01 Mar 2016 | 18 Jun 2016 | 13 | 109 | 0 | 43
A1-9th Floor Wiring (M+L) | 56695 | Sft. | 16 Sep 2016 | 24 Sep 2016 | 20 Jul 2016 | 20 Jul 2016 | 8 | 0 | 0 | 0
A1-9th Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 14 Sep 2016 | 27 Sep 2016 | 20 Jul 2016 | 22 Aug 2016 | 13 | 33 | 0 | 0
A1-9th Floor MCB-DB (M)- 2BHK 2T | 4 | No. | 14 Sep 2016 | 22 Sep 2016 | 04 Jul 2016 | 02 Sep 2016 | 8 | 60 | 0 | 0
A1-9th Floor ACCL | 4 | NO | 14 Sep 2016 | 22 Sep 2016 | 07 Sep 2016 | 13 Sep 2016 | 8 | 6 | 0 | 0
A1-10TH FLOOR | 0 | No Unit | 04 Mar 2016 | 08 Oct 2016 |  |  | 218 | 0 | 0 | 0
A1-10th Floor Slab conduiting (M+L) | 56695 | Sft. | 04 Mar 2016 | 08 Mar 2016 | 23 Dec 2015 | 09 Jan 2016 | 4 | 17 | 0 | 0
A1-10th Floor Wall Dropping (M+L) | 56695 | Sft. | 05 May 2016 | 18 May 2016 | 22 Mar 2016 | 18 Jun 2016 | 13 | 88 | 0 | 31
A1-10th Floor Wiring (M+L) | 56695 | Sft. | 26 Sep 2016 | 04 Oct 2016 | 20 Jul 2016 | 20 Jul 2016 | 8 | 0 | 0 | 0
A1-10th Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 26 Sep 2016 | 08 Oct 2016 | 09 Aug 2016 | 22 Aug 2016 | 12 | 13 | 0 | 0
A1-10th Floor MCB-DB (M)- 2BHK 2T | 4 | No. | 26 Sep 2016 | 04 Oct 2016 | 04 Jul 2016 | 13 Sep 2016 | 8 | 71 | 0 | 0
A1-10th Floor ACCL | 4 | NO | 26 Sep 2016 | 04 Oct 2016 | 07 Sep 2016 | 13 Sep 2016 | 8 | 6 | 0 | 0
A1-11TH FLOOR | 0 | No Unit | 22 Mar 2016 | 25 Oct 2016 |  |  | 217 | 0 | 0 | 0
A1-11th Floor Slab conduiting (M+L) | 56695 | Sft. | 22 Mar 2016 | 24 Mar 2016 | 03 Feb 2016 | 23 Feb 2016 | 2 | 20 | 0 | 0
A1-11th Floor Wall Dropping (M+L) | 56695 | Sft. | 20 May 2016 | 02 Jun 2016 | 30 Mar 2016 | 18 Jun 2016 | 13 | 80 | 0 | 16
A1-11th Floor Wiring (M+L) | 56695 | Sft. | 12 Oct 2016 | 20 Oct 2016 | 20 Jul 2016 | 08 Sep 2016 | 8 | 50 | 0 | 0
A1-11th Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 12 Oct 2016 | 25 Oct 2016 | 05 Oct 2016 | 04 Dec 2016 | 13 | 60 | 0 | 40
A1-11th Floor MCB-DB (M)- 2BHK 2T | 4 | No. | 12 Oct 2016 | 20 Oct 2016 | 10 Sep 2016 | 26 Dec 2016 | 8 | 107 | 0 | 67
A1-11th Floor ACCL | 4 | NO | 12 Oct 2016 | 20 Oct 2016 | 16 Sep 2016 | 26 Dec 2016 | 8 | 101 | 0 | 67
A1-12TH FLOOR | 0 | No Unit | 06 Apr 2016 | 22 Nov 2016 |  |  | 230 | 0 | 0 | 0
A1-12th Floor Slab conduiting (M+L) | 56695 | Sft. | 06 Apr 2016 | 08 Apr 2016 | 09 Feb 2016 | 23 Feb 2016 | 2 | 14 | 0 | 0
A1-12th Floor Wall Dropping (M+L) | 56695 | Sft. | 31 May 2016 | 13 Jun 2016 | 20 Jul 2016 | 20 Jul 2016 | 13 | 0 | 50 | 37
A1-12th Floor Wiring (M+L) | 56695 | Sft. | 09 Nov 2016 | 17 Nov 2016 | 20 Jul 2016 | 08 Sep 2016 | 8 | 50 | 0 | 0
A1-12th Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 09 Nov 2016 | 22 Nov 2016 | 12 Nov 2016 | 04 Dec 2016 | 13 | 22 | 3 | 12
A1-12th Floor MCB-DB (M)- 2BHK 2T | 4 | No. | 09 Nov 2016 | 17 Nov 2016 | 10 Sep 2016 | 26 Dec 2016 | 8 | 107 | 0 | 39
A1-12th Floor ACCL | 4 | NO | 09 Nov 2016 | 17 Nov 2016 | 16 Sep 2016 | 26 Dec 2016 | 8 | 101 | 0 | 39
A1-13TH FLOOR | 0 | No Unit | 17 May 2016 | 24 Nov 2016 |  |  | 191 | 0 | 0 | 0
A1-13th Floor Slab conduiting (M+L) | 56695 | Sft. | 17 May 2016 | 19 May 2016 | 08 Sep 2016 | 08 Sep 2016 | 2 | 0 | 114 | 112
A1-13th Floor Wall Dropping (M+L) | 56695 | Sft. | 18 Jun 2016 | 01 Jul 2016 | 05 Oct 2016 | 04 Dec 2016 | 13 | 60 | 109 | 156
A1-13th Floor Wiring (M+L) | 56695 | Sft. | 11 Nov 2016 | 19 Nov 2016 | 12 Nov 2016 | 04 Dec 2016 | 8 | 22 | 1 | 15
A1-13th Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 11 Nov 2016 | 24 Nov 2016 | 12 Nov 2016 | 26 Dec 2016 | 13 | 44 | 1 | 32
A1-13th Floor MCB-DB (M)- 2BHK 2T | 3 | No. | 11 Nov 2016 | 19 Nov 2016 | 22 Oct 2016 | 26 Dec 2016 | 8 | 65 | 0 | 37
A1-13th Floor ACCL | 3 | NO | 11 Nov 2016 | 19 Nov 2016 | 22 Oct 2016 | 26 Dec 2016 | 8 | 65 | 0 | 37
A1-14TH FLOOR | 0 | No Unit | 02 Jun 2016 | 01 Dec 2016 |  |  | 182 | 0 | 0 | 0
A1-14th Floor Slab conduiting (M+L) | 56695 | Sft. | 02 Jun 2016 | 04 Jun 2016 | 22 Dec 2016 |  | 2 | 0 | 203 | 0
A1-14th Floor Wall Dropping (M+L) | 56695 | Sft. | 05 Jul 2016 | 18 Jul 2016 | 12 Nov 2016 | 04 Dec 2016 | 13 | 22 | 130 | 139
A1-14th Floor Wiring (M+L) | 56695 | Sft. | 11 Nov 2016 | 19 Nov 2016 | 12 Nov 2016 | 26 Dec 2016 | 8 | 44 | 1 | 37
A1-14th Floor Switches,Plates & Acc. (M+L) | 56695 | Sft. | 18 Nov 2016 | 01 Dec 2016 | 12 Nov 2016 | 26 Dec 2016 | 13 | 44 | 0 | 25
A1-14th Floor MCB-DB (M)- 2BHK 2T | 4 | No. | 18 Nov 2016 | 26 Nov 2016 | 04 Jul 2016 | 26 Dec 2016 | 8 | 175 | 0 | 30
A1-14th Floor ACCL | 2 | NO | 18 Nov 2016 | 26 Nov 2016 | 07 Sep 2016 | 26 Dec 2016 | 8 | 110 | 0 | 30
A1-EARTHING PITS | 0 | No Unit | 29 Mar 2016 | 06 Apr 2016 |  |  | 8 | 0 | 0 | 0
A1-Earthing pits 9`` X 12`` Chamber | 7 | NO | 29 Mar 2016 | 06 Apr 2016 | 01 Feb 2017 | 01 Feb 2017 | 8 | 0 | 309 | 301
A1-COMMON AREA | 0 | No Unit | 11 Dec 2015 | 07 Dec 2016 |  |  | 362 | 0 | 0 | 0
A1-Common Area Building Earthing (M+L) | 56695 | Sft. | 03 May 2016 | 05 May 2016 | 05 Jan 2017 | 13 Jan 2017 | 2 | 8 | 247 | 253
A1-Common Area Building Electrical Testing (M+L) | 56695 | Sft. | 08 Jul 2016 | 07 Dec 2016 | 01 Feb 2017 |  | 152 | 0 | 208 | 0
A1-Common Area Lift 1- Electrification (M+L) | 56695 | Sft. | 07 Jun 2016 | 23 Jun 2016 | 06 Jun 2016 | 27 Jul 2016 | 16 | 51 | 0 | 34
A1-Common Area Lift 2- Electrification (M+L) | 56695 | Sft. | 07 Jun 2016 | 23 Jun 2016 | 06 Jun 2016 | 08 Sep 2016 | 16 | 94 | 0 | 77
A1-Common Area Lightening Arrestor (M+L) | 56695 | Sft. | 20 Jun 2016 | 28 Jun 2016 | 05 Jan 2017 | 13 Jan 2017 | 8 | 8 | 199 | 199
A1-Common Area Mains Conduiting (M+L) | 56695 | Sft. | 11 Dec 2015 | 28 Dec 2015 | 25 Aug 2016 | 13 Jan 2017 | 17 | 141 | 258 | 382
A1-Common Area Meter Room Electrification (M+L) | 56695 | Sft. | 10 Jun 2016 | 18 Jun 2016 | 08 Sep 2016 |  | 8 | 0 | 90 | 0
A1-Common Area Flat testing & handing over | 56695 | Sft. | 08 Jul 2016 | 07 Dec 2016 | 01 Feb 2017 |  | 152 | 0 | 208 | 0
A1-Common Area Mains Wiring (M+L) | 56695 | Sft. | 10 Jun 2016 | 27 Jun 2016 | 25 Aug 2016 | 13 Jan 2017 | 17 | 141 | 76 | 200
A1-TOTAL MCB, DB (LAB) | 0 | No Unit | 29 Jun 2016 | 09 Dec 2016 |  |  | 163 | 0 | 0 | 0
A1-Total MCB, DB (Lab) MCB, DB fixing (Lab) | 56695 | Sft. | 29 Jun 2016 | 09 Dec 2016 | 01 Feb 2017 |  | 163 | 0 | 217 | 0
A1-MISC.LIGHT FITTINGS | 0 | No Unit | 20 Jun 2016 | 12 Jul 2016 |  |  | 22 | 0 | 0 | 0
A1-Misc.Light Fittings Lobby Light Fitting | 1 | No. | 20 Jun 2016 | 12 Jul 2016 | 10 Oct 2016 |  | 22 | 0 | 112 | 0
A1-Misc.Light Fittings Common Area Light Fitting | 1 | No. | 20 Jun 2016 | 12 Jul 2016 | 02 Aug 2016 |  | 22 | 0 | 43 | 0
A1-Misc.Light Fittings Parking Light Fitting | 1 | No. | 20 Jun 2016 | 12 Jul 2016 | 06 Oct 2016 |  | 22 | 0 | 108 | 0
A1-Misc.Light Fittings Misc. Light Fitting (Lab) | 1 | Job | 20 Jun 2016 | 12 Jul 2016 | 23 Feb 2016 |  | 22 | 0 | 0 | 0
A1-PLUMBING & SANITATION | 0 | No Unit | 07 Dec 2015 | 26 Dec 2016 |  |  | 385 | 0 | 0 | 0
A1- INTERNAL PLUMBING | 1 | No Unit | 07 Dec 2015 | 26 Dec 2016 |  |  | 385 | 0 | 0 | 0
A1- PARKING FLOOR PLUMBING | 0 | No Unit | 06 Aug 2016 | 19 Aug 2016 |  |  | 13 | 0 | 0 | 0
A1- PARKING FLOOR LEDGE WALL | 1 | No Unit | 06 Aug 2016 | 08 Aug 2016 |  |  | 2 | 0 | 0 | 0
A1- Parking Floor ledge wall CLC Block Masonry 4" (OS) | 0 | Sft. | 06 Aug 2016 | 08 Aug 2016 | 03 Feb 2017 | 03 Feb 2017 | 2 | 0 | 181 | 179
A1- Parking Floor ledge wall CLC Block Making 500 x 200 x 10 | 0 | No. | 06 Aug 2016 | 08 Aug 2016 | 03 Feb 2017 | 03 Feb 2017 | 2 | 0 | 181 | 179
A1- Parking Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 06 Aug 2016 | 08 Aug 2016 | 03 Feb 2017 | 03 Feb 2017 | 2 | 0 | 181 | 179
A1- Parking Floor Plumbing Internnal Plumbing (Lab) | 56695 | Sft. | 06 Aug 2016 | 08 Aug 2016 | 03 Feb 2017 |  | 2 | 0 | 181 | 0
A1- Parking Floor Plumbing Int.CP sanitary ( Lab) | 56695 | Sft. | 18 Aug 2016 | 19 Aug 2016 | 03 Feb 2017 |  | 1 | 0 | 169 | 0
A1- Parking Floor Plumbing Parking Plumbing | 1 | No. | 18 Aug 2016 | 19 Aug 2016 | 23 Feb 2016 |  | 1 | 0 | 0 | 0
A1- 1ST FLOOR PLUMBING | 0 | No Unit | 07 Dec 2015 | 24 Aug 2016 |  |  | 261 | 0 | 0 | 0
A1-101 | 1 | No Unit | 07 Dec 2015 | 17 Aug 2016 |  |  | 254 | 0 | 0 | 0
A1-101 CP Fitting (Kit+2T) | 1 | No. | 16 Aug 2016 | 17 Aug 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 134
A1-101 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 07 Dec 2015 | 09 Dec 2015 | 20 Nov 2015 | 27 Feb 2016 | 2 | 99 | 0 | 80
A1-101 Sanitaryware( Kit+2T) | 1 | No. | 16 Aug 2016 | 17 Aug 2016 | 29 Sep 2016 | 29 Dec 2016 | 1 | 91 | 44 | 134
A1-102 | 1 | No Unit | 10 Dec 2015 | 19 Aug 2016 |  |  | 253 | 0 | 0 | 0
A1-102 CP Fitting (Kit+2T) | 1 | No. | 18 Aug 2016 | 19 Aug 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 132
A1-102 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 10 Dec 2015 | 12 Dec 2015 | 20 Nov 2015 | 27 Feb 2016 | 2 | 99 | 0 | 77
A1-102 Sanitaryware( Kit+2T) | 1 | No. | 18 Aug 2016 | 19 Aug 2016 | 01 Aug 2016 | 29 Dec 2016 | 1 | 150 | 0 | 132
A1-103 | 1 | No Unit | 14 Dec 2015 | 22 Aug 2016 |  |  | 252 | 0 | 0 | 0
A1-103 CP Fitting (Kit+2T) | 1 | No. | 20 Aug 2016 | 22 Aug 2016 | 07 Jun 2016 | 29 Dec 2016 | 2 | 205 | 0 | 129
A1-103 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 14 Dec 2015 | 16 Dec 2015 | 20 Nov 2015 | 27 Feb 2016 | 2 | 99 | 0 | 73
A1-103 Sanitaryware( Kit+2T) | 1 | No. | 20 Aug 2016 | 22 Aug 2016 | 01 Aug 2016 | 29 Dec 2016 | 2 | 150 | 0 | 129
A1-104 | 27650633.39 | No Unit | 17 Dec 2015 | 24 Aug 2016 |  |  | 251 | 0 | 0 | 0
A1-104 CP Fitting (Kit+2T) | 1 | No. | 23 Aug 2016 | 24 Aug 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 127
A1-104 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 17 Dec 2015 | 19 Dec 2015 | 20 Nov 2015 | 27 Feb 2016 | 2 | 99 | 0 | 70
A1-104 Sanitaryware( Kit+2T) | 1 | No. | 23 Aug 2016 | 24 Aug 2016 | 10 Sep 2016 | 29 Dec 2016 | 1 | 110 | 18 | 127
A1-1ST FLOOR LEDGE WALL | 0 | No Unit | 07 Dec 2015 | 24 Dec 2015 |  |  | 17 | 0 | 0 | 0
A1-1st Floor ledge wall CLC Block Masonry 4" (OS) | 50 | Sft. | 07 Dec 2015 | 24 Dec 2015 | 22 Dec 2015 | 27 Feb 2016 | 17 | 67 | 15 | 65
A1-1st Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 07 Dec 2015 | 24 Dec 2015 | 27 Feb 2016 | 27 Feb 2016 | 17 | 0 | 82 | 65
A1-1st Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 07 Dec 2015 | 24 Dec 2015 | 27 Feb 2016 | 27 Feb 2016 | 17 | 0 | 82 | 65
A1-1ST FLOOR (LAB) | 0 | No Unit | 07 Dec 2015 | 24 Aug 2016 |  |  | 261 | 0 | 0 | 0
A1-1st Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 07 Dec 2015 | 19 Dec 2015 | 23 Dec 2015 | 02 Mar 2016 | 12 | 70 | 16 | 74
A1-1st Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 16 Aug 2016 | 24 Aug 2016 | 23 Aug 2016 | 13 Jan 2017 | 8 | 143 | 7 | 142
A1- 2ND FLOOR PLUMBING | 0 | No Unit | 15 Dec 2015 | 31 Aug 2016 |  |  | 260 | 0 | 0 | 0
A1-201 | 1 | No Unit | 15 Dec 2015 | 24 Aug 2016 |  |  | 253 | 0 | 0 | 0
A1-201 CP Fitting (Kit+2T) | 1 | No. | 23 Aug 2016 | 24 Aug 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 127
A1-201 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 15 Dec 2015 | 17 Dec 2015 | 20 Nov 2015 | 27 Feb 2016 | 2 | 99 | 0 | 72
A1-201 Sanitaryware( Kit+2T) | 1 | No. | 23 Aug 2016 | 24 Aug 2016 | 10 Sep 2016 | 29 Dec 2016 | 1 | 110 | 18 | 127
A1-202 | 1 | No Unit | 18 Dec 2015 | 26 Aug 2016 |  |  | 252 | 0 | 0 | 0
A1-202 CP Fitting (Kit+2T) | 1 | No. | 25 Aug 2016 | 26 Aug 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 125
A1-202 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 18 Dec 2015 | 21 Dec 2015 | 20 Nov 2015 | 27 Feb 2016 | 3 | 99 | 0 | 68
A1-202 Sanitaryware( Kit+2T) | 1 | No. | 25 Aug 2016 | 26 Aug 2016 | 01 Aug 2016 | 29 Dec 2016 | 1 | 150 | 0 | 125
A1-203 | 1 | No Unit | 22 Dec 2015 | 29 Aug 2016 |  |  | 251 | 0 | 0 | 0
A1-203 CP Fitting (Kit+2T) | 1 | No. | 27 Aug 2016 | 29 Aug 2016 | 07 Jun 2016 | 29 Dec 2016 | 2 | 205 | 0 | 122
A1-203 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 22 Dec 2015 | 24 Dec 2015 | 20 Nov 2015 | 27 Feb 2016 | 2 | 99 | 0 | 65
A1-203 Sanitaryware( Kit+2T) | 1 | No. | 27 Aug 2016 | 29 Aug 2016 | 01 Aug 2016 | 29 Dec 2016 | 2 | 150 | 0 | 122
A1-204 | 27650633.39 | No Unit | 25 Dec 2015 | 31 Aug 2016 |  |  | 250 | 0 | 0 | 0
A1-204 CP Fitting (Kit+2T) | 1 | No. | 30 Aug 2016 | 31 Aug 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 120
A1-204 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 25 Dec 2015 | 28 Dec 2015 | 20 Nov 2015 | 27 Feb 2016 | 3 | 99 | 0 | 61
A1-204 Sanitaryware( Kit+2T) | 1 | No. | 30 Aug 2016 | 31 Aug 2016 | 10 Sep 2016 | 29 Dec 2016 | 1 | 110 | 11 | 120
A1- 2ND FLOOR LEDGE WALL | 0 | No Unit | 15 Dec 2015 | 02 Jan 2016 |  |  | 18 | 0 | 0 | 0
A1- 2nd Floor ledge wall CLC Block Masonry 4" (OS) | 50 | Sft. | 15 Dec 2015 | 02 Jan 2016 | 26 Dec 2015 | 27 Feb 2016 | 18 | 63 | 11 | 56
A1- 2nd Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 15 Dec 2015 | 02 Jan 2016 | 27 Feb 2016 | 27 Feb 2016 | 18 | 0 | 74 | 56
A1- 2nd Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 15 Dec 2015 | 02 Jan 2016 | 27 Feb 2016 | 27 Feb 2016 | 18 | 0 | 74 | 56
A1- 2ND FLOOR (LAB) | 0 | No Unit | 15 Dec 2015 | 31 Aug 2016 |  |  | 260 | 0 | 0 | 0
A1- 2nd Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 15 Dec 2015 | 28 Dec 2015 | 23 Dec 2015 | 02 Mar 2016 | 13 | 70 | 8 | 65
A1- 2nd Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 23 Aug 2016 | 31 Aug 2016 | 23 Aug 2016 | 13 Jan 2017 | 8 | 143 | 0 | 135
A1- 3RD FLOOR PLUMBING | 0 | No Unit | 05 Jan 2016 | 09 Sep 2016 |  |  | 248 | 0 | 0 | 0
A1-301 | 1 | No Unit | 05 Jan 2016 | 02 Sep 2016 |  |  | 241 | 0 | 0 | 0
A1-301 CP Fitting (Kit+2T) | 1 | No. | 01 Sep 2016 | 02 Sep 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 118
A1-301 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 05 Jan 2016 | 07 Jan 2016 | 20 Nov 2015 | 29 Feb 2016 | 2 | 101 | 0 | 53
A1-301 Sanitaryware( Kit+2T) | 1 | No. | 01 Sep 2016 | 02 Sep 2016 | 10 Sep 2016 | 29 Dec 2016 | 1 | 110 | 9 | 118
A1-302 | 1 | No Unit | 08 Jan 2016 | 05 Sep 2016 |  |  | 241 | 0 | 0 | 0
A1-302 CP Fitting (Kit+2T) | 1 | No. | 03 Sep 2016 | 05 Sep 2016 | 07 Jun 2016 | 29 Dec 2016 | 2 | 205 | 0 | 115
A1-302 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 08 Jan 2016 | 11 Jan 2016 | 20 Nov 2015 | 29 Feb 2016 | 3 | 101 | 0 | 49
A1-302 Sanitaryware( Kit+2T) | 1 | No. | 03 Sep 2016 | 05 Sep 2016 | 01 Aug 2016 | 29 Dec 2016 | 2 | 150 | 0 | 115
A1-303 | 1 | No Unit | 12 Jan 2016 | 07 Sep 2016 |  |  | 239 | 0 | 0 | 0
A1-303 CP Fitting (Kit+2T) | 1 | No. | 06 Sep 2016 | 07 Sep 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 113
A1-303 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 12 Jan 2016 | 14 Jan 2016 | 20 Nov 2015 | 29 Feb 2016 | 2 | 101 | 0 | 46
A1-303 Sanitaryware( Kit+2T) | 1 | No. | 06 Sep 2016 | 07 Sep 2016 | 01 Aug 2016 | 29 Dec 2016 | 1 | 150 | 0 | 113
A1-304 | 1 | No Unit | 15 Jan 2016 | 09 Sep 2016 |  |  | 238 | 0 | 0 | 0
A1-304 CP Fitting (Kit+2T) | 1 | No. | 08 Sep 2016 | 09 Sep 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 111
A1-304 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 15 Jan 2016 | 18 Jan 2016 | 20 Nov 2015 | 29 Feb 2016 | 3 | 101 | 0 | 42
A1-304 Sanitaryware( Kit+2T) | 1 | No. | 08 Sep 2016 | 09 Sep 2016 | 10 Sep 2016 | 29 Dec 2016 | 1 | 110 | 2 | 111
A1-3RD FLOOR LEDGE WALL | 0 | No Unit | 05 Jan 2016 | 22 Jan 2016 |  |  | 17 | 0 | 0 | 0
A1-3rd Floor ledge wall CLC Block Masonry 4" (OS) | 50 | Sft. | 05 Jan 2016 | 22 Jan 2016 | 08 Jan 2016 | 29 Feb 2016 | 17 | 52 | 3 | 38
A1-3rd Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 05 Jan 2016 | 22 Jan 2016 | 29 Feb 2016 | 29 Feb 2016 | 17 | 0 | 55 | 38
A1-3rd Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 05 Jan 2016 | 22 Jan 2016 | 29 Feb 2016 | 29 Feb 2016 | 17 | 0 | 55 | 38
A1-3RD FLOOR (LAB) | 0 | No Unit | 05 Jan 2016 | 09 Sep 2016 |  |  | 248 | 0 | 0 | 0
A1-3rd Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 05 Jan 2016 | 18 Jan 2016 | 23 Dec 2015 | 02 Mar 2016 | 13 | 70 | 0 | 44
A1-3rd Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 01 Sep 2016 | 09 Sep 2016 | 23 Aug 2016 | 13 Jan 2017 | 8 | 143 | 0 | 126
A1- 4TH FLOOR PLUMBING | 0 | No Unit | 27 Jan 2016 | 20 Sep 2016 |  |  | 237 | 0 | 0 | 0
A1-401 | 1 | No Unit | 27 Jan 2016 | 13 Sep 2016 |  |  | 230 | 0 | 0 | 0
A1-401 CP Fitting (Kit+2T) | 1 | No. | 12 Sep 2016 | 13 Sep 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 107
A1-401 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 27 Jan 2016 | 29 Jan 2016 | 07 Jan 2016 | 29 Feb 2016 | 2 | 53 | 0 | 31
A1-401 Sanitaryware( Kit+2T) | 1 | No. | 12 Sep 2016 | 13 Sep 2016 | 19 Sep 2016 | 29 Dec 2016 | 1 | 101 | 7 | 107
A1-402 | 1 | No Unit | 30 Jan 2016 | 15 Sep 2016 |  |  | 229 | 0 | 0 | 0
A1-402 CP Fitting (Kit+2T) | 1 | No. | 14 Sep 2016 | 15 Sep 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 105
A1-402 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 30 Jan 2016 | 02 Feb 2016 | 07 Jan 2016 | 29 Feb 2016 | 3 | 53 | 0 | 27
A1-402 Sanitaryware( Kit+2T) | 1 | No. | 14 Sep 2016 | 15 Sep 2016 | 01 Aug 2016 | 29 Dec 2016 | 1 | 150 | 0 | 105
A1-403 | 1 | No Unit | 03 Feb 2016 | 17 Sep 2016 |  |  | 227 | 0 | 0 | 0
A1-403 CP Fitting (Kit+2T) | 1 | No. | 16 Sep 2016 | 17 Sep 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 103
A1-403 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 03 Feb 2016 | 05 Feb 2016 | 07 Jan 2016 | 29 Feb 2016 | 2 | 53 | 0 | 24
A1-403 Sanitaryware( Kit+2T) | 1 | No. | 16 Sep 2016 | 17 Sep 2016 | 01 Aug 2016 | 29 Dec 2016 | 1 | 150 | 0 | 103
A1-404 | 27650633.39 | No Unit | 06 Feb 2016 | 20 Sep 2016 |  |  | 227 | 0 | 0 | 0
A1-404 CP Fitting (Kit+2T) | 1 | No. | 19 Sep 2016 | 20 Sep 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 100
A1-404 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 06 Feb 2016 | 09 Feb 2016 | 07 Jan 2016 | 29 Feb 2016 | 3 | 53 | 0 | 20
A1-404 Sanitaryware( Kit+2T) | 1 | No. | 19 Sep 2016 | 20 Sep 2016 | 17 Dec 2016 | 29 Dec 2016 | 1 | 12 | 89 | 100
A1-4TH FLOOR LEDGE WALL | 0 | No Unit | 27 Jan 2016 | 13 Feb 2016 |  |  | 17 | 0 | 0 | 0
A1-4th Floor ledge wall CLC Block Masonry 4" (OS) | 50 | Sft. | 27 Jan 2016 | 13 Feb 2016 | 18 Jan 2016 | 29 Feb 2016 | 17 | 42 | 0 | 16
A1-4th Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 27 Jan 2016 | 13 Feb 2016 | 29 Feb 2016 | 29 Feb 2016 | 17 | 0 | 33 | 16
A1-4th Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 27 Jan 2016 | 13 Feb 2016 | 29 Feb 2016 | 29 Feb 2016 | 17 | 0 | 33 | 16
A1-4TH FLOOR (LAB) | 0 | No Unit | 27 Jan 2016 | 20 Sep 2016 |  |  | 237 | 0 | 0 | 0
A1-4th Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 27 Jan 2016 | 09 Feb 2016 | 19 Jan 2016 | 02 Mar 2016 | 13 | 43 | 0 | 22
A1-4th Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 12 Sep 2016 | 20 Sep 2016 | 23 Aug 2016 | 13 Jan 2017 | 8 | 143 | 0 | 115
A1- 5TH FLOOR PLUMBING | 0 | No Unit | 18 Feb 2016 | 28 Sep 2016 |  |  | 223 | 0 | 0 | 0
A1-501 | 1 | No Unit | 18 Feb 2016 | 21 Sep 2016 |  |  | 216 | 0 | 0 | 0
A1-501 CP Fitting (Kit+2T) | 1 | No. | 20 Sep 2016 | 21 Sep 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 99
A1-501 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 18 Feb 2016 | 20 Feb 2016 | 04 Jan 2016 | 29 Feb 2016 | 2 | 56 | 0 | 9
A1-501 Sanitaryware( Kit+2T) | 1 | No. | 20 Sep 2016 | 21 Sep 2016 | 19 Sep 2016 | 29 Dec 2016 | 1 | 101 | 0 | 99
A1-502 | 1 | No Unit | 22 Feb 2016 | 23 Sep 2016 |  |  | 214 | 0 | 0 | 0
A1-502 CP Fitting (Kit+2T) | 1 | No. | 22 Sep 2016 | 23 Sep 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 97
A1-502 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 22 Feb 2016 | 24 Feb 2016 | 11 Jan 2016 | 29 Feb 2016 | 2 | 49 | 0 | 5
A1-502 Sanitaryware( Kit+2T) | 1 | No. | 22 Sep 2016 | 23 Sep 2016 | 30 Aug 2016 | 29 Dec 2016 | 1 | 121 | 0 | 97
A1-503 | 1 | No Unit | 25 Feb 2016 | 26 Sep 2016 |  |  | 214 | 0 | 0 | 0
A1-503 CP Fitting (Kit+2T) | 1 | No. | 24 Sep 2016 | 26 Sep 2016 | 07 Jun 2016 | 29 Dec 2016 | 2 | 205 | 0 | 94
A1-503 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 25 Feb 2016 | 27 Feb 2016 | 11 Jan 2016 | 29 Feb 2016 | 2 | 49 | 0 | 2
A1-503 Sanitaryware( Kit+2T) | 1 | No. | 24 Sep 2016 | 26 Sep 2016 | 30 Aug 2016 | 29 Dec 2016 | 2 | 121 | 0 | 94
A1-504 | 27650633.39 | No Unit | 29 Feb 2016 | 28 Sep 2016 |  |  | 212 | 0 | 0 | 0
A1-504 CP Fitting (Kit+2T) | 1 | No. | 27 Sep 2016 | 28 Sep 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 92
A1-504 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 29 Feb 2016 | 02 Mar 2016 | 11 Jan 2016 | 29 Feb 2016 | 2 | 49 | 0 | 0
A1-504 Sanitaryware( Kit+2T) | 1 | No. | 27 Sep 2016 | 28 Sep 2016 | 19 Sep 2016 | 29 Dec 2016 | 1 | 101 | 0 | 92
A1-5TH FLOOR LEDGE WALL | 0 | No Unit | 18 Feb 2016 | 08 Mar 2016 |  |  | 19 | 0 | 0 | 0
A1-5th Floor ledge wall CLC Block Masonry 4" (OS) | 50 | Sft. | 18 Feb 2016 | 08 Mar 2016 | 29 Feb 2016 | 29 Feb 2016 | 19 | 0 | 11 | 0
A1-5th Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 18 Feb 2016 | 08 Mar 2016 | 29 Feb 2016 | 29 Feb 2016 | 19 | 0 | 11 | 0
A1-5th Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 18 Feb 2016 | 08 Mar 2016 | 29 Feb 2016 | 29 Feb 2016 | 19 | 0 | 11 | 0
A1-5TH FLOOR (LAB) | 0 | No Unit | 18 Feb 2016 | 28 Sep 2016 |  |  | 223 | 0 | 0 | 0
A1-5th Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 18 Feb 2016 | 02 Mar 2016 | 19 Jan 2016 | 02 Mar 2016 | 13 | 43 | 0 | 0
A1-5th Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 20 Sep 2016 | 28 Sep 2016 | 23 Aug 2016 | 13 Jan 2017 | 8 | 143 | 0 | 107
A1- 6TH FLOOR PLUMBING | 0 | No Unit | 11 Mar 2016 | 10 Oct 2016 |  |  | 213 | 0 | 0 | 0
A1-601 | 1 | No Unit | 11 Mar 2016 | 03 Oct 2016 |  |  | 206 | 0 | 0 | 0
A1-601 CP Fitting (Kit+2T) | 1 | No. | 01 Oct 2016 | 03 Oct 2016 | 07 Jun 2016 | 29 Dec 2016 | 2 | 205 | 0 | 87
A1-601 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 11 Mar 2016 | 14 Mar 2016 | 21 Jan 2016 | 18 Mar 2016 | 3 | 57 | 0 | 4
A1-601 Sanitaryware( Kit+2T) | 1 | No. | 01 Oct 2016 | 03 Oct 2016 | 19 Sep 2016 | 29 Dec 2016 | 2 | 101 | 0 | 87
A1-602 | 1 | No Unit | 15 Mar 2016 | 05 Oct 2016 |  |  | 204 | 0 | 0 | 0
A1-602 CP Fitting (Kit+2T) | 1 | No. | 04 Oct 2016 | 05 Oct 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 85
A1-602 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 15 Mar 2016 | 17 Mar 2016 | 21 Jan 2016 | 18 Mar 2016 | 2 | 57 | 0 | 1
A1-602 Sanitaryware( Kit+2T) | 1 | No. | 04 Oct 2016 | 05 Oct 2016 | 30 Aug 2016 | 29 Dec 2016 | 1 | 121 | 0 | 85
A1-603 | 1 | No Unit | 18 Mar 2016 | 07 Oct 2016 |  |  | 203 | 0 | 0 | 0
A1-603 CP Fitting (Kit+2T) | 1 | No. | 06 Oct 2016 | 07 Oct 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 83
A1-603 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 18 Mar 2016 | 21 Mar 2016 | 21 Jan 2016 | 18 Mar 2016 | 3 | 57 | 0 | 0
A1-603 Sanitaryware( Kit+2T) | 1 | No. | 06 Oct 2016 | 07 Oct 2016 | 30 Aug 2016 | 29 Dec 2016 | 1 | 121 | 0 | 83
A1-604 | 27650633.39 | No Unit | 22 Mar 2016 | 10 Oct 2016 |  |  | 202 | 0 | 0 | 0
A1-604 CP Fitting (Kit+2T) | 1 | No. | 08 Oct 2016 | 10 Oct 2016 | 07 Jun 2016 | 29 Dec 2016 | 2 | 205 | 0 | 80
A1-604 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 22 Mar 2016 | 24 Mar 2016 | 21 Jan 2016 | 18 Mar 2016 | 2 | 57 | 0 | 0
A1-604 Sanitaryware( Kit+2T) | 1 | No. | 08 Oct 2016 | 10 Oct 2016 | 19 Sep 2016 | 29 Dec 2016 | 2 | 101 | 0 | 80
A1-6TH FLOOR LEDGE WALL | 0 | No Unit | 11 Mar 2016 | 29 Mar 2016 |  |  | 18 | 0 | 0 | 0
A1-6th Floor ledge wall CLC Block Masonry 4" (OS) | 50 | Sft. | 11 Mar 2016 | 29 Mar 2016 | 29 Feb 2016 | 18 Mar 2016 | 18 | 18 | 0 | 0
A1-6th Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 11 Mar 2016 | 29 Mar 2016 | 29 Feb 2016 | 18 Mar 2016 | 18 | 18 | 0 | 0
A1-6th Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 11 Mar 2016 | 29 Mar 2016 | 29 Feb 2016 | 18 Mar 2016 | 18 | 18 | 0 | 0
A1-6TH FLOOR (LAB) | 0 | No Unit | 11 Mar 2016 | 01 Oct 2016 |  |  | 204 | 0 | 0 | 0
A1-6th Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 11 Mar 2016 | 24 Mar 2016 | 16 Feb 2016 | 18 Mar 2016 | 13 | 31 | 0 | 0
A1-6th Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 01 Oct 2016 | 01 Oct 2016 | 22 Sep 2016 | 13 Jan 2017 | 0 | 113 | 0 | 104
A1- 7TH FLOOR PLUMBING | 0 | No Unit | 08 Mar 2016 | 19 Oct 2016 |  |  | 225 | 0 | 0 | 0
A1-701 | 1 | No Unit | 08 Mar 2016 | 12 Oct 2016 |  |  | 218 | 0 | 0 | 0
A1-701 CP Fitting (Kit+2T) | 1 | No. | 11 Oct 2016 | 12 Oct 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 78
A1-701 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 08 Mar 2016 | 10 Mar 2016 | 11 Feb 2016 | 27 Jun 2016 | 2 | 137 | 0 | 109
A1-701 Sanitaryware( Kit+2T) | 1 | No. | 11 Oct 2016 | 12 Oct 2016 | 23 Sep 2016 | 29 Dec 2016 | 1 | 97 | 0 | 78
A1-702 | 1 | No Unit | 11 Mar 2016 | 14 Oct 2016 |  |  | 217 | 0 | 0 | 0
A1-702 CP Fitting (Kit+2T) | 1 | No. | 13 Oct 2016 | 14 Oct 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 76
A1-702 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 11 Mar 2016 | 14 Mar 2016 | 11 Feb 2016 | 27 Jun 2016 | 3 | 137 | 0 | 105
A1-702 Sanitaryware( Kit+2T) | 1 | No. | 13 Oct 2016 | 14 Oct 2016 | 06 Sep 2016 | 29 Dec 2016 | 1 | 114 | 0 | 76
A1-703 | 1 | No Unit | 15 Mar 2016 | 17 Oct 2016 |  |  | 216 | 0 | 0 | 0
A1-703 CP Fitting (Kit+2T) | 1 | No. | 15 Oct 2016 | 17 Oct 2016 | 07 Jun 2016 | 29 Dec 2016 | 2 | 205 | 0 | 73
A1-703 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 15 Mar 2016 | 17 Mar 2016 | 11 Feb 2016 | 27 Jun 2016 | 2 | 137 | 0 | 102
A1-703 Sanitaryware( Kit+2T) | 1 | No. | 15 Oct 2016 | 17 Oct 2016 | 06 Sep 2016 | 29 Dec 2016 | 2 | 114 | 0 | 73
A1-704 | 27650633.39 | No Unit | 18 Mar 2016 | 19 Oct 2016 |  |  | 215 | 0 | 0 | 0
A1-704 CP Fitting (Kit+2T) | 1 | No. | 18 Oct 2016 | 19 Oct 2016 | 07 Jun 2016 | 29 Dec 2016 | 1 | 205 | 0 | 71
A1-704 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 18 Mar 2016 | 21 Mar 2016 | 11 Feb 2016 | 27 Jun 2016 | 3 | 137 | 0 | 98
A1-704 Sanitaryware( Kit+2T) | 1 | No. | 18 Oct 2016 | 19 Oct 2016 | 23 Sep 2016 | 29 Dec 2016 | 1 | 97 | 0 | 71
A1-7TH FLOOR LEDGE WALL | 0 | No Unit | 08 Mar 2016 | 25 Mar 2016 |  |  | 17 | 0 | 0 | 0
A1-7th Floor ledge wall CLC Block Masonry 4" (OS) | 50 | Sft. | 08 Mar 2016 | 25 Mar 2016 | 03 Mar 2016 | 18 Mar 2016 | 17 | 15 | 0 | 0
A1-7th Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 08 Mar 2016 | 25 Mar 2016 | 18 Mar 2016 | 18 Mar 2016 | 17 | 0 | 10 | 0
A1-7th Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 08 Mar 2016 | 25 Mar 2016 | 18 Mar 2016 | 18 Mar 2016 | 17 | 0 | 10 | 0
A1-7TH FLOOR (LAB) | 39.05 | No Unit | 08 Mar 2016 | 11 Oct 2016 |  |  | 217 | 0 | 0 | 0
A1-7th Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 08 Mar 2016 | 21 Mar 2016 | 01 Mar 2016 | 18 Mar 2016 | 13 | 17 | 0 | 0
A1-7th Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 11 Oct 2016 | 11 Oct 2016 | 22 Sep 2016 | 13 Jan 2017 | 0 | 113 | 0 | 94
A1- 8TH FLOOR PLUMBING | 1 | No Unit | 22 Mar 2016 | 27 Oct 2016 |  |  | 219 | 0 | 0 | 0
A1-801 | 1 | No Unit | 22 Mar 2016 | 20 Oct 2016 |  |  | 212 | 0 | 0 | 0
A1-801 CP Fitting (Kit+2T) | 1 | No. | 19 Oct 2016 | 20 Oct 2016 | 18 Jun 2016 | 29 Dec 2016 | 1 | 194 | 0 | 70
A1-801 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 22 Mar 2016 | 24 Mar 2016 | 01 Mar 2016 | 27 Jun 2016 | 2 | 118 | 0 | 95
A1-801 Sanitaryware( Kit+2T) | 1 | No. | 19 Oct 2016 | 20 Oct 2016 | 23 Sep 2016 | 29 Dec 2016 | 1 | 97 | 0 | 70
A1-802 | 1 | No Unit | 25 Mar 2016 | 22 Oct 2016 |  |  | 211 | 0 | 0 | 0
A1-802 CP Fitting (Kit+2T) | 1 | No. | 21 Oct 2016 | 22 Oct 2016 | 18 Jun 2016 | 29 Dec 2016 | 1 | 194 | 0 | 68
A1-802 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 25 Mar 2016 | 28 Mar 2016 | 01 Mar 2016 | 27 Jun 2016 | 3 | 118 | 0 | 91
A1-802 Sanitaryware( Kit+2T) | 1 | No. | 21 Oct 2016 | 22 Oct 2016 | 06 Sep 2016 | 29 Dec 2016 | 1 | 114 | 0 | 68
A1-803 | 27650633.39 | No Unit | 29 Mar 2016 | 25 Oct 2016 |  |  | 210 | 0 | 0 | 0
A1-803 CP Fitting (Kit+2T) | 1 | No. | 24 Oct 2016 | 25 Oct 2016 | 18 Jun 2016 | 29 Dec 2016 | 1 | 194 | 0 | 65
A1-803 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 29 Mar 2016 | 31 Mar 2016 | 01 Mar 2016 | 27 Jun 2016 | 2 | 118 | 0 | 88
A1-803 Sanitaryware( Kit+2T) | 1 | No. | 24 Oct 2016 | 25 Oct 2016 | 06 Sep 2016 | 29 Dec 2016 | 1 | 114 | 0 | 65
A1-8TH FLOOR LEDGE WALL | 0 | No Unit | 22 Mar 2016 | 04 Apr 2016 |  |  | 13 | 0 | 0 | 0
A1-8th Floor ledge wall CLC Block Masonry 4" (OS) | 37.5 | Sft. | 22 Mar 2016 | 04 Apr 2016 | 16 Mar 2016 | 03 May 2016 | 13 | 48 | 0 | 29
A1-8th Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 22 Mar 2016 | 04 Apr 2016 | 01 Mar 2016 | 03 May 2016 | 13 | 63 | 0 | 29
A1-8th Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 22 Mar 2016 | 04 Apr 2016 | 16 Mar 2016 | 03 May 2016 | 13 | 48 | 0 | 29
A1-8TH FLOOR (LAB) | 0 | No Unit | 22 Mar 2016 | 27 Oct 2016 |  |  | 219 | 0 | 0 | 0
A1-8th Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 22 Mar 2016 | 04 Apr 2016 | 15 Mar 2016 | 23 Apr 2016 | 13 | 39 | 0 | 19
A1-8th Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 19 Oct 2016 | 27 Oct 2016 | 22 Sep 2016 | 13 Jan 2017 | 8 | 113 | 0 | 78
A1- 9TH FLOOR PLUMBING | 0 | No Unit | 25 Mar 2016 | 08 Nov 2016 |  |  | 228 | 0 | 0 | 0
A1-901 | 1 | No Unit | 25 Mar 2016 | 01 Nov 2016 |  |  | 221 | 0 | 0 | 0
A1-901 CP Fitting (Kit+2T) | 1 | No. | 31 Oct 2016 | 01 Nov 2016 | 18 Jun 2016 | 29 Dec 2016 | 1 | 194 | 0 | 58
A1-901 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 25 Mar 2016 | 28 Mar 2016 | 01 Mar 2016 | 27 Jun 2016 | 3 | 118 | 0 | 91
A1-901 Sanitaryware( Kit+2T) | 1 | No. | 31 Oct 2016 | 01 Nov 2016 | 23 Sep 2016 | 29 Dec 2016 | 1 | 97 | 0 | 58
A1-902 | 1 | No Unit | 29 Mar 2016 | 03 Nov 2016 |  |  | 219 | 0 | 0 | 0
A1-902 CP Fitting (Kit+2T) | 1 | No. | 02 Nov 2016 | 03 Nov 2016 | 18 Jun 2016 | 29 Dec 2016 | 1 | 194 | 0 | 56
A1-902 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 29 Mar 2016 | 31 Mar 2016 | 08 Mar 2016 | 27 Jun 2016 | 2 | 111 | 0 | 88
A1-902 Sanitaryware( Kit+2T) | 1 | No. | 02 Nov 2016 | 03 Nov 2016 | 29 Sep 2016 | 29 Dec 2016 | 1 | 91 | 0 | 56
A1-903 | 1 | No Unit | 01 Apr 2016 | 05 Nov 2016 |  |  | 218 | 0 | 0 | 0
A1-903 CP Fitting (Kit+2T) | 1 | No. | 04 Nov 2016 | 05 Nov 2016 | 18 Jun 2016 | 29 Dec 2016 | 1 | 194 | 0 | 54
A1-903 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 01 Apr 2016 | 04 Apr 2016 | 08 Mar 2016 | 27 Jun 2016 | 3 | 111 | 0 | 84
A1-903 Sanitaryware( Kit+2T) | 1 | No. | 04 Nov 2016 | 05 Nov 2016 | 29 Sep 2016 | 29 Dec 2016 | 1 | 91 | 0 | 54
A1-904 | 1 | No Unit | 05 Apr 2016 | 08 Nov 2016 |  |  | 217 | 0 | 0 | 0
A1-904 CP Fitting (Kit+2T) | 1 | No. | 07 Nov 2016 | 08 Nov 2016 | 18 Jun 2016 | 29 Dec 2016 | 1 | 194 | 0 | 51
A1-904 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 05 Apr 2016 | 07 Apr 2016 | 08 Mar 2016 | 27 Jun 2016 | 2 | 111 | 0 | 81
A1-904 Sanitaryware( Kit+2T) | 1 | No. | 07 Nov 2016 | 08 Nov 2016 | 29 Sep 2016 | 29 Dec 2016 | 1 | 91 | 0 | 51
A1-9TH FLOOR LEDGE WALL | 0 | No Unit | 25 Mar 2016 | 12 Apr 2016 |  |  | 18 | 0 | 0 | 0
A1-9th Floor ledge wall CLC Block Masonry 4" (OS) | 50 | Sft. | 25 Mar 2016 | 12 Apr 2016 | 04 Apr 2016 | 22 Apr 2016 | 18 | 18 | 10 | 10
A1-9th Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 25 Mar 2016 | 12 Apr 2016 | 04 Apr 2016 | 22 Apr 2016 | 18 | 18 | 10 | 10
A1-9th Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 25 Mar 2016 | 12 Apr 2016 | 04 Apr 2016 | 22 Apr 2016 | 18 | 18 | 10 | 10
A1-9TH FLOOR (LAB) | 0 | No Unit | 25 Mar 2016 | 08 Nov 2016 |  |  | 228 | 0 | 0 | 0
A1-9th Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 25 Mar 2016 | 07 Apr 2016 | 15 Mar 2016 | 23 Apr 2016 | 13 | 39 | 0 | 16
A1-9th Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 31 Oct 2016 | 08 Nov 2016 | 13 Oct 2016 | 13 Jan 2017 | 8 | 92 | 0 | 66
A1- 10TH FLOOR PLUMBING | 0 | No Unit | 01 Apr 2016 | 19 Nov 2016 |  |  | 232 | 0 | 0 | 0
A1-1001 | 1 | No Unit | 01 Apr 2016 | 12 Nov 2016 |  |  | 225 | 0 | 0 | 0
A1-1001 CP Fitting (Kit+2T) | 1 | No. | 11 Nov 2016 | 12 Nov 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 47
A1-1001 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 01 Apr 2016 | 04 Apr 2016 | 08 Mar 2016 | 27 Jun 2016 | 3 | 111 | 0 | 84
A1-1001 Sanitaryware( Kit+2T) | 1 | No. | 11 Nov 2016 | 12 Nov 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 47
A1-1002 | 1 | No Unit | 05 Apr 2016 | 15 Nov 2016 |  |  | 224 | 0 | 0 | 0
A1-1002 CP Fitting (Kit+2T) | 1 | No. | 14 Nov 2016 | 15 Nov 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 44
A1-1002 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 05 Apr 2016 | 07 Apr 2016 | 08 Mar 2016 | 27 Jun 2016 | 2 | 111 | 0 | 81
A1-1002 Sanitaryware( Kit+2T) | 1 | No. | 14 Nov 2016 | 15 Nov 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 44
A1-1003 | 1 | No Unit | 08 Apr 2016 | 17 Nov 2016 |  |  | 223 | 0 | 0 | 0
A1-1003 CP Fitting (Kit+2T) | 1 | No. | 16 Nov 2016 | 17 Nov 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 42
A1-1003 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 08 Apr 2016 | 11 Apr 2016 | 08 Mar 2016 | 27 Jun 2016 | 3 | 111 | 0 | 77
A1-1003 Sanitaryware( Kit+2T) | 1 | No. | 16 Nov 2016 | 17 Nov 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 42
A1-1004 | 27650633.39 | No Unit | 12 Apr 2016 | 19 Nov 2016 |  |  | 221 | 0 | 0 | 0
A1-1004 CP Fitting (Kit+2T) | 1 | No. | 18 Nov 2016 | 19 Nov 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 40
A1-1004 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 12 Apr 2016 | 14 Apr 2016 | 08 Mar 2016 | 27 Jun 2016 | 2 | 111 | 0 | 74
A1-1004 Sanitaryware( Kit+2T) | 1 | No. | 18 Nov 2016 | 19 Nov 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 40
A1-10TH FLOOR LEDGE WALL | 0 | No Unit | 01 Apr 2016 | 19 Apr 2016 |  |  | 18 | 0 | 0 | 0
A1-10th Floor ledge wall CLC Block Masonry 4" (OS) | 50 | Sft. | 01 Apr 2016 | 19 Apr 2016 | 22 Apr 2016 | 03 May 2016 | 18 | 11 | 21 | 14
A1-10th Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 01 Apr 2016 | 19 Apr 2016 | 22 Apr 2016 | 03 May 2016 | 18 | 11 | 21 | 14
A1-10th Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 01 Apr 2016 | 19 Apr 2016 | 22 Apr 2016 | 03 May 2016 | 18 | 11 | 21 | 14
A1-10TH FLOOR (LAB) | 0 | No Unit | 01 Apr 2016 | 19 Nov 2016 |  |  | 232 | 0 | 0 | 0
A1-10th Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 01 Apr 2016 | 14 Apr 2016 | 30 Mar 2016 | 23 Apr 2016 | 13 | 24 | 0 | 9
A1-10th Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 11 Nov 2016 | 19 Nov 2016 | 11 Nov 2016 | 13 Jan 2017 | 8 | 63 | 0 | 55
A1- 11TH FLOOR PLUMBING | 0 | No Unit | 01 Apr 2016 | 06 Dec 2016 |  |  | 249 | 0 | 0 | 0
A1-1101 | 1 | No Unit | 01 Apr 2016 | 29 Nov 2016 |  |  | 242 | 0 | 0 | 0
A1-1101 CP Fitting (Kit+2T) | 1 | No. | 28 Nov 2016 | 29 Nov 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 30
A1-1101 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 01 Apr 2016 | 04 Apr 2016 | 30 Mar 2016 | 29 Dec 2016 | 3 | 274 | 0 | 269
A1-1101 Sanitaryware( Kit+2T) | 1 | No. | 28 Nov 2016 | 29 Nov 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 30
A1-1102 | 1 | No Unit | 05 Apr 2016 | 01 Dec 2016 |  |  | 240 | 0 | 0 | 0
A1-1102 CP Fitting (Kit+2T) | 1 | No. | 30 Nov 2016 | 01 Dec 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 28
A1-1102 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 05 Apr 2016 | 07 Apr 2016 | 15 Apr 2016 | 29 Dec 2016 | 2 | 258 | 10 | 266
A1-1102 Sanitaryware( Kit+2T) | 1 | No. | 30 Nov 2016 | 01 Dec 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 28
A1-1103 | 1 | No Unit | 08 Apr 2016 | 03 Dec 2016 |  |  | 239 | 0 | 0 | 0
A1-1103 CP Fitting (Kit+2T) | 1 | No. | 02 Dec 2016 | 03 Dec 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 26
A1-1103 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 08 Apr 2016 | 11 Apr 2016 | 15 Apr 2016 | 29 Dec 2016 | 3 | 258 | 7 | 262
A1-1103 Sanitaryware( Kit+2T) | 1 | No. | 02 Dec 2016 | 03 Dec 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 26
A1-1104 | 27650633.39 | No Unit | 12 Apr 2016 | 06 Dec 2016 |  |  | 238 | 0 | 0 | 0
A1-1104 CP Fitting (Kit+2T) | 1 | No. | 05 Dec 2016 | 06 Dec 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 23
A1-1104 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 12 Apr 2016 | 14 Apr 2016 | 09 Mar 2016 | 29 Dec 2016 | 2 | 295 | 0 | 259
A1-1104 Sanitaryware( Kit+2T) | 1 | No. | 05 Dec 2016 | 06 Dec 2016 | 24 Oct 2016 | 29 Dec 2016 | 1 | 66 | 0 | 23
A1-11TH FLOOR LEDGE WALL | 0 | No Unit | 01 Apr 2016 | 19 Apr 2016 |  |  | 18 | 0 | 0 | 0
A1-11th Floor ledge wall CLC Block Masonry 4" (OS) | 50 | Sft. | 01 Apr 2016 | 19 Apr 2016 | 03 May 2016 | 27 Jun 2016 | 18 | 55 | 32 | 69
A1-11th Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 01 Apr 2016 | 19 Apr 2016 | 03 May 2016 | 27 Jun 2016 | 18 | 55 | 32 | 69
A1-11th Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 01 Apr 2016 | 19 Apr 2016 | 03 May 2016 | 27 Jun 2016 | 18 | 55 | 32 | 69
A1-11TH FLOOR (LAB) | 0 | No Unit | 01 Apr 2016 | 28 Nov 2016 |  |  | 241 | 0 | 0 | 0
A1-11th Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 01 Apr 2016 | 14 Apr 2016 | 10 May 2016 | 27 Jun 2016 | 13 | 48 | 39 | 74
A1-11th Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 28 Nov 2016 | 28 Nov 2016 | 11 Nov 2016 | 13 Jan 2017 | 0 | 63 | 0 | 46
A1- 12TH FLOOR PLUMBING | 0 | No Unit | 11 Jun 2016 | 10 Dec 2016 |  |  | 182 | 0 | 0 | 0
A1-1201 | 1 | No Unit | 11 Jun 2016 | 03 Dec 2016 |  |  | 175 | 0 | 0 | 0
A1-1201 CP Fitting (Kit+2T) | 1 | No. | 02 Dec 2016 | 03 Dec 2016 | 25 Oct 2016 | 30 Jan 2017 | 1 | 97 | 0 | 58
A1-1201 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 11 Jun 2016 | 14 Jun 2016 | 26 Apr 2016 | 29 Dec 2016 | 3 | 247 | 0 | 198
A1-1201 Sanitaryware( Kit+2T) | 1 | No. | 02 Dec 2016 | 03 Dec 2016 | 25 Oct 2016 | 30 Jan 2017 | 1 | 97 | 0 | 58
A1-1202 | 1 | No Unit | 15 Jun 2016 | 06 Dec 2016 |  |  | 174 | 0 | 0 | 0
A1-1202 CP Fitting (Kit+2T) | 1 | No. | 05 Dec 2016 | 06 Dec 2016 | 25 Oct 2016 | 30 Jan 2017 | 1 | 97 | 0 | 55
A1-1202 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 15 Jun 2016 | 17 Jun 2016 | 26 Apr 2016 | 29 Dec 2016 | 2 | 247 | 0 | 195
A1-1202 Sanitaryware( Kit+2T) | 1 | No. | 05 Dec 2016 | 06 Dec 2016 | 25 Oct 2016 | 30 Jan 2017 | 1 | 97 | 0 | 55
A1-1203 | 1 | No Unit | 18 Jun 2016 | 08 Dec 2016 |  |  | 173 | 0 | 0 | 0
A1-1203 CP Fitting (Kit+2T) | 1 | No. | 07 Dec 2016 | 08 Dec 2016 | 25 Oct 2016 | 30 Jan 2017 | 1 | 97 | 0 | 53
A1-1203 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 18 Jun 2016 | 21 Jun 2016 | 23 Apr 2016 | 29 Dec 2016 | 3 | 250 | 0 | 191
A1-1203 Sanitaryware( Kit+2T) | 1 | No. | 07 Dec 2016 | 08 Dec 2016 | 25 Oct 2016 | 30 Jan 2017 | 1 | 97 | 0 | 53
A1-1204 | 27650633.39 | No Unit | 22 Jun 2016 | 10 Dec 2016 |  |  | 171 | 0 | 0 | 0
A1-1204 CP Fitting (Kit+2T) | 1 | No. | 09 Dec 2016 | 10 Dec 2016 | 25 Oct 2016 | 30 Jan 2017 | 1 | 97 | 0 | 51
A1-1204 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 22 Jun 2016 | 24 Jun 2016 | 16 Mar 2016 | 29 Dec 2016 | 2 | 288 | 0 | 188
A1-1204 Sanitaryware( Kit+2T) | 1 | No. | 09 Dec 2016 | 10 Dec 2016 | 25 Oct 2016 | 30 Jan 2017 | 1 | 97 | 0 | 51
A1-12TH FLOOR LEDGE WALL | 0 | No Unit | 11 Jun 2016 | 29 Jun 2016 |  |  | 18 | 0 | 0 | 0
A1-12th Floor ledge wall CLC Block Masonry 4" (OS) | 50 | Sft. | 11 Jun 2016 | 29 Jun 2016 | 07 Jul 2016 | 30 Jan 2017 | 18 | 207 | 26 | 215
A1-12th Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 11 Jun 2016 | 29 Jun 2016 | 07 Jul 2016 |  | 18 | 0 | 26 | 0
A1-12th Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 11 Jun 2016 | 29 Jun 2016 | 07 Jul 2016 | 30 Jan 2017 | 18 | 207 | 26 | 215
A1-12TH FLOOR (LAB) | 0 | No Unit | 11 Jun 2016 | 10 Dec 2016 |  |  | 182 | 0 | 0 | 0
A1-12th Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 11 Jun 2016 | 24 Jun 2016 | 26 Jul 2016 | 27 Jul 2016 | 13 | 1 | 45 | 33
A1-12th Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 02 Dec 2016 | 10 Dec 2016 | 06 Dec 2016 | 13 Jan 2017 | 8 | 38 | 4 | 34
A1- 13TH FLOOR PLUMBING | 0 | No Unit | 07 Jul 2016 | 19 Dec 2016 |  |  | 165 | 0 | 0 | 0
A1-1301 | 1 | No Unit | 07 Jul 2016 | 12 Dec 2016 |  |  | 158 | 0 | 0 | 0
A1-1301 CP Fitting (Kit+2T) | 1 | No. | 10 Dec 2016 | 12 Dec 2016 | 30 Nov 2016 | 30 Jan 2017 | 2 | 61 | 0 | 49
A1-1301 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 07 Jul 2016 | 09 Jul 2016 | 19 Sep 2016 | 29 Dec 2016 | 2 | 101 | 74 | 173
A1-1301 Sanitaryware( Kit+2T) | 1 | No. | 10 Dec 2016 | 12 Dec 2016 | 30 Nov 2016 | 30 Jan 2017 | 2 | 61 | 0 | 49
A1-1302 | 1 | No Unit | 11 Jul 2016 | 14 Dec 2016 |  |  | 156 | 0 | 0 | 0
A1-1302 CP Fitting (Kit+2T) | 1 | No. | 13 Dec 2016 | 14 Dec 2016 | 30 Nov 2016 | 30 Jan 2017 | 1 | 61 | 0 | 47
A1-1302 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 11 Jul 2016 | 13 Jul 2016 | 19 Sep 2016 | 29 Dec 2016 | 2 | 101 | 70 | 169
A1-1302 Sanitaryware( Kit+2T) | 1 | No. | 13 Dec 2016 | 14 Dec 2016 | 30 Nov 2016 | 30 Jan 2017 | 1 | 61 | 0 | 47
A1-1303 | 27650633.39 | No Unit | 14 Jul 2016 | 14 Dec 2016 |  |  | 153 | 0 | 0 | 0
A1-1303 CP Fitting (Kit+2T) | 1 | No. | 13 Dec 2016 | 14 Dec 2016 | 30 Nov 2016 | 30 Jan 2017 | 1 | 61 | 0 | 47
A1-1303 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 14 Jul 2016 | 16 Jul 2016 | 19 Sep 2016 | 29 Dec 2016 | 2 | 101 | 67 | 166
A1-1303 Sanitaryware( Kit+2T) | 1 | No. | 13 Dec 2016 | 14 Dec 2016 | 30 Nov 2016 | 30 Jan 2017 | 1 | 61 | 0 | 47
A1-13TH FLOOR LEDGE WALL | 0 | No Unit | 07 Jul 2016 | 20 Jul 2016 |  |  | 13 | 0 | 0 | 0
A1-13th Floor ledge wall CLC Block Masonry 4" (OS) | 37.5 | Sft. | 07 Jul 2016 | 20 Jul 2016 | 01 Oct 2016 | 30 Jan 2017 | 13 | 121 | 86 | 194
A1-13th Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 07 Jul 2016 | 20 Jul 2016 | 29 Dec 2016 |  | 13 | 0 | 175 | 0
A1-13th Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 07 Jul 2016 | 20 Jul 2016 | 29 Dec 2016 | 30 Jan 2017 | 13 | 32 | 175 | 194
A1-13TH FLOOR (LAB) | 0 | No Unit | 07 Jul 2016 | 19 Dec 2016 |  |  | 165 | 0 | 0 | 0
A1-13th Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 07 Jul 2016 | 20 Jul 2016 | 14 Nov 2016 | 13 Jan 2017 | 13 | 60 | 130 | 177
A1-13th Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 10 Dec 2016 | 19 Dec 2016 | 06 Dec 2016 | 13 Jan 2017 | 9 | 38 | 0 | 25
A1- 14TH FLOOR PLUMBING | 0 | No Unit | 23 Jul 2016 | 26 Dec 2016 |  |  | 156 | 0 | 0 | 0
A1-1401 | 1 | No Unit | 23 Jul 2016 | 24 Dec 2016 |  |  | 154 | 0 | 0 | 0
A1-1401 CP Fitting (Kit+2T) | 1 | No. | 23 Dec 2016 | 24 Dec 2016 | 29 Dec 2016 | 30 Jan 2017 | 1 | 32 | 6 | 37
A1-1401 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 23 Jul 2016 | 26 Jul 2016 | 29 Dec 2016 | 30 Jan 2017 | 3 | 32 | 159 | 188
A1-1401 Sanitaryware( Kit+2T) | 1 | No. | 23 Dec 2016 | 24 Dec 2016 | 29 Dec 2016 | 30 Jan 2017 | 1 | 32 | 6 | 37
A1-1402 | 1 | No Unit | 27 Jul 2016 | 24 Dec 2016 |  |  | 150 | 0 | 0 | 0
A1-1402 CP Fitting (Kit+2T) | 1 | No. | 23 Dec 2016 | 24 Dec 2016 | 29 Dec 2016 | 30 Jan 2017 | 1 | 32 | 6 | 37
A1-1402 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 27 Jul 2016 | 29 Jul 2016 | 30 Jul 2016 | 30 Jan 2017 | 2 | 184 | 3 | 185
A1-1402 Sanitaryware( Kit+2T) | 1 | No. | 23 Dec 2016 | 24 Dec 2016 | 29 Dec 2016 | 30 Jan 2017 | 1 | 32 | 6 | 37
A1-1403 | 1 | No Unit | 30 Jul 2016 | 24 Dec 2016 |  |  | 147 | 0 | 0 | 0
A1-1403 CP Fitting (Kit+2T) | 1 | No. | 23 Dec 2016 | 24 Dec 2016 | 18 Jun 2016 | 30 Jan 2017 | 1 | 226 | 0 | 37
A1-1403 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 30 Jul 2016 | 02 Aug 2016 | 13 Jun 2016 | 30 Jan 2017 | 3 | 231 | 0 | 181
A1-1403 Sanitaryware( Kit+2T) | 1 | No. | 23 Dec 2016 | 24 Dec 2016 | 23 Sep 2016 | 30 Jan 2017 | 1 | 129 | 0 | 37
A1-1404 | 27650633.39 | No Unit | 03 Aug 2016 | 24 Dec 2016 |  |  | 143 | 0 | 0 | 0
A1-1404 CP Fitting (Kit+2T) | 1 | No. | 23 Dec 2016 | 24 Dec 2016 | 30 Nov 2016 | 30 Jan 2017 | 1 | 61 | 0 | 37
A1-1404 PVC/PPRC/GI/CI Concealed (Kit+2T) | 1 | NO | 03 Aug 2016 | 05 Aug 2016 | 13 Jun 2016 | 30 Jan 2017 | 2 | 231 | 0 | 178
A1-1404 Sanitaryware( Kit+2T) | 1 | No. | 23 Dec 2016 | 24 Dec 2016 | 30 Nov 2016 | 30 Jan 2017 | 1 | 61 | 0 | 37
A1-14TH FLOOR LEDGE WALL | 0 | No Unit | 23 Jul 2016 | 10 Aug 2016 |  |  | 18 | 0 | 0 | 0
A1-14th Floor ledge wall CLC Block Masonry 4" (OS) | 50 | Sft. | 23 Jul 2016 | 10 Aug 2016 | 29 Dec 2016 | 30 Jan 2017 | 18 | 32 | 159 | 173
A1-14th Floor ledge wall CLC Block Making 500 x 200 x 100 | 0 | No. | 23 Jul 2016 | 10 Aug 2016 | 29 Dec 2016 | 30 Jan 2017 | 18 | 32 | 159 | 173
A1-14th Floor ledge wall CLC Block Masonry 4" | 0 | Sft. | 23 Jul 2016 | 10 Aug 2016 | 29 Dec 2016 | 30 Jan 2017 | 18 | 32 | 159 | 173
A1-14TH FLOOR (LAB) | 0 | No Unit | 23 Jul 2016 | 26 Dec 2016 |  |  | 156 | 0 | 0 | 0
A1-14th Floor (Lab) Internnal Plumbing (Lab) | 56695 | Sft. | 23 Jul 2016 | 05 Aug 2016 | 29 Dec 2016 | 13 Jan 2017 | 13 | 15 | 159 | 161
A1-14th Floor (Lab) Int.CP sanitary ( Lab) | 56695 | Sft. | 23 Dec 2016 | 26 Dec 2016 | 29 Dec 2016 | 13 Jan 2017 | 3 | 15 | 6 | 18
A1- TOP TERRACE PLUMBING | 0 | No Unit | 29 Sep 2016 | 15 Oct 2016 |  |  | 16 | 0 | 0 | 0
A1- Top Terrace plumbing Terrace Plumbing | 1 | NO | 29 Sep 2016 | 15 Oct 2016 | 06 Dec 2016 |  | 16 | 0 | 68 | 0
A1- CEMENT FOR NAHANI TRAP GALA FINISHING | 4120 | No Unit | 21 Dec 2015 | 29 Sep 2016 |  |  | 283 | 0 | 0 | 0
A1- Cement for Nahani trap Gala finishing Cement for Nahani | 28 | NO | 21 Dec 2015 | 29 Sep 2016 | 06 Dec 2016 |  | 283 | 0 | 351 | 0
A1- EXTERNAL PLUMBING | 0 | No Unit | 03 Aug 2016 | 03 Dec 2016 |  |  | 122 | 0 | 0 | 0
A1-BLDG- EXT.PLUMBING (MAT | 0 | No Unit | 03 Aug 2016 | 16 Nov 2016 |  |  | 105 | 0 | 0 | 0
A1-BLDG- Ext.Plumbing (Mat Ext. Plumbing Misc. (Kit+2T) | 1 | No. | 03 Aug 2016 | 16 Nov 2016 | 15 Jul 2016 |  | 105 | 0 | 0 | 0
A1-BLDG- Ext.Plumbing (Mat GI Pipes & Fittings | 200 | Rft | 03 Aug 2016 | 16 Nov 2016 | 06 Aug 2016 |  | 105 | 0 | 3 | 0
A1-BLDG- Ext.Plumbing (Mat SWR UPVC Pipes & Fittings . | 10 | NO | 03 Aug 2016 | 16 Nov 2016 | 23 Jan 2016 |  | 105 | 0 | 0 | 0
A1-BLDG- Ext.Plumbing (Mat GI Pipes & Fittings | 1000 | Rft | 03 Aug 2016 | 16 Nov 2016 | 06 Aug 2016 |  | 105 | 0 | 3 | 0
A1-BLDG- Ext.Plumbing (Mat C.I.Fittings | 0 | NO | 03 Aug 2016 | 16 Nov 2016 |  |  | 105 | 0 | 0 | 0
A1-BLDG- Ext.Plumbing (Mat Plumbing | 1 | Nos | 03 Aug 2016 | 16 Nov 2016 | 25 Jul 2016 |  | 105 | 0 | 0 | 0
A1-KIT. BOOSTING LINE DUCT BETWEEN 101-4 | 1 | No Unit | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-Kit. Boosting Line duct between 101-4 Kit. Busting/Domest | 1 | NO | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-Kit. Boosting Line duct between 101-4 Kitchen Busting /Wh | 1 | NO | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-Kit. Boosting Line duct between 101-4 Kitchen Busting/PPR | 1 | NO | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-Kit. Boosting Line duct between 101-4 Kit. Busting /G.I. | 1 | NO | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-Kit. Boosting Line duct between 101-4 Kit. Busting /G.I. | 1 | NO | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-KIT. BOOSTING LINE DUCT BETWEEN 102-3 | 0 | No Unit | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-Kit. Boosting Line duct between 102-3 Kit. Busting/Domest | 1 | NO | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-Kit. Boosting Line duct between 102-3 Kitchen Busting /Wh | 1 | NO | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-Kit. Boosting Line duct between 102-3 Kitchen Busting/PPR | 1 | NO | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-Kit. Boosting Line duct between 102-3 Kit. Busting /G.I. | 1 | NO | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-Kit. Boosting Line duct between 102-3 Kit. Busting /G.I. | 1 | NO | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-PVC MATERIAL DUCT BETWEEN 101-4 | 0 | No Unit | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-PVC Material duct between 101-4 PVC Material (Kit+2T) | 1 | No. | 03 Aug 2016 | 12 Oct 2016 | 16 Aug 2016 |  | 70 | 0 | 13 | 0
A1-PVC MATERIAL DUCT BETWEEN 102-3 | 1 | No Unit | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-PVC Material duct between 102-3 PVC Material (Kit+2T) | 1 | No. | 03 Aug 2016 | 12 Oct 2016 | 08 Jul 2016 |  | 70 | 0 | 0 | 0
A1-WHITE PVC/PPRC MATERIAL DUCT BETWEEN | 0 | No Unit | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-White PVC/PPRC Material duct between White PVC/PPRC Pipes | 1 | No. | 03 Aug 2016 | 12 Oct 2016 | 26 Aug 2016 |  | 70 | 0 | 23 | 0
A1-WHITE PVC/PPRC MATERIAL DUCT BETWEEN | 0 | No Unit | 03 Aug 2016 | 12 Oct 2016 |  |  | 70 | 0 | 0 | 0
A1-White PVC/PPRC Material duct between White PVC/PPRC Pipes | 1 | No. | 03 Aug 2016 | 12 Oct 2016 | 13 Jul 2016 |  | 70 | 0 | 0 | 0
A1-BLDG- EXT. PLUMBING (LAB) | 0 | No Unit | 03 Aug 2016 | 16 Nov 2016 |  |  | 105 | 0 | 0 | 0
A1-BLDG- Ext. Plumbing (Lab) Terrace & OHWT Plumbing (Lab) | 56695 | Sft. | 29 Sep 2016 | 15 Oct 2016 | 22 Nov 2016 | 01 Feb 2017 | 16 | 71 | 54 | 109
A1-BLDG- Ext. Plumbing (Lab) Downtake Line (Lab) | 56695 | Sft. | 03 Aug 2016 | 16 Nov 2016 | 13 Jul 2016 | 01 Feb 2017 | 105 | 203 | 0 | 77
A1- External Plumbing Misc. Repairing Work | 23217 | Job | 17 Nov 2016 | 03 Dec 2016 | 30 Jan 2017 |  | 16 | 0 | 74 | 0
A1-FABRICATION (M+L) | 0 | No Unit | 29 Jun 2015 | 19 Nov 2016 |  |  | 509 | 0 | 0 | 0
A1- PARKING | 57.24 | No Unit | 17 Oct 2016 | 19 Nov 2016 |  |  | 33 | 0 | 0 | 0
A1- Parking Main Entrance Canopy+FRP (M+L) | 1 | No. | 17 Oct 2016 | 02 Nov 2016 | 30 Jan 2017 |  | 16 | 0 | 105 | 0
A1- Parking Meter Room Grating (M+L) | 36 | Rft. | 09 Nov 2016 | 19 Nov 2016 | 30 Jan 2017 |  | 10 | 0 | 82 | 0
A1- Parking Meter Room Grating chamber (M+L) | 2 | No. | 09 Nov 2016 | 19 Nov 2016 | 30 Jan 2017 |  | 10 | 0 | 82 | 0
A1- Parking Railing Main St.Case (M+L) | 56 | Sft. | 17 Oct 2016 | 20 Oct 2016 | 05 Jan 2016 | 02 Mar 2016 | 3 | 57 | 0 | 0
A1- Parking Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 17 Oct 2016 | 20 Oct 2016 | 05 Jan 2016 | 02 Mar 2016 | 3 | 57 | 0 | 0
A1- 1ST FL | 0 | No Unit | 02 Dec 2015 | 26 Dec 2015 |  |  | 24 | 0 | 0 | 0
A1- 1st Fl Railing- Living (M+L) | 175.02 | Sft. | 02 Dec 2015 | 19 Dec 2015 | 11 Dec 2015 | 29 Dec 2015 | 17 | 18 | 9 | 10
A1- 1st Fl Railing- Master Bed (M+L) | 0 | Sft. | 02 Dec 2015 | 19 Dec 2015 | 11 Dec 2015 | 29 Dec 2015 | 17 | 18 | 9 | 10
A1- 1st Fl Railing Main St.Case (M+L) | 55 | Sft. | 21 Dec 2015 | 23 Dec 2015 | 05 Jan 2016 | 02 Mar 2016 | 2 | 57 | 15 | 70
A1- 1st Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 21 Dec 2015 | 23 Dec 2015 | 05 Jan 2016 | 02 Mar 2016 | 2 | 57 | 15 | 70
A1- 1st Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 24 Dec 2015 | 26 Dec 2015 | 16 Feb 2016 | 02 Mar 2016 | 2 | 15 | 54 | 67
A1- 2ND FL | 0 | No Unit | 10 Dec 2015 | 05 Jan 2016 |  |  | 26 | 0 | 0 | 0
A1- 2nd Fl Railing- Living (M+L) | 116.99 | Sft. | 10 Dec 2015 | 28 Dec 2015 | 11 Dec 2015 | 29 Dec 2015 | 18 | 18 | 1 | 1
A1- 2nd Fl Railing- Master Bed (M+L) | 253.67 | Sft. | 10 Dec 2015 | 28 Dec 2015 | 11 Dec 2015 | 29 Dec 2015 | 18 | 18 | 1 | 1
A1- 2nd Fl Railing Main St.Case (M+L) | 55 | Sft. | 29 Dec 2015 | 01 Jan 2016 | 05 Jan 2016 | 02 Mar 2016 | 3 | 57 | 7 | 61
A1- 2nd Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 29 Dec 2015 | 01 Jan 2016 | 05 Jan 2016 | 02 Mar 2016 | 3 | 57 | 7 | 61
A1- 2nd Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 02 Jan 2016 | 05 Jan 2016 | 16 Feb 2016 | 02 Mar 2016 | 3 | 15 | 45 | 57
A1- 3RD FL | 0 | No Unit | 30 Dec 2015 | 25 Jan 2016 |  |  | 26 | 0 | 0 | 0
A1- 3rd Fl Railing- Living (M+L) | 175.02 | Sft. | 30 Dec 2015 | 18 Jan 2016 | 26 Dec 2015 | 29 Dec 2015 | 19 | 3 | 0 | 0
A1- 3rd Fl Railing- Master Bed (M+L) | 0 | Sft. | 30 Dec 2015 | 18 Jan 2016 | 16 Feb 2016 | 02 Mar 2016 | 19 | 15 | 48 | 44
A1- 3rd Fl Railing Main St.Case (M+L) | 55 | Sft. | 19 Jan 2016 | 21 Jan 2016 | 05 Jan 2016 | 02 Mar 2016 | 2 | 57 | 0 | 41
A1- 3rd Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 19 Jan 2016 | 21 Jan 2016 | 05 Jan 2016 | 02 Mar 2016 | 2 | 57 | 0 | 41
A1- 3rd Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 22 Jan 2016 | 25 Jan 2016 | 16 Feb 2016 | 02 Mar 2016 | 3 | 15 | 25 | 37
A1- 4TH FL | 0 | No Unit | 21 Jan 2016 | 16 Feb 2016 |  |  | 26 | 0 | 0 | 0
A1- 4th Fl Railing- Living (M+L) | 80 | Sft. | 21 Jan 2016 | 09 Feb 2016 | 19 Jan 2016 | 02 Mar 2016 | 19 | 43 | 0 | 22
A1- 4th Fl Railing- Master Bed (M+L) | 208 | Sft. | 21 Jan 2016 | 09 Feb 2016 | 19 Jan 2016 | 02 Mar 2016 | 19 | 43 | 0 | 22
A1- 4th Fl Railing Main St.Case (M+L) | 55 | Sft. | 10 Feb 2016 | 12 Feb 2016 | 05 Jan 2016 | 02 Mar 2016 | 2 | 57 | 0 | 19
A1- 4th Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 10 Feb 2016 | 12 Feb 2016 | 05 Jan 2016 | 02 Mar 2016 | 2 | 57 | 0 | 19
A1- 4th Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 13 Feb 2016 | 16 Feb 2016 | 16 Feb 2016 | 02 Mar 2016 | 3 | 15 | 3 | 15
A1- 5TH FL | 0 | No Unit | 13 Feb 2016 | 10 Mar 2016 |  |  | 26 | 0 | 0 | 0
A1- 5th Fl Railing- Living (M+L) | 162 | Sft. | 13 Feb 2016 | 02 Mar 2016 | 19 Jan 2016 | 02 Mar 2016 | 18 | 43 | 0 | 0
A1- 5th Fl Railing- Master Bed (M+L) | 0 | Sft. | 13 Feb 2016 | 02 Mar 2016 | 19 Jan 2016 | 02 Mar 2016 | 18 | 43 | 0 | 0
A1- 5th Fl Railing Main St.Case (M+L) | 55 | Sft. | 03 Mar 2016 | 05 Mar 2016 | 05 Jan 2016 | 02 Mar 2016 | 2 | 57 | 0 | 0
A1- 5th Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 03 Mar 2016 | 05 Mar 2016 | 05 Jan 2016 | 02 Mar 2016 | 2 | 57 | 0 | 0
A1- 5th Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 08 Mar 2016 | 10 Mar 2016 | 16 Feb 2016 | 02 Mar 2016 | 2 | 15 | 0 | 0
A1- 6TH FL | 0 | No Unit | 05 Mar 2016 | 31 Mar 2016 |  |  | 26 | 0 | 0 | 0
A1- 6th Fl Railing- Living (M+L) | 80 | Sft. | 05 Mar 2016 | 24 Mar 2016 | 19 Jan 2016 | 02 Mar 2016 | 19 | 43 | 0 | 0
A1- 6th Fl Railing- Master Bed (M+L) | 208 | Sft. | 05 Mar 2016 | 24 Mar 2016 | 19 Jan 2016 | 02 Mar 2016 | 19 | 43 | 0 | 0
A1- 6th Fl Railing Main St.Case (M+L) | 55 | Sft. | 25 Mar 2016 | 28 Mar 2016 | 05 Jan 2016 | 17 Mar 2016 | 3 | 72 | 0 | 0
A1- 6th Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 25 Mar 2016 | 28 Mar 2016 | 05 Jan 2016 | 17 Mar 2016 | 3 | 72 | 0 | 0
A1- 6th Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 29 Mar 2016 | 31 Mar 2016 | 16 Feb 2016 | 02 Mar 2016 | 2 | 15 | 0 | 0
A1- 7TH FL | 1 | No Unit | 27 Feb 2016 | 21 Mar 2016 |  |  | 23 | 0 | 0 | 0
A1- 7th Fl Railing- Living (M+L) | 162 | Sft. | 27 Feb 2016 | 17 Mar 2016 | 16 Feb 2016 | 02 Mar 2016 | 19 | 15 | 0 | 0
A1- 7th Fl Railing- Master Bed (M+L) | 0 | Sft. | 27 Feb 2016 | 17 Mar 2016 | 16 Feb 2016 | 02 Mar 2016 | 19 | 15 | 0 | 0
A1- 7th Fl Railing Main St.Case (M+L) | 55 | Sft. | 18 Mar 2016 | 21 Mar 2016 | 16 Feb 2016 | 17 Mar 2016 | 3 | 30 | 0 | 0
A1- 7th Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 18 Mar 2016 | 21 Mar 2016 | 16 Feb 2016 | 17 Mar 2016 | 3 | 30 | 0 | 0
A1- 7th Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 18 Mar 2016 | 21 Mar 2016 | 16 Feb 2016 | 02 Mar 2016 | 3 | 15 | 0 | 0
A1- 8TH FL | 1 | No Unit | 08 Apr 2016 | 03 May 2016 |  |  | 25 | 0 | 0 | 0
A1- 8th Fl Railing- Living (M+L) | 80 | Sft. | 08 Apr 2016 | 26 Apr 2016 | 26 Apr 2016 | 03 May 2016 | 18 | 7 | 18 | 7
A1- 8th Fl Railing- Master Bed (M+L) | 208 | Sft. | 08 Apr 2016 | 26 Apr 2016 | 07 Mar 2016 | 17 Mar 2016 | 18 | 10 | 0 | 0
A1- 8th Fl Railing Main St.Case (M+L) | 55 | Sft. | 27 Apr 2016 | 29 Apr 2016 | 15 Mar 2016 | 17 Mar 2016 | 2 | 2 | 0 | 0
A1- 8th Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 27 Apr 2016 | 29 Apr 2016 | 15 Mar 2016 | 17 Mar 2016 | 2 | 2 | 0 | 0
A1- 8th Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 30 Apr 2016 | 03 May 2016 | 15 Mar 2016 | 17 Mar 2016 | 3 | 2 | 0 | 0
A1- 9TH FL | 1 | No Unit | 30 Apr 2016 | 25 May 2016 |  |  | 25 | 0 | 0 | 0
A1- 9th Fl Railing- Living (M+L) | 162 | Sft. | 30 Apr 2016 | 18 May 2016 | 01 Mar 2016 | 02 Mar 2016 | 18 | 1 | 0 | 0
A1- 9th Fl Railing- Master Bed (M+L) | 0 | Sft. | 30 Apr 2016 | 18 May 2016 | 01 Mar 2016 | 02 Mar 2016 | 18 | 1 | 0 | 0
A1- 9th Fl Railing Main St.Case (M+L) | 55 | Sft. | 19 May 2016 | 21 May 2016 | 01 Mar 2016 | 17 Mar 2016 | 2 | 16 | 0 | 0
A1- 9th Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 19 May 2016 | 21 May 2016 | 01 Mar 2016 | 17 Mar 2016 | 2 | 16 | 0 | 0
A1- 9th Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 23 May 2016 | 25 May 2016 | 20 Jul 2016 | 11 Nov 2016 | 2 | 114 | 58 | 170
A1- 10TH FL | 1 | No Unit | 12 May 2016 | 06 Jun 2016 |  |  | 25 | 0 | 0 | 0
A1- 10th Fl Railing- Living (M+L) | 80 | Sft. | 12 May 2016 | 30 May 2016 | 30 Mar 2016 | 02 Apr 2016 | 18 | 3 | 0 | 0
A1- 10th Fl Railing- Master Bed (M+L) | 208 | Sft. | 12 May 2016 | 30 May 2016 | 30 Mar 2016 | 02 Apr 2016 | 18 | 3 | 0 | 0
A1- 10th Fl Railing Main St.Case (M+L) | 55 | Sft. | 31 May 2016 | 02 Jun 2016 | 15 Mar 2016 | 08 Sep 2016 | 2 | 177 | 0 | 98
A1- 10th Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 31 May 2016 | 02 Jun 2016 | 15 Mar 2016 | 02 Apr 2016 | 2 | 18 | 0 | 0
A1- 10th Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 03 Jun 2016 | 06 Jun 2016 | 15 Mar 2016 | 11 Nov 2016 | 3 | 241 | 0 | 158
A1- 11TH FL | 1 | No Unit | 27 May 2016 | 21 Jun 2016 |  |  | 25 | 0 | 0 | 0
A1- 11th Fl Railing- Living (M+L) | 162 | Sft. | 27 May 2016 | 14 Jun 2016 | 30 Mar 2016 | 02 Apr 2016 | 18 | 3 | 0 | 0
A1- 11th Fl Railing- Master Bed (M+L) | 0 | Sft. | 27 May 2016 | 14 Jun 2016 | 30 Mar 2016 | 08 Sep 2016 | 18 | 162 | 0 | 86
A1- 11th Fl Railing Main St.Case (M+L) | 55 | Sft. | 15 Jun 2016 | 17 Jun 2016 | 08 Sep 2016 | 08 Sep 2016 | 2 | 0 | 85 | 83
A1- 11th Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 15 Jun 2016 | 17 Jun 2016 | 24 Jun 2016 | 08 Sep 2016 | 2 | 76 | 9 | 83
A1- 11th Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 18 Jun 2016 | 21 Jun 2016 | 30 Aug 2016 | 11 Nov 2016 | 3 | 73 | 73 | 143
A1- 12TH FL | 1 | No Unit | 07 Jun 2016 | 01 Jul 2016 |  |  | 24 | 0 | 0 | 0
A1- 12th Fl Railing- Living (M+L) | 80 | Sft. | 07 Jun 2016 | 24 Jun 2016 | 26 Apr 2016 | 08 Sep 2016 | 17 | 135 | 0 | 76
A1- 12th Fl Railing- Master Bed (M+L) | 208 | Sft. | 07 Jun 2016 | 24 Jun 2016 | 26 Apr 2016 | 08 Sep 2016 | 17 | 135 | 0 | 76
A1- 12th Fl Railing Main St.Case (M+L) | 55 | Sft. | 25 Jun 2016 | 28 Jun 2016 | 08 Sep 2016 | 08 Sep 2016 | 3 | 0 | 75 | 72
A1- 12th Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 25 Jun 2016 | 28 Jun 2016 | 24 Jun 2016 | 08 Sep 2016 | 3 | 76 | 0 | 72
A1- 12th Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 29 Jun 2016 | 01 Jul 2016 | 30 Aug 2016 | 11 Nov 2016 | 2 | 73 | 62 | 133
A1- 13TH FL | 1 | No Unit | 25 Jun 2016 | 20 Jul 2016 |  |  | 25 | 0 | 0 | 0
A1- 13th Fl Railing- Living (M+L) | 162 | Sft. | 25 Jun 2016 | 13 Jul 2016 | 08 Sep 2016 | 12 Nov 2016 | 18 | 65 | 75 | 122
A1- 13th Fl Railing- Master Bed (M+L) | 0 | Sft. | 25 Jun 2016 | 13 Jul 2016 | 08 Sep 2016 | 11 Nov 2016 | 18 | 64 | 75 | 121
A1- 13th Fl Railing Main St.Case (M+L) | 55 | Sft. | 14 Jul 2016 | 16 Jul 2016 | 08 Sep 2016 | 08 Sep 2016 | 2 | 0 | 56 | 54
A1- 13th Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 14 Jul 2016 | 16 Jul 2016 | 08 Sep 2016 | 08 Sep 2016 | 2 | 0 | 56 | 54
A1- 13th Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 18 Jul 2016 | 20 Jul 2016 | 08 Sep 2016 | 11 Nov 2016 | 2 | 64 | 52 | 114
A1- 14TH FL | 1 | No Unit | 12 Jul 2016 | 05 Aug 2016 |  |  | 24 | 0 | 0 | 0
A1- 14th Fl Railing- Living (M+L) | 80 | Sft. | 12 Jul 2016 | 29 Jul 2016 | 29 Dec 2016 | 29 Dec 2016 | 17 | 0 | 170 | 153
A1- 14th Fl Railing- Master Bed (M+L) | 208 | Sft. | 12 Jul 2016 | 29 Jul 2016 | 29 Dec 2016 | 29 Dec 2016 | 17 | 0 | 170 | 153
A1- 14th Fl Railing Main St.Case (M+L) | 55 | Sft. | 30 Jul 2016 | 02 Aug 2016 | 08 Sep 2016 | 08 Sep 2016 | 3 | 0 | 40 | 37
A1- 14th Fl Railing Fire St.Case (M+L) | 40 | Sq.Ft. | 30 Jul 2016 | 02 Aug 2016 | 08 Sep 2016 | 08 Sep 2016 | 3 | 0 | 40 | 37
A1- 14th Fl Railing Floor Lobby (M+L) | 19.83 | Sft. | 03 Aug 2016 | 05 Aug 2016 | 08 Sep 2016 | 11 Nov 2016 | 2 | 64 | 36 | 98
A1- TERRACE FLOOR | 0 | No Unit | 12 Sep 2016 | 24 Oct 2016 |  |  | 42 | 0 | 0 | 0
A1- Terrace Floor M.S.Cover OHWT (M+L) | 5 | No. | 12 Sep 2016 | 20 Sep 2016 | 29 Dec 2016 |  | 8 | 0 | 108 | 0
A1- Terrace Floor Monkey Ladder (M+L) | 2 | No. | 12 Sep 2016 | 28 Sep 2016 | 30 Jul 2016 |  | 16 | 0 | 0 | 0
A1- Terrace Floor Railing Elevetional & Top Terrace (M+L) | 808.37 | Sft. | 12 Sep 2016 | 15 Oct 2016 | 01 Dec 2016 |  | 33 | 0 | 80 | 0
A1- Terrace Floor Smoke Windows (M+L) | 2 | No. | 17 Oct 2016 | 24 Oct 2016 | 30 Jul 2016 |  | 7 | 0 | 0 | 0
A1- Terrace Floor Railing Main St.Case (M+L) | 0 | Sft. | 12 Sep 2016 | 15 Sep 2016 | 29 Dec 2016 |  | 3 | 0 | 108 | 0
A1- FARMA & ARCHES | 0 | No Unit | 29 Jun 2015 | 15 Jul 2015 |  |  | 16 | 0 | 0 | 0
A1- Farma & Arches Gypsum Farma (Lab) | 4 | No. | 29 Jun 2015 | 15 Jul 2015 | 28 Aug 2015 | 29 Dec 2016 | 16 | 489 | 60 | 533
A1- Farma & Arches Loft Farma (M+L) | 0 | No. | 29 Jun 2015 | 15 Jul 2015 | 28 Aug 2015 | 29 Dec 2016 | 16 | 489 | 60 | 533
A1- Farma & Arches M.S. Arch Farma (M+L) | 0 | No. | 29 Jun 2015 | 15 Jul 2015 | 28 Aug 2015 | 29 Dec 2016 | 16 | 489 | 60 | 533
A1- Farma & Arches M.S. Tray (M+L) | 2 | No. | 29 Jun 2015 | 15 Jul 2015 | 28 Aug 2015 | 29 Dec 2016 | 16 | 489 | 60 | 533
A1- Farma & Arches Measuring Farma Ext.Plaster (M+L) | 2 | No. | 29 Jun 2015 | 15 Jul 2015 | 28 Aug 2015 | 29 Dec 2016 | 16 | 489 | 60 | 533
A1- Farma & Arches Measuring Farma Int.Plaster (M+L) | 2 | No. | 29 Jun 2015 | 15 Jul 2015 | 28 Aug 2015 | 29 Dec 2016 | 16 | 489 | 60 | 533
A1- Farma & Arches Measuring Farma Masonary (M+L) | 2 | No. | 29 Jun 2015 | 15 Jul 2015 | 28 Aug 2015 | 29 Dec 2016 | 16 | 489 | 60 | 533
A1- Farma & Arches Measuring Farma Tiling (M+L) | 2 | No. | 29 Jun 2015 | 15 Jul 2015 | 28 Aug 2015 | 29 Dec 2016 | 16 | 489 | 60 | 533
A1- Farma & Arches Round Column Farma (M+L) | 0 | No. | 29 Jun 2015 | 15 Jul 2015 | 28 Aug 2015 | 29 Dec 2016 | 16 | 489 | 60 | 533
A1- Farma & Arches Window Cill Farma (M+L) | 0 | No. | 29 Jun 2015 | 15 Jul 2015 | 28 Aug 2015 | 29 Dec 2016 | 16 | 489 | 60 | 533
A1- MISC. & OTHER | 0 | No Unit | 12 Sep 2016 | 15 Oct 2016 |  |  | 33 | 0 | 0 | 0
A1- Misc. & Other M.S. Ghoddi (Lab) | 30 | No. | 12 Sep 2016 | 15 Oct 2016 | 20 Aug 2016 |  | 33 | 0 | 0 | 0
A1- Misc. & Other Lift Hook (M+L) | 1 | NO | 12 Sep 2016 | 15 Oct 2016 | 29 Dec 2016 |  | 33 | 0 | 108 | 0
A1- Misc. & Other M.S. Saddle (M+L) | 1 | No. | 12 Sep 2016 | 15 Oct 2016 | 29 Dec 2016 |  | 33 | 0 | 108 | 0
A1- Misc. & Other Parking Shed Misc. Fabrication (M+L) | 1 | No. | 12 Sep 2016 | 15 Oct 2016 | 16 Sep 2015 |  | 33 | 0 | 0 | 0
A1-WINDOWS (M+L) | 54 | No Unit | 02 Dec 2015 | 21 Oct 2016 |  |  | 324 | 0 | 0 | 0
A1-M.S. WINDOW SUB FRAME | 0 | No Unit | 02 Dec 2015 | 21 Oct 2016 |  |  | 324 | 0 | 0 | 0
A1-PARKING | 54 | No Unit | 26 Jul 2016 | 26 Jul 2016 |  |  | 0 | 0 | 0 | 0
A1-Parking M.S. Subframe for Fire Stair | 1 | No. | 26 Jul 2016 | 26 Jul 2016 | 06 Jan 2016 | 14 Jul 2016 | 0 | 190 | 0 | 0
A1-1ST FLOOR | 0 | No Unit | 02 Dec 2015 | 30 Jan 2016 |  |  | 59 | 0 | 0 | 0
A1-1st Floor M.S. Subframe | 16 | No. | 02 Dec 2015 | 10 Dec 2015 | 19 Nov 2015 | 11 Dec 2015 | 8 | 22 | 0 | 1
A1-1st Floor M.S. Subframe for Fire Stair | 1 | No. | 30 Jan 2016 | 30 Jan 2016 | 22 Dec 2015 | 31 Dec 2015 | 0 | 9 | 0 | 0
A1-2ND FLOOR | 0 | No Unit | 10 Dec 2015 | 01 Feb 2016 |  |  | 53 | 0 | 0 | 0
A1-2nd Floor M.S. Subframe | 14 | No. | 10 Dec 2015 | 18 Dec 2015 | 21 Nov 2015 | 11 Dec 2015 | 8 | 20 | 0 | 0
A1-2nd Floor M.S. Subframe for Fire Stair | 1 | No. | 01 Feb 2016 | 01 Feb 2016 | 22 Dec 2015 | 31 Dec 2015 | 0 | 9 | 0 | 0
A1-3RD FLOOR | 0 | No Unit | 30 Dec 2015 | 02 Feb 2016 |  |  | 34 | 0 | 0 | 0
A1-3rd Floor M.S. Subframe | 16 | No. | 30 Dec 2015 | 08 Jan 2016 | 14 Dec 2015 | 31 Dec 2015 | 9 | 17 | 0 | 0
A1-3rd Floor M.S. Subframe for Fire Stair | 1 | No. | 02 Feb 2016 | 02 Feb 2016 | 22 Dec 2015 | 31 Dec 2015 | 0 | 9 | 0 | 0
A1-4TH FLOOR | 0 | No Unit | 21 Jan 2016 | 03 Feb 2016 |  |  | 13 | 0 | 0 | 0
A1-4th Floor M.S. Subframe | 14 | No. | 21 Jan 2016 | 30 Jan 2016 | 30 Dec 2015 | 18 Feb 2016 | 9 | 50 | 0 | 19
A1-4th Floor M.S. Subframe for Fire Stair | 1 | No. | 03 Feb 2016 | 03 Feb 2016 | 22 Dec 2015 | 31 Dec 2015 | 0 | 9 | 0 | 0
A1-5TH FLOOR | 0 | No Unit | 04 Feb 2016 | 22 Feb 2016 |  |  | 18 | 0 | 0 | 0
A1-5th Floor M.S. Subframe | 16 | No. | 13 Feb 2016 | 22 Feb 2016 | 12 Jan 2016 | 18 Feb 2016 | 9 | 37 | 0 | 0
A1-5th Floor M.S. Subframe for Fire Stair | 1 | No. | 04 Feb 2016 | 04 Feb 2016 | 22 Dec 2015 | 31 Dec 2015 | 0 | 9 | 0 | 0
A1-6TH FLOOR | 0 | No Unit | 05 Feb 2016 | 15 Mar 2016 |  |  | 39 | 0 | 0 | 0
A1-6th Floor M.S. Subframe | 14 | No. | 05 Mar 2016 | 15 Mar 2016 | 16 Jan 2016 | 18 Feb 2016 | 10 | 33 | 0 | 0
A1-6th Floor M.S. Subframe for Fire Stair | 1 | No. | 05 Feb 2016 | 05 Feb 2016 | 24 Feb 2016 | 27 Feb 2016 | 0 | 3 | 19 | 22
A1-7TH FLOOR | 0 | No Unit | 06 Feb 2016 | 08 Mar 2016 |  |  | 31 | 0 | 0 | 0
A1-7th Floor M.S. Subframe | 16 | No. | 27 Feb 2016 | 08 Mar 2016 | 05 Feb 2016 | 18 Feb 2016 | 10 | 13 | 0 | 0
A1-7th Floor M.S. Subframe for Fire Stair | 1 | No. | 06 Feb 2016 | 06 Feb 2016 | 24 Feb 2016 | 27 Feb 2016 | 0 | 3 | 18 | 21
A1-8TH FLOOR | 0 | No Unit | 08 Feb 2016 | 08 Mar 2016 |  |  | 29 | 0 | 0 | 0
A1-8th Floor M.S. Subframe | 14 | No. | 27 Feb 2016 | 08 Mar 2016 | 11 Feb 2016 | 27 Feb 2016 | 10 | 16 | 0 | 0
A1-8th Floor M.S. Subframe for Fire Stair | 1 | No. | 08 Feb 2016 | 08 Feb 2016 | 24 Feb 2016 | 05 Mar 2016 | 0 | 10 | 16 | 26
A1-9TH FLOOR | 0 | No Unit | 09 Feb 2016 | 08 Mar 2016 |  |  | 28 | 0 | 0 | 0
A1-9th Floor M.S. Subframe | 16 | No. | 27 Feb 2016 | 08 Mar 2016 | 01 Mar 2016 | 21 Mar 2016 | 10 | 20 | 3 | 13
A1-9th Floor M.S. Subframe for Fire Stair | 1 | No. | 09 Feb 2016 | 09 Feb 2016 | 11 Mar 2016 | 21 Mar 2016 | 0 | 10 | 31 | 41
A1-10TH FLOOR | 0 | No Unit | 10 Feb 2016 | 08 Mar 2016 |  |  | 27 | 0 | 0 | 0
A1-10th Floor M.S. Subframe | 14 | No. | 27 Feb 2016 | 08 Mar 2016 | 14 Mar 2016 | 23 Apr 2016 | 10 | 40 | 16 | 46
A1-10th Floor M.S. Subframe for Fire Stair | 1 | No. | 10 Feb 2016 | 10 Feb 2016 | 11 Mar 2016 | 23 Apr 2016 | 0 | 43 | 30 | 73
A1-11TH FLOOR | 0 | No Unit | 11 Feb 2016 | 04 Jun 2016 |  |  | 114 | 0 | 0 | 0
A1-11th Floor M.S. Subframe | 16 | No. | 27 May 2016 | 04 Jun 2016 | 05 Apr 2016 | 03 May 2016 | 8 | 28 | 0 | 0
A1-11th Floor M.S. Subframe for Fire Stair | 1 | No. | 11 Feb 2016 | 11 Feb 2016 | 03 May 2016 | 14 Jul 2016 | 0 | 72 | 82 | 154
A1-12TH FLOOR | 0 | No Unit | 12 Feb 2016 | 15 Jun 2016 |  |  | 124 | 0 | 0 | 0
A1-12th Floor M.S. Subframe | 14 | No. | 07 Jun 2016 | 15 Jun 2016 | 07 Jun 2016 | 14 Jul 2016 | 8 | 37 | 0 | 29
A1-12th Floor M.S. Subframe for Fire Stair | 1 | No. | 12 Feb 2016 | 12 Feb 2016 | 06 Jun 2016 | 14 Jul 2016 | 0 | 38 | 115 | 153
A1-13TH FLOOR | 0 | No Unit | 13 Feb 2016 | 04 Jul 2016 |  |  | 142 | 0 | 0 | 0
A1-13th Floor M.S. Subframe | 16 | No. | 25 Jun 2016 | 04 Jul 2016 | 14 Sep 2016 | 29 Dec 2016 | 9 | 106 | 81 | 178
A1-13th Floor M.S. Subframe for Fire Stair | 1 | No. | 13 Feb 2016 | 13 Feb 2016 | 05 Jul 2016 | 29 Dec 2016 | 0 | 177 | 143 | 320
A1-14TH FLOOR | 0 | No Unit | 15 Feb 2016 | 20 Jul 2016 |  |  | 156 | 0 | 0 | 0
A1-14th Floor M.S. Subframe | 14 | No. | 12 Jul 2016 | 20 Jul 2016 | 29 Dec 2016 | 29 Dec 2016 | 8 | 0 | 170 | 162
A1-14th Floor M.S. Subframe for Fire Stair | 1 | No. | 15 Feb 2016 | 15 Feb 2016 | 05 Jul 2016 | 29 Dec 2016 | 0 | 177 | 141 | 318
A1-WASTAGE FACTOR | 0 | No Unit | 02 Dec 2015 | 21 Oct 2016 |  |  | 324 | 0 | 0 | 0
A1-Wastage factor Extra Cost | 0 | R.S. | 02 Dec 2015 | 21 Oct 2016 | 29 Dec 2016 | 29 Dec 2016 | 324 | 0 | 393 | 69
A1-DOORS (M+L) | 0 | No Unit | 25 Dec 2015 | 10 Dec 2016 |  |  | 351 | 0 | 0 | 0
A1-DOOR FRAME | 1 | No Unit | 25 Dec 2015 | 01 Nov 2016 |  |  | 312 | 0 | 0 | 0
A1-PARKING | 1 | No Unit | 31 Oct 2016 | 01 Nov 2016 |  |  | 1 | 0 | 0 | 0
A1-Parking Parking Toilet Door Frame | 1 | No. | 31 Oct 2016 | 01 Nov 2016 | 06 Feb 2016 |  | 1 | 0 | 0 | 0
A1-Parking Main Lobby Below Stair Door shutter | 1 | No. | 31 Oct 2016 | 01 Nov 2016 | 29 Dec 2016 |  | 1 | 0 | 59 | 0
A1-1ST FLOOR | 0 | No Unit | 25 Dec 2015 | 08 Jan 2016 |  |  | 14 | 0 | 0 | 0
A1-1st Floor Main Door Frame | 4 | No. | 25 Dec 2015 | 08 Jan 2016 | 18 Jan 2016 | 18 Feb 2016 | 14 | 31 | 24 | 41
A1-1st Floor Bed Room Door Frame | 8 | No. | 25 Dec 2015 | 08 Jan 2016 | 24 Dec 2015 | 18 Feb 2016 | 14 | 56 | 0 | 41
A1-2ND FLOOR | 0 | No Unit | 04 Jan 2016 | 16 Jan 2016 |  |  | 12 | 0 | 0 | 0
A1-2nd Floor Main Door Frame | 4 | No. | 04 Jan 2016 | 16 Jan 2016 | 18 Jan 2016 | 18 Feb 2016 | 12 | 31 | 14 | 33
A1-2nd Floor Bed Room Door Frame | 8 | No. | 04 Jan 2016 | 16 Jan 2016 | 18 Jan 2016 | 18 Feb 2016 | 12 | 31 | 14 | 33
A1-3RD FLOOR | 0 | No Unit | 23 Jan 2016 | 06 Feb 2016 |  |  | 14 | 0 | 0 | 0
A1-3rd Floor Main Door Frame | 4 | No. | 23 Jan 2016 | 06 Feb 2016 | 18 Jan 2016 | 18 Feb 2016 | 14 | 31 | 0 | 12
A1-3rd Floor Bed Room Door Frame | 8 | No. | 23 Jan 2016 | 06 Feb 2016 | 18 Jan 2016 | 18 Feb 2016 | 14 | 31 | 0 | 12
A1-4TH FLOOR | 0 | No Unit | 15 Feb 2016 | 27 Feb 2016 |  |  | 12 | 0 | 0 | 0
A1-4th Floor Main Door Frame | 4 | No. | 15 Feb 2016 | 27 Feb 2016 | 09 Feb 2016 | 27 Feb 2016 | 12 | 18 | 0 | 0
A1-4th Floor Bed Room Door Frame | 8 | No. | 15 Feb 2016 | 27 Feb 2016 | 09 Feb 2016 | 18 Feb 2016 | 12 | 9 | 0 | 0
A1-5TH FLOOR | 4 | No Unit | 09 Mar 2016 | 22 Mar 2016 |  |  | 13 | 0 | 0 | 0
A1-5th Floor Main Door Frame | 4 | No. | 09 Mar 2016 | 22 Mar 2016 | 09 Feb 2016 | 27 Feb 2016 | 13 | 18 | 0 | 0
A1-5th Floor Bed Room Door Frame | 8 | No. | 09 Mar 2016 | 22 Mar 2016 | 09 Feb 2016 | 27 Feb 2016 | 13 | 18 | 0 | 0
A1-6TH FLOOR | 0 | No Unit | 09 Mar 2016 | 22 Mar 2016 |  |  | 13 | 0 | 0 | 0
A1-6th Floor Main Door Frame | 4 | No. | 09 Mar 2016 | 22 Mar 2016 | 24 Feb 2016 | 27 Feb 2016 | 13 | 3 | 0 | 0
A1-6th Floor Bed Room Door Frame | 8 | No. | 09 Mar 2016 | 22 Mar 2016 | 24 Feb 2016 | 27 Feb 2016 | 13 | 3 | 0 | 0
A1-7TH FLOOR | 0 | No Unit | 09 Mar 2016 | 22 Mar 2016 |  |  | 13 | 0 | 0 | 0
A1-7th Floor Main Door Frame | 4 | No. | 09 Mar 2016 | 22 Mar 2016 | 24 Feb 2016 | 02 Apr 2016 | 13 | 38 | 0 | 11
A1-7th Floor Bed Room Door Frame | 8 | No. | 09 Mar 2016 | 22 Mar 2016 | 24 Feb 2016 | 02 Apr 2016 | 13 | 38 | 0 | 11
A1-8TH FLOOR | 0 | No Unit | 09 Mar 2016 | 22 Mar 2016 |  |  | 13 | 0 | 0 | 0
A1-8th Floor Main Door Frame | 3 | No. | 09 Mar 2016 | 22 Mar 2016 | 29 Mar 2016 | 02 Apr 2016 | 13 | 4 | 20 | 11
A1-8th Floor Bed Room Door Frame | 6 | No. | 09 Mar 2016 | 22 Mar 2016 | 29 Mar 2016 | 02 Apr 2016 | 13 | 4 | 20 | 11
A1-9TH FLOOR | 0 | No Unit | 09 Mar 2016 | 22 Mar 2016 |  |  | 13 | 0 | 0 | 0
A1-9th Floor Main Door Frame | 4 | No. | 09 Mar 2016 | 22 Mar 2016 | 29 Mar 2016 | 02 Apr 2016 | 13 | 4 | 20 | 11
A1-9th Floor Bed Room Door Frame | 8 | No. | 09 Mar 2016 | 22 Mar 2016 | 29 Mar 2016 | 02 Apr 2016 | 13 | 4 | 20 | 11
A1-10TH FLOOR | 0 | No Unit | 04 Jun 2016 | 17 Jun 2016 |  |  | 13 | 0 | 0 | 0
A1-10th Floor Main Door Frame | 4 | No. | 04 Jun 2016 | 17 Jun 2016 | 31 Mar 2016 | 03 May 2016 | 13 | 33 | 0 | 0
A1-10th Floor Bed Room Door Frame | 8 | No. | 04 Jun 2016 | 17 Jun 2016 | 31 Mar 2016 | 21 Jun 2016 | 13 | 82 | 0 | 4
A1-11TH FLOOR | 0 | No Unit | 20 Jun 2016 | 02 Jul 2016 |  |  | 12 | 0 | 0 | 0
A1-11th Floor Main Door Frame | 4 | No. | 20 Jun 2016 | 02 Jul 2016 | 27 Apr 2016 | 21 Jun 2016 | 12 | 55 | 0 | 0
A1-11th Floor Bed Room Door Frame | 8 | No. | 20 Jun 2016 | 02 Jul 2016 | 27 Apr 2016 | 21 Jun 2016 | 12 | 55 | 0 | 0
A1-12TH FLOOR | 0 | No Unit | 30 Jun 2016 | 13 Jul 2016 |  |  | 13 | 0 | 0 | 0
A1-12th Floor Main Door Frame | 4 | No. | 30 Jun 2016 | 13 Jul 2016 | 06 Jun 2016 | 29 Dec 2016 | 13 | 206 | 0 | 169
A1-12th Floor Bed Room Door Frame | 8 | No. | 30 Jun 2016 | 13 Jul 2016 | 06 Jun 2016 | 29 Dec 2016 | 13 | 206 | 0 | 169
A1-13TH FLOOR | 0 | No Unit | 19 Jul 2016 | 01 Aug 2016 |  |  | 13 | 0 | 0 | 0
A1-13th Floor Main Door Frame | 3 | No. | 19 Jul 2016 | 01 Aug 2016 | 07 Oct 2016 | 29 Dec 2016 | 13 | 83 | 80 | 150
A1-13th Floor Bed Room Door Frame | 6 | No. | 19 Jul 2016 | 01 Aug 2016 | 07 Oct 2016 | 29 Dec 2016 | 13 | 83 | 80 | 150
A1-14TH FLOOR | 0 | No Unit | 04 Aug 2016 | 18 Aug 2016 |  |  | 14 | 0 | 0 | 0
A1-14th Floor Main Door Frame | 4 | No. | 04 Aug 2016 | 18 Aug 2016 | 17 Jun 2016 | 29 Dec 2016 | 14 | 195 | 0 | 133
A1-14th Floor Bed Room Door Frame | 8 | No. | 04 Aug 2016 | 18 Aug 2016 | 17 Jun 2016 | 29 Dec 2016 | 14 | 195 | 0 | 133
A1-TERRACE FLOOR | 0 | No Unit | 23 Sep 2016 | 24 Sep 2016 |  |  | 1 | 0 | 0 | 0
A1-Terrace Floor LMR Door Frame | 0 | No. | 23 Sep 2016 | 24 Sep 2016 | 29 Dec 2016 | 29 Dec 2016 | 1 | 0 | 97 | 96
A1-Terrace Floor Top Terrace Door Frame | 4 | No. | 23 Sep 2016 | 24 Sep 2016 | 04 Oct 2016 | 29 Dec 2016 | 1 | 86 | 11 | 96
A1-WASTAGE FACTOR | 0 | No Unit | 25 Dec 2015 | 15 Oct 2016 |  |  | 295 | 0 | 0 | 0
A1-Wastage factor Extra Cost | 17586.1 | R.S. | 25 Dec 2015 | 15 Oct 2016 | 25 Nov 2015 |  | 295 | 0 | 0 | 0
A1-DOOR SHUTTER | 7000 | No Unit | 20 Feb 2016 | 10 Dec 2016 |  |  | 294 | 0 | 0 | 0
A1-PARKING | 0 | No Unit | 16 Aug 2016 | 17 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1-Parking Parking Toilet Door Shutter | 1 | No. | 16 Aug 2016 | 17 Aug 2016 | 11 Jan 2017 | 01 Feb 2017 | 1 | 21 | 148 | 168
A1-Parking Main Lobby Below Stair Door shutter | 1 | No. | 16 Aug 2016 | 17 Aug 2016 |  |  | 1 | 0 | 0 | 0
A1-Parking Meter Room Ply with Backelite (Lab) | 56695 | Sft. | 16 Aug 2016 | 17 Aug 2016 | 23 Jun 2016 |  | 1 | 0 | 0 | 0
A1-1ST FLOOR | 1 | No Unit | 20 Feb 2016 | 07 Jun 2016 |  |  | 108 | 0 | 0 | 0
A1-1st Floor Main Door Shutter | 4 | No. | 20 Feb 2016 | 22 Feb 2016 | 15 Feb 2017 |  | 2 | 0 | 361 | 0
A1-1st Floor Bed Room Door Shutter | 8 | No. | 25 May 2016 | 07 Jun 2016 | 06 Jun 2016 | 25 Jan 2017 | 13 | 233 | 12 | 232
A1-1st Floor Toilet Door Shutter | 8 | No. | 25 May 2016 | 07 Jun 2016 | 06 Jun 2016 | 25 Jan 2017 | 13 | 233 | 12 | 232
A1-1st Floor Door Shutter fixing (Lab) | 56695 | Sft. | 25 May 2016 | 07 Jun 2016 | 13 Jun 2016 | 01 Feb 2017 | 13 | 233 | 19 | 239
A1-1st Floor Door Misc. | 1 | No. | 25 May 2016 | 07 Jun 2016 | 30 Jan 2017 | 01 Feb 2017 | 13 | 2 | 250 | 239
A1-2ND FLOOR | 1 | No Unit | 01 Mar 2016 | 16 Jun 2016 |  |  | 107 | 0 | 0 | 0
A1-2nd Floor Main Door Shutter | 4 | No. | 01 Mar 2016 | 02 Mar 2016 | 15 Feb 2017 |  | 1 | 0 | 351 | 0
A1-2nd Floor Bed Room Door Shutter | 8 | No. | 03 Jun 2016 | 16 Jun 2016 | 06 Jun 2016 | 25 Jan 2017 | 13 | 233 | 3 | 223
A1-2nd Floor Toilet Door Shutter | 8 | No. | 03 Jun 2016 | 16 Jun 2016 | 06 Jun 2016 | 25 Jan 2017 | 13 | 233 | 3 | 223
A1-2nd Floor Door Shutter fixing (Lab) | 56695 | Sft. | 03 Jun 2016 | 16 Jun 2016 | 13 Jun 2016 | 01 Feb 2017 | 13 | 233 | 10 | 230
A1-2nd Floor Door Misc. | 1 | No. | 03 Jun 2016 | 16 Jun 2016 | 30 Jan 2017 | 01 Feb 2017 | 13 | 2 | 241 | 230
A1-3RD FLOOR | 1 | No Unit | 14 Mar 2016 | 28 Jun 2016 |  |  | 106 | 0 | 0 | 0
A1-3rd Floor Main Door Shutter | 4 | No. | 14 Mar 2016 | 15 Mar 2016 | 15 Feb 2017 |  | 1 | 0 | 338 | 0
A1-3rd Floor Bed Room Door Shutter | 8 | No. | 15 Jun 2016 | 28 Jun 2016 | 08 Jun 2016 | 25 Jan 2017 | 13 | 231 | 0 | 211
A1-3rd Floor Toilet Door Shutter | 8 | No. | 15 Jun 2016 | 28 Jun 2016 | 08 Jun 2016 | 25 Jan 2017 | 13 | 231 | 0 | 211
A1-3rd Floor Door Shutter fixing (Lab) | 56695 | Sft. | 15 Jun 2016 | 28 Jun 2016 | 13 Jun 2016 | 01 Feb 2017 | 13 | 233 | 0 | 218
A1-3rd Floor Door Misc. | 1 | No. | 15 Jun 2016 | 28 Jun 2016 |  |  | 13 | 0 | 0 | 0
A1-4TH FLOOR | 1 | No Unit | 09 Apr 2016 | 25 Jul 2016 |  |  | 107 | 0 | 0 | 0
A1-4th Floor Main Door Shutter | 4 | No. | 09 Apr 2016 | 11 Apr 2016 | 15 Feb 2017 |  | 2 | 0 | 312 | 0
A1-4th Floor Bed Room Door Shutter | 8 | No. | 12 Jul 2016 | 25 Jul 2016 | 08 Jun 2016 | 25 Jan 2017 | 13 | 231 | 0 | 184
A1-4th Floor Toilet Door Shutter | 8 | No. | 12 Jul 2016 | 25 Jul 2016 | 08 Jun 2016 | 25 Jan 2017 | 13 | 231 | 0 | 184
A1-4th Floor Door Shutter fixing (Lab) | 56695 | Sft. | 12 Jul 2016 | 25 Jul 2016 | 13 Jun 2016 | 01 Feb 2017 | 13 | 233 | 0 | 191
A1-4th Floor Door Misc. | 1 | No. | 12 Jul 2016 | 25 Jul 2016 | 30 Jan 2017 |  | 13 | 0 | 202 | 0
A1-5TH FLOOR | 1 | No Unit | 07 May 2016 | 23 Aug 2016 |  |  | 108 | 0 | 0 | 0
A1-5th Floor Main Door Shutter | 4 | No. | 07 May 2016 | 09 May 2016 | 15 Feb 2017 |  | 2 | 0 | 284 | 0
A1-5th Floor Bed Room Door Shutter | 8 | No. | 09 Aug 2016 | 23 Aug 2016 | 20 Jun 2016 | 25 Jan 2017 | 14 | 219 | 0 | 155
A1-5th Floor Toilet Door Shutter | 8 | No. | 09 Aug 2016 | 23 Aug 2016 | 20 Jun 2016 | 25 Jan 2017 | 14 | 219 | 0 | 155
A1-5th Floor Door Shutter fixing (Lab) | 56695 | Sft. | 09 Aug 2016 | 23 Aug 2016 | 13 Jun 2016 | 01 Feb 2017 | 14 | 233 | 0 | 162
A1-5th Floor Door Misc. | 1 | No. | 09 Aug 2016 | 23 Aug 2016 | 30 Jan 2017 | 30 Jan 2017 | 14 | 0 | 174 | 160
A1-6TH FLOOR | 1 | No Unit | 13 May 2016 | 29 Aug 2016 |  |  | 108 | 0 | 0 | 0
A1-6th Floor Main Door Shutter | 4 | No. | 13 May 2016 | 14 May 2016 | 15 Feb 2017 |  | 1 | 0 | 278 | 0
A1-6th Floor Bed Room Door Shutter | 8 | No. | 16 Aug 2016 | 29 Aug 2016 | 20 Jun 2016 | 25 Jan 2017 | 13 | 219 | 0 | 149
A1-6th Floor Toilet Door Shutter | 8 | No. | 16 Aug 2016 | 29 Aug 2016 | 20 Jun 2016 | 25 Jan 2017 | 13 | 219 | 0 | 149
A1-6th Floor Door Shutter fixing (Lab) | 56695 | Sft. | 16 Aug 2016 | 29 Aug 2016 | 13 Jun 2016 | 01 Feb 2017 | 13 | 233 | 0 | 156
A1-6th Floor Door Misc. | 1 | No. | 16 Aug 2016 | 29 Aug 2016 | 30 Jan 2017 |  | 13 | 0 | 167 | 0
A1-7TH FLOOR | 1 | No Unit | 23 May 2016 | 07 Sep 2016 |  |  | 107 | 0 | 0 | 0
A1-7th Floor Main Door Shutter | 4 | No. | 23 May 2016 | 24 May 2016 | 15 Feb 2017 |  | 1 | 0 | 268 | 0
A1-7th Floor Bed Room Door Shutter | 8 | No. | 25 Aug 2016 | 07 Sep 2016 | 20 Jun 2016 | 25 Jan 2017 | 13 | 219 | 0 | 140
A1-7th Floor Toilet Door Shutter | 8 | No. | 25 Aug 2016 | 07 Sep 2016 | 20 Jun 2016 | 25 Jan 2017 | 13 | 219 | 0 | 140
A1-7th Floor Door Shutter fixing (Lab) | 56695 | Sft. | 25 Aug 2016 | 07 Sep 2016 | 13 Jun 2016 | 01 Feb 2017 | 13 | 233 | 0 | 147
A1-7th Floor Door Misc. | 1 | No. | 25 Aug 2016 | 07 Sep 2016 | 30 Jan 2017 |  | 13 | 0 | 158 | 0
A1-8TH FLOOR | 1 | No Unit | 21 May 2016 | 29 Aug 2016 |  |  | 100 | 0 | 0 | 0
A1-8th Floor Main Door Shutter | 3 | No. | 21 May 2016 | 23 May 2016 | 15 Feb 2017 |  | 2 | 0 | 270 | 0