## Task Details637397344604532297_
Task Details
Project Name : A SAMPLE PROJECT 3
Task Name : CONSTRUCTION
Total Records: 13876 Records 4001 to 6000
Page 3 of 7
Task (1) | Qty (2) | Unit (3) | Planned Start (4) | Planned Finish (5) | Actual Start (6) | Actual Finish (7) | Planned Duration (8)=(4)-(5) Days | Actual Duration (9)=(6)-(7) Days | Start Variance (10)=(4)-(6) Days | Finish Variance (11)=(4)-(5) Days | Remark
A1-8th Floor Bed Room Door Shutter | 6 | No. | 16 Aug 2016 | 29 Aug 2016 | 04 Jul 2016 | 25 Jan 2017 | 13 | 205 | 0 | 149
A1-8th Floor Toilet Door Shutter | 6 | No. | 16 Aug 2016 | 29 Aug 2016 | 04 Jul 2016 | 25 Jan 2017 | 13 | 205 | 0 | 149
A1-8th Floor Door Shutter fixing (Lab) | 56695 | Sft. | 16 Aug 2016 | 29 Aug 2016 | 13 Jun 2016 | 01 Feb 2017 | 13 | 233 | 0 | 156
A1-8th Floor Door Misc. | 1 | No. | 16 Aug 2016 | 29 Aug 2016 |  |  | 13 | 0 | 0 | 0
A1-9TH FLOOR | 1 | No Unit | 21 Jul 2016 | 29 Sep 2016 |  |  | 70 | 0 | 0 | 0
A1-9th Floor Main Door Shutter | 4 | No. | 21 Jul 2016 | 22 Jul 2016 | 15 Feb 2017 |  | 1 | 0 | 209 | 0
A1-9th Floor Bed Room Door Shutter | 8 | No. | 16 Sep 2016 | 29 Sep 2016 | 04 Jul 2016 | 25 Jan 2017 | 13 | 205 | 0 | 118
A1-9th Floor Toilet Door Shutter | 8 | No. | 16 Sep 2016 | 29 Sep 2016 | 04 Jul 2016 | 25 Jan 2017 | 13 | 205 | 0 | 118
A1-9th Floor Door Shutter fixing (Lab) | 56695 | Sft. | 16 Sep 2016 | 29 Sep 2016 | 13 Jun 2016 | 01 Feb 2017 | 13 | 233 | 0 | 125
A1-9th Floor Door Misc. | 1 | No. | 16 Sep 2016 | 29 Sep 2016 | 30 Jan 2017 |  | 13 | 0 | 136 | 0
A1-10TTH FLOOR | 1 | No Unit | 22 Aug 2016 | 20 Oct 2016 |  |  | 59 | 0 | 0 | 0
A1-10tth Floor Main Door Shutter | 4 | No. | 22 Aug 2016 | 23 Aug 2016 | 15 Feb 2017 |  | 1 | 0 | 177 | 0
A1-10tth Floor Bed Room Door Shutter | 8 | No. | 07 Oct 2016 | 20 Oct 2016 | 29 Jul 2016 | 25 Jan 2017 | 13 | 180 | 0 | 97
A1-10tth Floor Toilet Door Shutter | 8 | No. | 07 Oct 2016 | 20 Oct 2016 | 29 Jul 2016 | 25 Jan 2017 | 13 | 180 | 0 | 97
A1-10tth Floor Door Shutter fixing (Lab) | 56695 | Sft. | 07 Oct 2016 | 20 Oct 2016 | 25 Aug 2016 | 01 Feb 2017 | 13 | 160 | 0 | 104
A1-10tth Floor Door Misc. | 1 | No. | 07 Oct 2016 | 20 Oct 2016 | 13 Oct 2016 |  | 13 | 0 | 6 | 0
A1-11TTH FLOOR | 1 | No Unit | 19 Sep 2016 | 17 Nov 2016 |  |  | 59 | 0 | 0 | 0
A1-11tth Floor Main Door Shutter | 4 | No. | 19 Sep 2016 | 20 Sep 2016 | 15 Feb 2017 |  | 1 | 0 | 149 | 0
A1-11tth Floor Bed Room Door Shutter | 8 | No. | 04 Nov 2016 | 17 Nov 2016 | 06 Sep 2016 | 25 Jan 2017 | 13 | 141 | 0 | 69
A1-11tth Floor Toilet Door Shutter | 8 | No. | 04 Nov 2016 | 17 Nov 2016 | 06 Sep 2016 | 25 Jan 2017 | 13 | 141 | 0 | 69
A1-11tth Floor Door Shutter fixing (Lab) | 56695 | Sft. | 04 Nov 2016 | 17 Nov 2016 | 06 Dec 2016 | 01 Feb 2017 | 13 | 57 | 32 | 76
A1-11tth Floor Door Misc. | 1 | No. | 04 Nov 2016 | 17 Nov 2016 | 06 Dec 2016 |  | 13 | 0 | 32 | 0
A1-12TH FLOOR | 1 | No Unit | 17 Oct 2016 | 28 Nov 2016 |  |  | 42 | 0 | 0 | 0
A1-12th Floor Main Door Shutter | 4 | No. | 17 Oct 2016 | 18 Oct 2016 | 15 Feb 2017 |  | 1 | 0 | 121 | 0
A1-12th Floor Bed Room Door Shutter | 8 | No. | 15 Nov 2016 | 28 Nov 2016 | 06 Dec 2016 | 25 Jan 2017 | 13 | 50 | 21 | 58
A1-12th Floor Toilet Door Shutter | 8 | No. | 15 Nov 2016 | 28 Nov 2016 | 06 Dec 2016 | 25 Jan 2017 | 13 | 50 | 21 | 58
A1-12th Floor Door Shutter fixing (Lab) | 56695 | Sft. | 15 Nov 2016 | 28 Nov 2016 | 06 Dec 2016 | 01 Feb 2017 | 13 | 57 | 21 | 65
A1-12th Floor Door Misc. | 1 | No. | 15 Nov 2016 | 28 Nov 2016 | 06 Dec 2016 |  | 13 | 0 | 21 | 0
A1-13TTH FLOOR | 1 | No Unit | 03 Oct 2016 | 30 Nov 2016 |  |  | 58 | 0 | 0 | 0
A1-13tth Floor Main Door Shutter | 3 | No. | 03 Oct 2016 | 04 Oct 2016 | 15 Feb 2017 |  | 1 | 0 | 135 | 0
A1-13tth Floor Bed Room Door Shutter | 6 | No. | 17 Nov 2016 | 30 Nov 2016 | 21 Dec 2016 | 25 Jan 2017 | 13 | 35 | 34 | 56
A1-13tth Floor Toilet Door Shutter | 6 | No. | 17 Nov 2016 | 30 Nov 2016 | 21 Dec 2016 | 25 Jan 2017 | 13 | 35 | 34 | 56
A1-13tth Floor Door Shutter fixing (Lab) | 56695 | Sft. | 17 Nov 2016 | 30 Nov 2016 | 22 Dec 2016 | 01 Feb 2017 | 13 | 41 | 35 | 63
A1-13tth Floor Door Misc. | 1 | No. | 17 Nov 2016 | 30 Nov 2016 | 30 Jan 2017 |  | 13 | 0 | 74 | 0
A1-14TH FLOOR | 1 | No Unit | 26 Oct 2016 | 07 Dec 2016 |  |  | 42 | 0 | 0 | 0
A1-14th Floor Main Door Shutter | 4 | No. | 26 Oct 2016 | 27 Oct 2016 | 15 Feb 2017 |  | 1 | 0 | 112 | 0
A1-14th Floor Bed Room Door Shutter | 8 | No. | 24 Nov 2016 | 07 Dec 2016 | 04 Jul 2016 | 25 Jan 2017 | 13 | 205 | 0 | 49
A1-14th Floor Toilet Door Shutter | 8 | No. | 24 Nov 2016 | 07 Dec 2016 | 04 Jul 2016 | 25 Jan 2017 | 13 | 205 | 0 | 49
A1-14th Floor Door Shutter fixing (Lab) | 56695 | Sft. | 24 Nov 2016 | 07 Dec 2016 | 30 Jan 2017 | 30 Jan 2017 | 13 | 0 | 67 | 54
A1-14th Floor Door Misc. | 1 | No. | 24 Nov 2016 | 07 Dec 2016 | 30 Jan 2017 | 30 Jan 2017 | 13 | 0 | 67 | 54
A1-TERRACE FLOOR | 0 | No Unit | 08 Dec 2016 | 10 Dec 2016 |  |  | 2 | 0 | 0 | 0
A1-Terrace Floor Top Terrace Door Shutter | 4 | No. | 08 Dec 2016 | 10 Dec 2016 | 01 Dec 2016 | 30 Jan 2017 | 2 | 60 | 0 | 51
A1-Terrace Floor LMR Door Shutter | 0 | No. | 08 Dec 2016 | 10 Dec 2016 | 30 Jan 2017 |  | 2 | 0 | 53 | 0
A1-WASTAGE FACTOR | 0 | No Unit | 08 Dec 2016 | 08 Dec 2016 |  |  | 0 | 0 | 0 | 0
A1-Wastage factor Extra Cost | 27390 | R.S. | 08 Dec 2016 | 08 Dec 2016 | 21 Jun 2016 |  | 0 | 0 | 0 | 0
A1-FOLDING DOOR (M+L) | 46.5 | No Unit | 13 May 2016 | 23 Sep 2016 |  |  | 133 | 0 | 0 | 0
A1-PARKING | 1 | No Unit | 22 Sep 2016 | 23 Sep 2016 |  |  | 1 | 0 | 0 | 0
A1-Parking Meter Room GI F.D.+frame(M+L) | 38.75 | Sft. | 22 Sep 2016 | 23 Sep 2016 | 07 Mar 2016 |  | 1 | 0 | 0 | 0
A1-1ST FLOOR | 0 | No Unit | 13 May 2016 | 21 May 2016 |  |  | 8 | 0 | 0 | 0
A1-1st Floor G.I. F.D. with frame(M+L) | 0 | Sft. | 13 May 2016 | 21 May 2016 | 19 Jan 2016 |  | 8 | 0 | 0 | 0
A1-2ND FLOOR | 0 | No Unit | 23 May 2016 | 31 May 2016 |  |  | 8 | 0 | 0 | 0
A1-2nd Floor G.I. F.D. with frame(M+L) | 46.5 | Sft. | 23 May 2016 | 31 May 2016 | 19 Jan 2016 |  | 8 | 0 | 0 | 0
A1-3RD FLOOR | 0 | No Unit | 01 Jun 2016 | 09 Jun 2016 |  |  | 8 | 0 | 0 | 0
A1-3rd Floor G.I. F.D. with frame(M+L) | 0 | Sft. | 01 Jun 2016 | 09 Jun 2016 | 19 Jan 2016 |  | 8 | 0 | 0 | 0
A1-4TH FLOOR | 0 | No Unit | 10 Jun 2016 | 18 Jun 2016 |  |  | 8 | 0 | 0 | 0
A1-4th Floor G.I. F.D. with frame(M+L) | 46.5 | Sft. | 10 Jun 2016 | 18 Jun 2016 | 19 Jan 2016 |  | 8 | 0 | 0 | 0
A1-5TH FLOOR | 0 | No Unit | 20 Jun 2016 | 28 Jun 2016 |  |  | 8 | 0 | 0 | 0
A1-5th Floor G.I. F.D. with frame(M+L) | 0 | Sft. | 20 Jun 2016 | 28 Jun 2016 | 19 Jan 2016 |  | 8 | 0 | 0 | 0
A1-6TH FLOOR | 0 | No Unit | 29 Jun 2016 | 07 Jul 2016 |  |  | 8 | 0 | 0 | 0
A1-6th Floor G.I. F.D. with frame(M+L) | 46.5 | Sft. | 29 Jun 2016 | 07 Jul 2016 | 19 Jan 2016 |  | 8 | 0 | 0 | 0
A1-7TH FLOOR | 0 | No Unit | 08 Jul 2016 | 16 Jul 2016 |  |  | 8 | 0 | 0 | 0
A1-7th Floor G.I. F.D. with frame(M+L) | 0 | Sft. | 08 Jul 2016 | 16 Jul 2016 | 15 Mar 2016 |  | 8 | 0 | 0 | 0
A1-8TH FLOOR | 0 | No Unit | 18 Jul 2016 | 26 Jul 2016 |  |  | 8 | 0 | 0 | 0
A1-8th Floor G.I. F.D. with frame(M+L) | 46.5 | Sft. | 18 Jul 2016 | 26 Jul 2016 | 15 Mar 2016 |  | 8 | 0 | 0 | 0
A1-9TH FLOOR | 0 | No Unit | 27 Jul 2016 | 04 Aug 2016 |  |  | 8 | 0 | 0 | 0
A1-9th Floor G.I. F.D. with frame(M+L) | 0 | Sft. | 27 Jul 2016 | 04 Aug 2016 | 15 Mar 2016 |  | 8 | 0 | 0 | 0
A1-10TH FLOOR | 0 | No Unit | 05 Aug 2016 | 13 Aug 2016 |  |  | 8 | 0 | 0 | 0
A1-10th Floor G.I. F.D. with frame(M+L) | 46.5 | Sft. | 05 Aug 2016 | 13 Aug 2016 | 15 Mar 2016 |  | 8 | 0 | 0 | 0
A1-11TH FLOOR | 0 | No Unit | 16 Aug 2016 | 24 Aug 2016 |  |  | 8 | 0 | 0 | 0
A1-11th Floor G.I. F.D. with frame(M+L) | 0 | Sft. | 16 Aug 2016 | 24 Aug 2016 | 17 Aug 2016 |  | 8 | 0 | 1 | 0
A1-12TH FLOOR | 0 | No Unit | 25 Aug 2016 | 02 Sep 2016 |  |  | 8 | 0 | 0 | 0
A1-12th Floor G.I. F.D. with frame(M+L) | 46.5 | Sft. | 25 Aug 2016 | 02 Sep 2016 | 17 Aug 2016 |  | 8 | 0 | 0 | 0
A1-13TH FLOOR | 0 | No Unit | 03 Sep 2016 | 12 Sep 2016 |  |  | 9 | 0 | 0 | 0
A1-13th Floor G.I. F.D. with frame(M+L) | 0 | Sft. | 03 Sep 2016 | 12 Sep 2016 | 12 Nov 2016 |  | 9 | 0 | 70 | 0
A1-14TH FLOOR | 0 | No Unit | 13 Sep 2016 | 21 Sep 2016 |  |  | 8 | 0 | 0 | 0
A1-14th Floor G.I. F.D. with frame(M+L) | 46.5 | Sft. | 13 Sep 2016 | 21 Sep 2016 | 12 Nov 2016 | 30 Jan 2017 | 8 | 79 | 60 | 131
A1-ALUMINIUM WORK | 0 | No Unit | 20 Apr 2016 | 07 Nov 2016 |  |  | 201 | 0 | 0 | 0
A1-ALU. DOOR (M+L) | 0 | No Unit | 20 Apr 2016 | 07 Nov 2016 |  |  | 201 | 0 | 0 | 0
A1-1ST FLOOR | 0 | No Unit | 20 Apr 2016 | 03 May 2016 |  |  | 13 | 0 | 0 | 0
A1-1st Floor Aluminium Door (M+L) | 155 | Sft. | 20 Apr 2016 | 03 May 2016 | 15 Jun 2016 | 25 Jan 2017 | 13 | 224 | 56 | 267
A1-2ND FLOOR | 0 | No Unit | 04 May 2016 | 17 May 2016 |  |  | 13 | 0 | 0 | 0
A1-2nd Floor Aluminium Door (M+L) | 155 | Sft. | 04 May 2016 | 17 May 2016 | 15 Jun 2016 | 23 Nov 2016 | 13 | 161 | 42 | 190
A1-3RD FLOOR | 0 | No Unit | 18 May 2016 | 31 May 2016 |  |  | 13 | 0 | 0 | 0
A1-3rd Floor Aluminium Door (M+L) | 155 | Sft. | 18 May 2016 | 31 May 2016 | 15 Jun 2016 | 23 Nov 2016 | 13 | 161 | 28 | 176
A1-4TH FLOOR | 0 | No Unit | 01 Jun 2016 | 14 Jun 2016 |  |  | 13 | 0 | 0 | 0
A1-4th Floor Aluminium Door (M+L) | 155 | Sft. | 01 Jun 2016 | 14 Jun 2016 | 17 Jun 2016 | 23 Nov 2016 | 13 | 159 | 16 | 162
A1-5TH FLOOR | 0 | No Unit | 15 Jun 2016 | 28 Jun 2016 |  |  | 13 | 0 | 0 | 0
A1-5th Floor Aluminium Door (M+L) | 155 | Sft. | 15 Jun 2016 | 28 Jun 2016 | 17 Jun 2016 | 23 Nov 2016 | 13 | 159 | 2 | 148
A1-6TH FLOOR | 0 | No Unit | 29 Jun 2016 | 12 Jul 2016 |  |  | 13 | 0 | 0 | 0
A1-6th Floor Aluminium Door (M+L) | 155 | Sft. | 29 Jun 2016 | 12 Jul 2016 | 17 Jun 2016 | 23 Nov 2016 | 13 | 159 | 0 | 134
A1-7TH FLOOR | 0 | No Unit | 13 Jul 2016 | 26 Jul 2016 |  |  | 13 | 0 | 0 | 0
A1-7th Floor Aluminium Door (M+L) | 155 | Sft. | 13 Jul 2016 | 26 Jul 2016 | 09 Aug 2016 | 23 Nov 2016 | 13 | 106 | 27 | 120
A1-8TH FLOOR | 0 | No Unit | 27 Jul 2016 | 09 Aug 2016 |  |  | 13 | 0 | 0 | 0
A1-8th Floor Aluminium Door (M+L) | 155 | Sft. | 27 Jul 2016 | 09 Aug 2016 | 09 Aug 2016 | 23 Nov 2016 | 13 | 106 | 13 | 106
A1-9TH FLOOR | 0 | No Unit | 10 Aug 2016 | 24 Aug 2016 |  |  | 14 | 0 | 0 | 0
A1-9th Floor Aluminium Door (M+L) | 155 | Sft. | 10 Aug 2016 | 24 Aug 2016 | 09 Aug 2016 | 23 Nov 2016 | 14 | 106 | 0 | 91
A1-10TH FLOOR | 0 | No Unit | 25 Aug 2016 | 07 Sep 2016 |  |  | 13 | 0 | 0 | 0
A1-10th Floor Aluminium Door (M+L) | 155 | Sft. | 25 Aug 2016 | 07 Sep 2016 | 05 Oct 2016 | 23 Nov 2016 | 13 | 49 | 41 | 77
A1-11TH FLOOR | 0 | No Unit | 08 Sep 2016 | 21 Sep 2016 |  |  | 13 | 0 | 0 | 0
A1-11th Floor Aluminium Door (M+L) | 155 | Sft. | 08 Sep 2016 | 21 Sep 2016 | 08 Sep 2016 | 25 Jan 2017 | 13 | 139 | 0 | 126
A1-12TH FLOOR | 0 | No Unit | 22 Sep 2016 | 05 Oct 2016 |  |  | 13 | 0 | 0 | 0
A1-12th Floor Aluminium Door (M+L) | 155 | Sft. | 22 Sep 2016 | 05 Oct 2016 | 22 Sep 2016 | 25 Jan 2017 | 13 | 125 | 0 | 112
A1-13TH FLOOR | 0 | No Unit | 06 Oct 2016 | 19 Oct 2016 |  |  | 13 | 0 | 0 | 0
A1-13th Floor Aluminium Door (M+L) | 155 | Sft. | 06 Oct 2016 | 19 Oct 2016 | 06 Dec 2016 | 25 Jan 2017 | 13 | 50 | 61 | 98
A1-14TH FLOOR | 0 | No Unit | 20 Oct 2016 | 02 Nov 2016 |  |  | 13 | 0 | 0 | 0
A1-14th Floor Aluminium Door (M+L) | 77 | Sft. | 20 Oct 2016 | 02 Nov 2016 | 30 Jan 2017 | 30 Jan 2017 | 13 | 0 | 102 | 89
A1-TERRACE FLOOR | 0 | No Unit | 03 Nov 2016 | 07 Nov 2016 |  |  | 4 | 0 | 0 | 0
A1-Terrace Floor Aluminium Door (M+L) | 0 | Sft. | 03 Nov 2016 | 07 Nov 2016 | 30 Jan 2017 |  | 4 | 0 | 88 | 0
A1-ALUMINIUM WINDOW & LOUVERS | 0 | No Unit | 20 Apr 2016 | 04 Nov 2016 |  |  | 198 | 0 | 0 | 0
A1-PARKING | 0 | No Unit | 21 Jun 2016 | 24 Jun 2016 |  |  | 3 | 0 | 0 | 0
A1-Parking Alu.Louvers for common Toilet (M+L) | 6 | Sft. | 21 Jun 2016 | 22 Jun 2016 | 25 Jan 2017 | 25 Jan 2017 | 1 | 0 | 218 | 217
A1-Parking Alu.Louvers for Ele. Duct (M+L) | 0 | Sft. | 23 Jun 2016 | 24 Jun 2016 | 25 Jan 2017 | 25 Jan 2017 | 1 | 0 | 216 | 215
A1-1ST FL | 0 | No Unit | 20 Apr 2016 | 20 May 2016 |  |  | 30 | 0 | 0 | 0
A1-1st Fl Alu. Window & lou. (P.C) (M+L) | 423.84 | Sft. | 20 Apr 2016 | 03 May 2016 | 15 Jun 2016 | 25 Jan 2017 | 13 | 224 | 56 | 267
A1-1st Fl Alu.Window for Fire Stair (M+L) | 22.5 | Sft. | 19 May 2016 | 20 May 2016 | 15 Jun 2016 |  | 1 | 0 | 27 | 0
A1-1st Fl Alu.Louvers for Ele. Duct (M+L) | 9 | Sft. | 19 May 2016 | 20 May 2016 | 15 Jun 2016 |  | 1 | 0 | 27 | 0
A1-2ND FL | 0 | No Unit | 04 May 2016 | 23 May 2016 |  |  | 19 | 0 | 0 | 0
A1-2nd Fl Alu. Window & lou. (P.C) (M+L) | 389.82 | Sft. | 04 May 2016 | 17 May 2016 | 15 Jun 2016 | 23 Nov 2016 | 13 | 161 | 42 | 190
A1-2nd Fl Alu.Window for Fire Stair (M+L) | 22.5 | Sft. | 21 May 2016 | 23 May 2016 | 15 Jun 2016 |  | 2 | 0 | 25 | 0
A1-2nd Fl Alu.Louvers for Ele. Duct (M+L) | 9 | Sft. | 21 May 2016 | 23 May 2016 | 15 Jun 2016 |  | 2 | 0 | 25 | 0
A1-3RD FL | 0 | No Unit | 18 May 2016 | 31 May 2016 |  |  | 13 | 0 | 0 | 0
A1-3rd Fl Alu. Window & lou. (P.C) (M+L) | 423.84 | Sft. | 18 May 2016 | 31 May 2016 | 15 Jun 2016 | 23 Nov 2016 | 13 | 161 | 28 | 176
A1-3rd Fl Alu.Window for Fire Stair (M+L) | 22.5 | Sft. | 24 May 2016 | 25 May 2016 | 15 Jun 2016 |  | 1 | 0 | 22 | 0
A1-3rd Fl Alu.Louvers for Ele. Duct (M+L) | 9.5625 | Sft. | 24 May 2016 | 25 May 2016 | 15 Jun 2016 |  | 1 | 0 | 22 | 0
A1-4TH FL | 0 | No Unit | 26 May 2016 | 14 Jun 2016 |  |  | 19 | 0 | 0 | 0
A1-4th Fl Alu. Window & lou. (P.C) (M+L) | 389.82 | Sft. | 01 Jun 2016 | 14 Jun 2016 | 17 Jun 2016 | 23 Nov 2016 | 13 | 159 | 16 | 162
A1-4th Fl Alu.Window for Fire Stair (M+L) | 22 | Sft. | 26 May 2016 | 27 May 2016 | 25 Jan 2017 |  | 1 | 0 | 244 | 0
A1-4th Fl Alu.Louvers for Ele. Duct (M+L) | 9.5625 | Sft. | 26 May 2016 | 27 May 2016 | 25 Jan 2017 |  | 1 | 0 | 244 | 0
A1-5TH FL | 0 | No Unit | 28 May 2016 | 28 Jun 2016 |  |  | 31 | 0 | 0 | 0
A1-5th Fl Alu. Window & lou. (P.C) (M+L) | 423.84 | Sft. | 15 Jun 2016 | 28 Jun 2016 | 17 Jun 2016 | 23 Nov 2016 | 13 | 159 | 2 | 148
A1-5th Fl Alu.Window for Fire Stair (M+L) | 22 | Sft. | 28 May 2016 | 30 May 2016 | 25 Jan 2017 |  | 2 | 0 | 242 | 0
A1-5th Fl Alu.Louvers for Ele. Duct (M+L) | 9.5625 | Sft. | 28 May 2016 | 30 May 2016 | 25 Jan 2017 |  | 2 | 0 | 242 | 0
A1-6TH FL | 0 | No Unit | 31 May 2016 | 12 Jul 2016 |  |  | 42 | 0 | 0 | 0
A1-6th Fl Alu. Window & lou. (P.C) (M+L) | 389.82 | Sft. | 29 Jun 2016 | 12 Jul 2016 | 17 Jun 2016 | 23 Nov 2016 | 13 | 159 | 0 | 134
A1-6th Fl Alu.Window for Fire Stair (M+L) | 22 | Sft. | 31 May 2016 | 01 Jun 2016 | 25 Jan 2017 |  | 1 | 0 | 239 | 0
A1-6th Fl Alu.Louvers for Ele. Duct (M+L) | 9.5625 | Sft. | 31 May 2016 | 01 Jun 2016 | 25 Jan 2017 |  | 1 | 0 | 239 | 0
A1-7TH FL | 0 | No Unit | 02 Jun 2016 | 26 Jul 2016 |  |  | 54 | 0 | 0 | 0
A1-7th Fl Alu. Window & lou. (P.C) (M+L) | 423.84 | Sft. | 13 Jul 2016 | 26 Jul 2016 | 09 Aug 2016 | 23 Nov 2016 | 13 | 106 | 27 | 120
A1-7th Fl Alu.Window for Fire Stair (M+L) | 22 | Sft. | 02 Jun 2016 | 03 Jun 2016 | 25 Jan 2017 |  | 1 | 0 | 237 | 0
A1-7th Fl Alu.Louvers for Ele. Duct (M+L) | 9.5625 | Sft. | 02 Jun 2016 | 03 Jun 2016 | 25 Jan 2017 |  | 1 | 0 | 237 | 0
A1-8TH FL | 0 | No Unit | 04 Jun 2016 | 09 Aug 2016 |  |  | 66 | 0 | 0 | 0
A1-8th Fl Alu. Window & lou. (P.C) (M+L) | 389.82 | Sft. | 27 Jul 2016 | 09 Aug 2016 | 09 Aug 2016 | 23 Nov 2016 | 13 | 106 | 13 | 106
A1-8th Fl Alu.Window for Fire Stair (M+L) | 22 | Sft. | 04 Jun 2016 | 06 Jun 2016 | 25 Jan 2017 |  | 2 | 0 | 235 | 0
A1-8th Fl Alu.Louvers for Ele. Duct (M+L) | 9.5625 | Sft. | 04 Jun 2016 | 06 Jun 2016 | 25 Jan 2017 |  | 2 | 0 | 235 | 0
A1-9TH FL | 0 | No Unit | 07 Jun 2016 | 24 Aug 2016 |  |  | 78 | 0 | 0 | 0
A1-9th Fl Alu. Window & lou. (P.C) (M+L) | 423.84 | Sft. | 10 Aug 2016 | 24 Aug 2016 | 09 Aug 2016 | 23 Nov 2016 | 14 | 106 | 0 | 91
A1-9th Fl Alu.Window for Fire Stair (M+L) | 22.5 | Sft. | 07 Jun 2016 | 08 Jun 2016 | 25 Jan 2017 |  | 1 | 0 | 232 | 0
A1-9th Fl Alu.Louvers for Ele. Duct (M+L) | 9 | Sft. | 07 Jun 2016 | 08 Jun 2016 | 25 Jan 2017 |  | 1 | 0 | 232 | 0
A1-10TH FL | 1 | No Unit | 09 Jun 2016 | 07 Sep 2016 |  |  | 90 | 0 | 0 | 0
A1-10th Fl Alu. Window & lou. (P.C) (M+L) | 389.82 | Sft. | 25 Aug 2016 | 07 Sep 2016 | 25 Jan 2017 | 25 Jan 2017 | 13 | 0 | 153 | 140
A1-10th Fl Alu.Window for Fire Stair (M+L) | 22.5 | Sft. | 09 Jun 2016 | 10 Jun 2016 | 05 Oct 2016 |  | 1 | 0 | 118 | 0
A1-10th Fl Alu.Louvers for Ele. Duct (M+L) | 9 | Sft. | 09 Jun 2016 | 10 Jun 2016 | 05 Oct 2016 |  | 1 | 0 | 118 | 0
A1-11TH FL | 1 | No Unit | 11 Jun 2016 | 21 Sep 2016 |  |  | 102 | 0 | 0 | 0
A1-11th Fl Alu. Window & lou. (P.C) (M+L) | 423.84 | Sft. | 08 Sep 2016 | 21 Sep 2016 | 25 Jan 2017 | 25 Jan 2017 | 13 | 0 | 139 | 126
A1-11th Fl Alu.Window for Fire Stair (M+L) | 22.5 | Sft. | 11 Jun 2016 | 13 Jun 2016 | 25 Jan 2017 |  | 2 | 0 | 228 | 0
A1-11th Fl Alu.Louvers for Ele. Duct (M+L) | 9 | Sft. | 11 Jun 2016 | 13 Jun 2016 | 25 Jan 2017 |  | 2 | 0 | 228 | 0
A1-12TH FL | 1 | No Unit | 14 Jun 2016 | 05 Oct 2016 |  |  | 113 | 0 | 0 | 0
A1-12th Fl Alu. Window & lou. (P.C) (M+L) | 389.82 | Sft. | 22 Sep 2016 | 05 Oct 2016 | 25 Jan 2017 | 25 Jan 2017 | 13 | 0 | 125 | 112
A1-12th Fl Alu.Window for Fire Stair (M+L) | 22.5 | Sft. | 14 Jun 2016 | 15 Jun 2016 | 25 Jan 2017 |  | 1 | 0 | 225 | 0
A1-12th Fl Alu.Louvers for Ele. Duct (M+L) | 9 | Sft. | 14 Jun 2016 | 15 Jun 2016 | 25 Jan 2017 |  | 1 | 0 | 225 | 0
A1-13TH FL | 1 | No Unit | 16 Jun 2016 | 19 Oct 2016 |  |  | 125 | 0 | 0 | 0
A1-13th Fl Alu. Window & lou. (P.C) (M+L) | 423.84 | Sft. | 06 Oct 2016 | 19 Oct 2016 | 25 Jan 2017 | 25 Jan 2017 | 13 | 0 | 111 | 98
A1-13th Fl Alu.Window for Fire Stair (M+L) | 22.5 | Sft. | 16 Jun 2016 | 17 Jun 2016 | 25 Jan 2017 |  | 1 | 0 | 223 | 0
A1-13th Fl Alu.Louvers for Ele. Duct (M+L) | 9 | Sft. | 16 Jun 2016 | 17 Jun 2016 | 25 Jan 2017 |  | 1 | 0 | 223 | 0
A1-14TH FL | 1 | No Unit | 18 Jun 2016 | 02 Nov 2016 |  |  | 137 | 0 | 0 | 0
A1-14th Fl Alu. Window & lou. (P.C) (M+L) | 194.91 | Sft. | 20 Oct 2016 | 02 Nov 2016 |  |  | 13 | 0 | 0 | 0
A1-14th Fl Alu.Window for Fire Stair (M+L) | 22.5 | Sft. | 18 Jun 2016 | 20 Jun 2016 | 25 Jan 2017 |  | 2 | 0 | 221 | 0
A1-14th Fl Alu.Louvers for Ele. Duct (M+L) | 11.62 | Sft. | 18 Jun 2016 | 20 Jun 2016 | 25 Jan 2017 |  | 2 | 0 | 221 | 0
A1-TERRACE FLOOR | 0 | No Unit | 03 Nov 2016 | 04 Nov 2016 |  |  | 1 | 0 | 0 | 0
A1-Terrace Floor Alu.Window for Fire Stair (M+L) | 25 | Sft. | 03 Nov 2016 | 04 Nov 2016 | 25 Jan 2017 |  | 1 | 0 | 83 | 0
A1-Terrace Floor Alu.Louvers for LMR (M+L) | 12 | Sft. | 03 Nov 2016 | 04 Nov 2016 | 25 Jan 2017 | 25 Jan 2017 | 1 | 0 | 83 | 82
A1-PAINTING (M+L) | 0 | No Unit | 16 Mar 2016 | 22 Dec 2016 |  |  | 281 | 0 | 0 | 0
A1- INTERNAL PAINTING | 1 | No Unit | 16 Mar 2016 | 22 Dec 2016 |  |  | 281 | 0 | 0 | 0
A1-PARKING | 0 | No Unit | 17 Jun 2016 | 13 Jul 2016 |  |  | 26 | 0 | 0 | 0
A1-Parking OBD Paint (M+L) | 56695 | Sft. | 17 Jun 2016 | 04 Jul 2016 | 23 Aug 2016 |  | 17 | 0 | 67 | 0
A1-Parking Fire Stair OBD Paint(M+L) | 56695 | Sft. | 17 Jun 2016 | 04 Jul 2016 | 13 Jul 2016 |  | 17 | 0 | 26 | 0
A1-Parking Fire Stair Oil Paint(M+L) | 0 | Sft. | 17 Jun 2016 | 04 Jul 2016 | 23 Nov 2016 |  | 17 | 0 | 159 | 0
A1-Parking Main Stair OBD Paint(M+L) | 56695 | Sft. | 17 Jun 2016 | 04 Jul 2016 | 08 Sep 2016 |  | 17 | 0 | 83 | 0
A1-Parking Main Stair Oil Paint(M+L) | 0 | Sft. | 17 Jun 2016 | 04 Jul 2016 | 23 Nov 2016 |  | 17 | 0 | 159 | 0
A- ENTRACNE LOBBY | 0 | No Unit | 05 Jul 2016 | 13 Jul 2016 |  |  | 8 | 0 | 0 | 0
A- Entracne Lobby Luster Paint (M+L) | 56695 | Sft. | 05 Jul 2016 | 13 Jul 2016 | 23 Nov 2016 |  | 8 | 0 | 141 | 0
A- Entracne Lobby Artistic Paint (M+L) | 0 | Sft. | 05 Jul 2016 | 13 Jul 2016 | 23 Nov 2016 |  | 8 | 0 | 141 | 0
A1- 1ST FLOOR | 0 | No Unit | 16 Mar 2016 | 13 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1-FLAT 101 | 0 | No Unit | 16 Mar 2016 | 13 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1-Flat 101 OBD Paint (M+L) | 56695 | Sft. | 16 Mar 2016 | 13 Aug 2016 | 31 Mar 2016 | 05 Jan 2017 | 150 | 280 | 15 | 145
A1-Flat 101 Oil Paint (M+L) | 56695 | Sft. | 16 Mar 2016 | 13 Aug 2016 | 31 Mar 2016 | 05 Jan 2017 | 150 | 280 | 15 | 145
A1-FLAT 102 | 0 | No Unit | 16 Mar 2016 | 13 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1-Flat 102 OBD Paint (M+L) | 56695 | Sft. | 16 Mar 2016 | 13 Aug 2016 | 31 Mar 2016 | 08 Sep 2016 | 150 | 161 | 15 | 26
A1-Flat 102 Oil Paint (M+L) | 56695 | Sft. | 16 Mar 2016 | 13 Aug 2016 | 31 Mar 2016 | 08 Sep 2016 | 150 | 161 | 15 | 26
A1-FLAT 103 | 0 | No Unit | 16 Mar 2016 | 13 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1-Flat 103 OBD Paint (M+L) | 56695 | Sft. | 16 Mar 2016 | 13 Aug 2016 | 31 Mar 2016 | 08 Sep 2016 | 150 | 161 | 15 | 26
A1-Flat 103 Oil Paint (M+L) | 56695 | Sft. | 16 Mar 2016 | 13 Aug 2016 | 31 Mar 2016 | 08 Sep 2016 | 150 | 161 | 15 | 26
A1-FLAT 104 | 0 | No Unit | 16 Mar 2016 | 13 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1-Flat 104 OBD Paint (M+L) | 56695 | Sft. | 16 Mar 2016 | 13 Aug 2016 | 31 Mar 2016 | 23 Nov 2016 | 150 | 237 | 15 | 102
A1-Flat 104 Oil Paint (M+L) | 56695 | Sft. | 16 Mar 2016 | 13 Aug 2016 | 31 Mar 2016 | 05 Jan 2017 | 150 | 280 | 15 | 145
A1- 1ST COMMON AREA | 0 | No Unit | 06 Jun 2016 | 16 Jun 2016 |  |  | 10 | 0 | 0 | 0
A1- 1ST.FL. FLOOR LOBBY | 0 | No Unit | 06 Jun 2016 | 16 Jun 2016 |  |  | 10 | 0 | 0 | 0
A1- 1st.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 06 Jun 2016 | 16 Jun 2016 | 31 Aug 2016 | 30 Jan 2017 | 10 | 152 | 86 | 228
A1-1ST.FL. MAIN STAIRCASE | 0 | No Unit | 06 Jun 2016 | 16 Jun 2016 |  |  | 10 | 0 | 0 | 0
A1-1st.fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 06 Jun 2016 | 16 Jun 2016 | 07 Sep 2016 | 30 Jan 2017 | 10 | 145 | 93 | 228
A1-1ST.FL. FIRE STAIRCASE | 0 | No Unit | 06 Jun 2016 | 16 Jun 2016 |  |  | 10 | 0 | 0 | 0
A1-1st.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 06 Jun 2016 | 16 Jun 2016 | 13 Jul 2016 | 30 Jan 2017 | 10 | 201 | 37 | 228
A1- 2ND FLOOR | 0 | No Unit | 25 Mar 2016 | 22 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1-FLAT 201 | 0 | No Unit | 25 Mar 2016 | 22 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1-Flat 201 OBD Paint (M+L) | 56695 | Sft. | 25 Mar 2016 | 22 Aug 2016 | 31 Mar 2016 | 23 Nov 2016 | 150 | 237 | 6 | 93
A1-Flat 201 Oil Paint (M+L) | 56695 | Sft. | 25 Mar 2016 | 22 Aug 2016 | 31 Mar 2016 | 22 Sep 2016 | 150 | 175 | 6 | 31
A1-FLAT 202 | 0 | No Unit | 25 Mar 2016 | 22 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1-Flat 202 OBD Paint (M+L) | 56695 | Sft. | 25 Mar 2016 | 22 Aug 2016 | 31 Mar 2016 | 08 Sep 2016 | 150 | 161 | 6 | 17
A1-Flat 202 Oil Paint (M+L) | 56695 | Sft. | 25 Mar 2016 | 22 Aug 2016 | 31 Mar 2016 | 08 Sep 2016 | 150 | 161 | 6 | 17
A1-FLAT 203 | 0 | No Unit | 25 Mar 2016 | 22 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1-Flat 203 OBD Paint (M+L) | 56695 | Sft. | 25 Mar 2016 | 22 Aug 2016 | 31 Mar 2016 | 07 Sep 2016 | 150 | 160 | 6 | 16
A1-Flat 203 Oil Paint (M+L) | 56695 | Sft. | 25 Mar 2016 | 22 Aug 2016 | 31 Mar 2016 | 08 Sep 2016 | 150 | 161 | 6 | 17
A1-FLAT 204 | 0 | No Unit | 25 Mar 2016 | 22 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1-Flat 204 OBD Paint (M+L) | 56695 | Sft. | 25 Mar 2016 | 22 Aug 2016 | 31 Mar 2016 | 23 Nov 2016 | 150 | 237 | 6 | 93
A1-Flat 204 Oil Paint (M+L) | 56695 | Sft. | 25 Mar 2016 | 22 Aug 2016 | 31 Mar 2016 | 22 Sep 2016 | 150 | 175 | 6 | 31
A1- 2ND COMMON AREA | 0 | No Unit | 17 Jun 2016 | 28 Jun 2016 |  |  | 11 | 0 | 0 | 0
A- 2ND.FL. FLOOR LOBBY | 0 | No Unit | 17 Jun 2016 | 28 Jun 2016 |  |  | 11 | 0 | 0 | 0
A- 2nd.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 17 Jun 2016 | 28 Jun 2016 | 31 Aug 2016 | 30 Jan 2017 | 11 | 152 | 75 | 216
A-2ND.FL. MAIN STAIRCASE | 0 | No Unit | 17 Jun 2016 | 28 Jun 2016 |  |  | 11 | 0 | 0 | 0
A-2nd.fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 17 Jun 2016 | 28 Jun 2016 | 07 Sep 2016 | 30 Jan 2017 | 11 | 145 | 82 | 216
A-2ND.FL. FIRE STAIRCASE | 0 | No Unit | 17 Jun 2016 | 28 Jun 2016 |  |  | 11 | 0 | 0 | 0
A-2nd.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 17 Jun 2016 | 28 Jun 2016 | 13 Jul 2016 | 30 Jan 2017 | 11 | 201 | 26 | 216
A1- 3RD FLOOR | 0 | No Unit | 06 Apr 2016 | 31 Aug 2016 |  |  | 147 | 0 | 0 | 0
A1-FLAT 301 | 0 | No Unit | 06 Apr 2016 | 31 Aug 2016 |  |  | 147 | 0 | 0 | 0
A1-Flat 301 OBD Paint (M+L) | 56695 | Sft. | 06 Apr 2016 | 31 Aug 2016 | 31 Mar 2016 | 23 Nov 2016 | 147 | 237 | 0 | 84
A1-Flat 301 Oil Paint (M+L) | 56695 | Sft. | 06 Apr 2016 | 31 Aug 2016 | 31 Mar 2016 | 22 Sep 2016 | 147 | 175 | 0 | 22
A1-FLAT 302 | 0 | No Unit | 06 Apr 2016 | 31 Aug 2016 |  |  | 147 | 0 | 0 | 0
A1-Flat 302 OBD Paint (M+L) | 56695 | Sft. | 06 Apr 2016 | 31 Aug 2016 | 31 Mar 2016 | 08 Sep 2016 | 147 | 161 | 0 | 8
A1-Flat 302 Oil Paint (M+L) | 56695 | Sft. | 06 Apr 2016 | 31 Aug 2016 | 31 Mar 2016 | 08 Sep 2016 | 147 | 161 | 0 | 8
A1-FLAT 303 | 0 | No Unit | 06 Apr 2016 | 31 Aug 2016 |  |  | 147 | 0 | 0 | 0
A1-Flat 303 OBD Paint (M+L) | 56695 | Sft. | 06 Apr 2016 | 31 Aug 2016 | 31 Mar 2016 | 08 Sep 2016 | 147 | 161 | 0 | 8
A1-Flat 303 Oil Paint (M+L) | 56695 | Sft. | 06 Apr 2016 | 31 Aug 2016 | 31 Mar 2016 | 08 Sep 2016 | 147 | 161 | 0 | 8
A1-FLAT 304 | 0 | No Unit | 06 Apr 2016 | 31 Aug 2016 |  |  | 147 | 0 | 0 | 0
A1-Flat 304 OBD Paint (M+L) | 56695 | Sft. | 06 Apr 2016 | 31 Aug 2016 | 31 Mar 2016 | 23 Nov 2016 | 147 | 237 | 0 | 84
A1-Flat 304 Oil Paint (M+L) | 56695 | Sft. | 06 Apr 2016 | 31 Aug 2016 | 31 Mar 2016 | 06 Dec 2016 | 147 | 250 | 0 | 97
A1- COMMON AREA | 0 | No Unit | 29 Jun 2016 | 09 Jul 2016 |  |  | 10 | 0 | 0 | 0
A- 3RD.FL. FLOOR LOBBY | 0 | No Unit | 29 Jun 2016 | 09 Jul 2016 |  |  | 10 | 0 | 0 | 0
A- 3rd.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 29 Jun 2016 | 09 Jul 2016 | 31 Aug 2016 | 30 Jan 2017 | 10 | 152 | 63 | 205
A-3RD.FL. MAIN STAIRCASE | 0 | No Unit | 29 Jun 2016 | 09 Jul 2016 |  |  | 10 | 0 | 0 | 0
A-3rd.fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 29 Jun 2016 | 09 Jul 2016 | 07 Sep 2016 | 30 Jan 2017 | 10 | 145 | 70 | 205
A-3RD.FL. FIRE STAIRCASE | 0 | No Unit | 29 Jun 2016 | 09 Jul 2016 |  |  | 10 | 0 | 0 | 0
A-3rd.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 29 Jun 2016 | 09 Jul 2016 | 13 Jul 2016 | 30 Jan 2017 | 10 | 201 | 14 | 205
A1- 4TH FLOOR | 0 | No Unit | 03 May 2016 | 10 Sep 2016 |  |  | 130 | 0 | 0 | 0
A1-FLAT 401 | 0 | No Unit | 03 May 2016 | 10 Sep 2016 |  |  | 130 | 0 | 0 | 0
A1-Flat 401 OBD Paint (M+L) | 56695 | Sft. | 03 May 2016 | 10 Sep 2016 | 31 Mar 2016 | 23 Nov 2016 | 130 | 237 | 0 | 74
A1-Flat 401 Oil Paint (M+L) | 56695 | Sft. | 03 May 2016 | 10 Sep 2016 | 31 Mar 2016 | 06 Dec 2016 | 130 | 250 | 0 | 87
A1-FLAT 402 | 0 | No Unit | 03 May 2016 | 10 Sep 2016 |  |  | 130 | 0 | 0 | 0
A1-Flat 402 OBD Paint (M+L) | 56695 | Sft. | 03 May 2016 | 10 Sep 2016 | 31 Mar 2016 | 08 Sep 2016 | 130 | 161 | 0 | 0
A1-Flat 402 Oil Paint (M+L) | 56695 | Sft. | 03 May 2016 | 10 Sep 2016 | 31 Mar 2016 | 08 Sep 2016 | 130 | 161 | 0 | 0
A1-FLAT 403 | 0 | No Unit | 03 May 2016 | 10 Sep 2016 |  |  | 130 | 0 | 0 | 0
A1-Flat 403 OBD Paint (M+L) | 56695 | Sft. | 03 May 2016 | 10 Sep 2016 | 31 Mar 2016 | 08 Sep 2016 | 130 | 161 | 0 | 0
A1-Flat 403 Oil Paint (M+L) | 56695 | Sft. | 03 May 2016 | 10 Sep 2016 | 31 Mar 2016 | 08 Sep 2016 | 130 | 161 | 0 | 0
A1-FLAT 404 | 0 | No Unit | 03 May 2016 | 10 Sep 2016 |  |  | 130 | 0 | 0 | 0
A1-Flat 404 OBD Paint (M+L) | 56695 | Sft. | 03 May 2016 | 10 Sep 2016 | 31 Mar 2016 | 23 Nov 2016 | 130 | 237 | 0 | 74
A1-Flat 404 Oil Paint (M+L) | 56695 | Sft. | 03 May 2016 | 10 Sep 2016 | 31 Mar 2016 | 06 Dec 2016 | 130 | 250 | 0 | 87
A1- COMMON AREA | 0 | No Unit | 11 Jul 2016 | 21 Jul 2016 |  |  | 10 | 0 | 0 | 0
A- 4TH.FL. FLOOR LOBBY | 0 | No Unit | 11 Jul 2016 | 21 Jul 2016 |  |  | 10 | 0 | 0 | 0
A- 4th.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 11 Jul 2016 | 21 Jul 2016 | 31 Aug 2016 | 30 Jan 2017 | 10 | 152 | 51 | 193
A-4TH.FL. MAIN STAIRCASE | 0 | No Unit | 11 Jul 2016 | 21 Jul 2016 |  |  | 10 | 0 | 0 | 0
A-4th.fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 11 Jul 2016 | 21 Jul 2016 | 07 Sep 2016 | 30 Jan 2017 | 10 | 145 | 58 | 193
A-4TH.FL. FIRE STAIRCASE | 0 | No Unit | 11 Jul 2016 | 21 Jul 2016 |  |  | 10 | 0 | 0 | 0
A-4th.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 11 Jul 2016 | 21 Jul 2016 | 13 Jul 2016 | 30 Jan 2017 | 10 | 201 | 2 | 193
A1- 5TH FLOOR | 0 | No Unit | 31 May 2016 | 19 Sep 2016 |  |  | 111 | 0 | 0 | 0
A1-FLAT 501 | 0 | No Unit | 31 May 2016 | 19 Sep 2016 |  |  | 111 | 0 | 0 | 0
A1-Flat 501 OBD Paint (M+L) | 56695 | Sft. | 31 May 2016 | 19 Sep 2016 | 09 Jun 2016 | 23 Nov 2016 | 111 | 167 | 9 | 65
A1-Flat 501 Oil Paint (M+L) | 56695 | Sft. | 31 May 2016 | 19 Sep 2016 | 09 Jun 2016 | 06 Dec 2016 | 111 | 180 | 9 | 78
A1-FLAT 502 | 0 | No Unit | 31 May 2016 | 19 Sep 2016 |  |  | 111 | 0 | 0 | 0
A1-Flat 502 OBD Paint (M+L) | 56695 | Sft. | 31 May 2016 | 19 Sep 2016 | 09 Jun 2016 | 23 Nov 2016 | 111 | 167 | 9 | 65
A1-Flat 502 Oil Paint (M+L) | 56695 | Sft. | 31 May 2016 | 19 Sep 2016 | 09 Jun 2016 | 06 Dec 2016 | 111 | 180 | 9 | 78
A1-FLAT 503 | 0 | No Unit | 31 May 2016 | 19 Sep 2016 |  |  | 111 | 0 | 0 | 0
A1-Flat 503 OBD Paint (M+L) | 56695 | Sft. | 31 May 2016 | 19 Sep 2016 | 09 Jun 2016 | 23 Nov 2016 | 111 | 167 | 9 | 65
A1-Flat 503 Oil Paint (M+L) | 56695 | Sft. | 31 May 2016 | 19 Sep 2016 | 09 Jun 2016 | 06 Dec 2016 | 111 | 180 | 9 | 78
A1-FLAT 504 | 0 | No Unit | 31 May 2016 | 19 Sep 2016 |  |  | 111 | 0 | 0 | 0
A1-Flat 504 OBD Paint (M+L) | 56695 | Sft. | 31 May 2016 | 19 Sep 2016 | 09 Jun 2016 | 23 Nov 2016 | 111 | 167 | 9 | 65
A1-Flat 504 Oil Paint (M+L) | 56695 | Sft. | 31 May 2016 | 19 Sep 2016 | 09 Jun 2016 | 06 Dec 2016 | 111 | 180 | 9 | 78
A1- COMMON AREA | 0 | No Unit | 22 Jul 2016 | 02 Aug 2016 |  |  | 11 | 0 | 0 | 0
A- 5TH.FL. FLOOR LOBBY | 0 | No Unit | 22 Jul 2016 | 02 Aug 2016 |  |  | 11 | 0 | 0 | 0
A- 5th.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 22 Jul 2016 | 02 Aug 2016 | 31 Aug 2016 | 30 Jan 2017 | 11 | 152 | 40 | 181
A-5THT.FL. MAIN STAIRCASE | 0 | No Unit | 22 Jul 2016 | 02 Aug 2016 |  |  | 11 | 0 | 0 | 0
A-5tht.fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 22 Jul 2016 | 02 Aug 2016 | 07 Sep 2016 | 30 Jan 2017 | 11 | 145 | 47 | 181
A-5TH.FL. FIRE STAIRCASE | 0 | No Unit | 22 Jul 2016 | 02 Aug 2016 |  |  | 11 | 0 | 0 | 0
A-5th.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 22 Jul 2016 | 02 Aug 2016 | 13 Jul 2016 | 30 Jan 2017 | 11 | 201 | 0 | 181
A1- 6TH FLOOR | 0 | No Unit | 06 Jun 2016 | 30 Sep 2016 |  |  | 116 | 0 | 0 | 0
A1-FLAT 601 | 0 | No Unit | 06 Jun 2016 | 30 Sep 2016 |  |  | 116 | 0 | 0 | 0
A1-Flat 601 OBD Paint (M+L) | 56695 | Sft. | 06 Jun 2016 | 30 Sep 2016 | 29 Apr 2016 | 30 Jan 2017 | 116 | 276 | 0 | 122
A1-Flat 601 Oil Paint (M+L) | 56695 | Sft. | 06 Jun 2016 | 30 Sep 2016 | 29 Apr 2016 | 30 Jan 2017 | 116 | 276 | 0 | 122
A1-FLAT 602 | 0 | No Unit | 06 Jun 2016 | 30 Sep 2016 |  |  | 116 | 0 | 0 | 0
A1-Flat 602 OBD Paint (M+L) | 56695 | Sft. | 06 Jun 2016 | 30 Sep 2016 | 09 Jun 2016 | 23 Nov 2016 | 116 | 167 | 3 | 54
A1-Flat 602 Oil Paint (M+L) | 56695 | Sft. | 06 Jun 2016 | 30 Sep 2016 | 09 Jun 2016 | 06 Dec 2016 | 116 | 180 | 3 | 67
A1-FLAT 603 | 0 | No Unit | 06 Jun 2016 | 30 Sep 2016 |  |  | 116 | 0 | 0 | 0
A1-Flat 603 OBD Paint (M+L) | 56695 | Sft. | 06 Jun 2016 | 30 Sep 2016 | 09 Jun 2016 | 23 Nov 2016 | 116 | 167 | 3 | 54
A1-Flat 603 Oil Paint (M+L) | 56695 | Sft. | 06 Jun 2016 | 30 Sep 2016 | 09 Jun 2016 | 06 Dec 2016 | 116 | 180 | 3 | 67
A1-FLAT 604 | 0 | No Unit | 06 Jun 2016 | 30 Sep 2016 |  |  | 116 | 0 | 0 | 0
A1-Flat 604 OBD Paint (M+L) | 56695 | Sft. | 06 Jun 2016 | 30 Sep 2016 | 09 Jun 2016 | 23 Nov 2016 | 116 | 167 | 3 | 54
A1-Flat 604 Oil Paint (M+L) | 56695 | Sft. | 06 Jun 2016 | 30 Sep 2016 | 09 Jun 2016 | 06 Dec 2016 | 116 | 180 | 3 | 67
A1- COMMON AREA | 0 | No Unit | 03 Aug 2016 | 13 Aug 2016 |  |  | 10 | 0 | 0 | 0
A- 6TH.FL. FLOOR LOBBY | 0 | No Unit | 03 Aug 2016 | 13 Aug 2016 |  |  | 10 | 0 | 0 | 0
A- 6th.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 03 Aug 2016 | 13 Aug 2016 | 07 Sep 2016 | 30 Jan 2017 | 10 | 145 | 35 | 170
A-6TH.FL. MAIN STAIRCASE | 0 | No Unit | 03 Aug 2016 | 13 Aug 2016 |  |  | 10 | 0 | 0 | 0
A-6th.fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 03 Aug 2016 | 13 Aug 2016 | 07 Sep 2016 | 30 Jan 2017 | 10 | 145 | 35 | 170
A-6TH.FL. FIRE STAIRCASE | 0 | No Unit | 03 Aug 2016 | 13 Aug 2016 |  |  | 10 | 0 | 0 | 0
A-6th.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 03 Aug 2016 | 13 Aug 2016 | 13 Jul 2016 | 30 Jan 2017 | 10 | 201 | 0 | 170
A1- 7TH FLOOR | 0 | No Unit | 15 Jun 2016 | 10 Oct 2016 |  |  | 117 | 0 | 0 | 0
A1-FLAT 701 | 0 | No Unit | 15 Jun 2016 | 10 Oct 2016 |  |  | 117 | 0 | 0 | 0
A1-Flat 701 OBD Paint (M+L) | 56695 | Sft. | 15 Jun 2016 | 10 Oct 2016 | 09 Jun 2016 | 23 Nov 2016 | 117 | 167 | 0 | 44
A1-Flat 701 Oil Paint (M+L) | 56695 | Sft. | 15 Jun 2016 | 10 Oct 2016 | 09 Jun 2016 | 06 Dec 2016 | 117 | 180 | 0 | 57
A1-FLAT 702 | 0 | No Unit | 15 Jun 2016 | 10 Oct 2016 |  |  | 117 | 0 | 0 | 0
A1-Flat 702 OBD Paint (M+L) | 56695 | Sft. | 15 Jun 2016 | 10 Oct 2016 | 09 Jun 2016 | 23 Nov 2016 | 117 | 167 | 0 | 44
A1-Flat 702 Oil Paint (M+L) | 56695 | Sft. | 15 Jun 2016 | 10 Oct 2016 | 09 Jun 2016 | 06 Dec 2016 | 117 | 180 | 0 | 57
A1-FLAT 703 | 0 | No Unit | 15 Jun 2016 | 10 Oct 2016 |  |  | 117 | 0 | 0 | 0
A1-Flat 703 OBD Paint (M+L) | 56695 | Sft. | 15 Jun 2016 | 10 Oct 2016 | 09 Jun 2016 | 23 Nov 2016 | 117 | 167 | 0 | 44
A1-Flat 703 Oil Paint (M+L) | 56695 | Sft. | 15 Jun 2016 | 10 Oct 2016 | 09 Jun 2016 | 06 Dec 2016 | 117 | 180 | 0 | 57
A1-FLAT 704 | 0 | No Unit | 15 Jun 2016 | 10 Oct 2016 |  |  | 117 | 0 | 0 | 0
A1-Flat 704 OBD Paint (M+L) | 56695 | Sft. | 15 Jun 2016 | 10 Oct 2016 | 09 Jun 2016 | 23 Nov 2016 | 117 | 167 | 0 | 44
A1-Flat 704 Oil Paint (M+L) | 56695 | Sft. | 15 Jun 2016 | 10 Oct 2016 | 09 Jun 2016 | 06 Dec 2016 | 117 | 180 | 0 | 57
A1- COMMON AREA | 0 | No Unit | 16 Aug 2016 | 26 Aug 2016 |  |  | 10 | 0 | 0 | 0
A- 7TH.FL. FLOOR LOBBY | 0 | No Unit | 16 Aug 2016 | 26 Aug 2016 |  |  | 10 | 0 | 0 | 0
A- 7th.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 16 Aug 2016 | 26 Aug 2016 | 07 Sep 2016 | 30 Jan 2017 | 10 | 145 | 22 | 157
A-7TH.FL. MAIN STAIRCASE | 0 | No Unit | 16 Aug 2016 | 26 Aug 2016 |  |  | 10 | 0 | 0 | 0
A-7th.fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 16 Aug 2016 | 26 Aug 2016 | 07 Sep 2016 | 30 Jan 2017 | 10 | 145 | 22 | 157
A-7TH.FL. FIRE STAIRCASE | 0 | No Unit | 16 Aug 2016 | 26 Aug 2016 |  |  | 10 | 0 | 0 | 0
A-7th.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 16 Aug 2016 | 26 Aug 2016 | 13 Jul 2016 | 30 Jan 2017 | 10 | 201 | 0 | 157
A1- 8TH FLOOR | 0 | No Unit | 11 Jul 2016 | 18 Oct 2016 |  |  | 99 | 0 | 0 | 0
A1-FLAT 801 | 0 | No Unit | 11 Jul 2016 | 18 Oct 2016 |  |  | 99 | 0 | 0 | 0
A1-Flat 801 OBD Paint (M+L) | 56695 | Sft. | 11 Jul 2016 | 18 Oct 2016 | 09 Jun 2016 | 23 Nov 2016 | 99 | 167 | 0 | 36
A1-Flat 801 Oil Paint (M+L) | 56695 | Sft. | 11 Jul 2016 | 18 Oct 2016 | 09 Jun 2016 | 06 Dec 2016 | 99 | 180 | 0 | 49
A1-FLAT 802 | 0 | No Unit | 11 Jul 2016 | 18 Oct 2016 |  |  | 99 | 0 | 0 | 0
A1-Flat 802 OBD Paint (M+L) | 56695 | Sft. | 11 Jul 2016 | 18 Oct 2016 | 28 Jun 2016 | 23 Nov 2016 | 99 | 148 | 0 | 36
A1-Flat 802 Oil Paint (M+L) | 56695 | Sft. | 11 Jul 2016 | 18 Oct 2016 | 28 Jun 2016 | 06 Dec 2016 | 99 | 161 | 0 | 49
A1-FLAT 803 | 0 | No Unit | 11 Jul 2016 | 18 Oct 2016 |  |  | 99 | 0 | 0 | 0
A1-Flat 803 OBD Paint (M+L) | 56695 | Sft. | 11 Jul 2016 | 18 Oct 2016 | 28 Jun 2016 | 23 Nov 2016 | 99 | 148 | 0 | 36
A1-Flat 803 Oil Paint (M+L) | 56695 | Sft. | 11 Jul 2016 | 18 Oct 2016 | 28 Jun 2016 | 06 Dec 2016 | 99 | 161 | 0 | 49
A1-REFUGE FLAT 804 | 0 | No Unit | 11 Jul 2016 | 18 Oct 2016 |  |  | 99 | 0 | 0 | 0
A1-Refuge Flat 804 OBD Paint (M+L) | 56695 | Sft. | 11 Jul 2016 | 18 Oct 2016 | 09 Jun 2016 | 23 Nov 2016 | 99 | 167 | 0 | 36
A1-Refuge Flat 804 Oil Paint (M+L) | 56695 | Sft. | 11 Jul 2016 | 18 Oct 2016 | 09 Jun 2016 | 30 Jan 2017 | 99 | 235 | 0 | 104
A1- COMMON AREA | 0 | No Unit | 27 Aug 2016 | 07 Sep 2016 |  |  | 11 | 0 | 0 | 0
A- 8TH.FL. FLOOR LOBBY | 0 | No Unit | 27 Aug 2016 | 07 Sep 2016 |  |  | 11 | 0 | 0 | 0
A- 8th.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 27 Aug 2016 | 07 Sep 2016 | 07 Sep 2016 | 30 Jan 2017 | 11 | 145 | 11 | 145
A-8TH.FL. MAIN STAIRCASE | 0 | No Unit | 27 Aug 2016 | 07 Sep 2016 |  |  | 11 | 0 | 0 | 0
A-8th.fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 27 Aug 2016 | 07 Sep 2016 | 07 Sep 2016 | 30 Jan 2017 | 11 | 145 | 11 | 145
A-8TH.FL. FIRE STAIRCASE | 0 | No Unit | 27 Aug 2016 | 07 Sep 2016 |  |  | 11 | 0 | 0 | 0
A-8th.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 27 Aug 2016 | 07 Sep 2016 | 13 Jul 2016 | 30 Jan 2017 | 11 | 201 | 0 | 145
A1- 9TH FLOOR | 0 | No Unit | 11 Aug 2016 | 29 Oct 2016 |  |  | 79 | 0 | 0 | 0
A1-FLAT 901 | 0 | No Unit | 11 Aug 2016 | 29 Oct 2016 |  |  | 79 | 0 | 0 | 0
A1-Flat 901 OBD Paint (M+L) | 56695 | Sft. | 11 Aug 2016 | 29 Oct 2016 | 28 Jun 2016 | 23 Nov 2016 | 79 | 148 | 0 | 25
A1-Flat 901 Oil Paint (M+L) | 56695 | Sft. | 11 Aug 2016 | 29 Oct 2016 | 28 Jun 2016 | 06 Dec 2016 | 79 | 161 | 0 | 38
A1-FLAT 902 | 0 | No Unit | 11 Aug 2016 | 29 Oct 2016 |  |  | 79 | 0 | 0 | 0
A1-Flat 902 OBD Paint (M+L) | 56695 | Sft. | 11 Aug 2016 | 29 Oct 2016 | 28 Jun 2016 | 23 Nov 2016 | 79 | 148 | 0 | 25
A1-Flat 902 Oil Paint (M+L) | 56695 | Sft. | 11 Aug 2016 | 29 Oct 2016 | 28 Jun 2016 | 06 Dec 2016 | 79 | 161 | 0 | 38
A1-FLAT 903 | 0 | No Unit | 11 Aug 2016 | 29 Oct 2016 |  |  | 79 | 0 | 0 | 0
A1-Flat 903 OBD Paint (M+L) | 56695 | Sft. | 11 Aug 2016 | 29 Oct 2016 | 28 Jun 2016 | 23 Nov 2016 | 79 | 148 | 0 | 25
A1-Flat 903 Oil Paint (M+L) | 56695 | Sft. | 11 Aug 2016 | 29 Oct 2016 | 28 Jun 2016 | 06 Dec 2016 | 79 | 161 | 0 | 38
A1-FLAT 904 | 0 | No Unit | 11 Aug 2016 | 29 Oct 2016 |  |  | 79 | 0 | 0 | 0
A1-Flat 904 OBD Paint (M+L) | 56695 | Sft. | 11 Aug 2016 | 29 Oct 2016 | 28 Jun 2016 | 23 Nov 2016 | 79 | 148 | 0 | 25
A1-Flat 904 Oil Paint (M+L) | 56695 | Sft. | 11 Aug 2016 | 29 Oct 2016 | 28 Jun 2016 | 06 Dec 2016 | 79 | 161 | 0 | 38
A1- COMMON AREA | 0 | No Unit | 08 Sep 2016 | 19 Sep 2016 |  |  | 11 | 0 | 0 | 0
A- 9TH.FL. FLOOR LOBBY | 0 | No Unit | 08 Sep 2016 | 19 Sep 2016 |  |  | 11 | 0 | 0 | 0
A- 9th.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 08 Sep 2016 | 19 Sep 2016 | 07 Sep 2016 | 30 Jan 2017 | 11 | 145 | 0 | 133
A-9TH FL. MAIN STAIRCASE | 0 | No Unit | 08 Sep 2016 | 19 Sep 2016 |  |  | 11 | 0 | 0 | 0
A-9th fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 08 Sep 2016 | 19 Sep 2016 | 07 Sep 2016 | 30 Jan 2017 | 11 | 145 | 0 | 133
A-9TH.FL. FIRE STAIRCASE | 0 | No Unit | 08 Sep 2016 | 19 Sep 2016 |  |  | 11 | 0 | 0 | 0
A-9th.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 08 Sep 2016 | 19 Sep 2016 | 07 Sep 2016 | 30 Jan 2017 | 11 | 145 | 0 | 133
A1- 10TH FLOOR | 0 | No Unit | 02 Sep 2016 | 10 Nov 2016 |  |  | 69 | 0 | 0 | 0
A1-FLAT 1001 | 0 | No Unit | 02 Sep 2016 | 10 Nov 2016 |  |  | 69 | 0 | 0 | 0
A1-Flat 1001 OBD Paint (M+L) | 56695 | Sft. | 02 Sep 2016 | 10 Nov 2016 | 27 Jul 2016 | 05 Jan 2017 | 69 | 162 | 0 | 56
A1-Flat 1001 Oil Paint (M+L) | 56695 | Sft. | 02 Sep 2016 | 10 Nov 2016 | 27 Jul 2016 | 06 Dec 2016 | 69 | 132 | 0 | 26
A1-FLAT 1002 | 0 | No Unit | 02 Sep 2016 | 10 Nov 2016 |  |  | 69 | 0 | 0 | 0
A1-Flat 1002 OBD Paint (M+L) | 56695 | Sft. | 02 Sep 2016 | 10 Nov 2016 | 13 Jul 2016 | 05 Jan 2017 | 69 | 176 | 0 | 56
A1-Flat 1002 Oil Paint (M+L) | 56695 | Sft. | 02 Sep 2016 | 10 Nov 2016 | 27 Jul 2016 | 06 Dec 2016 | 69 | 132 | 0 | 26
A1-FLAT 1003 | 0 | No Unit | 02 Sep 2016 | 10 Nov 2016 |  |  | 69 | 0 | 0 | 0
A1-Flat 1003 OBD Paint (M+L) | 56695 | Sft. | 02 Sep 2016 | 10 Nov 2016 | 27 Jul 2016 | 05 Jan 2017 | 69 | 162 | 0 | 56
A1-Flat 1003 Oil Paint (M+L) | 56695 | Sft. | 02 Sep 2016 | 10 Nov 2016 | 27 Jul 2016 | 06 Dec 2016 | 69 | 132 | 0 | 26
A1-FLAT 1004 | 0 | No Unit | 02 Sep 2016 | 10 Nov 2016 |  |  | 69 | 0 | 0 | 0
A1-Flat 1004 OBD Paint (M+L) | 56695 | Sft. | 02 Sep 2016 | 10 Nov 2016 | 27 Jul 2016 | 05 Jan 2017 | 69 | 162 | 0 | 56
A1-Flat 1004 Oil Paint (M+L) | 56695 | Sft. | 02 Sep 2016 | 10 Nov 2016 | 27 Jul 2016 | 06 Dec 2016 | 69 | 132 | 0 | 26
A1- COMMON AREA | 0 | No Unit | 20 Sep 2016 | 30 Sep 2016 |  |  | 10 | 0 | 0 | 0
A- 10TH.FL. FLOOR LOBBY | 0 | No Unit | 20 Sep 2016 | 30 Sep 2016 |  |  | 10 | 0 | 0 | 0
A- 10th.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 20 Sep 2016 | 30 Sep 2016 | 07 Sep 2016 | 30 Jan 2017 | 10 | 145 | 0 | 122
A-10TH.FL. MAIN STAIRCASE | 0 | No Unit | 20 Sep 2016 | 30 Sep 2016 |  |  | 10 | 0 | 0 | 0
A-10th.fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 20 Sep 2016 | 30 Sep 2016 | 07 Sep 2016 | 30 Jan 2017 | 10 | 145 | 0 | 122
A-10TH.FL. FIRE STAIRCASE | 0 | No Unit | 20 Sep 2016 | 30 Sep 2016 |  |  | 10 | 0 | 0 | 0
A-10th.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 20 Sep 2016 | 30 Sep 2016 | 07 Sep 2016 | 30 Jan 2017 | 10 | 145 | 0 | 122
A1- 11TH FLOOR | 0 | No Unit | 30 Sep 2016 | 26 Nov 2016 |  |  | 57 | 0 | 0 | 0
A1-FLAT 1101 | 0 | No Unit | 30 Sep 2016 | 26 Nov 2016 |  |  | 57 | 0 | 0 | 0
A1-Flat 1101 OBD Paint (M+L) | 56695 | Sft. | 30 Sep 2016 | 26 Nov 2016 | 09 Aug 2016 | 05 Jan 2017 | 57 | 149 | 0 | 40
A1-Flat 1101 Oil Paint (M+L) | 56695 | Sft. | 30 Sep 2016 | 26 Nov 2016 | 09 Aug 2016 | 05 Jan 2017 | 57 | 149 | 0 | 40
A1-FLAT 1102 | 0 | No Unit | 30 Sep 2016 | 26 Nov 2016 |  |  | 57 | 0 | 0 | 0
A1-Flat 1102 OBD Paint (M+L) | 56695 | Sft. | 30 Sep 2016 | 26 Nov 2016 | 09 Aug 2016 | 05 Jan 2017 | 57 | 149 | 0 | 40
A1-Flat 1102 Oil Paint (M+L) | 56695 | Sft. | 30 Sep 2016 | 26 Nov 2016 | 09 Aug 2016 | 05 Jan 2017 | 57 | 149 | 0 | 40
A1-FLAT 1103 | 0 | No Unit | 30 Sep 2016 | 26 Nov 2016 |  |  | 57 | 0 | 0 | 0
A1-Flat 1103 OBD Paint (M+L) | 56695 | Sft. | 30 Sep 2016 | 26 Nov 2016 | 09 Aug 2016 | 05 Jan 2017 | 57 | 149 | 0 | 40
A1-Flat 1103 Oil Paint (M+L) | 56695 | Sft. | 30 Sep 2016 | 26 Nov 2016 | 09 Aug 2016 | 05 Jan 2017 | 57 | 149 | 0 | 40
A1-FLAT 1104 | 0 | No Unit | 30 Sep 2016 | 26 Nov 2016 |  |  | 57 | 0 | 0 | 0
A1-Flat 1104 OBD Paint (M+L) | 56695 | Sft. | 30 Sep 2016 | 26 Nov 2016 | 09 Aug 2016 | 05 Jan 2017 | 57 | 149 | 0 | 40
A1-Flat 1104 Oil Paint (M+L) | 56695 | Sft. | 30 Sep 2016 | 26 Nov 2016 | 09 Aug 2016 | 05 Jan 2017 | 57 | 149 | 0 | 40
A1- COMMON AREA | 0 | No Unit | 01 Oct 2016 | 12 Oct 2016 |  |  | 11 | 0 | 0 | 0
A- 11TH.FL. FLOOR LOBBY | 0 | No Unit | 01 Oct 2016 | 12 Oct 2016 |  |  | 11 | 0 | 0 | 0
A- 11th.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 01 Oct 2016 | 12 Oct 2016 | 30 Jan 2017 | 30 Jan 2017 | 11 | 0 | 121 | 110
A-11TH.FL. MAIN STAIRCASE | 0 | No Unit | 01 Oct 2016 | 12 Oct 2016 |  |  | 11 | 0 | 0 | 0
A-11th.fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 01 Oct 2016 | 12 Oct 2016 | 30 Jan 2017 | 30 Jan 2017 | 11 | 0 | 121 | 110
A-11TH.FL. FIRE STAIRCASE | 0 | No Unit | 01 Oct 2016 | 12 Oct 2016 |  |  | 11 | 0 | 0 | 0
A-11th.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 01 Oct 2016 | 12 Oct 2016 | 30 Jan 2017 | 30 Jan 2017 | 11 | 0 | 121 | 110
A1- 12TH FLOOR | 0 | No Unit | 13 Oct 2016 | 01 Dec 2016 |  |  | 49 | 0 | 0 | 0
A1-FLAT 1201 | 0 | No Unit | 28 Oct 2016 | 01 Dec 2016 |  |  | 34 | 0 | 0 | 0
A1-Flat 1201 OBD Paint (M+L) | 56695 | Sft. | 28 Oct 2016 | 01 Dec 2016 | 14 Nov 2016 | 05 Jan 2017 | 34 | 52 | 17 | 35
A1-Flat 1201 Oil Paint (M+L) | 56695 | Sft. | 28 Oct 2016 | 01 Dec 2016 | 14 Nov 2016 | 05 Jan 2017 | 34 | 52 | 17 | 35
A1-FLAT 1202 | 0 | No Unit | 28 Oct 2016 | 01 Dec 2016 |  |  | 34 | 0 | 0 | 0
A1-Flat 1202 OBD Paint (M+L) | 56695 | Sft. | 28 Oct 2016 | 01 Dec 2016 | 14 Nov 2016 | 05 Jan 2017 | 34 | 52 | 17 | 35
A1-Flat 1202 Oil Paint (M+L) | 56695 | Sft. | 28 Oct 2016 | 01 Dec 2016 | 14 Nov 2016 | 05 Jan 2017 | 34 | 52 | 17 | 35
A1-FLAT 1203 | 0 | No Unit | 28 Oct 2016 | 01 Dec 2016 |  |  | 34 | 0 | 0 | 0
A1-Flat 1203 OBD Paint (M+L) | 56695 | Sft. | 28 Oct 2016 | 01 Dec 2016 | 14 Nov 2016 | 05 Jan 2017 | 34 | 52 | 17 | 35
A1-Flat 1203 Oil Paint (M+L) | 56695 | Sft. | 28 Oct 2016 | 01 Dec 2016 | 14 Nov 2016 | 05 Jan 2017 | 34 | 52 | 17 | 35
A1-FLAT 1204 | 0 | No Unit | 28 Oct 2016 | 01 Dec 2016 |  |  | 34 | 0 | 0 | 0
A1-Flat 1204 OBD Paint (M+L) | 56695 | Sft. | 28 Oct 2016 | 01 Dec 2016 | 14 Nov 2016 | 05 Jan 2017 | 34 | 52 | 17 | 35
A1-Flat 1204 Oil Paint (M+L) | 56695 | Sft. | 28 Oct 2016 | 01 Dec 2016 | 14 Nov 2016 | 05 Jan 2017 | 34 | 52 | 17 | 35
A1- COMMON AREA | 0 | No Unit | 13 Oct 2016 | 24 Oct 2016 |  |  | 11 | 0 | 0 | 0
A- 12TH.FL. FLOOR LOBBY | 0 | No Unit | 13 Oct 2016 | 24 Oct 2016 |  |  | 11 | 0 | 0 | 0
A- 12th.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 13 Oct 2016 | 24 Oct 2016 | 23 Nov 2016 | 30 Jan 2017 | 11 | 68 | 41 | 98
A-12TH.FL. MAIN STAIRCASE | 0 | No Unit | 13 Oct 2016 | 24 Oct 2016 |  |  | 11 | 0 | 0 | 0
A-12th.fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 13 Oct 2016 | 24 Oct 2016 | 23 Nov 2016 | 30 Jan 2017 | 11 | 68 | 41 | 98
A-12TH.FL. FIRE STAIRCASE | 0 | No Unit | 13 Oct 2016 | 24 Oct 2016 |  |  | 11 | 0 | 0 | 0
A-12th.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 13 Oct 2016 | 24 Oct 2016 | 23 Nov 2016 | 30 Jan 2017 | 11 | 68 | 41 | 98
A1- 13TH FLOOR | 0 | No Unit | 25 Oct 2016 | 09 Dec 2016 |  |  | 45 | 0 | 0 | 0
A1-FLAT 1301 | 0 | No Unit | 31 Oct 2016 | 09 Dec 2016 |  |  | 39 | 0 | 0 | 0
A1-Flat 1301 OBD Paint (M+L) | 56695 | Sft. | 31 Oct 2016 | 09 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 39 | 14 | 52 | 27
A1-Flat 1301 Oil Paint (M+L) | 56695 | Sft. | 31 Oct 2016 | 09 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 39 | 14 | 52 | 27
A1-FLAT 1302 | 0 | No Unit | 31 Oct 2016 | 09 Dec 2016 |  |  | 39 | 0 | 0 | 0
A1-Flat 1302 OBD Paint (M+L) | 56695 | Sft. | 31 Oct 2016 | 09 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 39 | 14 | 52 | 27
A1-Flat 1302 Oil Paint (M+L) | 56695 | Sft. | 31 Oct 2016 | 09 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 39 | 14 | 52 | 27
A1-FLAT 1303 | 0 | No Unit | 31 Oct 2016 | 09 Dec 2016 |  |  | 39 | 0 | 0 | 0
A1-Flat 1303 OBD Paint (M+L) | 56695 | Sft. | 31 Oct 2016 | 09 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 39 | 14 | 52 | 27
A1-Flat 1303 Oil Paint (M+L) | 56695 | Sft. | 31 Oct 2016 | 09 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 39 | 14 | 52 | 27
A1-REFUGE FLAT 1304 | 0 | No Unit | 31 Oct 2016 | 09 Dec 2016 |  |  | 39 | 0 | 0 | 0
A1-Refuge Flat 1304 OBD Paint (M+L) | 56695 | Sft. | 31 Oct 2016 | 09 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 39 | 14 | 52 | 27
A1-Refuge Flat 1304 Oil Paint (M+L) | 56695 | Sft. | 31 Oct 2016 | 09 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 39 | 14 | 52 | 27
A1- COMMON AREA | 0 | No Unit | 25 Oct 2016 | 04 Nov 2016 |  |  | 10 | 0 | 0 | 0
A- 13TH.FL. FLOOR LOBBY | 0 | No Unit | 25 Oct 2016 | 04 Nov 2016 |  |  | 10 | 0 | 0 | 0
A- 13th.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 25 Oct 2016 | 04 Nov 2016 | 30 Jan 2017 | 30 Jan 2017 | 10 | 0 | 97 | 87
A-13TH.FL. MAIN STAIRCASE | 0 | No Unit | 25 Oct 2016 | 04 Nov 2016 |  |  | 10 | 0 | 0 | 0
A-13th.fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 25 Oct 2016 | 04 Nov 2016 | 30 Jan 2017 | 30 Jan 2017 | 10 | 0 | 97 | 87
A-13TH.FL. FIRE STAIRCASE | 0 | No Unit | 25 Oct 2016 | 04 Nov 2016 |  |  | 10 | 0 | 0 | 0
A-13th.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 25 Oct 2016 | 04 Nov 2016 | 30 Jan 2017 | 30 Jan 2017 | 10 | 0 | 97 | 87
A1- 14TH FLOOR | 0 | No Unit | 05 Nov 2016 | 22 Dec 2016 |  |  | 47 | 0 | 0 | 0
A1-FLAT 1401 | 0 | No Unit | 07 Nov 2016 | 22 Dec 2016 |  |  | 45 | 0 | 0 | 0
A1-Flat 1401 OBD Paint (M+L) | 56695 | Sft. | 07 Nov 2016 | 22 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 45 | 14 | 45 | 14
A1-Flat 1401 Oil Paint (M+L) | 56695 | Sft. | 07 Nov 2016 | 22 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 45 | 14 | 45 | 14
A1-FLAT 1402 | 0 | No Unit | 07 Nov 2016 | 22 Dec 2016 |  |  | 45 | 0 | 0 | 0
A1-Flat 1402 OBD Paint (M+L) | 56695 | Sft. | 07 Nov 2016 | 22 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 45 | 14 | 45 | 14
A1-Flat 1402 Oil Paint (M+L) | 56695 | Sft. | 07 Nov 2016 | 22 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 45 | 14 | 45 | 14
A1-FLAT 1403 | 0 | No Unit | 07 Nov 2016 | 22 Dec 2016 |  |  | 45 | 0 | 0 | 0
A1-Flat 1403 OBD Paint (M+L) | 56695 | Sft. | 07 Nov 2016 | 22 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 45 | 14 | 45 | 14
A1-Flat 1403 Oil Paint (M+L) | 56695 | Sft. | 07 Nov 2016 | 22 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 45 | 14 | 45 | 14
A1-FLAT 1404 | 0 | No Unit | 07 Nov 2016 | 22 Dec 2016 |  |  | 45 | 0 | 0 | 0
A1-Flat 1404 OBD Paint (M+L) | 56695 | Sft. | 07 Nov 2016 | 22 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 45 | 14 | 45 | 14
A1-Flat 1404 Oil Paint (M+L) | 56695 | Sft. | 07 Nov 2016 | 22 Dec 2016 | 22 Dec 2016 | 05 Jan 2017 | 45 | 14 | 45 | 14
A1- COMMON AREA | 0 | No Unit | 05 Nov 2016 | 16 Nov 2016 |  |  | 11 | 0 | 0 | 0
A- 14TH.FL. FLOOR LOBBY | 0 | No Unit | 05 Nov 2016 | 16 Nov 2016 |  |  | 11 | 0 | 0 | 0
A- 14th.fl. Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 05 Nov 2016 | 16 Nov 2016 | 23 Nov 2016 | 30 Jan 2017 | 11 | 68 | 18 | 75
A-14TH.FL. MAIN STAIRCASE | 0 | No Unit | 05 Nov 2016 | 16 Nov 2016 |  |  | 11 | 0 | 0 | 0
A-14th.fl. Main Staircase Main Stair OBD Paint(M+L) | 56695 | Sft. | 05 Nov 2016 | 16 Nov 2016 | 23 Nov 2016 | 30 Jan 2017 | 11 | 68 | 18 | 75
A-14TH.FL. FIRE STAIRCASE | 0 | No Unit | 05 Nov 2016 | 16 Nov 2016 |  |  | 11 | 0 | 0 | 0
A-14th.fl. Fire Staircase Fire Stair OBD Paint(M+L) | 56695 | Sft. | 05 Nov 2016 | 16 Nov 2016 | 23 Nov 2016 | 30 Jan 2017 | 11 | 68 | 18 | 75
A1- TOP TERRACE FLOOR | 0 | No Unit | 17 Nov 2016 | 28 Nov 2016 |  |  | 11 | 0 | 0 | 0
A1- COMMON AREA | 0 | No Unit | 17 Nov 2016 | 28 Nov 2016 |  |  | 11 | 0 | 0 | 0
A- TOP TERRACE FLOOR LOBBY | 0 | No Unit | 17 Nov 2016 | 28 Nov 2016 |  |  | 11 | 0 | 0 | 0
A- Top terrace Floor Lobby OBD Paint (M+L) | 56695 | Sft. | 17 Nov 2016 | 28 Nov 2016 | 23 Nov 2016 |  | 11 | 0 | 6 | 0
A-TOP TERRACE FL. MAIN STAIRCASE | 0 | No Unit | 17 Nov 2016 | 28 Nov 2016 |  |  | 11 | 0 | 0 | 0
A-Top terrace Fl. Main Staircase Main Stair OBD Paint(M+L) | 0 | Sft. | 17 Nov 2016 | 28 Nov 2016 | 23 Nov 2016 |  | 11 | 0 | 6 | 0
A-TOP TERRACE FL. FIRE STAIRCASE | 0 | No Unit | 17 Nov 2016 | 28 Nov 2016 |  |  | 11 | 0 | 0 | 0
A-Top terrace Fl. Fire Staircase Fire Stair OBD Paint(M+L) | 0 | Sft. | 17 Nov 2016 | 28 Nov 2016 | 23 Nov 2016 |  | 11 | 0 | 6 | 0
A1- MAIN & FIRE STAIRCASE RAILING | 0 | No Unit | 26 Sep 2016 | 29 Oct 2016 |  |  | 33 | 0 | 0 | 0
A1- Main & Fire Staircase Railing Oil Paint (M+L) | 56695 | Sft. | 26 Sep 2016 | 29 Oct 2016 | 05 Oct 2016 |  | 33 | 0 | 9 | 0
A1- LIFT SHAFT | 0 | No Unit | 26 Jul 2016 | 03 Aug 2016 |  |  | 8 | 0 | 0 | 0
A1- Lift Shaft White Wash (M+L) | 56695 | Sft. | 26 Jul 2016 | 03 Aug 2016 | 23 Nov 2016 |  | 8 | 0 | 120 | 0
A1- MISC. OIL PAINT | 0 | No Unit | 16 Mar 2016 | 28 Nov 2016 |  |  | 257 | 0 | 0 | 0
A1- Misc. Oil Paint Oil Paint (M+L) | 56695 | Sft. | 16 Mar 2016 | 28 Nov 2016 | 09 Feb 2017 |  | 257 | 0 | 330 | 0
A1- EXTERNAL PAINTING | 0 | No Unit | 25 May 2016 | 29 Oct 2016 |  |  | 157 | 0 | 0 | 0
A1- PARKING | 0 | No Unit | 08 Sep 2016 | 30 Sep 2016 |  |  | 22 | 0 | 0 | 0
A1- Parking Ext. Painting (M+L) | 56695 | Sft. | 08 Sep 2016 | 30 Sep 2016 | 23 Aug 2016 |  | 22 | 0 | 0 | 0
A1- FRONT SIDE | 0 | No Unit | 25 May 2016 | 12 Oct 2016 |  |  | 140 | 0 | 0 | 0
A1- Front Side Ext. Painting (M+L) | 56695 | Sft. | 25 May 2016 | 12 Oct 2016 | 15 Jun 2016 |  | 140 | 0 | 21 | 0
A1- REAR SIDE | 0 | No Unit | 25 May 2016 | 12 Oct 2016 |  |  | 140 | 0 | 0 | 0
A1- Rear Side Ext. Painting (M+L) | 56695 | Sft. | 25 May 2016 | 12 Oct 2016 | 15 Jun 2016 |  | 140 | 0 | 21 | 0
A1- RIGHT SIDE | 0 | No Unit | 25 May 2016 | 12 Oct 2016 |  |  | 140 | 0 | 0 | 0
A1- Right Side Ext. Painting (M+L) | 0 | Sft. | 25 May 2016 | 12 Oct 2016 | 30 Jan 2017 |  | 140 | 0 | 250 | 0
A1- RIGHT SIDE DUCT | 0 | No Unit | 25 May 2016 | 12 Oct 2016 |  |  | 140 | 0 | 0 | 0
A1- Right Side Duct Ext. Painting (M+L) | 56695 | Sft. | 25 May 2016 | 12 Oct 2016 | 15 Jun 2016 |  | 140 | 0 | 21 | 0
A1- LEFT SIDE | 0 | No Unit | 25 May 2016 | 12 Oct 2016 |  |  | 140 | 0 | 0 | 0
A1- Left Side Ext. Painting (M+L) | 56695 | Sft. | 25 May 2016 | 12 Oct 2016 | 15 Jun 2016 |  | 140 | 0 | 21 | 0
A1- LEFT SIDE DUCT | 0 | No Unit | 25 May 2016 | 12 Oct 2016 |  |  | 140 | 0 | 0 | 0
A1- Left Side Duct Ext. Painting (M+L) | 56695 | Sft. | 25 May 2016 | 12 Oct 2016 | 15 Jun 2016 |  | 140 | 0 | 21 | 0
A1- LOBBY DUCT | 0 | No Unit | 25 May 2016 | 12 Oct 2016 |  |  | 140 | 0 | 0 | 0
A1- Lobby Duct Ext. Painting (M+L) | 56695 | Sft. | 25 May 2016 | 12 Oct 2016 | 15 Jun 2016 |  | 140 | 0 | 21 | 0
A1- ELECTRICAL DUCT | 0 | No Unit | 25 May 2016 | 12 Oct 2016 |  |  | 140 | 0 | 0 | 0
A1- Electrical Duct Ext. Painting (M+L) | 56695 | Sft. | 25 May 2016 | 12 Oct 2016 | 15 Jun 2016 |  | 140 | 0 | 21 | 0
A1- F.F. DUCT | 0 | No Unit | 25 May 2016 | 12 Oct 2016 |  |  | 140 | 0 | 0 | 0
A1- F.F. Duct Ext. Painting (M+L) | 56695 | Sft. | 25 May 2016 | 12 Oct 2016 | 15 Jun 2016 |  | 140 | 0 | 21 | 0
A1- ABOVE TERRACE | 0 | No Unit | 13 Oct 2016 | 29 Oct 2016 |  |  | 16 | 0 | 0 | 0
A1- Above Terrace Ext. Painting (M+L) | 56695 | Sft. | 13 Oct 2016 | 29 Oct 2016 | 13 Oct 2016 |  | 16 | 0 | 0 | 0
A1-MELAMNE POLISH (M+L) | 41.5 | No Unit | 16 Mar 2016 | 24 Dec 2016 |  |  | 283 | 0 | 0 | 0
A1- 1ST FLOOR | 0 | No Unit | 16 Mar 2016 | 17 Aug 2016 |  |  | 154 | 0 | 0 | 0
A1- FLAT 101 | 0 | No Unit | 16 Mar 2016 | 13 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1- Flat 101 Melamine Polish (M+L) | 56695 | Sft. | 16 Mar 2016 | 13 Aug 2016 | 28 Jun 2016 | 30 Jan 2017 | 150 | 216 | 104 | 170
A1- FLAT 102 | 0 | No Unit | 16 Mar 2016 | 13 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1- Flat 102 Melamine Polish (M+L) | 56695 | Sft. | 16 Mar 2016 | 13 Aug 2016 | 28 Jun 2016 | 07 Sep 2016 | 150 | 71 | 104 | 25
A1- FLAT 103 | 0 | No Unit | 16 Mar 2016 | 13 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1- Flat 103 Melamine Polish (M+L) | 56695 | Sft. | 16 Mar 2016 | 13 Aug 2016 | 28 Jun 2016 | 07 Sep 2016 | 150 | 71 | 104 | 25
A1- FLAT 104 | 0 | No Unit | 16 Mar 2016 | 13 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1- Flat 104 Melamine Polish (M+L) | 56695 | Sft. | 16 Mar 2016 | 13 Aug 2016 | 28 Jun 2016 | 30 Jan 2017 | 150 | 216 | 104 | 170
A1- 1st Floor Buffing (M+L) | 56695 | Sft. | 16 Aug 2016 | 17 Aug 2016 | 28 Jun 2016 |  | 1 | 0 | 0 | 0
A1- 2ND FLOOR | 0 | No Unit | 25 Mar 2016 | 24 Aug 2016 |  |  | 152 | 0 | 0 | 0
A1- FLAT 201 | 0 | No Unit | 25 Mar 2016 | 22 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1- Flat 201 Melamine Polish (M+L) | 56695 | Sft. | 25 Mar 2016 | 22 Aug 2016 | 28 Jun 2016 | 23 Nov 2016 | 150 | 148 | 95 | 93
A1- FLAT 202 | 0 | No Unit | 25 Mar 2016 | 22 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1- Flat 202 Melamine Polish (M+L) | 56695 | Sft. | 25 Mar 2016 | 22 Aug 2016 | 28 Jun 2016 | 07 Sep 2016 | 150 | 71 | 95 | 16
A1- FLAT 203 | 0 | No Unit | 25 Mar 2016 | 22 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1- Flat 203 Melamine Polish (M+L) | 56695 | Sft. | 25 Mar 2016 | 22 Aug 2016 | 28 Jun 2016 | 07 Sep 2016 | 150 | 71 | 95 | 16
A1- FLAT 204 | 0 | No Unit | 25 Mar 2016 | 22 Aug 2016 |  |  | 150 | 0 | 0 | 0
A1- Flat 204 Melamine Polish (M+L) | 56695 | Sft. | 25 Mar 2016 | 22 Aug 2016 | 28 Jun 2016 | 23 Nov 2016 | 150 | 148 | 95 | 93
A1- 2nd Floor Buffing (M+L) | 56695 | Sft. | 23 Aug 2016 | 24 Aug 2016 | 28 Jun 2016 |  | 1 | 0 | 0 | 0
A1- 3RD FLOOR | 0 | No Unit | 06 Apr 2016 | 02 Sep 2016 |  |  | 149 | 0 | 0 | 0
A1- FLAT 301 | 0 | No Unit | 06 Apr 2016 | 31 Aug 2016 |  |  | 147 | 0 | 0 | 0
A1- Flat 301 Melamine Polish (M+L) | 56695 | Sft. | 06 Apr 2016 | 31 Aug 2016 | 28 Jun 2016 | 23 Nov 2016 | 147 | 148 | 83 | 84
A1- FLAT 302 | 0 | No Unit | 06 Apr 2016 | 31 Aug 2016 |  |  | 147 | 0 | 0 | 0
A1- Flat 302 Melamine Polish (M+L) | 56695 | Sft. | 06 Apr 2016 | 31 Aug 2016 | 28 Jun 2016 | 07 Sep 2016 | 147 | 71 | 83 | 7
A1- FLAT 303 | 0 | No Unit | 06 Apr 2016 | 31 Aug 2016 |  |  | 147 | 0 | 0 | 0
A1- Flat 303 Melamine Polish (M+L) | 56695 | Sft. | 06 Apr 2016 | 31 Aug 2016 | 28 Jun 2016 | 07 Sep 2016 | 147 | 71 | 83 | 7
A1- FLAT 304 | 0 | No Unit | 06 Apr 2016 | 31 Aug 2016 |  |  | 147 | 0 | 0 | 0
A1- Flat 304 Melamine Polish (M+L) | 56695 | Sft. | 06 Apr 2016 | 31 Aug 2016 | 28 Jun 2016 | 23 Nov 2016 | 147 | 148 | 83 | 84
A1- 3rd Floor Buffing (M+L) | 56695 | Sft. | 01 Sep 2016 | 02 Sep 2016 | 28 Jun 2016 |  | 1 | 0 | 0 | 0
A1- 4TH FLOOR | 0 | No Unit | 03 May 2016 | 13 Sep 2016 |  |  | 133 | 0 | 0 | 0
A1- FLAT 401 | 0 | No Unit | 03 May 2016 | 10 Sep 2016 |  |  | 130 | 0 | 0 | 0
A1- Flat 401 Melamine Polish (M+L) | 56695 | Sft. | 03 May 2016 | 10 Sep 2016 | 12 Jul 2016 | 23 Nov 2016 | 130 | 134 | 70 | 74
A1- FLAT 402 | 0 | No Unit | 03 May 2016 | 10 Sep 2016 |  |  | 130 | 0 | 0 | 0
A1- Flat 402 Melamine Polish (M+L) | 56695 | Sft. | 03 May 2016 | 10 Sep 2016 | 12 Jul 2016 | 23 Nov 2016 | 130 | 134 | 70 | 74
A1- FLAT 403 | 0 | No Unit | 03 May 2016 | 10 Sep 2016 |  |  | 130 | 0 | 0 | 0
A1- Flat 403 Melamine Polish (M+L) | 56695 | Sft. | 03 May 2016 | 10 Sep 2016 | 12 Jul 2016 | 23 Nov 2016 | 130 | 134 | 70 | 74
A1- FLAT 404 | 0 | No Unit | 03 May 2016 | 10 Sep 2016 |  |  | 130 | 0 | 0 | 0
A1- Flat 404 Melamine Polish (M+L) | 56695 | Sft. | 03 May 2016 | 10 Sep 2016 | 12 Jul 2016 | 23 Nov 2016 | 130 | 134 | 70 | 74
A1- 4th Floor Buffing (M+L) | 56695 | Sft. | 12 Sep 2016 | 13 Sep 2016 | 12 Jul 2016 |  | 1 | 0 | 0 | 0
A1- 5TH FLOOR | 0 | No Unit | 31 May 2016 | 21 Sep 2016 |  |  | 113 | 0 | 0 | 0
A1- FLAT 501 | 0 | No Unit | 31 May 2016 | 19 Sep 2016 |  |  | 111 | 0 | 0 | 0
A1- Flat 501 Melamine Polish (M+L) | 56695 | Sft. | 31 May 2016 | 19 Sep 2016 | 12 Jul 2016 | 23 Nov 2016 | 111 | 134 | 42 | 65
A1- FLAT 502 | 0 | No Unit | 31 May 2016 | 19 Sep 2016 |  |  | 111 | 0 | 0 | 0
A1- Flat 502 Melamine Polish (M+L) | 56695 | Sft. | 31 May 2016 | 19 Sep 2016 | 12 Jul 2016 | 23 Nov 2016 | 111 | 134 | 42 | 65
A1- FLAT 503 | 0 | No Unit | 31 May 2016 | 19 Sep 2016 |  |  | 111 | 0 | 0 | 0
A1- Flat 503 Melamine Polish (M+L) | 56695 | Sft. | 31 May 2016 | 19 Sep 2016 | 12 Jul 2016 | 23 Nov 2016 | 111 | 134 | 42 | 65
A1- FLAT 504 | 0 | No Unit | 31 May 2016 | 19 Sep 2016 |  |  | 111 | 0 | 0 | 0
A1- Flat 504 Melamine Polish (M+L) | 56695 | Sft. | 31 May 2016 | 19 Sep 2016 | 12 Jul 2016 | 23 Nov 2016 | 111 | 134 | 42 | 65
A1- 5th Floor Buffing (M+L) | 56695 | Sft. | 20 Sep 2016 | 21 Sep 2016 | 12 Jul 2016 |  | 1 | 0 | 0 | 0
A1- 6TH FLOOR | 0 | No Unit | 06 Jun 2016 | 03 Oct 2016 |  |  | 119 | 0 | 0 | 0
A1- FLAT 601 | 0 | No Unit | 06 Jun 2016 | 30 Sep 2016 |  |  | 116 | 0 | 0 | 0
A1- Flat 601 Melamine Polish (M+L) | 56695 | Sft. | 06 Jun 2016 | 30 Sep 2016 | 12 Jul 2016 |  | 116 | 0 | 36 | 0
A1- FLAT 602 | 0 | No Unit | 06 Jun 2016 | 30 Sep 2016 |  |  | 116 | 0 | 0 | 0
A1- Flat 602 Melamine Polish (M+L) | 56695 | Sft. | 06 Jun 2016 | 30 Sep 2016 | 12 Jul 2016 | 23 Nov 2016 | 116 | 134 | 36 | 54
A1- FLAT 603 | 0 | No Unit | 06 Jun 2016 | 30 Sep 2016 |  |  | 116 | 0 | 0 | 0
A1- Flat 603 Melamine Polish (M+L) | 56695 | Sft. | 06 Jun 2016 | 30 Sep 2016 | 12 Jul 2016 | 23 Nov 2016 | 116 | 134 | 36 | 54
A1- FLAT 604 | 0 | No Unit | 06 Jun 2016 | 30 Sep 2016 |  |  | 116 | 0 | 0 | 0
A1- Flat 604 Melamine Polish (M+L) | 56695 | Sft. | 06 Jun 2016 | 30 Sep 2016 | 23 Nov 2016 |  | 116 | 0 | 170 | 0
A1- 6th Floor Buffing (M+L) | 56695 | Sft. | 01 Oct 2016 | 03 Oct 2016 | 12 Jul 2016 |  | 2 | 0 | 0 | 0
A1- 7TH FLOOR | 0 | No Unit | 15 Jun 2016 | 12 Oct 2016 |  |  | 119 | 0 | 0 | 0
A1- FLAT 701 | 0 | No Unit | 15 Jun 2016 | 10 Oct 2016 |  |  | 117 | 0 | 0 | 0
A1- Flat 701 Melamine Polish (M+L) | 56695 | Sft. | 15 Jun 2016 | 10 Oct 2016 | 12 Jul 2016 | 23 Nov 2016 | 117 | 134 | 27 | 44
A1- FLAT 702 | 0 | No Unit | 15 Jun 2016 | 10 Oct 2016 |  |  | 117 | 0 | 0 | 0
A1- Flat 702 Melamine Polish (M+L) | 56695 | Sft. | 15 Jun 2016 | 10 Oct 2016 | 12 Jul 2016 | 23 Nov 2016 | 117 | 134 | 27 | 44
A1- FLAT 703 | 0 | No Unit | 15 Jun 2016 | 10 Oct 2016 |  |  | 117 | 0 | 0 | 0
A1- Flat 703 Melamine Polish (M+L) | 56695 | Sft. | 15 Jun 2016 | 10 Oct 2016 | 12 Jul 2016 | 23 Nov 2016 | 117 | 134 | 27 | 44
A1- FLAT 704 | 0 | No Unit | 15 Jun 2016 | 10 Oct 2016 |  |  | 117 | 0 | 0 | 0
A1- Flat 704 Melamine Polish (M+L) | 56695 | Sft. | 15 Jun 2016 | 10 Oct 2016 | 12 Jul 2016 | 23 Nov 2016 | 117 | 134 | 27 | 44
A1- 7th Floor Buffing (M+L) | 56695 | Sft. | 11 Oct 2016 | 12 Oct 2016 | 12 Jul 2016 |  | 1 | 0 | 0 | 0
A1- 8TH FLOOR | 0 | No Unit | 11 Jul 2016 | 20 Oct 2016 |  |  | 101 | 0 | 0 | 0
A1- REFUGE FLAT 804 | 0 | No Unit | 11 Jul 2016 | 18 Oct 2016 |  |  | 99 | 0 | 0 | 0
A1- Refuge Flat 804 Melamine Polish (M+L) | 0 | Sft. | 11 Jul 2016 | 18 Oct 2016 | 12 Jul 2016 | 23 Nov 2016 | 99 | 134 | 1 | 36
A1- FLAT 802 | 0 | No Unit | 11 Jul 2016 | 18 Oct 2016 |  |  | 99 | 0 | 0 | 0
A1- Flat 802 Melamine Polish (M+L) | 56695 | Sft. | 11 Jul 2016 | 18 Oct 2016 | 12 Jul 2016 | 23 Nov 2016 | 99 | 134 | 1 | 36
A1- FLAT 803 | 0 | No Unit | 11 Jul 2016 | 18 Oct 2016 |  |  | 99 | 0 | 0 | 0
A1- Flat 803 Melamine Polish (M+L) | 56695 | Sft. | 11 Jul 2016 | 18 Oct 2016 | 12 Jul 2016 | 23 Nov 2016 | 99 | 134 | 1 | 36
A1- FLAT 801 | 0 | No Unit | 11 Jul 2016 | 18 Oct 2016 |  |  | 99 | 0 | 0 | 0
A1- Flat 801 Melamine Polish (M+L) | 56695 | Sft. | 11 Jul 2016 | 18 Oct 2016 | 12 Jul 2016 | 23 Nov 2016 | 99 | 134 | 1 | 36
A1- 8th Floor Buffing (M+L) | 56695 | Sft. | 19 Oct 2016 | 20 Oct 2016 | 12 Jul 2016 |  | 1 | 0 | 0 | 0
A1- 9TH FLOOR | 0 | No Unit | 11 Aug 2016 | 01 Nov 2016 |  |  | 82 | 0 | 0 | 0
A1- FLAT 901 | 0 | No Unit | 11 Aug 2016 | 29 Oct 2016 |  |  | 79 | 0 | 0 | 0
A1- Flat 901 Melamine Polish (M+L) | 56695 | Sft. | 11 Aug 2016 | 29 Oct 2016 | 12 Jul 2016 | 09 Dec 2016 | 79 | 150 | 0 | 41
A1- FLAT 902 | 0 | No Unit | 11 Aug 2016 | 29 Oct 2016 |  |  | 79 | 0 | 0 | 0
A1- Flat 902 Melamine Polish (M+L) | 56695 | Sft. | 11 Aug 2016 | 29 Oct 2016 | 12 Jul 2016 | 09 Dec 2016 | 79 | 150 | 0 | 41
A1- FLAT 903 | 0 | No Unit | 11 Aug 2016 | 29 Oct 2016 |  |  | 79 | 0 | 0 | 0
A1- Flat 903 Melamine Polish (M+L) | 56695 | Sft. | 11 Aug 2016 | 29 Oct 2016 | 12 Jul 2016 | 09 Dec 2016 | 79 | 150 | 0 | 41
A1- FLAT 904 | 0 | No Unit | 11 Aug 2016 | 29 Oct 2016 |  |  | 79 | 0 | 0 | 0
A1- Flat 904 Melamine Polish (M+L) | 56695 | Sft. | 11 Aug 2016 | 29 Oct 2016 | 12 Jul 2016 | 09 Dec 2016 | 79 | 150 | 0 | 41
A1- 9th Floor Buffing (M+L) | 56695 | Sft. | 31 Oct 2016 | 01 Nov 2016 | 12 Jul 2016 |  | 1 | 0 | 0 | 0
A1- 10TH FLOOR | 0 | No Unit | 02 Sep 2016 | 12 Nov 2016 |  |  | 71 | 0 | 0 | 0
A1- FLAT 1001 | 0 | No Unit | 02 Sep 2016 | 10 Nov 2016 |  |  | 69 | 0 | 0 | 0
A1- Flat 1001 Melamine Polish (M+L) | 56695 | Sft. | 02 Sep 2016 | 10 Nov 2016 | 23 Nov 2016 | 09 Dec 2016 | 69 | 16 | 82 | 29
A1- FLAT 1002 | 0 | No Unit | 02 Sep 2016 | 10 Nov 2016 |  |  | 69 | 0 | 0 | 0
A1- Flat 1002 Melamine Polish (M+L) | 56695 | Sft. | 02 Sep 2016 | 10 Nov 2016 | 23 Nov 2016 | 09 Dec 2016 | 69 | 16 | 82 | 29
A1- FLAT 1003 | 0 | No Unit | 02 Sep 2016 | 10 Nov 2016 |  |  | 69 | 0 | 0 | 0
A1- Flat 1003 Melamine Polish (M+L) | 56695 | Sft. | 02 Sep 2016 | 10 Nov 2016 | 23 Nov 2016 | 09 Dec 2016 | 69 | 16 | 82 | 29
A1- FLAT 1004 | 0 | No Unit | 02 Sep 2016 | 10 Nov 2016 |  |  | 69 | 0 | 0 | 0
A1- Flat 1004 Melamine Polish (M+L) | 56695 | Sft. | 02 Sep 2016 | 10 Nov 2016 | 23 Nov 2016 | 09 Dec 2016 | 69 | 16 | 82 | 29
A1- 10th Floor Buffing (M+L) | 56695 | Sft. | 11 Nov 2016 | 12 Nov 2016 | 23 Nov 2016 |  | 1 | 0 | 12 | 0
A1- 11TH FLOOR | 0 | No Unit | 30 Sep 2016 | 29 Nov 2016 |  |  | 60 | 0 | 0 | 0
A1- FLAT 1101 | 0 | No Unit | 30 Sep 2016 | 26 Nov 2016 |  |  | 57 | 0 | 0 | 0
A1- Flat 1101 Melamine Polish (M+L) | 56695 | Sft. | 30 Sep 2016 | 26 Nov 2016 | 23 Nov 2016 |  | 57 | 0 | 54 | 0
A1- FLAT 1102 | 0 | No Unit | 30 Sep 2016 | 26 Nov 2016 |  |  | 57 | 0 | 0 | 0
A1- Flat 1102 Melamine Polish (M+L) | 56695 | Sft. | 30 Sep 2016 | 26 Nov 2016 | 23 Nov 2016 |  | 57 | 0 | 54 | 0
A1- FLAT 1103 | 0 | No Unit | 30 Sep 2016 | 26 Nov 2016 |  |  | 57 | 0 | 0 | 0
A1- Flat 1103 Melamine Polish (M+L) | 56695 | Sft. | 30 Sep 2016 | 26 Nov 2016 | 23 Nov 2016 |  | 57 | 0 | 54 | 0
A1- FLAT 1104 | 0 | No Unit | 30 Sep 2016 | 26 Nov 2016 |  |  | 57 | 0 | 0 | 0
A1- Flat 1104 Melamine Polish (M+L) | 56695 | Sft. | 30 Sep 2016 | 26 Nov 2016 | 23 Nov 2016 |  | 57 | 0 | 54 | 0
A1- 11th Floor Buffing (M+L) | 56695 | Sft. | 28 Nov 2016 | 29 Nov 2016 | 23 Nov 2016 |  | 1 | 0 | 0 | 0
A1- 12TH FLOOR | 0 | No Unit | 28 Oct 2016 | 03 Dec 2016 |  |  | 36 | 0 | 0 | 0
A1- FLAT 1201 | 0 | No Unit | 28 Oct 2016 | 01 Dec 2016 |  |  | 34 | 0 | 0 | 0
A1- Flat 1201 Melamine Polish (M+L) | 56695 | Sft. | 28 Oct 2016 | 01 Dec 2016 | 23 Nov 2016 |  | 34 | 0 | 26 | 0
A1- FLAT 1202 | 0 | No Unit | 28 Oct 2016 | 01 Dec 2016 |  |  | 34 | 0 | 0 | 0
A1- Flat 1202 Melamine Polish (M+L) | 56695 | Sft. | 28 Oct 2016 | 01 Dec 2016 | 23 Nov 2016 |  | 34 | 0 | 26 | 0
A1- FLAT 1203 | 0 | No Unit | 28 Oct 2016 | 01 Dec 2016 |  |  | 34 | 0 | 0 | 0
A1- Flat 1203 Melamine Polish (M+L) | 56695 | Sft. | 28 Oct 2016 | 01 Dec 2016 | 23 Nov 2016 |  | 34 | 0 | 26 | 0
A1- FLAT 1204 | 0 | No Unit | 28 Oct 2016 | 01 Dec 2016 |  |  | 34 | 0 | 0 | 0
A1- Flat 1204 Melamine Polish (M+L) | 56695 | Sft. | 28 Oct 2016 | 01 Dec 2016 | 23 Nov 2016 |  | 34 | 0 | 26 | 0
A1- 12th Floor Buffing (M+L) | 56695 | Sft. | 02 Dec 2016 | 03 Dec 2016 | 23 Nov 2016 |  | 1 | 0 | 0 | 0
A1- 13TH FLOOR | 0 | No Unit | 31 Oct 2016 | 12 Dec 2016 |  |  | 42 | 0 | 0 | 0
A1- REFUGE FLAT 1304 | 0 | No Unit | 31 Oct 2016 | 09 Dec 2016 |  |  | 39 | 0 | 0 | 0
A1- Refuge Flat 1304 Melamine Polish (M+L) | 0 | Sft. | 31 Oct 2016 | 09 Dec 2016 | 06 Dec 2016 |  | 39 | 0 | 36 | 0
A1- FLAT 1302 | 0 | No Unit | 31 Oct 2016 | 09 Dec 2016 |  |  | 39 | 0 | 0 | 0
A1- Flat 1302 Melamine Polish (M+L) | 56695 | Sft. | 31 Oct 2016 | 09 Dec 2016 | 06 Dec 2016 |  | 39 | 0 | 36 | 0
A1- FLAT 1303 | 0 | No Unit | 31 Oct 2016 | 09 Dec 2016 |  |  | 39 | 0 | 0 | 0
A1- Flat 1303 Melamine Polish (M+L) | 56695 | Sft. | 31 Oct 2016 | 09 Dec 2016 | 06 Dec 2016 |  | 39 | 0 | 36 | 0
A1- FLAT 1301 | 0 | No Unit | 31 Oct 2016 | 09 Dec 2016 |  |  | 39 | 0 | 0 | 0
A1- Flat 1301 Melamine Polish (M+L) | 56695 | Sft. | 31 Oct 2016 | 09 Dec 2016 | 06 Dec 2016 |  | 39 | 0 | 36 | 0
A1- 13th Floor Buffing (M+L) | 56695 | Sft. | 10 Dec 2016 | 12 Dec 2016 | 06 Dec 2016 |  | 2 | 0 | 0 | 0
A1- 14TH FLOOR | 0 | No Unit | 07 Nov 2016 | 24 Dec 2016 |  |  | 47 | 0 | 0 | 0
A1- FLAT 1401 | 0 | No Unit | 07 Nov 2016 | 22 Dec 2016 |  |  | 45 | 0 | 0 | 0
A1- Flat 1401 Melamine Polish (M+L) | 56695 | Sft. | 07 Nov 2016 | 22 Dec 2016 | 30 Jan 2017 | 30 Jan 2017 | 45 | 0 | 84 | 39
A1- FLAT 1402 | 0 | No Unit | 07 Nov 2016 | 22 Dec 2016 |  |  | 45 | 0 | 0 | 0
A1- Flat 1402 Melamine Polish (M+L) | 56695 | Sft. | 07 Nov 2016 | 22 Dec 2016 | 30 Jan 2017 | 30 Jan 2017 | 45 | 0 | 84 | 39
A1- FLAT 1403 | 0 | No Unit | 07 Nov 2016 | 22 Dec 2016 |  |  | 45 | 0 | 0 | 0
A1- Flat 1403 Melamine Polish (M+L) | 56695 | Sft. | 07 Nov 2016 | 22 Dec 2016 | 23 Nov 2016 | 23 Nov 2016 | 45 | 0 | 16 | 0
A1- FLAT 1404 | 0 | No Unit | 07 Nov 2016 | 22 Dec 2016 |  |  | 45 | 0 | 0 | 0
A1- Flat 1404 Melamine Polish (M+L) | 56695 | Sft. | 07 Nov 2016 | 22 Dec 2016 | 06 Dec 2016 | 30 Jan 2017 | 45 | 55 | 29 | 39
A1- 14th Floor Buffing (M+L) | 56695 | Sft. | 23 Dec 2016 | 24 Dec 2016 | 01 Mar 2017 |  | 1 | 0 | 68 | 0
A1- MISC. ITEM | 0 | No Unit | 11 Oct 2016 | 14 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1- Misc. Item Melamine Polish (M+L) | 56695 | Sft. | 11 Oct 2016 | 14 Nov 2016 |  |  | 34 | 0 | 0 | 0
A1-BUILDING SERVICES | 1 | No Unit | 05 Jun 2015 | 21 Dec 2016 |  |  | 565 | 0 | 0 | 0
A1-Building Services LIFT | 1 | No. | 12 Jul 2016 | 29 Nov 2016 | 18 Feb 2016 | 30 Nov 2016 | 140 | 286 | 0 | 1
A1-Building Services FIRE FIGHTING SYSTEM | 1 | R.S. | 12 Jul 2016 | 10 Dec 2016 | 16 Oct 2015 |  | 151 | 0 | 0 | 0
A1-Building Services SOLAR HOT WATER | 0 | R.S. | 22 Aug 2016 | 29 Oct 2016 | 31 Dec 2016 | 31 Dec 2016 | 68 | 0 | 131 | 63
A1-Building Services RETICULATED PIPED GAS SYSTEM | 0 | R.S. | 20 Jul 2016 | 07 Dec 2016 | 14 Jul 2016 | 31 Dec 2016 | 140 | 170 | 0 | 24
A1-Building Services FIRE DOOR | 0 | No. | 21 Oct 2016 | 24 Nov 2016 | 31 Dec 2016 | 31 Dec 2016 | 34 | 0 | 71 | 37
A1-Building Services HYDRO-PNEUMATIC SYSTEM | 0 | No. | 16 Jul 2016 | 24 Sep 2016 | 31 Dec 2016 | 31 Dec 2016 | 70 | 0 | 168 | 98
A1-Building Services Lift scaffolding | 0 | Nos. | 02 Jul 2016 | 15 Jul 2016 | 31 Dec 2016 | 31 Dec 2016 | 13 | 0 | 182 | 169
A1-Building Services FABRICATION | 0 | NO | 07 Nov 2016 | 10 Dec 2016 | 31 Dec 2016 | 31 Dec 2016 | 33 | 0 | 54 | 21
A1-Building Services Auto Change Over Panel | 1 | NO | 07 Nov 2016 | 10 Dec 2016 | 18 Nov 2016 | 02 Feb 2017 | 33 | 76 | 11 | 54
A1-Building Services Bus Bar (Meter Room) | 1 | NO | 03 Oct 2016 | 10 Dec 2016 | 31 Dec 2016 | 02 Feb 2017 | 68 | 33 | 89 | 54
A1-Building Services MCB Flat DG Supply | 54 | NO | 03 Oct 2016 | 10 Dec 2016 | 24 Jan 2017 |  | 68 | 0 | 113 | 0
A1 SOLAR SYSTEM | 0 | No Unit | 22 Aug 2016 | 21 Dec 2016 |  |  | 121 | 0 | 0 | 0
A1 SOLAR SYSTEM 01 TANK AT SITE - 25% | 224766 | R.S. | 22 Aug 2016 | 16 Nov 2016 | 26 Jul 2016 | 30 Jan 2017 | 86 | 188 | 0 | 75
A1 SOLAR SYSTEM 02 COPPER PIPING 25% | 224766 | R.S. | 22 Aug 2016 | 16 Nov 2016 | 26 Jul 2016 | 30 Jan 2017 | 86 | 188 | 0 | 75
A1 SOLAR SYSTEM 03 COLLECTOR AT SITE 25% | 224766 | R.S. | 22 Aug 2016 | 16 Nov 2016 | 26 Jul 2016 | 02 Feb 2017 | 86 | 191 | 0 | 78
A1 SOLAR SYSTEM 04 INSTALLATION, TESTING & COMMISSIONING | 224766 | R.S. | 17 Nov 2016 | 21 Dec 2016 | 26 Jul 2016 |  | 34 | 0 | 0 | 0
A1 HYDRO-PNUEMATIC SYSTEM | 0 | No Unit | 07 May 2016 | 04 Oct 2016 |  |  | 150 | 0 | 0 | 0
A1 HYDRO-PNUEMATIC SYSTEM 01 WITH WORK ORDER - 20% | 29002 | R.S. | 07 May 2016 | 15 Jul 2016 | 26 Jul 2016 |  | 69 | 0 | 80 | 0
A1 HYDRO-PNUEMATIC SYSTEM 02 MATERIAL AT SITE -40% | 58004 | R.S. | 16 Jul 2016 | 07 Sep 2016 | 20 Sep 2016 |  | 53 | 0 | 66 | 0
A1 HYDRO-PNUEMATIC SYSTEM 03 INSTALLATION - 20% | 29002 | R.S. | 08 Sep 2016 | 24 Sep 2016 | 20 Sep 2016 |  | 16 | 0 | 12 | 0
A1 HYDRO-PNUEMATIC SYSTEM 04 COMMISSIONING & TESTING 20% | 29002 | R.S. | 26 Sep 2016 | 04 Oct 2016 |  |  | 8 | 0 | 0 | 0
A1 FIRE DOORS | 0 | No Unit | 05 Jun 2015 | 12 Oct 2016 |  |  | 495 | 0 | 0 | 0
LABOUR WORK - NOT IN USE | 0 | No Unit | 05 Jun 2015 | 09 Jul 2015 |  |  | 34 | 0 | 0 | 0
LABOUR WORK - NOT IN USE ON INSTALLATION 100% | 0 | No. | 05 Jun 2015 | 09 Jul 2015 | 14 Jul 2016 | 31 Dec 2016 | 34 | 170 | 405 | 541
FIRE DOORS (M+L) | 0 | No Unit | 29 Jun 2016 | 12 Oct 2016 |  |  | 105 | 0 | 0 | 0
FIRE DOORS (M+L) 03 HANDING OVER -15% | 16 | No. | 29 Jun 2016 | 07 Sep 2016 | 31 Mar 2016 | 30 Jan 2017 | 70 | 305 | 0 | 145
FIRE DOORS (M+L) 01 MATERIAL AT SITE - 55% | 16 | No. | 29 Jun 2016 | 07 Sep 2016 | 31 Mar 2016 | 10 May 2016 | 70 | 40 | 0 | 0
FIRE DOORS (M+L) 02 INSTALLATION - 30% | 16 | No. | 08 Sep 2016 | 12 Oct 2016 | 20 Jun 2016 | 20 Jun 2016 | 34 | 0 | 0 | 0
A1 PIPED GAS SYSTEM | 0 | No Unit | 20 Jul 2016 | 15 Oct 2016 |  |  | 87 | 0 | 0 | 0
A1 PIPED GAS SYSTEM 01 VERTICAL RISER - 20% | 139209.8 | R.S. | 20 Jul 2016 | 05 Aug 2016 | 14 Jul 2016 |  | 16 | 0 | 0 | 0
A1 PIPED GAS SYSTEM 02 SECOND STAGE REGULATION - 10% | 69604.9 | R.S. | 20 Jul 2016 | 05 Aug 2016 | 20 Sep 2016 |  | 16 | 0 | 62 | 0
A1 PIPED GAS SYSTEM 03 GAS BANK INTERNAL WORK - 20% | 139209.8 | R.S. | 20 Jul 2016 | 05 Aug 2016 | 20 Sep 2016 |  | 16 | 0 | 62 | 0
A1 PIPED GAS SYSTEM 04 INTERIOR WORKS OF FLATS - 25% | 174012.25 | R.S. | 20 Jul 2016 | 05 Aug 2016 | 20 Sep 2016 |  | 16 | 0 | 62 | 0
A1 PIPED GAS SYSTEM 05 METER INSTALLATION -10% | 69604.9 | R.S. | 06 Aug 2016 | 15 Oct 2016 | 20 Sep 2016 |  | 70 | 0 | 45 | 0
A1 PIPED GAS SYSTEM 06 TESTING, TPI, FINAL FIRE NOC - 10% | 69604.9 | R.S. | 25 Aug 2016 | 15 Oct 2016 | 30 Jan 2017 |  | 51 | 0 | 158 | 0
A1 PIPED GAS SYSTEM 07 TEST CERTIFICATE OF EQUIPMENTS- 5% | 34802.45 | R.S. | 25 Aug 2016 | 15 Oct 2016 | 30 Jan 2017 |  | 51 | 0 | 158 | 0
A1-DEPT. LABOUR | 0 | No Unit | 05 Jun 2015 | 30 Dec 2016 |  |  | 574 | 0 | 0 | 0
A1-CONTRACTOR DEPT. LABOUR | 0 | No Unit | 05 Jun 2015 | 30 Dec 2016 |  |  | 574 | 0 | 0 | 0
A1- MAY 15 | 0 | No Unit | 05 Jun 2015 | 30 Jun 2015 |  |  | 25 | 0 | 0 | 0
A1- May 15 Contractor Dept. Labour | 6388.1 | R.S. | 05 Jun 2015 | 30 Jun 2015 | 26 Aug 2015 | 27 Aug 2015 | 25 | 1 | 82 | 58
A1- JUNE 15 | 0 | No Unit | 05 Jun 2015 | 30 Jun 2015 |  |  | 25 | 0 | 0 | 0
A1- June 15 Contractor Dept. Labour | 6388.1 | R.S. | 05 Jun 2015 | 30 Jun 2015 | 26 Aug 2015 | 27 Aug 2015 | 25 | 1 | 82 | 58
A1- JULY 15 | 0 | No Unit | 01 Jul 2015 | 31 Jul 2015 |  |  | 30 | 0 | 0 | 0
A1- July 15 Contractor Dept. Labour | 6388.1 | R.S. | 01 Jul 2015 | 31 Jul 2015 | 20 Aug 2015 | 27 Aug 2015 | 30 | 7 | 50 | 27
A1- AUG 15 | 0 | No Unit | 01 Aug 2015 | 31 Aug 2015 |  |  | 30 | 0 | 0 | 0
A1- Aug 15 Contractor Dept. Labour | 6388.1 | R.S. | 01 Aug 2015 | 31 Aug 2015 | 20 Aug 2015 | 09 Dec 2015 | 30 | 111 | 19 | 100
A1-SEPT 15 | 0 | No Unit | 01 Sep 2015 | 30 Sep 2015 |  |  | 29 | 0 | 0 | 0
A1-Sept 15 Contractor Dept. Labour | 6388.1 | R.S. | 01 Sep 2015 | 30 Sep 2015 | 03 Oct 2015 | 09 Dec 2015 | 29 | 67 | 32 | 70
A1- OCT 15 | 0 | No Unit | 01 Oct 2015 | 31 Oct 2015 |  |  | 30 | 0 | 0 | 0
A1- Oct 15 Contractor Dept. Labour | 6388.1 | R.S. | 01 Oct 2015 | 31 Oct 2015 | 17 Oct 2015 | 10 May 2016 | 30 | 206 | 16 | 192
A1- NOV 15 | 0 | No Unit | 02 Nov 2015 | 30 Nov 2015 |  |  | 28 | 0 | 0 | 0
A1- Nov 15 Contractor Dept. Labour | 6388.1 | R.S. | 02 Nov 2015 | 30 Nov 2015 | 23 Nov 2015 | 10 May 2016 | 28 | 169 | 21 | 162
A1- DEC 15 | 0 | No Unit | 01 Dec 2015 | 30 Dec 2015 |  |  | 29 | 0 | 0 | 0
A1- Dec 15 Contractor Dept. Labour | 8517.47 | R.S. | 01 Dec 2015 | 30 Dec 2015 | 09 Dec 2015 | 10 May 2016 | 29 | 153 | 8 | 132
A1- JAN 16 | 0 | No Unit | 01 Jan 2016 | 30 Jan 2016 |  |  | 29 | 0 | 0 | 0
A1- Jan 16 Contractor Dept. Labour | 8517.47 | R.S. | 01 Jan 2016 | 30 Jan 2016 | 19 Jan 2016 | 10 May 2016 | 29 | 112 | 18 | 101
A1- FEB 16 | 0 | No Unit | 01 Feb 2016 | 29 Feb 2016 |  |  | 28 | 0 | 0 | 0
A1- Feb 16 Contractor Dept. Labour | 8517.47 | R.S. | 01 Feb 2016 | 29 Feb 2016 | 18 Feb 2016 | 10 May 2016 | 28 | 82 | 17 | 71
A1- MARCH 16 | 0 | No Unit | 01 Mar 2016 | 31 Mar 2016 |  |  | 30 | 0 | 0 | 0
A1- March 16 Contractor Dept. Labour | 8517.47 | R.S. | 01 Mar 2016 | 31 Mar 2016 | 18 Mar 2016 | 10 May 2016 | 30 | 53 | 17 | 40
A1-APRIL 16 | 0 | No Unit | 01 Apr 2016 | 30 Apr 2016 |  |  | 29 | 0 | 0 | 0
A1-April 16 Contractor Dept. Labour | 8517.47 | R.S. | 01 Apr 2016 | 30 Apr 2016 | 19 Apr 2016 | 08 Aug 2016 | 29 | 111 | 18 | 100
A1-MAY 16 | 0 | No Unit | 02 May 2016 | 31 May 2016 |  |  | 29 | 0 | 0 | 0
A1-May 16 Contractor Dept. Labour | 8517.47 | R.S. | 02 May 2016 | 31 May 2016 | 09 May 2016 | 08 Aug 2016 | 29 | 91 | 7 | 69
A1--JUNE 16 | 0 | No Unit | 01 Jun 2016 | 30 Jun 2016 |  |  | 29 | 0 | 0 | 0
A1--June 16 Contractor Dept. Labour | 8517.47 | R.S. | 01 Jun 2016 | 30 Jun 2016 | 04 Jul 2016 | 08 Aug 2016 | 29 | 35 | 33 | 39
A1 -JULY 16 | 0 | No Unit | 01 Jul 2016 | 30 Jul 2016 |  |  | 29 | 0 | 0 | 0
A1 -July 16 Contractor Dept. Labour | 8517.47 | R.S. | 01 Jul 2016 | 30 Jul 2016 | 08 Aug 2016 | 24 Sep 2016 | 29 | 47 | 38 | 56
A1- AUG 16 | 0 | No Unit | 01 Aug 2016 | 31 Aug 2016 |  |  | 30 | 0 | 0 | 0
A1- Aug 16 Contractor Dept. Labour | 8517.47 | R.S. | 01 Aug 2016 | 31 Aug 2016 | 08 Aug 2016 | 24 Sep 2016 | 30 | 47 | 7 | 24
A1- SEPT 16 | 0 | No Unit | 01 Sep 2016 | 30 Sep 2016 |  |  | 29 | 0 | 0 | 0
A1- Sept 16 Contractor Dept. Labour | 8517.47 | R.S. | 01 Sep 2016 | 30 Sep 2016 | 14 Sep 2016 |  | 29 | 0 | 13 | 0
A1-OCT 16 | 0 | No Unit | 01 Oct 2016 | 31 Oct 2016 |  |  | 30 | 0 | 0 | 0
A1-Oct 16 Contractor Dept. Labour | 20357.47 | R.S. | 01 Oct 2016 | 31 Oct 2016 | 10 Oct 2016 |  | 30 | 0 | 9 | 0
A1-NOV 16 | 0 | No Unit | 01 Nov 2016 | 30 Nov 2016 |  |  | 29 | 0 | 0 | 0
A1-Nov 16 Contractor Dept. Labour | 13534.34 | R.S. | 01 Nov 2016 | 30 Nov 2016 |  |  | 29 | 0 | 0 | 0
A1-DEC 16 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1-Dec 16 Contractor Dept. Labour | 13534.34 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1-JAN 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1-Jan 17 Contractor Dept. Labour | 13534.34 | R.S. | 01 Dec 2016 | 30 Dec 2016 | 21 Jan 2017 |  | 29 | 0 | 51 | 0
A1-FEB 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1-Feb 17 Contractor Dept. Labour | 13541.76 | R.S. | 01 Dec 2016 | 30 Dec 2016 | 22 Feb 2017 |  | 29 | 0 | 83 | 0
A1-MARCH 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1-March 17 Contractor Dept. Labour | 13541.76 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1-APRIL 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1-April 17 Contractor Dept. Labour | 8517.47 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1-MAY 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1-May 17 Contractor Dept. Labour | 8517.47 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- JUNE 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- June 17 Contractor Dept. Labour | 6388.1 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- JULY 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- July 17 Contractor Dept. Labour | 6388.1 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- AUG 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- Aug 17 Contractor Dept. Labour | 6388.1 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1-SEPT 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1-Sept 17 Contractor Dept. Labour | 6388.1 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- OCT 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- Oct 17 Contractor Dept. Labour | 6388.1 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- COMPANY DEPT. LABOUR | 0 | No Unit | 05 Jun 2015 | 30 Dec 2016 |  |  | 574 | 0 | 0 | 0
A1- MAY 15 | 0 | No Unit | 05 Jun 2015 | 30 Jun 2015 |  |  | 25 | 0 | 0 | 0
A1- May 15 Dept. Labour work | 22698.36 | R.S. | 05 Jun 2015 | 30 Jun 2015 | 04 Jul 2015 | 27 Aug 2015 | 25 | 54 | 29 | 58
A1- JUNE 15 | 0 | No Unit | 05 Jun 2015 | 30 Jun 2015 |  |  | 25 | 0 | 0 | 0
A1- June 15 Dept. Labour work | 22698.36 | R.S. | 05 Jun 2015 | 30 Jun 2015 | 04 Jul 2015 | 27 Aug 2015 | 25 | 54 | 29 | 58
A1- JULY 15 | 0 | No Unit | 01 Jul 2015 | 31 Jul 2015 |  |  | 30 | 0 | 0 | 0
A1- July 15 Dept. Labour work | 22698.36 | R.S. | 01 Jul 2015 | 31 Jul 2015 | 26 Aug 2015 | 27 Aug 2015 | 30 | 1 | 56 | 27
A1- AUG 15 | 0 | No Unit | 01 Aug 2015 | 31 Aug 2015 |  |  | 30 | 0 | 0 | 0
A1- Aug 15 Dept. Labour work | 22698.36 | R.S. | 01 Aug 2015 | 31 Aug 2015 | 26 Aug 2015 | 09 Dec 2015 | 30 | 105 | 25 | 100
A1- SEPT 15 | 0 | No Unit | 01 Sep 2015 | 30 Sep 2015 |  |  | 29 | 0 | 0 | 0
A1- Sept 15 Dept. Labour work | 22698.36 | R.S. | 01 Sep 2015 | 30 Sep 2015 | 01 Nov 2015 | 09 Dec 2015 | 29 | 38 | 61 | 70
A1- OCT 15 | 0 | No Unit | 01 Oct 2015 | 31 Oct 2015 |  |  | 30 | 0 | 0 | 0
A1- Oct 15 Dept. Labour work | 22698.36 | R.S. | 01 Oct 2015 | 31 Oct 2015 | 18 Oct 2015 | 10 May 2016 | 30 | 205 | 17 | 192
A1- NOV 15 | 0 | No Unit | 02 Nov 2015 | 30 Nov 2015 |  |  | 28 | 0 | 0 | 0
A1- Nov 15 Dept. Labour work | 22698.36 | R.S. | 02 Nov 2015 | 30 Nov 2015 | 23 Nov 2015 | 10 May 2016 | 28 | 169 | 21 | 162
A1- DEC 15 | 0 | No Unit | 01 Dec 2015 | 30 Dec 2015 |  |  | 29 | 0 | 0 | 0
A1- Dec 15 Dept. Labour work | 34678.64 | R.S. | 01 Dec 2015 | 30 Dec 2015 | 09 Dec 2015 | 10 May 2016 | 29 | 153 | 8 | 132
A1--JAN 16 | 0 | No Unit | 01 Jan 2016 | 30 Jan 2016 |  |  | 29 | 0 | 0 | 0
A1--Jan 16 Dept. Labour work | 34678.64 | R.S. | 01 Jan 2016 | 30 Jan 2016 | 19 Jan 2016 | 10 May 2016 | 29 | 112 | 18 | 101
A1- FEB 16 | 0 | No Unit | 01 Feb 2016 | 29 Feb 2016 |  |  | 28 | 0 | 0 | 0
A1- Feb 16 Dept. Labour work | 34678.64 | R.S. | 01 Feb 2016 | 29 Feb 2016 | 18 Feb 2016 | 10 May 2016 | 28 | 82 | 17 | 71
A1- MARCH 16 | 0 | No Unit | 01 Mar 2016 | 31 Mar 2016 |  |  | 30 | 0 | 0 | 0
A1- March 16 Dept. Labour work | 34678.64 | R.S. | 01 Mar 2016 | 31 Mar 2016 | 18 Mar 2016 | 10 May 2016 | 30 | 53 | 17 | 40
A1- APRIL 16 | 0 | No Unit | 01 Apr 2016 | 30 Apr 2016 |  |  | 29 | 0 | 0 | 0
A1- April 16 Dept. Labour work | 34678.64 | R.S. | 01 Apr 2016 | 30 Apr 2016 | 19 Apr 2016 | 08 Aug 2016 | 29 | 111 | 18 | 100
A1- MAY 16 | 0 | No Unit | 02 May 2016 | 31 May 2016 |  |  | 29 | 0 | 0 | 0
A1- May 16 Dept. Labour work | 34678.64 | R.S. | 02 May 2016 | 31 May 2016 | 09 May 2016 | 08 Aug 2016 | 29 | 91 | 7 | 69
A1- JUNE 16 | 0 | No Unit | 01 Jun 2016 | 30 Jun 2016 |  |  | 29 | 0 | 0 | 0
A1- June 16 Dept. Labour work | 34678.64 | R.S. | 01 Jun 2016 | 30 Jun 2016 | 04 Jul 2016 | 08 Aug 2016 | 29 | 35 | 33 | 39
A1- JULY 16 | 0 | No Unit | 01 Jul 2016 | 30 Jul 2016 |  |  | 29 | 0 | 0 | 0
A1- July 16 Dept. Labour work | 41279 | R.S. | 01 Jul 2016 | 30 Jul 2016 | 02 Aug 2016 | 08 Aug 2016 | 29 | 6 | 32 | 9
A1- AUG 16 | 0 | No Unit | 01 Aug 2016 | 31 Aug 2016 |  |  | 30 | 0 | 0 | 0
A1- Aug 16 Dept. Labour work | 34678.64 | R.S. | 01 Aug 2016 | 31 Aug 2016 | 08 Aug 2016 | 24 Sep 2016 | 30 | 47 | 7 | 24
A1- SEPT 16 | 0 | No Unit | 01 Sep 2016 | 30 Sep 2016 |  |  | 29 | 0 | 0 | 0
A1- Sept 16 Dept. Labour work | 41854 | R.S. | 01 Sep 2016 | 30 Sep 2016 | 14 Sep 2016 |  | 29 | 0 | 13 | 0
A1- OCT 16 | 0 | No Unit | 01 Oct 2016 | 31 Oct 2016 |  |  | 30 | 0 | 0 | 0
A1- Oct 16 Dept. Labour work | 34166 | R.S. | 01 Oct 2016 | 31 Oct 2016 | 05 Nov 2016 |  | 30 | 0 | 35 | 0
A1- NOV 16 | 0 | No Unit | 01 Nov 2016 | 30 Nov 2016 |  |  | 29 | 0 | 0 | 0
A1- Nov 16 Dept. Labour work | 37950 | R.S. | 01 Nov 2016 | 30 Nov 2016 | 30 Nov 2016 |  | 29 | 0 | 29 | 0
A1- DEC 16 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- Dec 16 Dept. Labour work | 85073 | R.S. | 01 Dec 2016 | 30 Dec 2016 | 20 Dec 2016 |  | 29 | 0 | 19 | 0
A1- -JAN 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- -Jan 17 Dept. Labour work | 71412 | R.S. | 01 Dec 2016 | 30 Dec 2016 | 21 Jan 2017 |  | 29 | 0 | 51 | 0
A1- FEB 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- Feb 17 Dept. Labour work | 59648 | R.S. | 01 Dec 2016 | 30 Dec 2016 | 22 Feb 2017 |  | 29 | 0 | 83 | 0
A1- MARCH 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- March 17 Dept. Labour work | 15025 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- APRIL 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- April 17 Dept. Labour work | 8633 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- MAY 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- May 17 Dept. Labour work | 3196.34 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- JUNE 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- June 17 Dept. Labour work | 22186 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- JULY 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- July 17 Dept. Labour work | 22186 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- AUG 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- Aug 17 Dept. Labour work | 4386 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- SEPT 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- Sept 17 Dept. Labour work | 4386 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- OCT 17 | 0 | No Unit | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- Oct 17 Dept. Labour work | 3548 | R.S. | 01 Dec 2016 | 30 Dec 2016 |  |  | 29 | 0 | 0 | 0
A1- EXTRA WORK DUE TO CHANGES | 0 | No Unit | 05 Jun 2015 | 08 Dec 2016 |  |  | 552 | 0 | 0 | 0
A1- Extra work due to changes Redo Work | 502315 | Job | 05 Jun 2015 | 08 Dec 2016 | 09 May 2016 |  | 552 | 0 | 339 | 0
A1-BLDG.MISC | 62476 | No Unit | 27 Jun 2015 | 30 Dec 2016 |  |  | 552 | 0 | 0 | 0
A1-Bldg.Misc Letter Box | 54 | NO | 05 Jul 2016 | 08 Jul 2016 | 30 Dec 2016 |  | 3 | 0 | 178 | 0
A1-Bldg.Misc Misc. S.S Flat owner name display board | 1 | R.S. | 05 Jul 2016 | 13 Jul 2016 | 17 Jan 2017 |  | 8 | 0 | 196 | 0
A1-Bldg.Misc Fixing Work | 54 | No. | 05 Jul 2016 | 13 Jul 2016 | 17 Jan 2017 |  | 8 | 0 | 196 | 0
A1-Bldg.Misc Notice Board | 2 | NO | 05 Jul 2016 | 07 Jul 2016 | 17 Jan 2017 |  | 2 | 0 | 196 | 0
A1-Bldg.Misc Local Trip Labour Shifting | 750 | Trip | 27 Jun 2015 | 30 Dec 2016 | 18 Jun 2015 |  | 552 | 0 | 0 | 0
A1-Bldg.Misc Core Cutting | 108 | No. | 29 Jun 2016 | 02 Aug 2016 | 09 May 2016 |  | 34 | 0 | 0 | 0
A1-Bldg.Misc Bldg. Misc (Lab) | 1 | Job | 27 Jun 2015 | 30 Dec 2016 | 30 Nov 2015 |  | 552 | 0 | 156 | 0
A1-Bldg.Misc Extra work-Other & Misc | 0 | Sft. | 27 Jun 2015 | 30 Dec 2016 | 09 Dec 2016 |  | 552 | 0 | 531 | 0
A1-Bldg.Misc Maintenance | 0 | NO | 05 Jul 2016 | 18 Oct 2016 |  |  | 105 | 0 | 0 | 0
A1-Bldg.Misc Artistic Painting | 1 | Job | 08 Jul 2016 | 16 Jul 2016 | 01 Mar 2017 |  | 8 | 0 | 236 | 0
A1-Bldg.Misc Bonus to labour Contractor | 0 | Sft. | 18 Jul 2016 | 22 Aug 2016 |  |  | 35 | 0 | 0 | 0
A1-Bldg.Misc Crack filler (Painting) | 1 | Lump-Sum | 28 Mar 2016 | 18 May 2016 |  |  | 51 | 0 | 0 | 0
A1-Bldg.Misc Parking Drive (Painting) | 1 | R.S. | 08 Jul 2016 | 16 Jul 2016 |  |  | 8 | 0 | 0 | 0
A1-Bldg.Misc Radium Patti (Column) | 0 | Rft | 08 Jul 2016 | 16 Jul 2016 |  |  | 8 | 0 | 0 | 0
A1-Bldg.Misc Reflection Paint (Column) | 0 | Sft. | 08 Jul 2016 | 16 Jul 2016 |  |  | 8 | 0 | 0 | 0
A1-Bldg.Misc Flat Maintenance (Lab) | 52 | Lump-Sum | 27 Jun 2015 | 30 Dec 2016 |  |  | 552 | 0 | 0 | 0
A1-Bldg.Misc QAD Paint NOC | 52 | No. | 09 Feb 2016 | 28 Nov 2016 | 09 May 2016 | 25 Jan 2017 | 293 | 261 | 90 | 58
A1-REFUGE AREA | 0 | No Unit | 21 Jan 2016 | 30 Jan 2016 |  |  | 9 | 0 | 0 | 0
A1-REFUGE AREA RCC | 0 | No Unit | 21 Jan 2016 | 30 Jan 2016 |  |  | 9 | 0 | 0 | 0
A1-Refuge Area RCC Steel | 0 | M.T. | 21 Jan 2016 | 30 Jan 2016 | 31 Mar 2016 |  | 9 | 0 | 70 | 0
A1-Refuge Area RCC RCC M-20 | 123.58 | Cft | 21 Jan 2016 | 30 Jan 2016 | 31 Mar 2016 |  | 9 | 0 | 70 | 0
A1-REFUGE AREA FABRICATION (M+L) | 0 | No Unit | 25 Jun 2014 |  |  |  | 0 | 0 | 0 | 0
A1-Refuge Area Fabrication (M+L) Railing- Living (M+L) | 192.07 | Sft. | 04 Jun 2016 |  | 07 Jun 2016 |  | 0 | 0 | 3 | 0
A1-REFUGE AREA ELECTRICAL (M+L) | 0 | No Unit | 25 Jun 2014 |  |  |  | 0 | 0 | 0 | 0
A1-Refuge Area Electrical (M+L) Slab conduiting (M+L) | 0 | Sft. | 18 Jun 2016 |  |  |  | 0 | 0 | 0 | 0
A1-Refuge Area Electrical (M+L) Wall Dropping (M+L) | 0 | Sft. | 18 Jun 2016 |  |  |  | 0 | 0 | 0 | 0
A1-Refuge Area Electrical (M+L) Wiring (M+L) | 0 | Sft. | 18 Jun 2016 |  |  |  | 0 | 0 | 0 | 0
A1-Refuge Area Electrical (M+L) Switches,Plates & Acc. (M+L | 0 | Sft. | 18 Jun 2016 |  |  |  | 0 | 0 | 0 | 0
A1-Refuge Area Electrical (M+L) MCB-DB (M)- 2BHK 2T | 0 | No. | 18 Jun 2016 |  |  |  | 0 | 0 | 0 | 0
A1-Refuge Area Electrical (M+L) ACCL | 0 | NO | 18 Jun 2016 |  |  |  | 0 | 0 | 0 | 0
A1-REFUGE AREA TILLING | 0 | No Unit | 25 Jun 2014 |  |  |  | 0 | 0 | 0 | 0
A1-Refuge Area Tilling Refuge Ceramic Flooring | 504.76 | Sft. | 04 Jul 2016 |  | 18 Jul 2016 |  | 0 | 0 | 14 | 0
A1-Refuge Area Tilling Refuge Ceramic Skirting | 0 | Rft | 04 Jul 2016 |  | 18 Jul 2016 |  | 0 | 0 | 14 | 0
A1-REFUGE AREA MISC. | 0 | No Unit | 23 May 2015 |  |  |  | 0 | 0 | 0 | 0
A1-Refuge Area Misc. Misc. & Other | 1 | No. | 23 May 2015 |  | 13 Dec 2016 |  | 0 | 0 | 570 | 0
A1-REFUGE AREA WATERPROOFING | 0 | No Unit | 23 May 2015 |  |  |  | 0 | 0 | 0 | 0
A1-Refuge Area Waterproofing Screed + Chemical W/P (Refuge) | 587.29 | Sft. | 23 May 2015 |  | 01 Dec 2016 |  | 0 | 0 | 558 | 0
A1-MEMO TO CONTRACTOR | 0 | No Unit | 23 May 2015 |  |  |  | 0 | 0 | 0 | 0
A1-MEMO TO CONTRACTOR Memo to Contractor (Lab) | 15057.5 | R.S. | 28 Sep 2016 |  | 28 Sep 2016 |  | 0 | 0 | 0 | 0
CLIENT EXTRA AMENITY | 0 | No Unit | 23 May 2015 |  |  |  | 0 | 0 | 0 | 0
A1 | 0 | No Unit | 23 May 2015 |  |  |  | 0 | 0 | 0 | 0
A1-601 | 0 | No Unit | 23 May 2015 |  |  |  | 0 | 0 | 0 | 0
A1-601 AAC Block Masonry 4" | 9 | Sft. | 23 May 2015 |  | 14 Mar 2017 |  | 0 | 0 | 661 | 0
A1-601 Gypsum Plaster | 19.5 | Sft. | 23 May 2015 |  | 14 Mar 2017 |  | 0 | 0 | 661 | 0
A1-601 Kitchen Granite Top | 1 | No. | 23 May 2015 |  | 14 Mar 2017 |  | 0 | 0 | 661 | 0
A1-601 Tiling Work | 690 | Job | 23 May 2015 |  | 14 Mar 2017 |  | 0 | 0 | 661 | 0
DRAWINGS | 0 | Dz 12nos) | 06 Aug 2016 |  |  |  | 0 | 0 | 0 | 0
RCC | 0 | Dz 12nos) | 06 Aug 2016 |  |  |  | 0 | 0 | 0 | 0
RCC 6th Fl Slab with Index & Schedule | 0 | No. | 06 Aug 2016 |  |  |  | 0 | 0 | 0 | 0
TOWER A1 Gypsum butt finish incl NOC (M+L) | 0 | Sft. | 06 Aug 2016 |  |  |  | 0 | 0 | 0 | 0
TOWER B1 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-EARTHWORK | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Earthwork Site cleaning | 6 | Day | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Earthwork Excavation in Soil/Soft Murum | 647.2183 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Earthwork Excavation in Bolder /Hard Murum | 1164.993 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Earthwork Excavation in Rock | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Earthwork Excavation in Manjra Rock | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Earthwork Royalty Charges | 0 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Earthwork Back Filling | 1883.4054 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Earthwork Antitermite Treatment | 6461.8445 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Earthwork Rubble Soling 9`` | 4755.4835 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Earthwork Carting away | 89508.7437 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Earthwork Carting away | 93025.1587 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-LINE OUT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Line out PCC M-10 | 50 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-W/P -PLINTH | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-W/P -plinth Box Type W/P(C) | 1077.4287 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-W/P -plinth W/P plaster(C) | 734.747 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- M & P | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- M & P BBM 9" | 318.8028 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PLUM CONCRETE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Plum Concrete Plum Concrete RCC M10 (60P, 40C) | 0 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Earthwork Shifting of Rabit by tractor (Morter Was | 36066.91 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-RCC | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PLINTH | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FOOTING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Footing Steel | 6.24 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Footing RMC M-10 Plant /Production | 27.23 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Footing RMC M-10 Site | 27.23 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Footing RMC M-30 Plant /Production | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Footing RMC M-30 Site | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Footing Buttering | 3 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Footing RMC M-25 Plant/Production | 107.44 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Footing RMC M-25 Site | 107.44 | Cum. | 15 Apr 2017 |  | 14 Aug 2019 |  | 0 | 0 | 851 | 0
B1- Footing RMC M-25 Plant /Production | 9.5 | Cum. | 24 Dec 2019 | 24 Dec 2019 |  |  | 0 | 0 | 0 | 0
B1- COL. UP TO PLINTH | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Col. Up to Plinth Steel | 10.45 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Col. Up to Plinth RMC M-30 Plant /Production | 43.94 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Col. Up to Plinth RMC M-30 Site | 43.94 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Col. Up to Plinth RCC M-30 | 0 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 PLINTH BEAM/ TIE BEAM | 7.7858 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 Plinth Beam/ Tie Beam Steel | 2.422 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 Plinth Beam/ Tie Beam RMC M-10 Plant /Production | 9.54 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 Plinth Beam/ Tie Beam RMC M-10 Site | 9.54 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 Plinth Beam/ Tie Beam RMC M-20 Plant /Production | 15.32 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1 Plinth Beam/ Tie Beam RMC M-20 Site | 15.32 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 Plinth Beam/ Tie Beam Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PLINTH FL. PCC | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Plinth Fl. PCC RMC M-10 Plant /Production | 30.43 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Plinth Fl. PCC RMC M-10 Site | 30.43 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-RCC PLINTH (LAB) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-RCC Plinth (Lab) RCC Plinth (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1 1ST SLAB (STILT FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- STILT COLUMN | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- Stilt column Steel | 10.57 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- Stilt column RCC M-30 | 1440.24 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST SLAB (STILT FL.) | 22.51 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Slab (Stilt Fl.) Steel | 9.389 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Slab (Stilt Fl.) RMC M-20 Plant /Production | 66.5 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B1-1st Slab (Stilt Fl.) RMC M-20 Site | 66.5 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Slab (Stilt Fl.) RCC M-20 | 162 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Slab (Stilt Fl.) RMC M-30 Plant /Production | 18.75 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Slab (Stilt Fl.) RMC M-30 Site | 18.75 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Slab (Stilt Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Slab (Stilt Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Slab (Stilt Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  | 04 Dec 2019 |  | 0 | 0 | 963 | 0
B-1- STILT FLR.CORNICE/PARDI/CILL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- Stilt Flr.Cornice/Pardi/Cill Steel | 0.11 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- Stilt Flr.Cornice/Pardi/Cill RCC M-20 | 19.288 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 2ND SLAB (1ST FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 1ST FL. COLUMN | 7.7858 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 1st Fl. column Steel | 7.62 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 1st Fl. column RCC M-30 | 1289.39 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 2ND SLAB (1ST FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 2nd Slab (1st Fl.) Steel | 7.72 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 2nd Slab (1st Fl.) RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1- 2nd Slab (1st Fl.) RMC M-20 Site | 77.57 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 2nd Slab (1st Fl.) RCC M-20 | 118.55 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 2nd Slab (1st Fl.) RMC M-30 Plant /Production | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 2nd Slab (1st Fl.) RMC M-30 Site | 10.91 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 2nd Slab (1st Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 2nd Slab (1st Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 2nd Slab (1st Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 1ST FLR.CORNICE/PARDI/CILL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 1st Flr.Cornice/Pardi/Cill Steel | 0.3 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 1st Flr.Cornice/Pardi/Cill RCC M-20 | 87.45 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 3RD SLAB (2ND FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 2ND FL. COLUMN | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 2nd Fl. column Steel | 6.64 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 2nd Fl. column RCC M-30 | 1089.02 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 3RD SLAB (2ND FL.) | 7.1859 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 3rd Slab (2nd Fl.) Steel | 6.84 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 3rd Slab (2nd Fl.) RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1- 3rd Slab (2nd Fl.) RMC M-20 Site | 77.88 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 3rd Slab (2nd Fl.) RCC M-20 | 184.17 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 3rd Slab (2nd Fl.) RMC M-30 Plant /Production | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 3rd Slab (2nd Fl.) RMC M-30 Site | 9.2 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 3rd Slab (2nd Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 3rd Slab (2nd Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 3rd Slab (2nd Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 2ND FLR.CORNICE/PARDI/CILL | 87.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 2nd Flr.Cornice/Pardi/Cill Steel | 0.12 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 2nd Flr.Cornice/Pardi/Cill RCC M-20 | 87.45 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 4TH SLAB (3RD FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 3RD FL. COLUMN | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 3rd Fl. column Steel | 5.95 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 3rd Fl. column RCC M-30 | 942.81 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 4TH SLAB (3RD FL.) | 4.71 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 4th Slab (3rd Fl.) Steel | 8.02 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 4th Slab (3rd Fl.) RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1- 4th Slab (3rd Fl.) RMC M-20 Site | 74.57 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 4th Slab (3rd Fl.) RCC M-20 | 184.17 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 4th Slab (3rd Fl.) RMC M-30 Plant /Production | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 4th Slab (3rd Fl.) RMC M-30 Site | 7.99 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 4th Slab (3rd Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 4th Slab (3rd Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 4th Slab (3rd Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 3RD FLR.CORNICE/PARDI/CILL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 3rd Flr.Cornice/Pardi/Cill Steel | 0.15 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 3rd Flr.Cornice/Pardi/Cill RCC M-20 | 87.45 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 5TH SLAB (4TH FL.) | 5.7416 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 4TH FL. COLUMN | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 4th Fl. column Steel | 5.9 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 4th Fl. column RCC M-30 | 942.81 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 5TH SLAB (4TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 5th Slab (4th Fl.) Steel | 6.97 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 5th Slab (4th Fl.) RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1- 5th Slab (4th Fl.) RMC M-20 Site | 77.88 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 5th Slab (4th Fl.) RCC M-20 | 184.17 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 5th Slab (4th Fl.) RMC M-30 Plant /Production | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 5th Slab (4th Fl.) RMC M-30 Site | 7.99 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 5th Slab (4th Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 5th Slab (4th Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 5th Slab (4th Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 4TH FLR.CORNICE/PARDI/CILL | 87.45 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 4th Flr.Cornice/Pardi/Cill Steel | 0.2 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 4th Flr.Cornice/Pardi/Cill RCC M-20 | 47.24 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 6TH SLAB (5TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 5TH FL. COLUMN | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 5th Fl. column Steel | 5.84 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 5th Fl. column RCC M-25 | 939.43 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 6TH SLAB (5TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 6th Slab (5th Fl.) Steel | 6.53 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 6th Slab (5th Fl.) RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1- 6th Slab (5th Fl.) RMC M-20 Site | 79.57 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 6th Slab (5th Fl.) RCC M-20 | 184.17 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 6th Slab (5th Fl.) RMC M-25 Plant /Production | 0 | Cum. | 24 Dec 2019 | 24 Dec 2019 |  |  | 0 | 0 | 0 | 0
B-1- 6th Slab (5th Fl.) RMC M-25 Site | 7.95 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 6th Slab (5th Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 6th Slab (5th Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 6th Slab (5th Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 5TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 5th Flr.Cornice/Pardi/Cill Steel | 0.12 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 5th Flr.Cornice/Pardi/Cill RCC M-20 | 30.99 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 7TH SLAB (6TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 6TH FL. COLUMN | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 6th Fl. column Steel | 5.57 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 6th Fl. column RCC M-25 | 907.31 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 7TH SLAB (6TH FL.) | 7.1859 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 7th Slab (6th Fl.) Steel | 5.82 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 7th Slab (6th Fl.) RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1- 7th Slab (6th Fl.) RMC M-20 Site | 76.88 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 7th Slab (6th Fl.) RCC M-20 | 184.17 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 7th Slab (6th Fl.) RMC M-25 Plant /Production | 0 | Cum. | 24 Dec 2019 | 24 Dec 2019 |  |  | 0 | 0 | 0 | 0
B-1- 7th Slab (6th Fl.) RMC M-25 Site | 7.68 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 7th Slab (6th Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 7th Slab (6th Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 7th Slab (6th Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-16TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-16th Flr.Cornice/Pardi/Cill Steel | 0.2 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-16th Flr.Cornice/Pardi/Cill RCC M-20 | 47.24 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 8TH SLAB (7TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 7TH FL. COLUMN | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 7th Fl. column Steel | 5.44 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 7th Fl. column RCC M-25 | 903.93 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 8TH SLAB (7TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 8th Slab (7th Fl.) Steel | 6.53 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 8th Slab (7th Fl.) RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1- 8th Slab (7th Fl.) RMC M-20 Site | 76.57 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 8th Slab (7th Fl.) RCC M-20 | 184.17 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 8th Slab (7th Fl.) RMC M-25 Plant /Production | 0 | Cum. | 24 Dec 2019 | 24 Dec 2019 |  |  | 0 | 0 | 0 | 0
B-1- 8th Slab (7th Fl.) RMC M-25 Site | 7.65 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 8th Slab (7th Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 8th Slab (7th Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 8th Slab (7th Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 7TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 7th Flr.Cornice/Pardi/Cill Steel | 0.12 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 7th Flr.Cornice/Pardi/Cill RCC M-20 | 30.99 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 9TH SLAB (8TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 8TH FL. COLUMN | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 8th Fl. column Steel | 5.45 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 8th Fl. column RCC M-25 | 921.2 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 9TH SLAB (8TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 9th Slab (8th Fl.) Steel | 5.82 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 9th Slab (8th Fl.) RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1- 9th Slab (8th Fl.) RMC M-20 Site | 74.28 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 9th Slab (8th Fl.) RCC M-20 | 463.42 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 9th Slab (8th Fl.) RMC M-25 Plant /Production | 0 | Cum. | 24 Dec 2019 | 24 Dec 2019 |  |  | 0 | 0 | 0 | 0
B-1- 9th Slab (8th Fl.) RMC M-25 Site | 6.97 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 9th Slab (8th Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 9th Slab (8th Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 9th Slab (8th Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 8TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 8th Flr.Cornice/Pardi/Cill Steel | 0.2 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 8th Flr.Cornice/Pardi/Cill RCC M-20 | 47.24 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1-10TH SLAB (9TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 9TH FL. COLUMN | 7.754 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 9th Fl. column Steel | 5.19 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 9th Fl. column RCC M-25 | 885.32 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 10TH SLAB (9TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 10th Slab (9th Fl.) Steel | 6.53 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 10th Slab (9th Fl.) RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1- 10th Slab (9th Fl.) RMC M-20 Site | 79.77 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 10th Slab (9th Fl.) RCC M-20 | 463.42 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 10th Slab (9th Fl.) RMC M-25 Plant /Production | 0 | Cum. | 24 Dec 2019 | 24 Dec 2019 |  |  | 0 | 0 | 0 | 0
B-1- 10th Slab (9th Fl.) RMC M-25 Site | 6.66 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 10th Slab (9th Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 10th Slab (9th Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 10th Slab (9th Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 9TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 9th Flr.Cornice/Pardi/Cill Steel | 0.12 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 9th Flr.Cornice/Pardi/Cill RCC M-20 | 30.99 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1-11TH SLAB (10TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 10TH FL. COLUMN | 5.6302 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 10th Fl. column Steel | 5.14 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 10th Fl. column RCC M-25 | 885.32 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 11 SLAB (10TH FL.) | 7.44 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 11 Slab (10th Fl.) Steel | 5.82 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 11 Slab (10th Fl.) RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1- 11 Slab (10th Fl.) RMC M-20 Site | 74.28 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 11 Slab (10th Fl.) RCC M-20 | 185.17 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 11 Slab (10th Fl.) RMC M-25 Plant /Production | 0 | Cum. | 24 Dec 2019 | 24 Dec 2019 |  |  | 0 | 0 | 0 | 0
B-1- 11 Slab (10th Fl.) RMC M-25 Site | 6.66 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 11 Slab (10th Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 11 Slab (10th Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 11 Slab (10th Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 10TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 10th Flr.Cornice/Pardi/Cill Steel | 0.2 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 10th Flr.Cornice/Pardi/Cill RCC M-20 | 47.24 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1-12TH SLAB (11TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 -11TH FL. COLUMN | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 -11th Fl. column Steel | 5.11 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 -11th Fl. column RCC M-25 | 881.91 | Cft | 15 Apr 2017 |  | 19 Nov 2019 |  | 0 | 0 | 948 | 0
B-1- 12TH SLAB (11TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 12th Slab (11th Fl.) Steel | 6.53 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 12th Slab (11th Fl.) RMC M-20 Site | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 12th Slab (11th Fl.) RMC M-20 Site | 79.77 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 12th Slab (11th Fl.) RCC M-20 | 185.17 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 12th Slab (11th Fl.) RMC M-25 Plant /Production | 0 | Cum. | 24 Dec 2019 | 24 Dec 2019 |  |  | 0 | 0 | 0 | 0
B-1- 12th Slab (11th Fl.) RMC M-25 Site | 6.64 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 12th Slab (11th Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 12th Slab (11th Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 12th Slab (11th Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 12th Slab (11th Fl.) RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1 11TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 11th Flr.Cornice/Pardi/Cill Steel | 0.2 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 11th Flr.Cornice/Pardi/Cill RCC M-20 | 30.99 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1-13TH SLAB (12TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 12TH FL. COLUMN | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 12th Fl. column Steel | 4.9 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 12th Fl. column RCC M-25 | 852.87 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 13TH SLAB (12TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 13th Slab (12th Fl.) Steel | 5.82 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 13th Slab (12th Fl.) RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1- 13th Slab (12th Fl.) RMC M-20 Site | 78.28 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 13th Slab (12th Fl.) RCC M-20 | 185.17 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 13th Slab (12th Fl.) RMC M-25 Plant /Production | 0 | Cum. | 24 Dec 2019 | 24 Dec 2019 |  |  | 0 | 0 | 0 | 0
B-1- 13th Slab (12th Fl.) RMC M-25 Site | 6.39 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 13th Slab (12th Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 13th Slab (12th Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 13th Slab (12th Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 12TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 12th Flr.Cornice/Pardi/Cill Steel | 0.12 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 12th Flr.Cornice/Pardi/Cill RCC M-20 | 47.24 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1-14TH SLAB (13TH FL.) | 7.754 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 13TH FL. COLUMN | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 13th Fl. column Steel | 4.87 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 13th Fl. column RCC M-25 | 849.45 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 14TH SLAB (13TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 14th Slab (13th Fl.) Steel | 6.53 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 14th Slab (13th Fl.) RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1- 14th Slab (13th Fl.) RMC M-20 Site | 94.77 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 14th Slab (13th Fl.) RCC M-20 | 185.17 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 14th Slab (13th Fl.) RMC M-25 Plant /Production | 0 | Cum. | 24 Dec 2019 | 24 Dec 2019 |  |  | 0 | 0 | 0 | 0
B-1- 14th Slab (13th Fl.) RMC M-25 Site | 6.36 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 14th Slab (13th Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 14th Slab (13th Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 14th Slab (13th Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 14th Slab (13th Fl.) Misc. Shuttering | 25000 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 13TH FLR.CORNICE/PARDI/CILL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 13th Flr.Cornice/Pardi/Cill Steel | 0 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 13th Flr.Cornice/Pardi/Cill RCC M-20 | 20 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1-15TH SLAB (14TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 14TH FL. COLUMN | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 14th Fl. column Steel | 5 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 14th Fl. column RCC M-25 | 449.45 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 15TH SLAB (14TH FL.) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 15th Slab (14th Fl.) Steel | 3.49 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 15th Slab (14th Fl.) RMC M-20 Plant /Production | 1.84 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B-1- 15th Slab (14th Fl.) RMC M-20 Site | 20.5 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 15th Slab (14th Fl.) RCC M-20 | 122.03 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 15th Slab (14th Fl.) RMC M-25 Plant /Production | 4.36 | Cum. | 24 Dec 2019 | 24 Dec 2019 |  |  | 0 | 0 | 0 | 0
B-1- 15th Slab (14th Fl.) RMC M-25 Site | 4 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 15th Slab (14th Fl.) Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 15th Slab (14th Fl.) Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- 15th Slab (14th Fl.) RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 14TH FLR.CORNICE/PARDI/CILL | 87.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 14th Flr.Cornice/Pardi/Cill Steel | 0 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1 14th Flr.Cornice/Pardi/Cill RCC M-20 | 20 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- ABOVE TERRACE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-ABOVE TERRACE COL. | 557.24 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Above Terrace Col. Steel | 2.03 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Above Terrace Col. RCC M-25 | 120 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Above Terrace Col. RCC M10 | 451.69 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- OHWT+ LMR | 4.72 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- OHWT+ LMR Steel | 4.35 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- OHWT+ LMR RMC M-25 Plant /Production | 0 | Cum. | 24 Dec 2019 | 24 Dec 2019 |  |  | 0 | 0 | 0 | 0
B1- OHWT+ LMR RMC M-25 Site | 6.16 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- OHWT+ LMR RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B1- OHWT+ LMR RMC M-20 Site | 60 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- OHWT+ LMR RCC M-20 | 0 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- OHWT+ LMR Buttering | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- OHWT+ LMR Ponding | 1 | Slab | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- OHWT+ LMR RCC Slab (Lab) | 61273 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-TERRACE LIN/CORNICE/PARDI/CILL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Terrace Lin/Cornice/Pardi/Cill Steel | 0 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Terrace Lin/Cornice/Pardi/Cill RCC M-20 | 0 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-ELEVATIONAL SLAB | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Elevational Slab Steel | 0 | M.T. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Elevational Slab RMC M-20 Plant /Production | 0 | Cum. | 24 Apr 2017 | 24 Apr 2017 |  |  | 0 | 0 | 0 | 0
B1-Elevational Slab RMC M-20 Site | 0 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Elevational Slab RCC M-20 | 183.61 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- CONCRETE PUMP | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- Concrete Pump Concrete Pump Operation | 15 | Month. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- RCC FARMA | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1- RCC Farma Misc. | 1 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1-SHUTTERING MATERIAL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1-Shuttering Material Shuttering Material - M.S | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1-COVER BLOCK | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1-Cover Block Cover Block 50 mm | 795 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1-Cover Block Cover Block 40 mm | 14416 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B-1-Cover Block Cover Block 20 mm | 22977 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-MASONRY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Floor CLC Block Making 500 x 200 x 100 | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Floor CLC Block Masonry 4" | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Floor CLC Block Making 500 x 200 x 150 | 1123.76 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Floor CLC Block Masonry 6" | 1353.92 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Floor CLC Block Making 500 x 200 x 100 | 126.971 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Floor CLC Block Masonry 4" | 152.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Floor CLC Block Making 500 x 200 x 150 | 3394.903 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Floor CLC Block Masonry 6" | 4090.24 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Floor CLC Block Making 500 x 200 x 100 | 126.971 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Floor CLC Block Masonry 4" | 152.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Floor CLC Block Making 500 x 200 x 150 | 3446.17 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Floor CLC Block Masonry 6" | 4152.01 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Floor CLC Block Making 500 x 200 x 100 | 126.971 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Floor CLC Block Masonry 4" | 152.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Floor CLC Block Making 500 x 200 x 150 | 3394.903 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Floor CLC Block Masonry 6" | 4090.24 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Floor CLC Block Making 500 x 200 x 100 | 126.971 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Floor CLC Block Masonry 4" | 152.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Floor CLC Block Making 500 x 200 x 150 | 3446.17 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Floor CLC Block Masonry 6" | 4152.01 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Floor CLC Block Making 500 x 200 x 100 | 126.971 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Floor CLC Block Masonry 4" | 152.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Floor CLC Block Making 500 x 200 x 150 | 3394.903 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Floor CLC Block Masonry 6" | 4090.24 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Floor CLC Block Making 500 x 200 x 100 | 126.971 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Floor CLC Block Masonry 4" | 152.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Floor CLC Block Making 500 x 200 x 150 | 3446.17 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Floor CLC Block Masonry 6" | 4152.01 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Floor CLC Block Making 500 x 200 x 100 | 179.45 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Floor CLC Block Masonry 4" | 152.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Floor CLC Block Making 500 x 200 x 150 | 3394.903 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Floor CLC Block Masonry 6" | 4090.24 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Floor CLC Block Making 500 x 200 x 100 | 179.45 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Floor CLC Block Masonry 4" | 152.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Floor CLC Block Making 500 x 200 x 150 | 3446.17 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Floor CLC Block Masonry 6" | 3807.31 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Floor CLC Block Making 500 x 200 x 100 | 179.45 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Floor CLC Block Masonry 4" | 152.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Floor CLC Block Making 500 x 200 x 150 | 3394.903 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Floor CLC Block Masonry 6" | 4090.24 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Floor CLC Block Making 500 x 200 x 100 | 229 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Floor CLC Block Masonry 4" | 221.69 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Floor CLC Block Making 500 x 200 x 150 | 3446.17 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Floor CLC Block Masonry 6" | 4152.01 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Floor CLC Block Making 500 x 200 x 100 | 229 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Floor CLC Block Masonry 4" | 221.69 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Floor CLC Block Making 500 x 200 x 150 | 3394.903 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Floor CLC Block Masonry 6" | 4090.24 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Floor CLC Block Making 500 x 200 x 100 | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Floor CLC Block Masonry 4" | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Floor CLC Block Making 500 x 200 x 150 | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Floor CLC Block Masonry 6" | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Floor AAC Block Masonry 150mm | 4152.01 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Floor AAC Block Masonry 100mm | 221.69 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Floor CLC Block Making 500 x 200 x 100 | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Floor CLC Block Masonry 4" | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Floor CLC Block Making 500 x 200 x 150 | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Floor CLC Block Masonry 6" | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Floor AAC Block Masonry 150mm | 4090.24 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Floor AAC Block Masonry 100mm | 221.69 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Floor CLC Block Making 500 x 200 x 100 | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Floor CLC Block Masonry 4" | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Floor CLC Block Making 500 x 200 x 150 | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Floor CLC Block Masonry 6" | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Floor Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Floor AAC Block Masonry 150mm | 4152.01 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Floor AAC Block Masonry 100mm | 221.69 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-ABOVE TERRACE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Above Terrace CLC Block Making 500 x 200 x 100 | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Above Terrace CLC Block Masonry 4" | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Above Terrace CLC Block Making 500 x 200 x 150 | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Above Terrace CLC Block Masonry 6" | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Above Terrace Above Terrace Masonry (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Above Terrace AAC Block Masonry 150mm | 2598.86 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-LIFT WALL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Lift Wall CLC Block Making 500 x 200 x 150 | 458.46 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Lift Wall CLC Block Masonry 6" | 552.36 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-ELEVATIONAL SIDE WALL | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Elevational Side Wall CLC Block Making 500 x 200 x 150 | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Elevational Side Wall CLC Block Masonry 6" | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-CLC BLOCK SHIFTING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-CLC Block shifting CLC Block shiffting | 0 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PLASTER | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-INTERNAL PLASTER | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- GYPSUM/PUTTY PLASTER | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-ENTRANCE LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Entrance lobby Entrance lobby | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-ELECTRICAL METER ROOM | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Electrical meter room Electrical meter room | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Floor Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 101 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 101 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 101 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 101 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 102 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 102 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 102 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 102 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 103 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 103 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 103 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 103 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 104 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 104 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 104 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 104 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 1ST FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 1st Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 1st Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 1st Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- FLAT 201 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- Flat 201 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- Flat 201 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- Flat 201 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- FLAT 202 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- Flat 202 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- Flat 202 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- Flat 202 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- FLAT 203 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- Flat 203 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- Flat 203 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- Flat 203 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- FLAT 204 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- Flat 204 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- Flat 204 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B- Flat 204 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 2ND FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 2nd Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 2nd Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 2nd Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 301 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 301 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 301 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 301 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 302 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 302 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 302 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 302 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 303 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 303 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 303 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 303 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 304 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 304 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 304 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 304 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 3RD FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 3rd Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 3rd Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 3rd Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 401 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 401 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 401 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 401 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 402 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 402 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 402 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 402 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 403 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 403 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 403 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 403 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 404 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 404 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 404 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 404 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 4TH FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 4th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 4th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 4th Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 501 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 501 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 501 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 501 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 502 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 502 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 502 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 502 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 503 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 503 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 503 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 503 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 504 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 504 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 504 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 504 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 5TH FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 5th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 5th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 5th Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 601 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 601 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 601 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 601 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 602 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 602 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 602 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 602 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 603 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 603 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 603 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 603 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 604 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 604 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 604 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 604 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 6TH FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 6th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 6th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 6th Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 701 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 701 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 701 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 701 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 702 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 702 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 702 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 702 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 703 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 703 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 703 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 703 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 704 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 704 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 704 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 704 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 7TH FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 7th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 7th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 7th Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 801 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 801 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 801 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 801 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 802 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 802 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 802 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 802 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 804 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 804 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 804 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 804 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- REFUGE FLAT 803 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Refuge Flat 803 Gypsum plaster incl NOC (M+L) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Refuge Flat 803 Gypsum butt finish incl NOC (M+L) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Refuge Flat 803 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 8TH FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 8th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 8th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 8th Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 901 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 901 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 901 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 901 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 902 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 902 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 902 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 902 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 903 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 903 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 903 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 903 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 904 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 904 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 904 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 904 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 9TH FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 9th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 9th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 9th Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1001 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1001 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1001 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1001 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1002 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1002 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1002 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1002 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1003 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1003 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1003 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1003 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1004 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1004 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1004 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1004 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 10TH FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 10th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 10th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 10th Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1101 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1101 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1101 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1101 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1102 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1102 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1102 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1102 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1103 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1103 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1103 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1103 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1104 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1104 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1104 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1104 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 11TH FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 11th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 11th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 11th Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1201 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1201 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1201 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1201 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1202 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1202 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1202 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1202 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1203 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1203 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1203 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1203 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1204 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1204 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1204 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1204 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 12TH FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 12th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 12th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 12th Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1301 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1301 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1301 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1301 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1302 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1302 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1302 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1302 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1304 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1304 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1304 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1304 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- REFUGE FLAT 1303 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Refuge Flat 1303 Gypsum plaster incl NOC (M+L) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Refuge Flat 1303 Gypsum butt finish incl NOC (M+L) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Refuge Flat 1303 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 13TH FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 13th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 13th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 13th Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1401 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1401 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1401 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1401 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1402 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1402 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1402 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1402 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1403 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1403 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1403 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1403 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1404 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1404 Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1404 Gypsum butt finish incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1404 Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 14TH FL. COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 14th Fl. COMMON PASSAGE Gypsum plaster incl NOC (M+L) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 14th Fl. COMMON PASSAGE Gypsum butt finish incl NOC (M+L | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 14th Fl. COMMON PASSAGE Putty Plaster | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-TOP TERRACE FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-TOP TERRACE COMMON PASSAGE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Top Terrace Common Passage Gypsum plaster incl NOC (M+L) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Top Terrace Common Passage Gypsum butt finish incl NOC (M | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Top Terrace Common Passage Putty Plaster | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-LMR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-LMR Gypsum plaster incl NOC (M+L) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-LMR Gypsum butt finish incl NOC (M+L) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-LMR Putty Plaster | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-SCAFFOLDING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Scaffolding Scaffolding (Base line) | 47803.88 | R.S. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Scaffolding Misc. scaffolding | 27196.12 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-TAR PLASTER | 54 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- PARKING FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Parking Floor Tar Plaster | 303.3 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Parking Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 1ST FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 101 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 101 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 102 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 102 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 103 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 103 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 104 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 104 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 1ST FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 1st Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 1st Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 1st Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 2ND FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 201 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 201 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 202 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 202 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 203 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 203 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 204 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 204 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 2ND FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 2nd Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 2nd Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 2nd Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 3RD FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 301 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 301 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 302 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 302 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 303 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 303 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 304 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 304 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 3RD FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 3rd Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 3rd Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 3rd Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 4TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 401 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 401 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 402 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 402 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 403 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 403 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 404 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 404 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 4TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 4th Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 4th Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 4th Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 5TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 501 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 501 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 502 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 502 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 503 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 503 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 504 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 504 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 5TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 5th Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 5th Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 5th Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 6TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 601 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 601 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 602 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 602 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 603 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 603 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 604 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 604 Tar Plaster | 734.17 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 6TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 6th Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 6th Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 6th Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 7TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 701 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 701 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 702 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 702 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 703 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 703 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 704 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 704 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 7TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 7th Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 7th Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 7th Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 8TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- REFUGE FLAT 803 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Refuge Flat 803 Tar Plaster | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 802 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 802 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 801 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 801 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 804 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 804 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 8TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 8th Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 8th Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 8th Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 9TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 901 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 901 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 902 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 902 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 903 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 903 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 904 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 904 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 9TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 9th Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 9th Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 9th Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 10TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1001 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1001 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1002 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1002 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1003 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1003 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1004 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1004 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 10TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 10th Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 10th Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 10th Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 11TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1101 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1101 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1102 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1102 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1103 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1103 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1104 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1104 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 11TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 11th Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 11th Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 11th Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 12TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1201 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1201 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1202 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1202 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1203 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1203 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1204 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1204 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 12TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 12th Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 12th Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 12th Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 13TH FLOOR | 62958 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-REFUGE FLAT 1303 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 1303 Tar Plaster | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1302 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1302 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1301 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1301 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1304 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1304 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 13TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 13th Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 13th Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 13th Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 14TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1401 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1401 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1402 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1402 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1403 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1403 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1404 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1404 Tar Plaster | 697 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 14TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 14th Floor Lobby Tar Plaster | 101.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 14th Floor Int. Plaster (Lab) | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 14th Floor Tar Plaster due to Uneven Thickness | 59863 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- TAR PLATSRE FOR ELECTRICAL, PLUMBING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Tar platsre for Electrical, Plumbing Tar Plaster | 1300 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-TOP TERRACE FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- TOP FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Top Floor Lobby Tar Plaster | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-CEMENT GHOTAI PLASTER | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING FLOOR FIRE STAIR | 59.56 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING FLOOR METER ROOM | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Floor Meter Room Cement Ghotai Plaster (Skirting) | 151.5223 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-101 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-101 Cement Ghotai Plaster (Skirting) | 167.7011 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-102 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-102 Cement Ghotai Plaster (Skirting) | 167.7011 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-103 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-103 Cement Ghotai Plaster (Skirting) | 167.7011 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-104 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-104 Cement Ghotai Plaster (Skirting) | 167.7011 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-201 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-201 Cement Ghotai Plaster (Skirting) | 171.3529 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-202 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-202 Cement Ghotai Plaster (Skirting) | 171.3529 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-203 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-203 Cement Ghotai Plaster (Skirting) | 171.3529 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-204 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-204 Cement Ghotai Plaster (Skirting) | 171.3529 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-301 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-301 Cement Ghotai Plaster (Skirting) | 167.7011 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-302 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-302 Cement Ghotai Plaster (Skirting) | 167.7011 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-303 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-303 Cement Ghotai Plaster (Skirting) | 167.7011 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-304 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-304 Cement Ghotai Plaster (Skirting) | 167.7011 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-401 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-401 Cement Ghotai Plaster (Skirting) | 171.3529 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-402 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-402 Cement Ghotai Plaster (Skirting) | 171.3529 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-403 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-403 Cement Ghotai Plaster (Skirting) | 171.3529 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-404 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-404 Cement Ghotai Plaster (Skirting) | 171.3529 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-501 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-501 Cement Ghotai Plaster (Skirting) | 167.7011 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-502 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-502 Cement Ghotai Plaster (Skirting) | 167.7011 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-503 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-503 Cement Ghotai Plaster (Skirting) | 167.7011 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-504 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-504 Cement Ghotai Plaster (Skirting) | 167.7011 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-601 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-601 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-602 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-602 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-603 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-603 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-604 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-604 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-701 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-701 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-702 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-702 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-703 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-703 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-704 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-704 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-801 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-801 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-802 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-802 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-804 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-804 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-REFUGE 803 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge 803 Cement Ghotai Plaster (Skirting) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-901 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-901 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-902 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-902 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-903 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-903 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-904 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-904 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1001 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1001 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1002 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1002 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1003 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1003 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1004 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1004 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1101 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1101 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1102 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1102 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1103 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1103 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1104 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1104 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1201 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1201 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1202 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1202 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1203 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1203 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1204 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1204 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0