## Task Details637397344604532297_
Task Details
Project Name : A SAMPLE PROJECT 3
Task Name : CONSTRUCTION
Total Records: 13876 Records 6001 to 8000
Page 4 of 7
Task (1) | Qty (2) | Unit (3) | Planned Start (4) | Planned Finish (5) | Actual Start (6) | Actual Finish (7) | Planned Duration (8)=(4)-(5) Days | Actual Duration (9)=(6)-(7) Days | Start Variance (10)=(4)-(6) Days | Finish Variance (11)=(4)-(5) Days | Remark
B1-12th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1301 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1301 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1302 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1302 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1304 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1304 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-REFUGE 1303 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge 1303 Cement Ghotai Plaster (Skirting) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1401 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1401 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1402 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1402 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1403 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1403 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1404 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1404 Cement Ghotai Plaster (Skirting) | 139.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FLOOR LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Floor Lobby Cement Ghotai Plaster (Skirting) | 11.9426 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FLOOR MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Floor Main Stair Cement Ghotai Plaster (Skirting) | 30.7402 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FLOOR FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Floor Fire Stair Cement Ghotai Plaster (Skirting) | 54.6362 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- ABOVE TERRACE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- ABOVE TERRACE LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Above Terrace Lobby Cement Ghotai Plaster (Skirting) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- ABOVE TERRACE FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Above Terrace Fire Stair Cement Ghotai Plaster (Skirting | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1 - LMR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1 - LMR Cement Ghotai Plaster (Skirting) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-SANLA PLASTER | 3023.73 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING FLOOR | 509.03 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Fl Main Stair Sanla Plaster | 497.76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING FL LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Fl Lobby Sanla Plaster | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 101 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 101 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 102 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 102 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 103 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 103 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 104 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 104 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Electrical Duct Sanla Plaster | 216 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Main Stair Sanla Plaster | 497.76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 201 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 201 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 202 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 202 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 203 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 203 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 204 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 204 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl Electrical Duct Sanla Plaster | 216 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl Main Stair Sanla Plaster | 497.76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2NDFL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ndFl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 301 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 301 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 302 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 302 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 303 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 303 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 304 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 304 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Electrical Duct Sanla Plaster | 216 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Main Stair Sanla Plaster | 497.76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 401 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 401 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 402 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 402 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 403 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 403 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 404 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 404 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl Electrical Duct Sanla Plaster | 216 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl Main Stair Sanla Plaster | 497.76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 501 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 501 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 502 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 502 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 503 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 503 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 504 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 504 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl Electrical Duct Sanla Plaster | 216 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl Main Stair Sanla Plaster | 497.76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 601 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 601 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 602 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 602 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 603 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 603 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 604 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 604 Sanla Plaster | 81.43 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl Electrical Duct Sanla Plaster | 216 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl Main Stair Sanla Plaster | 497.76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 701 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 701 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 702 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 702 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 703 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 703 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 704 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 704 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl Electrical Duct Sanla Plaster | 200 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl Main Stair Sanla Plaster | 475 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 7TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 7th Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 801 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 801 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 802 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 802 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 804 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 804 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- REFUGE FLAT 803 | 1184.52 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Refuge Flat 803 Sanla Plaster | 1140.83 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Electrical Duct Sanla Plaster | 200 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Main Stair Sanla Plaster | 475 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 901 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 901 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 902 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 902 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 903 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 903 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 904 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 904 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9THFL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9thFl Electrical Duct Sanla Plaster | 200 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl Main Stair Sanla Plaster | 475 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1001 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1001 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1002 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1002 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1003 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1003 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1004 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1004 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10THFL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10thFl Electrical Duct Sanla Plaster | 200 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl Main Stair Sanla Plaster | 475 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1101 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1101 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1102 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1102 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1103 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1103 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1104 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1104 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl Electrical Duct Sanla Plaster | 200 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl Main Stair Sanla Plaster | 475 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1201 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1201 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1202 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1202 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1203 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1203 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1204 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1204 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl Electrical Duct Sanla Plaster | 200 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl Main Stair Sanla Plaster | 475 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1301 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1301 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1302 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1302 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1304 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1304 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- REFUGE FLAT 1303 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Refuge Flat 1303 Sanla Plaster | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Electrical Duct Sanla Plaster | 200 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Main Stair Sanla Plaster | 475 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1401 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1401 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1402 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1402 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1403 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1403 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- FLAT 1404 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Flat 1404 Sanla Plaster | 30 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FL ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl Electrical Duct Sanla Plaster | 200 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FL MAIN STAIR | 751 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl Main Stair Sanla Plaster | 475 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- ABOVE TERRACE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- AB. TERRACE FL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Ab. Terrace Fl Main Stair Sanla Plaster | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- AB. TERRACE FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- Ab. Terrace Fl Fire Stair Sanla Plaster | 803.61 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-TOP TERRACE ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Top Terrace Electrical Duct Sanla Plaster | 493.99 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- LMR | 62958 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- LMR Sanla Plaster | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-TEXTURE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Texture Texture for Entrance Lobby (M+L) | 500 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Texture Texture for Bldg. Elevation (M+L) | 500 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-EXTERNAL PLASTER | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING | 7162.1 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Sand Faced Plaster 2 Coat | 7717 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-METER ROOM | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Meter Room Sand Faced Plaster 2 Coat | 1530.84 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Misc. | 1 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FRONT SIDE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Front Side Sand Faced Plaster 2 Coat | 18515.25 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-REAR SIDE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Rear Side Sand Faced Plaster 2 Coat | 19998.31 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-LEFT SIDE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Left Side Sand Faced Plaster 2 Coat | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-LEFT SIDE DUCT | 7763.1 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Left Side Duct Sand Faced Plaster 2 Coat | 5451.84 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-RIGHT SIDE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Right Side Sand Faced Plaster 2 Coat | 7308 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-RIGHT SIDE DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Right Side Duct Sand Faced Plaster 2 Coat | 7767.48 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-CENTRAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Central Duct Sand Faced Plaster 2 Coat | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-LOBBY DUCT | 1 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Lobby Duct Sand Faced Plaster 2 Coat | 4585.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-ELECTRICAL DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Electrical Duct Sand Faced Plaster 2 Coat | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-F.F. DUCT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-F.F. Duct Sand Faced Plaster 2 Coat | 3000 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-ABOVE TERRACE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Above Terrace Sand Faced Plaster 2 Coat | 7586.71 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-CHIKEN MESH | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Chiken Mesh Misc.M & P | 1 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PLUMBING GABADI/FINISH | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Plumbing gabadi/finish Plumbing gabadi/finish | 1200 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-WATERPROOFING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING FLOOR WATERPROOFING | 54.6 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Floor Waterproofing Brick Bat W/P (Toilet) | 40 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FL W/P | 255.97 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl W/P Brick Bat W/P (Toilet) | 318.31 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl W/P Brick Bat W/P entrance lobby | 108.18 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl W/P Screed + Chemical W/P (Ter.) | 257.73 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FL W/P | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl W/P Brick Bat W/P (Toilet) | 318.31 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl W/P Screed + Chemical W/P (Ter.) | 378.19 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FL W/P | 368.56 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl W/P Brick Bat W/P (Toilet) | 318.31 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl W/P Screed + Chemical W/P (Ter.) | 257.73 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FL W/P | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl W/P Brick Bat W/P (Toilet) | 318.31 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl W/P Screed + Chemical W/P (Ter.) | 378.19 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FL W/P | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl W/P Brick Bat W/P (Toilet) | 318.31 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl W/P Screed + Chemical W/P (Ter.) | 257.73 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FL W/P | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl W/P Brick Bat W/P (Toilet) | 288.31 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl W/P Screed + Chemical W/P (Ter.) | 378.19 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FL W/P | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl W/P Brick Bat W/P (Toilet) | 288.31 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl W/P Screed + Chemical W/P (Ter.) | 257.73 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FL W/P | 162.46 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl W/P Brick Bat W/P (Toilet) | 238.73 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl W/P Screed + Chemical W/P (Refuge) | 567.16 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl W/P Screed + Chemical W/P (Ter.) | 378.19 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FL W/P | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl W/P Brick Bat W/P (Toilet) | 288.31 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl W/P Screed + Chemical W/P (Ter.) | 257.73 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FL W/P | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl W/P Brick Bat W/P (Toilet) | 288.31 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl W/P Screed + Chemical W/P (Ter.) | 378.19 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FL W/P | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl W/P Brick Bat W/P (Toilet) | 288.31 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl W/P Screed + Chemical W/P (Ter.) | 257.73 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FL W/P | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl W/P Brick Bat W/P (Toilet) | 288.31 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl W/P Screed + Chemical W/P (Ter.) | 378.19 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FL W/P | 380.2814 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl W/P Brick Bat W/P (Toilet) | 238.73 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl W/P Screed + Chemical W/P (Refuge) | 567.16 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl W/P Screed + Chemical W/P (Ter.) | 257.73 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FL W/P | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl W/P Brick Bat W/P (Toilet) | 138.05 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl W/P Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl W/P (Toilet)Screed + Chemical W/P | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl W/P Screed + Chemical W/P (Ter.) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-TOP TERRACE WATERPROOFING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Top Terrace Waterproofing Brick Bat W/P (Terrace) | 3455.2 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-LMR WATERPROOFING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-LMR Waterproofing Brick Bat W/P (Terrace) | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-OHWT WATERPROOFING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-OHWT Waterproofing Brick Bat W/P (Terrace) | 458.73 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-OHWT Waterproofing W/P Plaster | 826.82 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-TILLING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLOORING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING | 323.92 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING ENTRACE LOBBY | 3 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Entrace Lobby Floor Lobby Flooring | 338.18 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Entrace Lobby Floor Lobby Skirting | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Entrace Lobby Entracnce Lobby (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Entrace Lobby Entrance Lobby | 0 | Job | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Entrace Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-MAIN STAIRCASE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Main Staircase Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Main Staircase Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Main Staircase Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Main Staircase Main Staircase Tread | 76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Main Staircase Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FIRE STAIRCASE | 69.4 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Fire Staircase Fire Staircase Flooring | 63 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Fire Staircase Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Fire Staircase Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Fire Staircase Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Fire Staircase Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-LIFT CLADDING | 140.32 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Lift Cladding Lift Cladding-1 | 140.32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING CHUQUERD TILE FLOORING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Chuquerd Tile Flooring Chquered Tile Flooring | 2916.01 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Chuquerd Tile Flooring Chequred/Paving Flooring(L | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING TOILET | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Toilet Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Toilet Common Toilet Dado | 100 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING CENTRAL DUCT FLOORING | 1091.06 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Central Duct Flooring Rough Kotta Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Central Duct Flooring Cement Ghotai | 429 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Central Duct Flooring RMC M10 Outsource | 4 | Cum. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING METER ROOM(RUBBER MAT) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Meter Room(Rubber Mat) Misc. Item (Meter Room) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking 9" wide cudappa/Granite boarder in Parki | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-101 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-101 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-101 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-101 Kit. Dado Above | 59.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-101 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-101 Flat Skirting | 176.7 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-101 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-101 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-101 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-101 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-101 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-101 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-101 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-102 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-102 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-102 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-102 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-102 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-102 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-102 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-102 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-102 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-102 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-102 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-102 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-102 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-103 | 23 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-103 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-103 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-103 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-103 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-103 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-103 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-103 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-103 Sitout/Terrace Flooring | 76.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-103 Sitout/Terrace Skirting | 31 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-103 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-103 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-103 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-104 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-104 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-104 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-104 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-104 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-104 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-104 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-104 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-104 Sitout/Terrace Flooring | 76.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-104 Sitout/Terrace Skirting | 31 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-104 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-104 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-104 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Main Stair Main Staircase Tread | 76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FL LIFT CLADDING | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Floor 1st fl. duct over entran. lobby flooring | 119.04 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Floor 1st fl. duct over entran. lobby Skirting | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FLOOR | 44 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-201 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-201 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-201 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-201 Kit. Dado Above | 59.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-201 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-201 Flat Skirting | 167.83 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-201 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-201 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-201 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-201 Sitout/Terrace Skirting | 59 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-201 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-201 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-201 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-202 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-202 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-202 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-202 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-202 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-202 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-202 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-202 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-202 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-202 Sitout/Terrace Skirting | 59 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-202 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-202 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-202 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-203 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-203 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-203 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-203 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-203 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-203 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-203 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-203 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-203 Sitout/Terrace Flooring | 62.26 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-203 Sitout/Terrace Skirting | 30 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-203 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-203 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-203 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-204 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-204 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-204 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-204 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-204 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-204 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-204 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-204 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-204 Sitout/Terrace Flooring | 62.26 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-204 Sitout/Terrace Skirting | 30 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-204 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-204 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-204 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl Main Stair Main Staircase Tread | 76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FL.LIFT CLADDING | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl.Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-301 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-301 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-301 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-301 Kit. Dado Above | 59.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-301 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-301 Flat Skirting | 176.7 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-301 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-301 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-301 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-301 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-301 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-301 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-301 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-302 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-302 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-302 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-302 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-302 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-302 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-302 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-302 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-302 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-302 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-302 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-302 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-302 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-303 | 23 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-303 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-303 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-303 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-303 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-303 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-303 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-303 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-303 Sitout/Terrace Flooring | 76.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-303 Sitout/Terrace Skirting | 31 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-303 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-303 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-303 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-304 | 255.97 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-304 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-304 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-304 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-304 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-304 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-304 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-304 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-304 Sitout/Terrace Flooring | 76.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-304 Sitout/Terrace Skirting | 31 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-304 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-304 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-304 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Main Stair Main Staircase Tread | 76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FL.LIFT CLADDING | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl.Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FLOOR | 44 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-401 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-401 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-401 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-401 Kit. Dado Above | 59.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-401 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-401 Flat Skirting | 167.83 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-401 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-401 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-401 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-401 Sitout/Terrace Skirting | 59 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-401 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-401 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-401 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-402 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-402 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-402 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-402 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-402 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-402 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-402 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-402 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-402 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-402 Sitout/Terrace Skirting | 59 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-402 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-402 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-402 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-403 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-403 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-403 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-403 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-403 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-403 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-403 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-403 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-403 Sitout/Terrace Flooring | 62.26 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-403 Sitout/Terrace Skirting | 30 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-403 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-403 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-403 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-404 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-404 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-404 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-404 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-404 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-404 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-404 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-404 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-404 Sitout/Terrace Flooring | 62.26 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-404 Sitout/Terrace Skirting | 30 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-404 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-404 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-404 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl Main Stair Main Staircase Tread | 76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FL.LIFT CLADDING | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl.Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FLOOR | 323.92 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-501 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-501 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-501 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-501 Kit. Dado Above | 59.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-501 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-501 Flat Skirting | 176.7 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-501 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-501 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-501 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-501 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-501 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-501 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-501 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-502 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-502 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-502 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-502 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-502 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-502 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-502 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-502 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-502 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-502 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-502 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-502 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-502 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-503 | 23 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-503 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-503 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-503 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-503 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-503 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-503 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-503 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-503 Sitout/Terrace Flooring | 76.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-503 Sitout/Terrace Skirting | 31 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-503 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-503 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-503 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-504 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-504 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-504 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-504 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-504 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-504 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-504 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-504 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-504 Sitout/Terrace Flooring | 76.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-504 Sitout/Terrace Skirting | 31 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-504 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-504 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-504 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl Main Stair Main Staircase Tread | 76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FL.LIFT CLADDING | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl.Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FLOOR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-601 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-601 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-601 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-601 Kit. Dado Above | 59.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-601 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-601 Flat Skirting | 167.83 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-601 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-601 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-601 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-601 Sitout/Terrace Skirting | 59 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-601 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-601 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-601 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-602 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-602 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-602 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-602 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-602 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-602 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-602 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-602 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-602 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-602 Sitout/Terrace Skirting | 59 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-602 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-602 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-602 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-603 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-603 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-603 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-603 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-603 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-603 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-603 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-603 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-603 Sitout/Terrace Flooring | 62.26 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-603 Sitout/Terrace Skirting | 30 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-603 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-603 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-603 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-604 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-604 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-604 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-604 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-604 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-604 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-604 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-604 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-604 Sitout/Terrace Flooring | 62.26 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-604 Sitout/Terrace Skirting | 30 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-604 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-604 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-604 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl Main Stair Main Staircase Tread | 76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FL.LIFT CLADDING | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl.Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-701 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-701 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-701 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-701 Kit. Dado Above | 59.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-701 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-701 Flat Skirting | 176.7 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-701 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-701 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-701 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-701 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-701 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-701 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-701 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-702 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-702 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-702 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-702 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-702 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-702 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-702 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-702 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-702 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-702 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-702 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-702 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-702 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-703 | 23 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-703 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-703 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-703 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-703 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-703 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-703 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-703 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-703 Sitout/Terrace Flooring | 76.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-703 Sitout/Terrace Skirting | 31 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-703 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-703 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-703 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-704 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-704 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-704 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-704 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-704 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-704 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-704 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-704 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-704 Sitout/Terrace Flooring | 76.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-704 Sitout/Terrace Skirting | 31 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-704 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-704 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-704 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7THFL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7thFl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7thFl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7thFl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7thFl Main Stair Main Staircase Tread | 76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7thFl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FL.LIFT CLADDING | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl.Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FLOOR | 44 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-REFUGE FLAT-803 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat-803 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat-803 Refuge Ceramic Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat-803 Refuge Ceramic Skirting | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-802 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-802 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-802 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-802 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-802 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-802 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-802 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-802 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-802 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-802 Sitout/Terrace Skirting | 59 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-802 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-802 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-802 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-804 | 68.5 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-804 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-804 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-804 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-804 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-804 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-804 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-804 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-804 Sitout/Terrace Flooring | 62.26 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-804 Sitout/Terrace Skirting | 30 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-804 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-804 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-804 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-801 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-801 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-801 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-801 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-801 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-801 Flat Skirting | 167.83 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-801 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-801 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-801 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-801 Sitout/Terrace Skirting | 59.09 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-801 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-801 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-801 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Main Stair Main Staircase Tread | 76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FL.LIFT CLADDING | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl.Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-901 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-901 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-901 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-901 Kit. Dado Above | 59.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-901 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-901 Flat Skirting | 176.7 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-901 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-901 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-901 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-901 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-901 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-901 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-901 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-902 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-902 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-902 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-902 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-902 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-902 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-902 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-902 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-902 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-902 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-902 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-902 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-902 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-903 | 23 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-903 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-903 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-903 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-903 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-903 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-903 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-903 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-903 Sitout/Terrace Flooring | 76.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-903 Sitout/Terrace Skirting | 31 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-903 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-903 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-903 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-904 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-904 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-904 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-904 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-904 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-904 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-904 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-904 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-904 Sitout/Terrace Flooring | 76.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-904 Sitout/Terrace Skirting | 31 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-904 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-904 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-904 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl Main Stair Main Staircase Tread | 76 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl Fire Stair Fire Staircase Flooring | 63 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FL.LIFT CLADDING | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl.Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FLOOR | 44 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1001 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1001 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1001 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1001 Kit. Dado Above | 59.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1001 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1001 Flat Skirting | 167.83 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1001 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1001 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1001 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1001 Sitout/Terrace Skirting | 59 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1001 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1001 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1001 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1002 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1002 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1002 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1002 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1002 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1002 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1002 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1002 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1002 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1002 Sitout/Terrace Skirting | 59 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1002 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1002 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1002 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1003 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1003 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1003 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1003 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1003 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1003 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1003 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1003 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1003 Sitout/Terrace Flooring | 62.26 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1003 Sitout/Terrace Skirting | 30 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1003 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1003 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1003 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1004 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1004 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1004 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1004 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1004 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1004 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1004 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1004 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1004 Sitout/Terrace Flooring | 62.26 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1004 Sitout/Terrace Skirting | 30 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1004 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1004 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1004 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl Main Stair Main Staircase Tread | 90 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl Fire Stair Fire Staircase Flooring | 309 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FL.LIFT CLADDING | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl.Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1101 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1101 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1101 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1101 Kit. Dado Above | 59.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1101 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1101 Flat Skirting | 176.7 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1101 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1101 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1101 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1101 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1101 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1101 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1101 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT1102 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat1102 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat1102 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat1102 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat1102 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat1102 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat1102 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat1102 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat1102 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat1102 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat1102 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat1102 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat1102 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1103 | 23 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1103 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1103 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1103 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1103 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1103 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1103 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1103 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1103 Sitout/Terrace Flooring | 76.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1103 Sitout/Terrace Skirting | 31 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1103 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1103 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1103 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1104 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1104 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1104 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1104 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1104 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1104 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1104 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1104 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1104 Sitout/Terrace Flooring | 76.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1104 Sitout/Terrace Skirting | 31 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1104 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1104 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1104 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl Main Stair Main Staircase Tread | 90 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl Fire Stair Fire Staircase Flooring | 309 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11THFL.LIFT CLADDING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11thFl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11thFl.Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11thFl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FLOOR | 44 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1201 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1201 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1201 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1201 Kit. Dado Above | 59.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1201 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1201 Flat Skirting | 167.83 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1201 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1201 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1201 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1201 Sitout/Terrace Skirting | 59 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1201 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1201 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1201 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1202 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1202 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1202 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1202 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1202 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1202 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1202 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1202 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1202 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1202 Sitout/Terrace Skirting | 59 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1202 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1202 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1202 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1203 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1203 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1203 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1203 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1203 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1203 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1203 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1203 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1203 Sitout/Terrace Flooring | 62.26 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1203 Sitout/Terrace Skirting | 30 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1203 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1203 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1203 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1204 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1204 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1204 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1204 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1204 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1204 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1204 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1204 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1204 Sitout/Terrace Flooring | 62.26 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1204 Sitout/Terrace Skirting | 30 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1204 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1204 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1204 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl Main Stair Main Staircase Tread | 90 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl Fire Stair Fire Staircase Flooring | 309 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FL.LIFT CLADDING | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl.Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-REFUGE FLAT-1303 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat-1303 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat-1303 Refuge Ceramic Skirting | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat-1303 Refuge Ceramic Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1302 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1302 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1302 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1302 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1302 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1302 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1302 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1302 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1302 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1302 Sitout/Terrace Skirting | 23 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1302 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1302 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1302 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1304 | 23 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1304 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1304 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1304 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1304 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1304 Flat Skirting | 174.07 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1304 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1304 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1304 Sitout/Terrace Flooring | 76.33 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1304 Sitout/Terrace Skirting | 31 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1304 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1304 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1304 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1301 | 56693 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1301 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1301 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1301 Kit. Dado Above | 59.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1301 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1301 Flat Skirting | 176.7 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1301 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1301 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1301 Sitout/Terrace Flooring | 48.62 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1301 Sitout/Terrace Skirting | 23.09 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1301 Window Box Flooring | 14.53 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1301 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1301 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Main Stair Main Staircase Tread | 90 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Fire Stair Fire Staircase Flooring | 309 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FL.LIFT CLADDING | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl.Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FLOOR | 44 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1401 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1401 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1401 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1401 Kit. Dado Above | 59.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1401 Flat Flooring | 596.104 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1401 Flat Skirting | 167.83 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1401 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1401 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1401 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1401 Sitout/Terrace Skirting | 59 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1401 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1401 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1401 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1402 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1402 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1402 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1402 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1402 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1402 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1402 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1402 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1402 Sitout/Terrace Flooring | 125.06 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1402 Sitout/Terrace Skirting | 59 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1402 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1402 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1402 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1403 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1403 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1403 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1403 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1403 Flat Flooring | 589.648 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1403 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1403 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1403 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1403 Sitout/Terrace Flooring | 62.26 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1403 Sitout/Terrace Skirting | 30 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1403 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1403 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1403 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT-1404 | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1404 Common Toilet Dado | 164.75 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1404 Master Toilet Dado | 157.46 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1404 Kit. Dado Above | 53.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1404 Flat Flooring | 587.6036 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1404 Flat Skirting | 165.2 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1404 Common Toilet Flooring | 33.77 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1404 Master Toilet Flooring | 35.98 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1404 Sitout/Terrace Flooring | 62.26 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1404 Sitout/Terrace Skirting | 30 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1404 Window Box Flooring | 7.27 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1404 Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat-1404 Flat Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl.Lobby Floor Lobby Flooring | 239.68 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl.Lobby Floor Lobby Skirting | 47.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl.Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl.Lobby Misc. Material (White Cement) | 1 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FL MAIN STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl Main Stair Main Staircase Flooring | 32 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl Main Stair Main Staircase Riser | 76 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl Main Stair Main Staircase Skirting | 62.25 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl Main Stair Main Staircase Tread | 90 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl Main Stair Main Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl Fire Stair Fire Staircase Flooring | 309 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl Fire Stair Fire Staircase Riser | 95 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl Fire Stair Fire Staircase Skirting | 93 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl Fire Stair Fire Staircase Tread | 95 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FL.LIFT CLADDING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl.Lift Cladding Lift Cladding-1 | 216.93 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl.Lift Cladding Lift Cladding (lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14th Fl.Lift Cladding Misc. Material (White Cement) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-TOP TERRACE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-TERRACE LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Terrace Lobby Floor lobby Tiling (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Terrace Lobby Floor Lobby Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Terrace Lobby Floor Lobby Skirting | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-TERRACE FIRE STAIR | 56693 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Terrace Fire Stair Fire Staircase Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Terrace Fire Stair Fire Staircase Riser | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Terrace Fire Stair Fire Staircase Skirting | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Terrace Fire Stair Fire Staircase Tread | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Terrace Fire Stair Fire Staircase (Lab) | 53542 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-TERRACE MACHINE ROOM | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Terrace Machine Room IPS Finish | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-MAINTENANACE | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-MAINT.ALL FLATS | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Flats Common Toilet Dado | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Flats Master Toilet Dado | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Flats Kit. Dado Above | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Flats Flat Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Flats Flat Skirting | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Flats Common Toilet Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Flats Master Toilet Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Flats Sitout/Terrace Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Flats Sitout/Terrace Skirting | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Flats Window Box Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Flats Umara Patti | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-MAINT.ALL COMMON AREA | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-MAINT.ALL LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Lobby Floor Lobby Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Lobby Floor Lobby Skirting | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Lobby Misc. Material (White Cement) | 0 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-MAINT.ALL MAIN STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Main Stair Main Staircase Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Main Stair Main Staircase Riser | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Main Stair Main Staircase Skirting | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Main Stair Main Staircase Tread | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-MAINT.ALL FIRE STAIR | 343.15 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Fire Stair Fire Staircase Flooring | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Fire Stair Fire Staircase Riser | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Fire Stair Fire Staircase Skirting | 0 | Rft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Fire Stair Fire Staircase Tread | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-MAINT.ALL LIFT CLADDING | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Lift Cladding Lift Cladding-1 | 0 | Sft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Maint.All Lift Cladding Misc. Material (White Cement) | 0 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-SHIFTING OF RABIT | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Shifting of Rabit Shifting of Rabit by tractor (Morter Wa | 0 | Cft | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-MISC. | 750 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Misc. HCL Acid | 500 | lit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B 1-TILING (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING TILE | 1 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Tile Granite Door Frame (M+L) | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Tile Granite Window Jambs (M+L) | 0 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Tile Granite Ledge wall (M+L) | 0 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-PARKING FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Parking Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 101 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 101 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 101 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 101 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 101 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 101 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 101 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 101 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 102 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 102 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 102 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 102 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 102 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 102 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 102 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 102 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 103 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 103 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 103 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 103 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 103 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 103 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 103 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 103 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 104 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 104 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 104 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 104 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 104 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 104 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 104 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 104 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1ST FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-1st Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 1ST FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 1st Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 201 TILE (M+L) | 11 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 201 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 201 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 201 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 201 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 201 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 201 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 201 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 202 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 202 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 202 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 202 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 202 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 202 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 202 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 202 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 203 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 203 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 203 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 203 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 203 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 203 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 203 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 203 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 204 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 204 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 204 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 204 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 204 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 204 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 204 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 204 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2ND FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-2nd Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 301 TILE (M+L) | 11 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 301 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 301 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 301 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 301 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 301 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 301 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 301 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 302 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 302 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 302 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 302 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 302 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 302 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 302 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 302 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 303 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 303 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 303 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 303 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 303 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 303 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 303 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 303 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 304 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 304 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 304 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 304 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 304 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 304 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 304 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 304 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3RD FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-3rd Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 401 TILE (M+L) | 11 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 401 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 401 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 401 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 401 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 401 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 401 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 401 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 402 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 402 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 402 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 402 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 402 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 402 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 402 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 402 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 403 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 403 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 403 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 403 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 403 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 403 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 403 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 403 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 404 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 404 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 404 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 404 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 404 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 404 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 404 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 404 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-4th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 4TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 4th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 501 TILE (M+L) | 11 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 501 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 501 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 501 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 501 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 501 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 501 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 501 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 502 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 502 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 502 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 502 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 502 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 502 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 502 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 502 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 503 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 503 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 503 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 503 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 503 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 503 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 503 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 503 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 504 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 504 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 504 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 504 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 504 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 504 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 504 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 504 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-5th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 5TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 5th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 601 TILE (M+L) | 11 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 601 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 601 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 601 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 601 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 601 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 601 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 601 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 602 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 602 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 602 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 602 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 602 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 602 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 602 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 602 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 603 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 603 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 603 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 603 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 603 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 603 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 603 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 603 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 604 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 604 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 604 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 604 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 604 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 604 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 604 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 604 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-6th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 6TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 6th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 701 TILE (M+L) | 11 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 701 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 701 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 701 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 701 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 701 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 701 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 701 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 702 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 702 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 702 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 702 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 702 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 702 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 702 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 702 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 703 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 703 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 703 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 703 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 703 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 703 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 703 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 703 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 704 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 704 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 704 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 704 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 704 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 704 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 704 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 704 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-7th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 7TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 7th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FLOOR | 1 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 801 TILE (M+L) | 11 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 801 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 801 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 801 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 801 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 801 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 801 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 801 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 802 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 802 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 802 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 802 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 802 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 802 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 802 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 802 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 804 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 804 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 804 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 804 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 804 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 804 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 804 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 804 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-REFUGE FLAT 803 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 803 Tile (M+L) Granite Kitchen Otta (M+L) | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 803 Tile (M+L) Granite Door Frame (M+L) | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 803 Tile (M+L) Granite Window Jambs (M+L) | 0 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 803 Tile (M+L) Granite WHB Counter (M+L) | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 803 Tile (M+L) Granite Ledge wall (M+L) | 0 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 803 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+ | 0 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 803 Tile (M+L) Granite Window Cill upto 3"(M+ | 0 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-8th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 901 TILE (M+L) | 11 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 901 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 901 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 901 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 901 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 901 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 901 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 901 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 902 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 902 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 902 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 902 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 902 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 902 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 902 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 902 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT- 903 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat- 903 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat- 903 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat- 903 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat- 903 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat- 903 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat- 903 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat- 903 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 904 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 904 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 904 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 904 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 904 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 904 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 904 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 904 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9THT FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-9tht Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1001 TILE (M+L) | 11 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1001 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1001 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1001 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1001 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1001 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1001 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1001 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1002 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1002 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1002 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1002 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1002 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1002 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1002 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1002 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1003 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1003 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1003 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1003 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1003 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1003 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1003 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1003 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1004 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1004 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1004 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1004 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1004 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1004 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1004 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1004 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-10th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 10TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 10th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1101 TILE (M+L) | 11 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1101 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1101 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1101 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1101 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1101 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1101 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1101 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1102 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1102 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1102 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1102 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1102 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1102 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1102 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1102 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1103 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1103 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1103 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1103 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1103 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1103 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1103 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1103 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1104 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1104 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1104 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1104 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1104 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1104 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1104 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1104 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-11th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 11TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 11th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FLOOR | 1 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1201 TILE (M+L) | 11 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1201 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1201 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1201 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1201 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1201 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1201 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1201 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1202 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1202 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1202 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1202 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1202 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1202 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1202 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1202 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1203 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1203 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1203 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1203 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1203 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1203 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1203 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1203 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1204 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1204 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1204 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1204 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1204 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1204 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1204 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1204 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-12th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 12TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1- 12th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1301 TILE (M+L) | 11 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1301 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1301 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1301 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1301 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1301 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1301 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1301 Tile (M+L) Granite Window Cill upto 3"(M+L) | 3 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1302 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1302 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1302 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1302 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1302 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1302 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1302 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1302 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1304 TILE (M+L) | 1 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1304 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1304 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1304 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1304 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1304 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1304 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 10 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1304 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-REFUGE FLAT 1303 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 1303 Tile (M+L) Granite Kitchen Otta (M+L) | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 1303 Tile (M+L) Granite Door Frame (M+L) | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 1303 Tile (M+L) Granite Window Jambs (M+L) | 0 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 1303 Tile (M+L) Granite WHB Counter (M+L) | 0 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 1303 Tile (M+L) Granite Ledge wall (M+L) | 0 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 1303 Tile (M+L) Granite Wnd Cill- 4" to 6" (M | 0 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Refuge Flat 1303 Tile (M+L) Granite Window Cill upto 3"(M | 0 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FL.LOBBY | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl.Lobby Granite SitoutCill- 7"to9" (M+L) | 8.5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13TH FL FIRE STAIR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-13th Fl Fire Stair Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-14TH FLOOR | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1401 TILE (M+L) | 11 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1401 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1401 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1401 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1401 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1401 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1401 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1401 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1402 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1402 Tile (M+L) Granite Kitchen Otta (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1402 Tile (M+L) Granite Door Frame (M+L) | 2 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1402 Tile (M+L) Granite Window Jambs (M+L) | 2 | NO | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1402 Tile (M+L) Granite WHB Counter (M+L) | 1 | No. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1402 Tile (M+L) Granite Ledge wall (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1402 Tile (M+L) Granite Wnd Cill- 4" to 6" (M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-Flat 1402 Tile (M+L) Granite Window Cill upto 3"(M+L) | 5 | Rft. | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0
B1-FLAT 1403 TILE (M+L) | 0 | No Unit | 15 Apr 2017 |  |  |  | 0 | 0 | 0 | 0