## GRNRegisteritemwise638820576258
Material Wise GRN Report
Page 1 of 1
Total Records: 115 Records 1 to 115
Project_Name | Material_Category1 | Material_Name | Brand | GRN_No | GRN_Date | GRNType | Supplier_Issue_Store | Good_Qty | Unit_Name | Received_Store | Amount | PO_SrNo | PO_Qty | Rate | Transport_Others | Challan_No | Challan_Date | Bill_No | Bill_date | Billing_Status | VehicleNo | GateReg_No | GateReg date | GateReg Time | GateReg Out Date | GateReg Out Time | Po_Date | GRN_Remark | GRN_Status | Material_Category2 | GTN_SrNo | Created_BY | Challan_Qty | Entry_Date
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54671 | 2025-04-29 10:51 | Purchase | GREY CORE INFRA LLP | 3 | CUM | BUILDTECH STORE | 16016.94 | 9585 | 284.5 | 5338.98 | 0 | 383 | 2025-04-28 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-28 10:41 | 10:41 AM | 2025-04-28 10:41 | 10:41 AM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 3 | 2025-04-29 10:51
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54670 | 2025-04-29 10:49 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 26694.9 | 9585 | 284.5 | 5338.98 | 0 | 380 | 2025-04-28 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-28 10:41 | 10:41 AM | 2025-04-28 10:41 | 10:41 AM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-29 10:49
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 54644 | 2025-04-28 14:35 | Purchase | GREY CORE INFRA LLP | 1 | CUM | BUILDTECH STORE | 4703.4 | 9585 | 414.9 | 4703.4 | 0 | 377 | 2025-04-27 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-27 14:15 | 2:15 PM | 2025-04-27 14:15 | 2:15 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 1 | 2025-04-28 14:35
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 54643 | 2025-04-28 14:33 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9585 | 414.9 | 4703.4 | 0 | 371 | 2025-04-27 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-27 14:15 | 2:15 PM | 2025-04-27 14:15 | 2:15 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-28 14:33
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 54642 | 2025-04-28 14:32 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9585 | 414.9 | 4703.4 | 0 | 370 | 2025-04-27 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-27 14:15 | 2:15 PM | 2025-04-27 14:15 | 2:15 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-28 14:32
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 54641 | 2025-04-28 14:30 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9585 | 414.9 | 4703.4 | 0 | 369 | 2025-04-27 | 0 |  | Unbilled | MH12 SX9138 |  | 2025-04-27 14:15 | 2:15 PM | 2025-04-27 14:15 | 2:15 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-28 14:30
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 54640 | 2025-04-28 14:29 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9585 | 414.9 | 4703.4 | 0 | 367 | 2025-04-27 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-27 14:15 | 2:15 PM | 2025-04-27 14:15 | 2:15 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-28 14:29
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 54639 | 2025-04-28 14:27 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9585 | 414.9 | 4703.4 | 0 | 366 | 2025-04-27 | 0 |  | Unbilled | MH12 SX9138 |  | 2025-04-27 14:15 | 2:15 PM | 2025-04-27 14:15 | 2:15 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-28 14:27
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 54638 | 2025-04-28 14:25 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9585 | 414.9 | 4703.4 | 0 | 364 | 2025-04-27 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-27 14:15 | 2:15 PM | 2025-04-27 14:15 | 2:15 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-28 14:25
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 54637 | 2025-04-28 14:24 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9585 | 414.9 | 4703.4 | 0 | 362 | 2025-04-27 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-27 14:15 | 2:15 PM | 2025-04-27 14:15 | 2:15 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-28 14:24
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 54636 | 2025-04-28 14:23 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9585 | 414.9 | 4703.4 | 0 | 361 | 2025-04-27 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-27 14:15 | 2:15 PM | 2025-04-27 14:15 | 2:15 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-28 14:23
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 54635 | 2025-04-28 14:22 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9585 | 414.9 | 4703.4 | 0 | 365 | 2025-04-27 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-27 14:15 | 2:15 PM | 2025-04-27 14:15 | 2:15 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-28 14:22
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54634 | 2025-04-28 14:20 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 26694.9 | 9585 | 284.5 | 5338.98 | 0 | 359 | 2025-04-27 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-27 14:15 | 2:15 PM | 2025-04-27 14:15 | 2:15 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-28 14:20
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54633 | 2025-04-28 14:19 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 21355.92 | 9585 | 284.5 | 5338.98 | 0 | 357 | 2025-04-27 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-27 14:15 | 2:15 PM | 2025-04-27 14:15 | 2:15 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-28 14:19
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54632 | 2025-04-28 14:17 | Purchase | GREY CORE INFRA LLP | 1 | CUM | BUILDTECH STORE | 5338.98 | 9585 | 284.5 | 5338.98 | 0 | 354 | 2025-04-26 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-26 14:15 | 2:15 PM | 2025-04-26 14:15 | 2:15 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 1 | 2025-04-28 14:17
41 LUXOVERT | 00 RMC | RMC M40 (Out Source) |  | 54631 | 2025-04-28 14:11 | Purchase | GREY CORE INFRA LLP | 3 | CUM | BUILDTECH STORE | 15000 | 9985 | 19.5 | 5000 | 0 | 348 | 2025-04-26 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-26 14:10 | 2:10 PM | 2025-04-26 14:10 | 2:10 PM | 2025-04-05 17:07 |  | Approved |  | 0 | Luxovert.Store | 3 | 2025-04-28 14:11
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54481 | 2025-04-26 10:49 | Purchase | GREY CORE INFRA LLP | 1 | CUM | BUILDTECH STORE | 5338.98 | 9961 | 126.5 | 5338.98 | 0 | 342 | 2025-04-25 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-25 10:42 | 10:42 AM | 2025-04-25 10:42 | 10:42 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 1 | 2025-04-26 10:49
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54480 | 2025-04-26 10:48 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 32033.88 | 9961 | 126.5 | 5338.98 | 0 | 340 | 2025-04-25 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-25 10:42 | 10:42 AM | 2025-04-25 10:42 | 10:42 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-26 10:48
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54479 | 2025-04-26 10:47 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 37372.86 | 9961 | 126.5 | 5338.98 | 0 | 337 | 2025-04-25 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-25 10:42 | 10:42 AM | 2025-04-25 10:42 | 10:42 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-26 10:47
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54478 | 2025-04-26 10:47 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 37372.86 | 9961 | 126.5 | 5338.98 | 0 | 333 | 2025-04-25 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-25 10:42 | 10:42 AM | 2025-04-25 10:42 | 10:42 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-26 10:47
41 LUXOVERT | 00 RMC | RMC M70 (OUTSOURCE) |  | 54477 | 2025-04-26 10:46 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 45254.22 | 9961 | 45 | 7542.37 | 0 | 327 | 2025-04-25 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-25 10:42 | 10:42 AM | 2025-04-25 10:42 | 10:42 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-26 10:46
41 LUXOVERT | 00 RMC | RMC M70 (OUTSOURCE) |  | 54476 | 2025-04-26 10:45 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 45254.22 | 9961 | 45 | 7542.37 | 0 | 323 | 2025-04-25 | 0 |  | Unbilled | MH12HD4752 |  | 2025-04-25 10:42 | 10:42 AM | 2025-04-25 10:42 | 10:42 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-26 10:45
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54450 | 2025-04-25 11:44 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 21355.92 | 9961 | 126.5 | 5338.98 | 0 | 311 | 2025-04-24 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-24 11:32 | 11:32 AM | 2025-04-24 11:32 | 11:32 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-25 11:44
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54449 | 2025-04-25 11:42 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 21355.92 | 9961 | 126.5 | 5338.98 | 0 | 302 | 2025-04-24 | 0 |  | Unbilled | mh14gd4834 |  | 2025-04-24 11:32 | 11:32 AM | 2025-04-24 11:32 | 11:32 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-25 11:42
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 54448 | 2025-04-25 11:40 | Purchase | GREY CORE INFRA LLP | 3 | CUM | BUILDTECH STORE | 14110.2 | 9961 | 162 | 4703.4 | 0 | 309 | 2025-04-24 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-24 11:32 | 11:32 AM | 2025-04-24 11:32 | 11:32 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 3 | 2025-04-25 11:40
41 LUXOVERT | 00 RMC | RMC M70 (OUTSOURCE) |  | 54447 | 2025-04-25 11:37 | Purchase | GREY CORE INFRA LLP | 2 | CUM | BUILDTECH STORE | 15084.74 | 9961 | 45 | 7542.37 | 0 | 313 | 2025-04-24 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-24 11:32 | 11:32 AM | 2025-04-24 11:32 | 11:32 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 2 | 2025-04-25 11:37
41 LUXOVERT | 00 RMC | RMC M70 (OUTSOURCE) |  | 54277 | 2025-04-24 11:51 | Purchase | GREY CORE INFRA LLP | 1.5 | CUM | BUILDTECH STORE | 11313.555 | 9961 | 45 | 7542.37 | 0 | 283 | 2025-04-23 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-23 11:25 | 11:25 AM | 2025-04-23 11:25 | 11:25 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 1.5 | 2025-04-24 11:51
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54276 | 2025-04-24 11:49 | Purchase | GREY CORE INFRA LLP | 2 | CUM | BUILDTECH STORE | 10677.96 | 9961 | 126.5 | 5338.98 | 0 | 289 | 2025-04-23 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-23 11:25 | 11:25 AM | 2025-04-23 11:25 | 11:25 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 2 | 2025-04-24 11:49
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54275 | 2025-04-24 11:48 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 21355.92 | 9961 | 126.5 | 5338.98 | 0 | 287 | 2025-04-23 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-23 11:25 | 11:25 AM | 2025-04-23 11:25 | 11:25 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-24 11:48
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54274 | 2025-04-24 11:47 | Purchase | GREY CORE INFRA LLP | 2.5 | CUM | BUILDTECH STORE | 13347.45 | 9961 | 126.5 | 5338.98 | 0 | 286 | 2025-04-23 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-23 11:25 | 11:25 AM | 2025-04-23 11:25 | 11:25 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 2.5 | 2025-04-24 11:47
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54273 | 2025-04-24 11:46 | Purchase | GREY CORE INFRA LLP | 3 | CUM | BUILDTECH STORE | 16016.94 | 9961 | 126.5 | 5338.98 | 0 | 276 | 2025-04-23 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-23 11:25 | 11:25 AM | 2025-04-23 11:25 | 11:25 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 3 | 2025-04-24 11:46
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 54272 | 2025-04-24 11:45 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 27203.88 | 9961 | 63.5 | 4533.98 | 0 | 280 | 2025-04-23 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-23 11:25 | 11:25 AM | 2025-04-23 11:25 | 11:25 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-24 11:45
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 54271 | 2025-04-24 11:43 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 27203.88 | 9961 | 63.5 | 4533.98 | 0 | 279 | 2025-04-23 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-23 11:25 | 11:25 AM | 2025-04-23 11:25 | 11:25 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-24 11:43
41 LUXOVERT | 00 RMC | RMC M70 (OUTSOURCE) |  | 54128 | 2025-04-23 10:38 | Purchase | GREY CORE INFRA LLP | 3 | CUM | BUILDTECH STORE | 22627.11 | 9961 | 45 | 7542.37 | 0 | 270 | 2025-04-22 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-22 10:32 | 10:32 AM | 2025-04-22 10:32 | 10:32 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 3 | 2025-04-23 10:38
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54127 | 2025-04-23 10:34 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 26694.9 | 9961 | 126.5 | 5338.98 | 0 | 273 | 2025-04-22 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-22 10:32 | 10:32 AM | 2025-04-22 10:32 | 10:32 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-23 10:34
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 54037 | 2025-04-22 14:57 | Purchase | GREY CORE INFRA LLP | 5.5 | CUM | BUILDTECH STORE | 24936.89 | 9961 | 63.5 | 4533.98 | 0 | 255 | 2025-04-21 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-21 14:45 | 2:45 PM | 2025-04-21 14:45 | 2:45 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5.5 | 2025-04-22 14:57
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 54036 | 2025-04-22 14:56 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 27203.88 | 9961 | 63.5 | 4533.98 | 0 | 254 | 2025-04-21 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-21 14:45 | 2:45 PM | 2025-04-21 14:45 | 2:45 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-22 14:56
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54035 | 2025-04-22 14:54 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 21355.92 | 9961 | 126.5 | 5338.98 | 0 | 243 | 2025-04-21 | 0 |  | Unbilled | MH04FD3284 |  | 2025-04-21 14:45 | 2:45 PM | 2025-04-21 14:45 | 2:45 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-22 14:54
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54034 | 2025-04-22 14:52 | Purchase | GREY CORE INFRA LLP | 1.5 | CUM | BUILDTECH STORE | 8008.47 | 9961 | 126.5 | 5338.98 | 0 | 247 | 2025-04-21 | 0 |  | Unbilled | MH04FD3284 |  | 2025-04-21 14:45 | 2:45 PM | 2025-04-21 14:45 | 2:45 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 1.5 | 2025-04-22 14:52
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54033 | 2025-04-22 14:51 | Purchase | GREY CORE INFRA LLP | 3.5 | CUM | BUILDTECH STORE | 18686.43 | 9961 | 126.5 | 5338.98 | 0 | 248 | 2025-04-21 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-21 14:45 | 2:45 PM | 2025-04-21 14:45 | 2:45 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 3.5 | 2025-04-22 14:51
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 54032 | 2025-04-22 14:49 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 21355.92 | 9961 | 126.5 | 5338.98 | 0 | 253 | 2025-04-21 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-21 14:45 | 2:45 PM | 2025-04-21 14:45 | 2:45 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-22 14:49
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 53860 | 2025-04-21 10:38 | Purchase | GREY CORE INFRA LLP | 3.5 | CUM | BUILDTECH STORE | 18686.43 | 9961 | 126.5 | 5338.98 | 0 | 236 | 2025-04-19 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-19 10:14 | 10:14 AM | 2025-04-19 10:14 | 10:14 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 3.5 | 2025-04-21 10:38
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 53859 | 2025-04-21 10:36 | Purchase | GREY CORE INFRA LLP | 2.5 | CUM | BUILDTECH STORE | 13347.45 | 9961 | 126.5 | 5338.98 | 0 | 234 | 2025-04-19 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-19 10:14 | 10:14 AM | 2025-04-19 10:14 | 10:14 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 2.5 | 2025-04-21 10:36
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 53858 | 2025-04-21 10:35 | Purchase | GREY CORE INFRA LLP | 3.5 | CUM | BUILDTECH STORE | 18686.43 | 9961 | 126.5 | 5338.98 | 0 | 231 | 2025-04-19 | 0 |  | Unbilled | MH12 SX9138 |  | 2025-04-19 10:14 | 10:14 AM | 2025-04-19 10:14 | 10:14 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 3.5 | 2025-04-21 10:35
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 53857 | 2025-04-21 10:31 | Purchase | GREY CORE INFRA LLP | 3 | CUM | BUILDTECH STORE | 16016.94 | 9961 | 126.5 | 5338.98 | 0 | 226 | 2025-04-19 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-19 10:14 | 10:14 AM | 2025-04-19 10:14 | 10:14 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 3 | 2025-04-21 10:31
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 53427 | 2025-04-19 11:17 | Purchase | GREY CORE INFRA LLP | 3 | CUM | BUILDTECH STORE | 13601.94 | 9961 | 63.5 | 4533.98 | 0 | 224 | 2025-04-18 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-18 11:07 | 11:07 AM | 2025-04-18 11:07 | 11:07 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 3 | 2025-04-19 11:17
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 53426 | 2025-04-19 11:17 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 22669.9 | 9961 | 63.5 | 4533.98 | 0 | 222 | 2025-04-18 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-18 11:07 | 11:07 AM | 2025-04-18 11:07 | 11:07 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-19 11:17
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 53425 | 2025-04-19 11:17 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 22669.9 | 9961 | 63.5 | 4533.98 | 0 | 218 | 2025-04-18 | 0 |  | Unbilled | mh14gd4834 |  | 2025-04-18 11:07 | 11:07 AM | 2025-04-18 11:07 | 11:07 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-19 11:17
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 53424 | 2025-04-19 11:16 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 22669.9 | 9961 | 63.5 | 4533.98 | 0 | 216 | 2025-04-18 | 0 |  | Unbilled | mh14gd4834 |  | 2025-04-18 11:07 | 11:07 AM | 2025-04-18 11:07 | 11:07 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-19 11:16
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 53357 | 2025-04-18 12:06 | Purchase | GREY CORE INFRA LLP | 1 | CUM | BUILDTECH STORE | 5338.98 | 9961 | 126.5 | 5338.98 | 0 | 205 | 2025-04-17 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-17 11:52 | 11:52 AM | 2025-04-17 11:52 | 11:52 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 1 | 2025-04-18 12:06
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 53356 | 2025-04-18 12:05 | Purchase | GREY CORE INFRA LLP | 4.5 | CUM | BUILDTECH STORE | 24025.41 | 9961 | 126.5 | 5338.98 | 0 | 201 | 2025-04-17 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-17 11:52 | 11:52 AM | 2025-04-17 11:52 | 11:52 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 4.5 | 2025-04-18 12:05
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 53355 | 2025-04-18 12:03 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 21355.92 | 9961 | 126.5 | 5338.98 | 0 | 199 | 2025-04-17 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-17 11:52 | 11:52 AM | 2025-04-17 11:52 | 11:52 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-18 12:03
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 53353 | 2025-04-18 12:00 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 22669.9 | 9961 | 63.5 | 4533.98 | 0 | 204 | 2025-04-17 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-17 11:52 | 11:52 AM | 2025-04-17 11:52 | 11:52 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-18 12:00
41 LUXOVERT | 00 RMC | RMC M40 (Out Source) |  | 53351 | 2025-04-18 11:58 | Purchase | GREY CORE INFRA LLP | 3.5 | CUM | BUILDTECH STORE | 17500 | 9985 | 19.5 | 5000 | 0 | 207 | 2025-04-17 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-17 11:52 | 11:52 AM | 2025-04-17 11:52 | 11:52 AM | 2025-04-05 17:07 |  | Approved |  | 0 | Luxovert.Store | 3.5 | 2025-04-18 11:58
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 53335 | 2025-04-17 11:01 | Purchase | GREY CORE INFRA LLP | 4.5 | CUM | BUILDTECH STORE | 24025.41 | 9961 | 126.5 | 5338.98 | 0 | 194 | 2025-04-16 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-16 10:49 | 10:49 AM | 2025-04-16 10:49 | 10:49 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 4.5 | 2025-04-17 11:01
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 53334 | 2025-04-17 11:01 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 21355.92 | 9961 | 126.5 | 5338.98 | 0 | 189 | 2025-04-16 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-16 10:49 | 10:49 AM | 2025-04-16 10:49 | 10:49 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-17 11:01
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 53333 | 2025-04-17 11:00 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 22669.9 | 9961 | 63.5 | 4533.98 | 0 | 196 | 2025-04-16 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-16 10:49 | 10:49 AM | 2025-04-16 10:49 | 10:49 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-17 11:00
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 53312 | 2025-04-16 11:23 | Purchase | GREY CORE INFRA LLP | 4.5 | CUM | BUILDTECH STORE | 20402.91 | 9961 | 63.5 | 4533.98 | 0 | 182 | 2025-04-15 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-15 11:21 | 11:21 AM | 2025-04-15 11:21 | 11:21 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 4.5 | 2025-04-16 11:23
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 53309 | 2025-04-16 10:25 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 26694.9 | 9961 | 126.5 | 5338.98 | 0 | 184 | 2025-04-15 | 0 |  | Unbilled | NH12 PQ 5483 |  | 2025-04-15 10:13 | 10:13 AM | 2025-04-15 10:13 | 10:13 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-16 10:25
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 53275 | 2025-04-15 11:02 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 26694.9 | 9961 | 126.5 | 5338.98 | 0 | 154 | 2025-04-14 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-14 11:00 | 11:00 AM | 2025-04-14 11:00 | 11:00 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-15 11:02
41 LUXOVERT | 00 RMC | RMC M70 (OUTSOURCE) |  | 53130 | 2025-04-14 10:36 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 37711.85 | 9961 | 45 | 7542.37 | 0 | 140 | 2025-04-12 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-12 10:29 | 10:29 AM | 2025-04-12 10:29 | 10:29 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-14 10:36
41 LUXOVERT | 00 RMC | RMC M70 (OUTSOURCE) |  | 53129 | 2025-04-14 10:34 | Purchase | GREY CORE INFRA LLP | 2 | CUM | BUILDTECH STORE | 15084.74 | 9961 | 45 | 7542.37 | 0 | 136 | 2025-04-12 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-12 10:29 | 10:29 AM | 2025-04-12 10:29 | 10:29 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 2 | 2025-04-14 10:34
41 LUXOVERT | 00 RMC | RMC M70 (OUTSOURCE) |  | 53127 | 2025-04-14 10:33 | Purchase | GREY CORE INFRA LLP | 5.5 | CUM | BUILDTECH STORE | 41483.035 | 9961 | 45 | 7542.37 | 0 | 141 | 2025-04-12 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-12 10:29 | 10:29 AM | 2025-04-12 10:29 | 10:29 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5.5 | 2025-04-14 10:33
41 LUXOVERT | 00 RMC | RMC M40 (Out Source) |  | 53024 | 2025-04-12 10:57 | Purchase | GREY CORE INFRA LLP | 2 | CUM | BUILDTECH STORE | 10000 | 9985 | 19.5 | 5000 | 0 | 111. | 2025-04-11 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-11 10:42 | 10:42 AM | 2025-04-11 10:42 | 10:42 AM | 2025-04-05 17:07 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-12 10:57
41 LUXOVERT | 00 RMC | RMC M40 (Out Source) |  | 53010 | 2025-04-12 10:56 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 20000 | 9744 | 22 | 5000 | 0 | 111 | 2025-04-11 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-11 10:42 | 10:42 AM | 2025-04-11 10:42 | 10:42 AM | 2025-03-15 14:07 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-12 10:56
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 53005 | 2025-04-12 10:46 | Purchase | GREY CORE INFRA LLP | 2.5 | CUM | BUILDTECH STORE | 11334.95 | 9961 | 63.5 | 4533.98 | 0 | 116 | 2025-04-11 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-11 10:42 | 10:42 AM | 2025-04-11 10:42 | 10:42 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 2.5 | 2025-04-12 10:46
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 53004 | 2025-04-12 10:44 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 22669.9 | 9961 | 63.5 | 4533.98 | 0 | 114 | 2025-04-11 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-11 10:42 | 10:42 AM | 2025-04-11 10:42 | 10:42 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-12 10:44
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52981 | 2025-04-11 14:50 | Purchase | GREY CORE INFRA LLP | 4.5 | CUM | BUILDTECH STORE | 24025.41 | 9961 | 126.5 | 5338.98 | 0 | 102 | 2025-04-10 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-10 14:35 | 2:35 PM | 2025-04-10 14:35 | 2:35 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Admin ho | 4.5 | 2025-04-11 14:50
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52980 | 2025-04-11 14:49 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 32033.88 | 9961 | 126.5 | 5338.98 | 0 | 99 | 2025-04-10 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-10 14:35 | 2:35 PM | 2025-04-10 14:35 | 2:35 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Admin ho | 6 | 2025-04-11 14:49
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52979 | 2025-04-11 14:48 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 37372.86 | 9961 | 126.5 | 5338.98 | 0 | 97 | 2025-04-10 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-10 14:35 | 2:35 PM | 2025-04-10 14:35 | 2:35 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Admin ho | 7 | 2025-04-11 14:48
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52978 | 2025-04-11 14:47 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 28220.4 | 9585 | 414.9 | 4703.4 | 0 | 89 | 2025-04-10 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-10 14:35 | 2:35 PM | 2025-04-10 14:35 | 2:35 PM | 2025-03-03 10:12 |  | Approved |  | 0 | Admin ho | 6 | 2025-04-11 14:47
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52977 | 2025-04-11 14:44 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 28220.4 | 9961 | 162 | 4703.4 | 0 | 88 | 2025-04-10 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-10 14:35 | 2:35 PM | 2025-04-10 14:35 | 2:35 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Admin ho | 6 | 2025-04-11 14:44
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52976 | 2025-04-11 14:39 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 28220.4 | 9961 | 162 | 4703.4 | 0 | 85 | 2025-04-10 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-10 14:35 | 2:35 PM | 2025-04-10 14:35 | 2:35 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Admin ho | 6 | 2025-04-11 14:39
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52974 | 2025-04-11 14:36 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 28220.4 | 9961 | 162 | 4703.4 | 0 | 83 | 2025-04-10 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-10 14:35 | 2:35 PM | 2025-04-10 14:35 | 2:35 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Admin ho | 6 | 2025-04-11 14:36
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52911 | 2025-04-10 15:04 | Purchase | GREY CORE INFRA LLP | 8 | CUM | BUILDTECH STORE | 37627.2 | 9961 | 162 | 4703.4 | 0 | 80 | 2025-04-09 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-09 14:42 | 2:42 PM | 2025-04-09 14:42 | 2:42 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 8 | 2025-04-10 15:04
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52910 | 2025-04-10 15:03 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 26694.9 | 9961 | 126.5 | 5338.98 | 0 | 70 | 2025-04-09 | 0 |  | Unbilled | MH12KP8181 |  | 2025-04-09 14:42 | 2:42 PM | 2025-04-09 14:42 | 2:42 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-10 15:03
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52907 | 2025-04-10 15:02 | Purchase | GREY CORE INFRA LLP | 5 | CUM | BUILDTECH STORE | 26694.9 | 9961 | 126.5 | 5338.98 | 0 | 56 | 2025-04-09 | 0 |  | Unbilled | MH12KP8181 |  | 2025-04-09 14:42 | 2:42 PM | 2025-04-09 14:42 | 2:42 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 5 | 2025-04-10 15:02
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52905 | 2025-04-10 15:00 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 28220.4 | 9961 | 162 | 4703.4 | 0 | 82 | 2025-04-09 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-09 14:42 | 2:42 PM | 2025-04-09 14:42 | 2:42 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-10 15:00
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52903 | 2025-04-10 14:56 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9961 | 162 | 4703.4 | 0 | 79 | 2025-04-09 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-09 14:42 | 2:42 PM | 2025-04-09 14:42 | 2:42 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-10 14:56
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52900 | 2025-04-10 14:55 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9961 | 162 | 4703.4 | 0 | 78 | 2025-04-09 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-09 14:42 | 2:42 PM | 2025-04-09 14:42 | 2:42 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-10 14:55
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52899 | 2025-04-10 14:53 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 28220.4 | 9961 | 162 | 4703.4 | 0 | 77 | 2025-04-09 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-09 14:42 | 2:42 PM | 2025-04-09 14:42 | 2:42 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-10 14:53
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52898 | 2025-04-10 14:52 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 28220.4 | 9961 | 162 | 4703.4 | 0 | 76 | 2025-04-09 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-09 14:42 | 2:42 PM | 2025-04-09 14:42 | 2:42 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-10 14:52
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52897 | 2025-04-10 14:49 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 28220.4 | 9961 | 162 | 4703.4 | 0 | 75 | 2025-04-09 | 0 |  | Unbilled | MH12KP8181 |  | 2025-04-09 14:42 | 2:42 PM | 2025-04-09 14:42 | 2:42 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-10 14:49
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52894 | 2025-04-10 14:46 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9961 | 162 | 4703.4 | 0 | 74 | 2025-04-09 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-09 14:42 | 2:42 PM | 2025-04-09 14:42 | 2:42 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-10 14:46
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52884 | 2025-04-10 13:12 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9961 | 162 | 4703.4 | 0 | 73 | 2025-04-09 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-09 12:29 | 12:29 PM | 2025-04-09 12:29 | 12:29 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-10 13:12
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52883 | 2025-04-10 13:11 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9961 | 162 | 4703.4 | 0 | 71 | 2025-04-09 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-09 12:29 | 12:29 PM | 2025-04-09 12:29 | 12:29 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-10 13:11
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52882 | 2025-04-10 13:11 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 28220.4 | 9961 | 162 | 4703.4 | 0 | 72 | 2025-04-09 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-09 12:29 | 12:29 PM | 2025-04-09 12:29 | 12:29 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-10 13:11
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52881 | 2025-04-10 13:10 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9961 | 162 | 4703.4 | 0 | 68 | 2025-04-09 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-09 12:29 | 12:29 PM | 2025-04-09 12:29 | 12:29 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-10 13:10
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52880 | 2025-04-10 13:08 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 28220.4 | 9961 | 162 | 4703.4 | 0 | 67 | 2025-04-09 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-09 12:29 | 12:29 PM | 2025-04-09 12:29 | 12:29 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-10 13:08
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52879 | 2025-04-10 13:06 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9961 | 162 | 4703.4 | 0 | 66 | 2025-04-09 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-09 12:29 | 12:29 PM | 2025-04-09 12:29 | 12:29 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-10 13:06
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52878 | 2025-04-10 13:05 | Purchase | GREY CORE INFRA LLP | 8 | CUM | BUILDTECH STORE | 37627.2 | 9961 | 162 | 4703.4 | 0 | 65 | 2025-04-09 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-09 12:29 | 12:29 PM | 2025-04-09 12:29 | 12:29 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 8 | 2025-04-10 13:05
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52877 | 2025-04-10 13:00 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 28220.4 | 9961 | 162 | 4703.4 | 0 | 64 | 2025-04-09 | 0 |  | Unbilled | MH12KP8181 |  | 2025-04-09 12:29 | 12:29 PM | 2025-04-09 12:29 | 12:29 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-10 13:00
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52876 | 2025-04-10 12:59 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9961 | 162 | 4703.4 | 0 | 63 | 2025-04-09 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-09 12:29 | 12:29 PM | 2025-04-09 12:29 | 12:29 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-10 12:59
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52875 | 2025-04-10 12:58 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 32923.8 | 9961 | 162 | 4703.4 | 0 | 62 | 2025-04-09 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-09 12:29 | 12:29 PM | 2025-04-09 12:29 | 12:29 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-10 12:58
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52874 | 2025-04-10 12:57 | Purchase | GREY CORE INFRA LLP | 8 | CUM | BUILDTECH STORE | 37627.2 | 9961 | 162 | 4703.4 | 0 | 61 | 2025-04-09 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-09 12:29 | 12:29 PM | 2025-04-09 12:29 | 12:29 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 8 | 2025-04-10 12:57
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52873 | 2025-04-10 12:55 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 28220.4 | 9961 | 162 | 4703.4 | 0 | 59 | 2025-04-09 | 0 |  | Unbilled | MH12KP8181 |  | 2025-04-09 12:29 | 12:29 PM | 2025-04-09 12:29 | 12:29 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-10 12:55
41 LUXOVERT | 00 RMC | RMC M35 (Out Source) |  | 52872 | 2025-04-10 12:51 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 28220.4 | 9961 | 162 | 4703.4 | 0 | 81 | 2025-04-09 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-09 12:29 | 12:29 PM | 2025-04-09 12:29 | 12:29 PM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-10 12:51
41 LUXOVERT | 00 RMC | RMC M70 (OUTSOURCE) |  | 52865 | 2025-04-10 10:57 | Purchase | GREY CORE INFRA LLP | 6 | CUM | BUILDTECH STORE | 45254.22 | 9961 | 45 | 7542.37 | 0 | 55 | 2025-04-08 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-08 10:47 | 10:47 AM | 2025-04-08 10:47 | 10:47 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 6 | 2025-04-10 10:57
41 LUXOVERT | 00 RMC | RMC M70 (OUTSOURCE) |  | 52864 | 2025-04-10 10:54 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 30169.48 | 9961 | 45 | 7542.37 | 0 | 54 | 2025-04-08 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-08 10:47 | 10:47 AM | 2025-04-08 10:47 | 10:47 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-10 10:54
41 LUXOVERT | 00 RMC | RMC M70 (OUTSOURCE) |  | 52862 | 2025-04-10 10:52 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 30169.48 | 9961 | 45 | 7542.37 | 0 | 53 | 2025-04-08 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-08 10:47 | 10:47 AM | 2025-04-08 10:47 | 10:47 AM | 2025-04-03 11:01 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-10 10:52
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52534 | 2025-04-07 11:07 | Purchase | GREY CORE INFRA LLP | 2.5 | CUM | BUILDTECH STORE | 13347.45 | 9585 | 284.5 | 5338.98 | 0 | 43 | 2025-04-05 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-05 10:48 | 10:48 AM | 2025-04-05 10:48 | 10:48 AM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 2.5 | 2025-04-07 11:07
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52533 | 2025-04-07 11:04 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 21355.92 | 9585 | 284.5 | 5338.98 | 0 | 39 | 2025-04-05 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-05 10:48 | 10:48 AM | 2025-04-05 10:48 | 10:48 AM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-07 11:04
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52532 | 2025-04-07 11:00 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 21355.92 | 9585 | 284.5 | 5338.98 | 0 | 37 | 2025-04-05 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-05 10:48 | 10:48 AM | 2025-04-05 10:48 | 10:48 AM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-07 11:00
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 52435 | 2025-04-05 10:34 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | BUILDTECH STORE | 29470.87 | 9916 | 183 | 4533.98 | 0 | 30 | 2025-04-04 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-04 10:30 | 10:30 AM | 2025-04-04 10:30 | 10:30 AM | 2025-03-28 18:54 |  | Approved |  | 0 | Luxovert.Store | 6.5 | 2025-04-05 10:34
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 52371 | 2025-04-04 12:44 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 31737.86 | 9916 | 183 | 4533.98 | 0 | 19 | 2025-04-02 | 0 |  | Unbilled | MH12SX9138 |  | 2025-03-02 11:23 | 11:23 AM | 2025-03-02 11:23 | 11:23 AM | 2025-03-28 18:54 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-04 12:44
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52370 | 2025-04-04 12:34 | Purchase | GREY CORE INFRA LLP | 1 | CUM | BUILDTECH STORE | 5338.98 | 9585 | 284.5 | 5338.98 | 0 | 18 | 2025-04-02 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-03-02 11:23 | 11:23 AM | 2025-03-02 11:23 | 11:23 AM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 1 | 2025-04-04 12:43
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52366 | 2025-04-04 12:32 | Purchase | GREY CORE INFRA LLP | 3 | CUM | BUILDTECH STORE | 16016.94 | 9585 | 284.5 | 5338.98 | 0 | 28 | 2025-04-03 | 0 |  | Unbilled | MH14JL1493 |  | 2025-03-03 11:23 | 11:23 AM | 2025-03-03 11:23 | 11:23 AM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 3 | 2025-04-04 12:34
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52365 | 2025-04-04 12:31 | Purchase | GREY CORE INFRA LLP | 7 | CUM | BUILDTECH STORE | 37372.86 | 9585 | 284.5 | 5338.98 | 0 | 27 | 2025-04-03 | 0 |  | Unbilled | MH12SX9138 |  | 2025-03-03 11:23 | 11:23 AM | 2025-03-03 11:23 | 11:23 AM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 7 | 2025-04-04 12:32
41 LUXOVERT | 00 RMC | RMC M70 (OUTSOURCE) |  | 52363 | 2025-04-04 12:28 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 30169.48 | 9867 | 70.5 | 7542.37 | 0 | 22 | 2025-04-03 | 0 |  | Unbilled | MH12HD4750 |  | 2025-03-03 11:23 | 11:23 AM | 2025-03-03 11:23 | 11:23 AM | 2025-03-01 17:34 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-04 12:29
41 LUXOVERT | 00 RMC | RMC M70 (OUTSOURCE) |  | 52362 | 2025-04-04 12:26 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 30169.48 | 9867 | 70.5 | 7542.37 | 0 | 26 | 2025-04-03 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-03-03 11:23 | 11:23 AM | 2025-03-03 11:23 | 11:23 AM | 2025-03-01 17:34 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-04 12:27
41 LUXOVERT | 00 RMC | RMC M30 (Out Source) |  | 52360 | 2025-04-04 12:17 | Purchase | GREY CORE INFRA LLP | 4.5 | CUM | BUILDTECH STORE | 20402.91 | 9916 | 183 | 4533.98 | 0 | 21 | 2025-04-02 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-03-02 11:23 | 11:23 AM | 2025-03-02 11:23 | 11:23 AM | 2025-03-28 18:54 |  | Approved |  | 0 | Luxovert.Store | 4.5 | 2025-04-04 12:23
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52279 | 2025-04-02 11:08 | Purchase | GREY CORE INFRA LLP | 2 | CUM | BUILDTECH STORE | 10677.96 | 9585 | 284.5 | 5338.98 | 0 | 6 | 2025-04-01 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-01 10:53 | 10:53 AM | 2025-04-01 10:53 | 10:53 AM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 2 | 2025-04-02 11:09
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52278 | 2025-04-02 11:07 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 21355.92 | 9585 | 284.5 | 5338.98 | 0 | 5 | 2025-04-01 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-01 10:53 | 10:53 AM | 2025-04-01 10:53 | 10:53 AM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-02 11:08
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52277 | 2025-04-02 11:00 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 21355.92 | 9585 | 284.5 | 5338.98 | 0 | 4 | 2025-04-01 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-01 10:53 | 10:53 AM | 2025-04-01 10:53 | 10:53 AM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-02 11:02
41 LUXOVERT | 00 RMC | RMC M50 (Out Source) |  | 52276 | 2025-04-02 10:59 | Purchase | GREY CORE INFRA LLP | 4 | CUM | BUILDTECH STORE | 21355.92 | 9585 | 284.5 | 5338.98 | 0 | 2 | 2025-04-01 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-01 10:53 | 10:53 AM | 2025-04-01 10:53 | 10:53 AM | 2025-03-03 10:12 |  | Approved |  | 0 | Luxovert.Store | 4 | 2025-04-02 11:00