## GRNRegisteritemwise638820584975
Material Wise GRN Report
From 01-04-2025 To 30-04-2025
Page 1 of 1
Total Records: 91 Records 1 to 91
Project_Name | Material_Category1 | Material_Name | Brand | GRN_No | GRN_Date | GRNType | Supplier_Issue_Store | Good_Qty | Unit_Name | Received_Store | Amount | PO_SrNo | PO_Qty | Rate | Transport_Others | Challan_No | Challan_Date | Bill_No | Bill_date | Billing_Status | VehicleNo | GateReg_No | GateReg date | GateReg Time | GateReg Out Date | GateReg Out Time | Po_Date | GRN_Remark | GRN_Status | Material_Category2 | GTN_SrNo | Created_BY | Challan_Qty | Entry_Date
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54711 | 2025-04-29 15:47 | Purchase | GREY CORE INFRA LLP | 1 | CUM | 41 RIZZ STORE | 4472.03 | 10164 | 25 | 4472.03 | 0 | 233 | 2025-04-19 | 0 |  | Unbilled | MH12 SX9138 |  | 2025-04-19 15:37 | 3:37 PM | 2025-04-19 15:37 | 3:37 PM | 2025-04-23 14:52 |  | Approved |  | 0 | RIZZ.STORE | 2 | 2025-04-29 15:47
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54709 | 2025-04-29 15:45 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10164 | 25 | 4472.03 | 0 | 232 | 2025-04-19 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-19 15:37 | 3:37 PM | 2025-04-19 15:37 | 3:37 PM | 2025-04-23 14:52 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-29 15:45
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54708 | 2025-04-29 15:44 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10164 | 25 | 4472.03 | 0 | 360 | 2025-04-27 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-27 15:37 | 3:37 PM | 2025-04-27 15:37 | 3:37 PM | 2025-04-23 14:52 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-29 15:44
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54707 | 2025-04-29 15:44 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10164 | 25 | 4472.03 | 0 | 373 | 2025-04-27 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-27 15:37 | 3:37 PM | 2025-04-27 15:37 | 3:37 PM | 2025-04-23 14:52 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-29 15:44
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54706 | 2025-04-29 15:42 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10164 | 25 | 4472.03 | 0 | 372 | 2025-04-27 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-27 15:37 | 3:37 PM | 2025-04-27 15:37 | 3:37 PM | 2025-04-23 14:52 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-29 15:42
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54656 | 2025-04-28 17:18 | Purchase | GREY CORE INFRA LLP | 3 | CUM | 41 RIZZ STORE | 13416.09 | 10137 | 90 | 4472.03 | 0 | 190 | 2025-04-16 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-16 17:07 | 5:07 PM | 2025-04-16 17:07 | 5:07 PM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 4 | 2025-04-28 17:18
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54655 | 2025-04-28 17:17 | Purchase | GREY CORE INFRA LLP | 4 | CUM | 41 RIZZ STORE | 17888.12 | 10137 | 90 | 4472.03 | 0 | 192 | 2025-04-16 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-16 17:07 | 5:07 PM | 2025-04-16 17:07 | 5:07 PM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 4 | 2025-04-28 17:17
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54654 | 2025-04-28 17:13 | Purchase | GREY CORE INFRA LLP | 5 | CUM | 41 RIZZ STORE | 22360.15 | 10137 | 90 | 4472.03 | 0 | 210 | 2025-04-18 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-18 17:07 | 5:07 PM | 2025-04-18 17:07 | 5:07 PM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 5 | 2025-04-28 17:13
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54436 | 2025-04-25 08:43 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 10137 | 90 | 4472.03 | 0 | 284 | 2025-04-23 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-23 08:11 | 8:11 AM | 2025-04-23 08:11 | 8:11 AM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-25 08:43
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54435 | 2025-04-25 08:42 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 10137 | 90 | 4472.03 | 0 | 268 | 2025-04-22 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-22 08:11 | 8:11 AM | 2025-04-22 08:11 | 8:11 AM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-25 08:42
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54434 | 2025-04-25 08:40 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 10137 | 90 | 4472.03 | 0 | 271 | 2025-04-22 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-22 08:11 | 8:11 AM | 2025-04-22 08:11 | 8:11 AM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-25 08:40
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54433 | 2025-04-25 08:39 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10137 | 90 | 4472.03 | 0 | 269 | 2025-04-22 | 0 |  | Unbilled | mh14gd4834 |  | 2025-04-22 08:11 | 8:11 AM | 2025-04-22 08:11 | 8:11 AM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-25 08:39
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54432 | 2025-04-25 08:38 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 10137 | 90 | 4472.03 | 0 | 267 | 2025-04-22 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-22 08:11 | 8:11 AM | 2025-04-22 08:11 | 8:11 AM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-25 08:38
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54431 | 2025-04-25 08:36 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 10137 | 90 | 4472.03 | 0 | 258 | 2025-04-22 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-22 08:11 | 8:11 AM | 2025-04-22 08:11 | 8:11 AM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-25 08:36
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54430 | 2025-04-25 08:34 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41 RIZZ STORE | 31304.21 | 10137 | 90 | 4472.03 | 0 | 265 | 2025-04-22 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-22 08:11 | 8:11 AM | 2025-04-22 08:11 | 8:11 AM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 7 | 2025-04-25 08:34
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54429 | 2025-04-25 08:32 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10137 | 90 | 4472.03 | 0 | 264 | 2025-04-22 | 0 |  | Unbilled | mh14gd4834 |  | 2025-04-22 08:11 | 8:11 AM | 2025-04-22 08:11 | 8:11 AM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-25 08:32
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54428 | 2025-04-25 08:31 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 10137 | 90 | 4472.03 | 0 | 263 | 2025-04-22 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-22 08:11 | 8:11 AM | 2025-04-22 08:11 | 8:11 AM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-25 08:31
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54427 | 2025-04-25 08:29 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 10137 | 90 | 4472.03 | 0 | 262 | 2025-04-22 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-22 08:11 | 8:11 AM | 2025-04-22 08:11 | 8:11 AM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-25 08:29
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54426 | 2025-04-25 08:28 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41 RIZZ STORE | 31304.21 | 10137 | 90 | 4472.03 | 0 | 260 | 2025-04-22 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-22 08:11 | 8:11 AM | 2025-04-22 08:11 | 8:11 AM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 7 | 2025-04-25 08:28
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54425 | 2025-04-25 08:26 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 10137 | 90 | 4472.03 | 0 | 256 | 2025-04-21 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-21 08:11 | 8:11 AM | 2025-04-21 08:11 | 8:11 AM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-25 08:26
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54424 | 2025-04-25 08:21 | Purchase | GREY CORE INFRA LLP | 2.5 | CUM | 41 RIZZ STORE | 11180.075 | 10086 | 15 | 4472.03 | 0 | 261. | 2025-04-22 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-22 08:11 | 8:11 AM | 2025-04-22 08:11 | 8:11 AM | 2025-04-14 18:20 |  | Approved |  | 0 | RIZZ.STORE | 2.5 | 2025-04-25 08:21
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54423 | 2025-04-25 08:19 | Purchase | GREY CORE INFRA LLP | 3.5 | CUM | 41 RIZZ STORE | 15652.105 | 10125 | 10 | 4472.03 | 0 | 261 | 2025-04-22 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-22 08:11 | 8:11 AM | 2025-04-22 08:11 | 8:11 AM | 2025-04-18 17:07 |  | Approved |  | 0 | RIZZ.STORE | 3.5 | 2025-04-25 08:19
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54422 | 2025-04-25 08:16 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 10125 | 10 | 4472.03 | 0 | 285 | 2025-04-23 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-23 08:11 | 8:11 AM | 2025-04-23 08:11 | 8:11 AM | 2025-04-18 17:07 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-25 08:16
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54421 | 2025-04-25 08:15 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 10086 | 15 | 4472.03 | 0 | 252 | 2025-04-21 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-21 08:11 | 8:11 AM | 2025-04-21 08:11 | 8:11 AM | 2025-04-14 18:20 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-25 08:15
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 54420 | 2025-04-25 08:13 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10086 | 15 | 4472.03 | 0 | 250 | 2025-04-21 | 0 |  | Unbilled | MH04FD3284 |  | 2025-04-21 08:11 | 8:11 AM | 2025-04-21 08:11 | 8:11 AM | 2025-04-14 18:20 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-25 08:13
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53627 | 2025-04-20 23:13 | Purchase | GREY CORE INFRA LLP | 0.5 | CUM | 41 RIZZ STORE | 2236.015 | 10077 | 12.5 | 4472.03 | 0 | 139... | 2025-04-12 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-12 23:07 | 11:07 PM | 2025-04-12 23:07 | 11:07 PM | 2025-04-12 17:21 |  | Approved |  | 0 | RIZZ.STORE | 0.5 | 2025-04-20 23:13
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53626 | 2025-04-20 23:12 | Purchase | GREY CORE INFRA LLP | 1 | CUM | 41 RIZZ STORE | 4472.03 | 9964 | 35 | 4472.03 | 0 | 139.. | 2025-04-12 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-12 23:07 | 11:07 PM | 2025-04-12 23:07 | 11:07 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 1 | 2025-04-20 23:12
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53625 | 2025-04-20 23:12 | Purchase | GREY CORE INFRA LLP | 3.5 | CUM | 41 RIZZ STORE | 15652.105 | 10032 | 50 | 4472.03 | 0 | 139. | 2025-04-12 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-12 23:07 | 11:07 PM | 2025-04-12 23:07 | 11:07 PM | 2025-04-03 16:19 |  | Approved |  | 0 | RIZZ.STORE | 3.5 | 2025-04-20 23:12
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53624 | 2025-04-20 23:11 | Purchase | GREY CORE INFRA LLP | 1.5 | CUM | 41 RIZZ STORE | 6708.045 | 9891 | 180 | 4472.03 | 0 | 139 | 2025-04-12 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-12 23:07 | 11:07 PM | 2025-04-12 23:07 | 11:07 PM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 1.5 | 2025-04-20 23:11
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53623 | 2025-04-20 23:04 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10077 | 12.5 | 4472.03 | 0 | 138 | 2025-04-12 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-12 22:53 | 10:53 PM | 2025-04-12 22:53 | 10:53 PM | 2025-04-12 17:21 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-20 23:04
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53622 | 2025-04-20 23:03 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10077 | 12.5 | 4472.03 | 0 | 137 | 2025-04-12 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-12 22:53 | 10:53 PM | 2025-04-12 22:53 | 10:53 PM | 2025-04-12 17:21 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-20 23:03
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53226 | 2025-04-14 17:47 | Purchase | GREY CORE INFRA LLP | 3.5 | CUM | 41 RIZZ STORE | 15652.105 | 10032 | 50 | 4472.03 | 0 | 113. | 2025-04-11 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-11 17:32 | 5:32 PM | 2025-04-11 17:32 | 5:32 PM | 2025-04-03 16:19 |  | Deleted |  | 0 | RIZZ.STORE | 3.5 | 2025-04-14 17:47
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53225 | 2025-04-14 17:46 | Purchase | GREY CORE INFRA LLP | 1.5 | CUM | 41 RIZZ STORE | 6708.045 | 9891 | 180 | 4472.03 | 0 | 113 | 2025-04-11 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-11 17:32 | 5:32 PM | 2025-04-11 17:32 | 5:32 PM | 2025-03-27 14:31 |  | Deleted |  | 0 | RIZZ.STORE | 1.5 | 2025-04-14 17:46
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53223 | 2025-04-14 17:45 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 9964 | 35 | 4472.03 | 0 | 110 | 2025-04-11 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-11 17:32 | 5:32 PM | 2025-04-11 17:32 | 5:32 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-14 17:45
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53221 | 2025-04-14 17:44 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9964 | 35 | 4472.03 | 0 | 109 | 2025-04-11 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-11 17:32 | 5:32 PM | 2025-04-11 17:32 | 5:32 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-14 17:44
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53219 | 2025-04-14 17:42 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10032 | 50 | 4472.03 | 0 | 108 | 2025-04-11 | 0 |  | Unbilled | MH12 SX9138 |  | 2025-04-11 17:32 | 5:32 PM | 2025-04-11 17:32 | 5:32 PM | 2025-04-03 16:19 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-14 17:42
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53218 | 2025-04-14 17:41 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 10032 | 50 | 4472.03 | 0 | 107 | 2025-04-11 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-11 17:32 | 5:32 PM | 2025-04-11 17:32 | 5:32 PM | 2025-04-03 16:19 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-14 17:41
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53217 | 2025-04-14 17:41 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41 RIZZ STORE | 31304.21 | 10032 | 50 | 4472.03 | 0 | 106 | 2025-04-11 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-11 17:32 | 5:32 PM | 2025-04-11 17:32 | 5:32 PM | 2025-04-03 16:19 |  | Approved |  | 0 | RIZZ.STORE | 7 | 2025-04-14 17:41
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53215 | 2025-04-14 17:40 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10032 | 50 | 4472.03 | 0 | 105 | 2025-04-11 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-11 17:32 | 5:32 PM | 2025-04-11 17:32 | 5:32 PM | 2025-04-03 16:19 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-14 17:40
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53213 | 2025-04-14 17:37 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10032 | 50 | 4472.03 | 0 | 103 | 2025-04-11 | 0 |  | Unbilled | MH12 SX9138 |  | 2025-04-11 17:32 | 5:32 PM | 2025-04-11 17:32 | 5:32 PM | 2025-04-03 16:19 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-14 17:37
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53212 | 2025-04-14 17:36 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10032 | 50 | 4472.03 | 0 | 60 | 2025-04-09 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-09 17:32 | 5:32 PM | 2025-04-09 17:32 | 5:32 PM | 2025-04-03 16:19 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-14 17:36
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53211 | 2025-04-14 17:35 | Purchase | GREY CORE INFRA LLP | 3 | CUM | 41 RIZZ STORE | 13416.09 | 10032 | 50 | 4472.03 | 0 | 58 | 2025-04-09 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-09 17:32 | 5:32 PM | 2025-04-09 17:32 | 5:32 PM | 2025-04-03 16:19 |  | Approved |  | 0 | RIZZ.STORE | 3 | 2025-04-14 17:35
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 53209 | 2025-04-14 17:34 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 10032 | 50 | 4472.03 | 0 | 57 | 2025-04-09 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-09 17:32 | 5:32 PM | 2025-04-09 17:32 | 5:32 PM | 2025-04-03 16:19 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-14 17:34
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52932 | 2025-04-10 18:33 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9964 | 35 | 4472.03 | 0 | 50 | 2025-04-07 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-07 18:29 | 6:29 PM | 2025-04-07 18:29 | 6:29 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-10 18:33
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52931 | 2025-04-10 18:32 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9964 | 35 | 4472.03 | 0 | 44 | 2025-04-07 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-07 18:29 | 6:29 PM | 2025-04-07 18:29 | 6:29 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-10 18:32
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52930 | 2025-04-10 16:50 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9964 | 35 | 4472.03 | 0 | 45 | 2025-04-07 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-07 16:40 | 4:40 PM | 2025-04-07 16:40 | 4:40 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-10 16:50
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52929 | 2025-04-10 16:50 | Purchase | GREY CORE INFRA LLP | 3.5 | CUM | 41 RIZZ STORE | 15652.105 | 9964 | 35 | 4472.03 | 0 | 47 | 2025-04-07 | 0 |  | Unbilled | MH12 SX9138 |  | 2025-04-07 16:40 | 4:40 PM | 2025-04-07 16:40 | 4:40 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 3.5 | 2025-04-10 16:50
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52928 | 2025-04-10 16:48 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9987 | 50 | 4472.03 | 0 | 46 | 2025-04-07 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-07 16:40 | 4:40 PM | 2025-04-07 16:40 | 4:40 PM | 2025-04-03 17:13 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-10 16:48
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52927 | 2025-04-10 16:47 | Purchase | GREY CORE INFRA LLP | 3 | CUM | 41 RIZZ STORE | 13416.09 | 9987 | 50 | 4472.03 | 0 | 52 | 2025-04-07 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-07 16:40 | 4:40 PM | 2025-04-07 16:40 | 4:40 PM | 2025-04-03 17:13 |  | Approved |  | 0 | RIZZ.STORE | 3 | 2025-04-10 16:47
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52802 | 2025-04-09 08:11 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9987 | 50 | 4472.03 | 0 | 36 | 2025-04-05 | 0 |  | Unbilled | MH12 SX9138 | 224 | 2025-04-05 08:02 | 8:02 AM | 2025-04-05 08:02 | 8:02 AM | 2025-04-03 17:13 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 08:11
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52801 | 2025-04-09 08:11 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9987 | 50 | 4472.03 | 0 | 35 | 2025-04-05 | 0 |  | Unbilled | MH12PQ5483 | 223 | 2025-04-05 08:02 | 8:02 AM | 2025-04-05 08:02 | 8:02 AM | 2025-04-03 17:13 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 08:11
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52800 | 2025-04-09 08:09 | Purchase | GREY CORE INFRA LLP | 5 | CUM | 41 RIZZ STORE | 22360.15 | 9987 | 50 | 4472.03 | 0 | 42 | 2025-04-05 | 0 |  | Unbilled | MH12 SX9138 | 220 | 2025-04-05 08:02 | 8:02 AM | 2025-04-05 08:02 | 8:02 AM | 2025-04-03 17:13 |  | Approved |  | 0 | RIZZ.STORE | 5 | 2025-04-09 08:09
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52799 | 2025-04-09 08:08 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9987 | 50 | 4472.03 | 0 | 41 | 2025-04-05 | 0 |  | Unbilled | MH12HD4750 | 227 | 2025-04-05 08:02 | 8:02 AM | 2025-04-05 08:02 | 8:02 AM | 2025-04-03 17:13 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 08:08
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52798 | 2025-04-09 08:07 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9987 | 50 | 4472.03 | 0 | 40 | 2025-04-05 | 0 |  | Unbilled | MH12PQ5483 | 226 | 2025-04-05 08:02 | 8:02 AM | 2025-04-05 08:02 | 8:02 AM | 2025-04-03 17:13 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 08:07
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52797 | 2025-04-09 08:07 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9987 | 50 | 4472.03 | 0 | 38 | 2025-04-05 | 0 |  | Unbilled | MH14JL1493 | 225 | 2025-04-05 08:02 | 8:02 AM | 2025-04-05 08:02 | 8:02 AM | 2025-04-03 17:13 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 08:07
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52796 | 2025-04-09 08:06 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9987 | 50 | 4472.03 | 0 | 34 | 2025-04-05 | 0 |  | Unbilled | MH14/LL 8687 | 222 | 2025-04-05 08:02 | 8:02 AM | 2025-04-05 08:02 | 8:02 AM | 2025-04-03 17:13 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 08:06
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52795 | 2025-04-09 07:20 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | 33 | 2025-04-05 | 0 |  | Unbilled | MH14JL1493 | 221 | 2025-04-05 06:34 | 6:34 AM | 2025-04-05 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:20
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52794 | 2025-04-09 07:19 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | 7 | 2025-04-02 | 0 |  | Unbilled | MH14JL1493 | 202 | 2025-04-02 06:34 | 6:34 AM | 2025-04-02 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:19
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52793 | 2025-04-09 07:18 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | 9 | 2025-04-02 | 0 |  | Unbilled | MH12PQ5483 | 203 | 2025-04-02 06:34 | 6:34 AM | 2025-04-02 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:18
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52792 | 2025-04-09 07:17 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | 10 | 2025-04-02 | 0 |  | Unbilled | MH12HD4750 | 204 | 2025-04-02 06:34 | 6:34 AM | 2025-04-02 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:17
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52791 | 2025-04-09 07:16 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | 11 | 2025-04-02 | 0 |  | Unbilled | MH14/LL 8687 | 205 | 2025-04-02 06:34 | 6:34 AM | 2025-04-02 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:16
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52790 | 2025-04-09 07:15 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | 12 | 2025-04-02 | 0 |  | Unbilled | MH14JL1493 | 206 | 2025-04-02 06:34 | 6:34 AM | 2025-04-02 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:15
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52789 | 2025-04-09 07:15 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | 13 | 2025-04-02 | 0 |  | Unbilled | MH12PQ5483 | 207 | 2025-04-02 06:34 | 6:34 AM | 2025-04-02 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:15
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52788 | 2025-04-09 07:14 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | 14 | 2025-04-02 | 0 |  | Unbilled | MH12HD4750 | 208 | 2025-04-02 06:34 | 6:34 AM | 2025-04-02 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:14
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52787 | 2025-04-09 07:13 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 9891 | 180 | 4472.03 | 0 | GC2773 | 2025-03-31 | 1368 | 2025-03-31 | Billed | MH12 SX9138 | 194 | 2025-03-31 06:34 | 6:34 AM | 2025-03-31 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-09 07:13
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52786 | 2025-04-09 07:12 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | GC2772 | 2025-03-31 | 1368 | 2025-03-31 | Billed | MH12HD4750 | 193 | 2025-03-31 06:34 | 6:34 AM | 2025-03-31 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:12
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52785 | 2025-04-09 07:11 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | GC2767 | 2025-03-31 | 1368 | 2025-03-31 | Billed | MH12HD4750 | 191 | 2025-03-31 06:34 | 6:34 AM | 2025-03-31 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:11
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52784 | 2025-04-09 07:11 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 9891 | 180 | 4472.03 | 0 | GC2768 | 2025-03-31 | 1368 | 2025-03-31 | Billed | MH12 SX9138 | 192 | 2025-03-31 06:34 | 6:34 AM | 2025-03-31 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-09 07:11
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52783 | 2025-04-09 07:10 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | GC2766 | 2025-03-31 | 1368 | 2025-03-31 | Billed | MH12PQ5483 | 190 | 2025-03-31 06:34 | 6:34 AM | 2025-03-31 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:10
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52782 | 2025-04-09 07:09 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 9891 | 180 | 4472.03 | 0 | GC2765 | 2025-03-31 | 1368 | 2025-03-31 | Billed | MH12 SX9138 | 189 | 2025-03-31 06:34 | 6:34 AM | 2025-03-31 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-09 07:09
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52781 | 2025-04-09 07:08 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | GC2763 | 2025-03-31 | 1368 | 2025-03-31 | Billed | MH12HD4750 | 188 | 2025-03-31 06:34 | 6:34 AM | 2025-03-31 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:08
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52780 | 2025-04-09 07:07 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | GC2774 | 2025-03-31 | 1368 | 2025-03-31 | Billed | MH12PQ5483 | 195 | 2025-03-31 06:34 | 6:34 AM | 2025-03-31 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:07
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52779 | 2025-04-09 07:06 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | GC2775 | 2025-03-31 | 0 |  | Unbilled | MH14JL1493 | 196 | 2025-03-31 06:34 | 6:34 AM | 2025-03-31 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Deleted |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:06
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52778 | 2025-04-09 07:05 | Purchase | GREY CORE INFRA LLP | 5 | CUM | 41 RIZZ STORE | 22360.15 | 9891 | 180 | 4472.03 | 0 | GC2777 | 2025-03-31 | 1371 | 2025-03-31 | Billed | MH12HD4750 | 197 | 2025-03-31 06:34 | 6:34 AM | 2025-03-31 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 5 | 2025-04-09 07:05
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52777 | 2025-04-09 07:04 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | GC2689 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH 12 KP 8181 | 177 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 07:04
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52776 | 2025-04-09 07:03 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 9891 | 180 | 4472.03 | 0 | GC2687 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH12 SX9138 | 176 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-09 07:03
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52775 | 2025-04-09 07:02 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 9891 | 180 | 4472.03 | 0 | GC2692 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH14/LL 8687 | 175 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-09 07:02
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52774 | 2025-04-09 07:01 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41 RIZZ STORE | 31304.21 | 9891 | 180 | 4472.03 | 0 | GC2694 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH14JL1493 | 174 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 7 | 2025-04-09 07:01
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52773 | 2025-04-09 07:01 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 9891 | 180 | 4472.03 | 0 | GC2686 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH14/LL 8687 | 173 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-09 07:01
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52772 | 2025-04-09 06:59 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | GC2685 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH12PQ5483 | 172 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 06:59
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52771 | 2025-04-09 06:58 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 9891 | 180 | 4472.03 | 0 | GC2683 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH12 SX9138 | 171 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-09 06:58
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52770 | 2025-04-09 06:58 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 9891 | 180 | 4472.03 | 0 | GC2682 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH14/LL 8687 | 170 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-09 06:58
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52769 | 2025-04-09 06:57 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | GC2681 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH12KP8181 | 170 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 06:57
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52768 | 2025-04-09 06:56 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9891 | 180 | 4472.03 | 0 | GC2678 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH12PQ5483 | 168 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 06:56
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52767 | 2025-04-09 06:55 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 9891 | 180 | 4472.03 | 0 | GC2676 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH12 SX9138 | 166 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-27 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-09 06:55
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52766 | 2025-04-09 06:54 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41 RIZZ STORE | 31304.21 | 9856 | 150 | 4472.03 | 0 | GC2677 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH14JL1493 | 167 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-24 18:52 |  | Approved |  | 0 | RIZZ.STORE | 7 | 2025-04-09 06:54
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52765 | 2025-04-09 06:53 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9856 | 150 | 4472.03 | 0 | GC2674 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH12KP8181 | 165 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-24 18:52 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 06:53
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52764 | 2025-04-09 06:53 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41 RIZZ STORE | 31304.21 | 9856 | 150 | 4472.03 | 0 | GC2667 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH14JL1493 | 164 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-24 18:52 |  | Approved |  | 0 | RIZZ.STORE | 7 | 2025-04-09 06:53
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52763 | 2025-04-09 06:52 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 26832.18 | 9856 | 150 | 4472.03 | 0 | GC2665 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH12KP8181 | 163 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-24 18:52 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-09 06:52
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52762 | 2025-04-09 06:51 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 9856 | 150 | 4472.03 | 0 | GC2664 | 2025-03-28 | 1359 | 2025-03-28 | Billed | MH12 SX9138 | 162 | 2025-03-28 06:34 | 6:34 AM | 2025-03-28 06:34 | 6:34 AM | 2025-03-24 18:52 |  | Approved |  | 0 | RIZZ.STORE | 6.5 | 2025-04-09 06:51
41 ZILLENIA PHASE 2 | 00 RMC | RMC M25 (Out Source) |  | 52761 | 2025-04-09 06:49 | Purchase | GREY CORE INFRA LLP | 6.5 | CUM | 41 RIZZ STORE | 29068.195 | 9856 | 150 | 4472.03 | 0 | GC2664 | 2025-03-29 | 0 |  | Unbilled | MH12 SX9138 | 162 | 2025-03-29 06:34 | 6:34 AM | 2025-03-29 06:34 | 6:34 AM | 2025-03-24 18:52 |  | Deleted |  | 0 | RIZZ.STORE | 6.5 | 2025-04-09 06:49