## GRNRegisteritemwise638820587580
Material Wise GRN Report
From 12-03-2025 To 05-05-2025
Page 1 of 1
Total Records: 176 Records 1 to 176
Project_Name | Material_Category1 | Material_Name | Brand | GRN_No | GRN_Date | GRNType | Supplier_Issue_Store | Good_Qty | Unit_Name | Received_Store | Amount | PO_SrNo | PO_Qty | Rate | Transport_Others | Challan_No | Challan_Date | Bill_No | Bill_date | Billing_Status | VehicleNo | GateReg_No | GateReg date | GateReg Time | GateReg Out Date | GateReg Out Time | Po_Date | GRN_Remark | GRN_Status | Material_Category2 | GTN_SrNo | Created_BY | Challan_Qty | Entry_Date
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54897 | 2025-05-03 15:43 | Purchase | RDC Concrete India Pvt. Ltd. | 3 | CUM | 41ORANGE KRISALA STORE | 13728.81 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-741 | 2025-05-03 | 0 |  | Unbilled | AP39 UD2006 | 3181 | 2025-05-03 11:00 | 11:00 AM | 2025-05-03 15:41 | 3:41 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 3 | 2025-05-03 15:43
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54772 | 2025-04-30 13:26 | Purchase | RDC Concrete India Pvt. Ltd. | 2.5 | CUM | 41ORANGE KRISALA STORE | 11440.675 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-668 | 2025-04-28 | 0 |  | Unbilled | AP39 UD2006 | 3161 | 2025-04-28 20:56 | 8:56 PM | 2025-04-28 21:30 | 9:30 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 2.5 | 2025-04-30 13:26
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54771 | 2025-04-30 13:23 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-667 | 2025-04-28 | 0 |  | Unbilled | AP39 UD2009 | 3160 | 2025-04-28 19:18 | 7:18 PM | 2025-04-28 20:21 | 8:21 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 13:23
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54770 | 2025-04-30 13:22 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-666 | 2025-04-28 | 0 |  | Unbilled | MH12UM 2890 | 3159 | 2025-04-28 19:11 | 7:11 PM | 2025-04-28 19:50 | 7:50 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 13:22
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54769 | 2025-04-30 13:20 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-665 | 2025-04-28 | 0 |  | Unbilled | AP39 UD2011 | 3156 | 2025-04-28 18:59 | 6:59 PM | 2025-04-28 19:38 | 7:38 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 13:20
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54768 | 2025-04-30 13:18 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-664 | 2025-04-28 | 0 |  | Unbilled | MH12/UM 7849 | 3157 | 2025-04-28 18:31 | 6:31 PM | 2025-04-28 19:10 | 7:10 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 13:18
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54767 | 2025-04-30 13:15 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-663 | 2025-04-28 | 0 |  | Unbilled | AP39 UD2008 | 3156 | 2025-04-28 16:11 | 4:11 PM | 2025-04-28 18:42 | 6:42 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 13:15
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54766 | 2025-04-30 13:14 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-662 | 2025-04-28 | 0 |  | Unbilled | MH14/KQ 2448 | 3155 | 2025-04-28 17:47 | 5:47 PM | 2025-04-28 18:11 | 6:11 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 13:14
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54765 | 2025-04-30 13:13 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-661 | 2025-04-28 | 0 |  | Unbilled | AP39 UD2010 | 3154 | 2025-04-28 16:45 | 4:45 PM | 2025-04-28 17:34 | 5:34 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 13:13
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54764 | 2025-04-30 13:10 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-660 | 2025-04-28 | 0 |  | Unbilled | AP39 UD2006 | 3153 | 2025-04-28 16:45 | 4:45 PM | 2025-04-28 17:34 | 5:34 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 13:10
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54763 | 2025-04-30 13:07 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-659 | 2025-04-28 | 0 |  | Unbilled | MH12UM 2890 | 3152 | 2025-04-28 16:22 | 4:22 PM | 2025-04-28 17:10 | 5:10 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 13:07
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54762 | 2025-04-30 13:05 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-656 | 2025-04-28 | 0 |  | Unbilled | AP39 UD2009 | 3151 | 2025-04-28 16:00 | 4:00 PM | 2025-04-28 16:52 | 4:52 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 13:05
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54761 | 2025-04-30 13:03 | Purchase | RDC Concrete India Pvt. Ltd. | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-658 | 2025-04-28 | 0 |  | Unbilled | AP39 UD2011 | 3150 | 2025-04-28 15:56 | 3:56 PM | 2025-04-28 16:41 | 4:41 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 6 | 2025-04-30 13:03
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54760 | 2025-04-30 13:01 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-657 | 2025-04-28 | 0 |  | Unbilled | MH12/UM 7849 | 3149 | 2025-04-28 15:42 | 3:42 PM | 2025-04-28 16:07 | 4:07 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 13:01
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54759 | 2025-04-30 12:58 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-654 | 2025-04-28 | 0 |  | Unbilled | AP39 UD2008 | 3148 | 2025-04-28 15:24 | 3:24 PM | 2025-04-28 15:58 | 3:58 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 12:58
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54758 | 2025-04-30 12:52 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10180 | 110 | 4576.27 | 0 | 3PU25BP1-653 | 2025-04-28 | 0 |  | Unbilled | MH14/KQ 2448 | 3447 | 2025-04-28 14:30 | 2:30 PM | 2025-04-28 15:16 | 3:16 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 12:52
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54444 | 2025-04-25 10:46 | Purchase | RDC Concrete India Pvt. Ltd. | 3 | CUM | 41ORANGE KRISALA STORE | 13728.81 | 10145 | 95.5 | 4576.27 | 0 | 3PU25BPP1-500 | 2025-04-22 | 3PU25BP1-500 | 2025-04-22 | Billed | AP39 UD2010 | 3120 | 2025-04-22 10:42 | 10:42 AM | 2025-04-22 10:42 | 10:42 AM | 2025-04-21 13:50 |  | Approved |  | 0 | Ashoks | 3 | 2025-04-25 10:46
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 54173 | 2025-04-23 14:34 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5911 | 2025-04-09 | 267 | 2025-04-16 | Billed | MH12 VF7655 | 3014 | 2025-04-23 14:29 | 2:29 PM | 2025-04-23 14:29 | 2:29 PM | 2025-04-07 15:40 | E BLDG 18 SLAB PART 2 | Approved |  | 0 | Ashoks | 7 | 2025-04-23 14:34
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53976 | 2025-04-21 20:51 | Purchase | RVK INFRATECH | 2.5 | CUM | 41ORANGE KRISALA STORE | 11440.675 | 10110 | 2.5 | 4576.27 | 0 | 354 | 2025-04-18 | 0 |  | Unbilled | MH12TV5513 | 3091 | 2025-04-18 10:35 | 10:35 AM | 2025-04-18 11:30 | 11:30 AM | 2025-04-17 16:55 |  | Approved |  | 0 | Ashoks | 2.5 | 2025-04-21 20:51
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53420 | 2025-04-18 21:27 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10079 | 98 | 4576.27 | 0 | 134 | 2025-04-12 | 0 |  | Unbilled | MH12 SX9138 | 3068 | 2025-04-12 12:30 | 12:30 PM | 2025-04-12 13:40 | 1:40 PM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-18 21:27
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53419 | 2025-04-18 21:25 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 10079 | 98 | 4576.27 | 0 | 133 | 2025-04-12 | 0 |  | Unbilled | MH12PQ5483 | 3067 | 2025-04-12 00:15 | 12:15 AM | 2025-04-12 01:20 | 1:20 AM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 6 | 2025-04-18 21:25
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53418 | 2025-04-18 21:23 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10079 | 98 | 4576.27 | 0 | 130 | 2025-04-12 | 0 |  | Unbilled | MH12 SX9138 | 3065 | 2025-04-12 01:17 | 1:17 AM | 2025-04-12 02:15 | 2:15 AM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-18 21:23
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53417 | 2025-04-18 21:21 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10079 | 98 | 4576.27 | 0 | 129 | 2025-04-12 | 0 |  | Unbilled | MH14/LL 8687 | 3064 | 2025-04-12 23:55 | 11:55 PM | 2025-04-12 01:45 | 1:45 AM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-18 21:21
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53416 | 2025-04-18 21:20 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10079 | 98 | 4576.27 | 0 | 128 | 2025-04-11 | 0 |  | Unbilled | MH14JL1493 | 3063 | 2025-04-11 23:55 | 11:55 PM | 2025-04-12 01:27 | 1:27 AM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-18 21:20
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53415 | 2025-04-18 21:18 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10079 | 98 | 4576.27 | 0 | 127 | 2025-04-11 | 0 |  | Unbilled | MH12SX9138 | 127 | 2025-04-11 23:35 | 11:35 PM | 2025-04-12 00:33 | 12:33 AM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-18 21:18
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53414 | 2025-04-18 21:17 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10079 | 98 | 4576.27 | 0 | 126 | 2025-04-11 | 0 |  | Unbilled | MH14/LL 8687 | 3061 | 2025-04-11 23:15 | 11:15 PM | 2025-04-11 23:35 | 11:35 PM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-18 21:17
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53413 | 2025-04-18 21:15 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10079 | 98 | 4576.27 | 0 | 125 | 2025-04-11 | 0 |  | Unbilled | MH14JL1493 | 3060 | 2025-04-11 23:06 | 11:06 PM | 2025-04-11 23:35 | 11:35 PM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-18 21:15
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53412 | 2025-04-18 21:14 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10079 | 98 | 4576.27 | 0 | 124 | 2025-04-11 | 0 |  | Unbilled | MH12SX9138 | 3059 | 2025-04-11 21:40 | 9:40 PM | 2025-04-11 22:20 | 10:20 PM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-18 21:14
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53411 | 2025-04-18 21:13 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10079 | 98 | 4576.27 | 0 | 123 | 2025-04-11 | 0 |  | Unbilled | MH14/LL 8687 | 3058 | 2025-04-11 21:40 | 9:40 PM | 2025-04-11 22:20 | 10:20 PM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-18 21:13
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53410 | 2025-04-18 21:11 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10079 | 98 | 4576.27 | 0 | 122 | 2025-04-11 | 0 |  | Unbilled | MH14JL1493 | 3057 | 2025-04-11 21:22 | 9:22 PM | 2025-04-11 22:45 | 10:45 PM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-18 21:11
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53409 | 2025-04-18 21:10 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10079 | 98 | 4576.27 | 0 | 120 | 2025-04-11 | 0 |  | Unbilled | MH12 SX9138 | 3055 | 2025-04-11 20:00 | 8:00 PM | 2025-04-11 20:44 | 8:44 PM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-18 21:10
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53408 | 2025-04-18 21:09 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 10079 | 98 | 4576.27 | 0 | 119 | 2025-04-11 | 0 |  | Unbilled | MH14/LL 8687 | 3054 | 2025-04-11 20:00 | 8:00 PM | 2025-04-11 20:44 | 8:44 PM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-18 21:09
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53406 | 2025-04-18 21:05 | Purchase | GREY CORE INFRA LLP | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 10079 | 98 | 4576.27 | 0 | 131 | 2025-04-12 | 0 |  | Unbilled | MH14JL1493 | 3066 | 2025-04-12 13:50 | 1:50 PM | 2025-04-12 13:50 | 1:50 PM | 2025-04-11 18:01 |  | Approved |  | 0 | Ashoks | 8 | 2025-04-18 21:05
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53162 | 2025-04-14 11:07 | Purchase | RVK INFRATECH | 3 | CUM | 41ORANGE KRISALA STORE | 13728.81 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5926 | 2025-04-10 | 255 | 2025-04-16 | Billed | MH12TV5517 | 3035 | 2025-04-10 08:50 | 8:50 AM | 2025-04-10 23:00 | 11:00 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 3 | 2025-04-14 11:07
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53161 | 2025-04-14 11:05 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-15/5925 | 2025-04-10 | 255 | 2025-04-16 | Billed | MH 12 TV 5516 | 3034 | 2025-04-10 08:50 | 8:50 AM | 2025-04-10 23:00 | 11:00 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-14 11:05
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53158 | 2025-04-14 11:04 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5924 | 2025-04-10 | 254 | 2025-04-16 | Billed | MH12TV1655 | 3033 | 2025-04-10 20:20 | 8:20 PM | 2025-04-10 21:55 | 9:55 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-14 11:04
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53157 | 2025-04-14 11:01 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5923 | 2025-04-10 | 254 | 2025-04-16 | Billed | MH 12 TV 1755 | 3032 | 2025-04-10 20:07 | 8:07 PM | 2025-04-10 21:05 | 9:05 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-14 11:01
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53156 | 2025-04-14 11:00 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | UNIT III /24-25/5922 | 2025-04-10 | 253 | 2025-04-16 | Billed | MH12 XM0255 | 3031 | 2025-04-10 19:36 | 7:36 PM | 2025-04-10 20:20 | 8:20 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-14 11:00
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53155 | 2025-04-14 10:58 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | 204 | 2025-04-10 | 248 | 2025-04-16 | Billed | MH 12 TV 5516 | 3030 | 2025-04-10 18:41 | 6:41 PM | 2025-04-10 19:18 | 7:18 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-14 10:58
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53154 | 2025-04-14 10:57 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5921 | 2025-04-10 | 253 | 2025-04-16 | Billed | MH12TV5519 | 3029 | 2025-04-10 18:10 | 6:10 PM | 2025-04-10 18:43 | 6:43 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-14 10:57
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53153 | 2025-04-14 10:56 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5919 | 2025-04-10 | 252 | 2025-04-16 | Billed | MH12TV1655 | 3028 | 2025-04-10 17:14 | 5:14 PM | 2025-04-10 18:21 | 6:21 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-14 10:56
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53152 | 2025-04-14 10:55 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5918 | 2025-04-10 | 252 | 2025-04-16 | Billed | MH12 XM0255 | 3027 | 2025-04-10 16:02 | 4:02 PM | 2025-04-10 17:21 | 5:21 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-14 10:55
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53151 | 2025-04-14 10:53 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5917 | 2025-04-10 | 251 | 2025-04-16 | Billed | MH12TV5519 | 3026 | 2025-04-10 14:40 | 2:40 PM | 2025-04-10 16:10 | 4:10 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-14 10:53
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53150 | 2025-04-14 10:52 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III /24-25/5916 | 2025-04-10 | 251 | 2025-04-16 | Billed | MH12TV1655 | 3025 | 2025-04-10 14:40 | 2:40 PM | 2025-04-10 16:10 | 4:10 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-14 10:52
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53146 | 2025-04-14 10:50 | Purchase | RVK INFRATECH | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9999 | 304 | 4576.27 | 0 | 187 | 2025-04-10 | 247 | 2025-04-16 | Billed | MH12 XN0255 | 3029 | 2025-04-10 13:44 | 1:44 PM | 2025-04-10 14:59 | 2:59 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 6 | 2025-04-14 10:50
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53142 | 2025-04-14 10:48 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5915 | 2025-04-10 | 250 | 2025-04-16 | Billed | MH12TV5519 | 3023 | 2025-04-10 13:30 | 1:30 PM | 2025-04-10 14:02 | 2:02 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-14 10:48
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53141 | 2025-04-14 10:47 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5913 | 2025-04-10 | 249 | 2025-04-16 | Billed | MH12TV1655 | 3022 | 2025-04-10 12:43 | 12:43 PM | 2025-04-10 13:35 | 1:35 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-14 10:47
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53140 | 2025-04-14 10:45 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5914 | 2025-04-10 | 250 | 2025-04-16 | Billed | MH 12 TV 5516 | 3021 | 2025-04-10 11:22 | 11:22 AM | 2025-04-10 12:40 | 12:40 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-14 10:45
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53139 | 2025-04-14 10:43 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | 181 | 2025-04-10 | 247 | 2025-04-16 | Billed | MH12/SX 1933 | 3020 | 2025-04-10 11:22 | 11:22 AM | 2025-04-10 12:40 | 12:40 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-14 10:43
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53138 | 2025-04-14 10:42 | Purchase | RVK INFRATECH | 9 | CUM | 41ORANGE KRISALA STORE | 41186.43 | 9999 | 304 | 4576.27 | 0 | 180 | 2025-04-10 | 246 | 2025-04-16 | Billed | MH14 JL9106 | 3019 | 2025-04-10 11:21 | 11:21 AM | 2025-04-10 12:26 | 12:26 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 9 | 2025-04-14 10:42
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53134 | 2025-04-14 10:41 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III /24-25/5912 | 2025-04-10 | 249 | 2025-04-16 | Billed | MH12TV5519 | 3018 | 2025-04-10 11:14 | 11:14 AM | 2025-04-10 11:42 | 11:42 AM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-14 10:41
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53133 | 2025-04-14 10:39 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | 179 | 2025-04-10 | 246 | 2025-04-16 | Billed | MH 12 TV 5516 | 3017 | 2025-04-10 10:47 | 10:47 AM | 2025-04-10 10:47 | 10:47 AM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-14 10:39
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53132 | 2025-04-14 10:38 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | 176 | 2025-04-10 | 266 | 2025-04-16 | Billed | MH12TV1655 | 3016 | 2025-04-10 20:37 | 8:37 PM | 2025-04-10 21:49 | 9:49 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-14 10:38
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53131 | 2025-04-14 10:37 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | 174 | 2025-04-10 | 266 | 2025-04-16 | Billed | MH12TV5519 | 8015 | 2025-04-10 20:37 | 8:37 PM | 2025-04-10 21:49 | 9:49 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-14 10:37
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53128 | 2025-04-14 10:34 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | 159 | 2025-04-09 | 238 | 2025-04-16 | Billed | MH12TV 7655 | 2998 | 2025-04-09 13:48 | 1:48 PM | 2025-04-09 15:24 | 3:24 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-14 10:34
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53126 | 2025-04-14 10:32 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | 155 | 2025-04-09 | 237 | 2025-04-16 | Billed | MH12TV5517 | 2996 | 2025-04-09 12:19 | 12:19 PM | 2025-04-09 14:06 | 2:06 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-14 10:32
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53125 | 2025-04-14 10:31 | Purchase | RVK INFRATECH | 9 | CUM | 41ORANGE KRISALA STORE | 41186.43 | 9999 | 304 | 4576.27 | 0 | 154 | 2025-04-09 | 265 | 2025-04-16 | Billed | MH14 JL9106 | 2995 | 2025-04-09 12:17 | 12:17 PM | 2025-04-09 12:51 | 12:51 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 9 | 2025-04-14 10:31
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53124 | 2025-04-14 10:29 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | 153 | 2025-04-09 | 265 | 2025-04-16 | Billed | MH 12 TV 1755 | 2994 | 2025-04-09 11:38 | 11:38 AM | 2025-04-09 12:23 | 12:23 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-14 10:29
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53123 | 2025-04-13 21:18 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | 149 | 2025-04-09 | 310 | 2025-04-21 | Billed | MH 12 TV 1755 | 2993 | 2025-04-09 10:00 | 10:00 AM | 2025-04-09 11:42 | 11:42 AM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-13 21:18
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53118 | 2025-04-13 21:11 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | 157 | 2025-04-09 | 237 | 2025-04-16 | Billed | MH12TV5518 | 2997 | 2025-04-09 12:49 | 12:49 PM | 2025-04-09 14:48 | 2:48 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-13 21:11
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53117 | 2025-04-13 21:09 | Purchase | RVK INFRATECH | 8.5 | CUM | 41ORANGE KRISALA STORE | 38898.295 | 9999 | 304 | 4576.27 | 0 | 162 | 2025-04-09 | 239 | 2025-04-16 | Billed | MH14 JL9106 | 2999 | 2025-04-09 14:21 | 2:21 PM | 2025-04-09 16:00 | 4:00 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8.5 | 2025-04-13 21:09
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53116 | 2025-04-13 21:08 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 36610.16 | 9999 | 304 | 4576.27 | 0 | 147 | 2025-04-09 | 310 | 2025-04-21 | Billed | MH12TV1655 | 2992 | 2025-04-09 09:46 | 9:46 AM | 2025-04-09 10:10 | 10:10 AM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 8 | 2025-04-13 21:08
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53115 | 2025-04-13 21:07 | Purchase | RVK INFRATECH | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9999 | 304 | 4576.27 | 0 | 161 | 2025-04-09 | 238 | 2025-04-16 | Billed | MH12TV1855 | 3000 | 2025-04-09 14:23 | 2:23 PM | 2025-04-09 15:00 | 3:00 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 6 | 2025-04-13 21:07
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53114 | 2025-04-13 21:06 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | 164 | 2025-04-09 | 239 | 2025-04-16 | Billed | MH 12 TV 1355 | 3001 | 2025-04-09 15:49 | 3:49 PM | 2025-04-09 16:35 | 4:35 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-13 21:06
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53113 | 2025-04-13 21:03 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | 165 | 2025-04-09 | 240 | 2025-04-16 | Billed | MH12TV5518 | 3002 | 2025-04-09 16:09 | 4:09 PM | 2025-04-09 17:00 | 5:00 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-13 21:03
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53112 | 2025-04-13 21:00 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5906 | 2025-04-09 | 243 | 2025-04-16 | Billed | MH12TV5518 | 3003 | 2025-04-09 16:16 | 4:16 PM | 2025-04-09 17:22 | 5:22 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-13 21:00
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53111 | 2025-04-13 20:57 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | 5905 | 2025-04-09 | 243 | 2025-04-16 | Billed | MH12TV5517 | 3004 | 2025-04-09 16:33 | 4:33 PM | 2025-04-09 17:56 | 5:56 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-13 20:57
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53110 | 2025-04-13 20:56 | Purchase | RVK INFRATECH | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9999 | 304 | 4576.27 | 0 | 167 | 2025-04-09 | 240 | 2025-04-16 | Billed | MH12TV1855 | 3005 | 2025-04-09 16:40 | 4:40 PM | 2025-04-09 18:18 | 6:18 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 6 | 2025-04-13 20:56
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53109 | 2025-04-13 20:55 | Purchase | RVK INFRATECH | 7.5 | CUM | 41ORANGE KRISALA STORE | 34322.025 | 9999 | 304 | 4576.27 | 0 | 168 | 2025-04-09 | 241 | 2025-04-16 | Billed | MH12TV 7655 | 3009 | 2025-04-09 17:35 | 5:35 PM | 2025-04-09 18:50 | 6:50 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7.5 | 2025-04-13 20:55
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53108 | 2025-04-13 20:54 | Purchase | RVK INFRATECH | 9 | CUM | 41ORANGE KRISALA STORE | 41186.43 | 9999 | 304 | 4576.27 | 0 | 170 | 2025-04-09 | 241 | 2025-04-16 | Billed | MH14 JL9106 | 3010 | 2025-04-09 18:00 | 6:00 PM | 2025-04-09 19:26 | 7:26 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 9 | 2025-04-13 20:54
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53107 | 2025-04-13 20:53 | Purchase | RVK INFRATECH | 9 | CUM | 41ORANGE KRISALA STORE | 41186.43 | 9999 | 304 | 4576.27 | 0 | 171 | 2025-04-09 | 242 | 2025-04-16 | Billed | MH46AE9197 | 3011 | 2025-04-09 18:46 | 6:46 PM | 2025-04-09 20:00 | 8:00 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 9 | 2025-04-13 20:53
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53106 | 2025-04-13 20:51 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5909 | 2025-04-09 | 244 | 2025-04-16 | Billed | MH12TV5518 | 3012 | 2025-04-09 18:59 | 6:59 PM | 2025-04-09 20:45 | 8:45 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTIING | Approved |  | 0 | Ashoks | 7 | 2025-04-13 20:51
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 53105 | 2025-04-13 20:49 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9999 | 304 | 4576.27 | 0 | UNIT III/24-25/5910 | 2025-04-09 | 244 | 2025-04-16 | Billed | MH12TV5517 | 3013 | 2025-04-09 19:00 | 7:00 PM | 2025-04-09 19:30 | 7:30 PM | 2025-04-07 15:40 | E BLDG 18 SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-13 20:49
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52433 | 2025-04-04 18:20 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2757 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH12HD4750 | 2952 | 2025-03-29 00:02 | 12:02 AM | 2025-03-29 01:15 | 1:15 AM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 18:20
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52432 | 2025-04-04 18:18 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2756 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH14JL1493 | 2951 | 2025-03-29 23:35 | 11:35 PM | 2025-03-29 00:45 | 12:45 AM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 18:18
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52431 | 2025-04-04 18:17 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2754 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH14/LL 8687 | 2950 | 2025-03-29 23:01 | 11:01 PM | 2025-03-29 00:12 | 12:12 AM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 18:17
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52430 | 2025-04-04 18:16 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2753 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH12HD4750 | 2949 | 2025-03-29 22:48 | 10:48 PM | 2025-03-29 23:38 | 11:38 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 18:16
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52429 | 2025-04-04 18:14 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2752 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH14JL1493 | 2948 | 2025-03-29 22:30 | 10:30 PM | 2025-03-29 23:00 | 11:00 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 18:14
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52428 | 2025-04-04 18:12 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2750 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH12PQ5483 | 2947 | 2025-03-29 21:54 | 9:54 PM | 2025-03-29 22:30 | 10:30 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 18:12
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52427 | 2025-04-04 18:11 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2749 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH14/LL 8687 | 2946 | 2025-03-29 21:09 | 9:09 PM | 2025-03-29 22:00 | 10:00 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 18:11
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52426 | 2025-04-04 18:09 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2748 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH14JL1493 | 2945 | 2025-03-29 09:06 | 9:06 AM | 2025-03-29 18:07 | 6:07 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 18:09
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52425 | 2025-04-04 17:44 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2747 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH12HD4750 | 2944 | 2025-03-29 20:55 | 8:55 PM | 2025-03-29 21:10 | 9:10 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 17:44
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52424 | 2025-04-04 17:41 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2746 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH12PQ5483 | 2943 | 2025-03-29 20:40 | 8:40 PM | 2025-03-29 20:56 | 8:56 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 17:41
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52423 | 2025-04-04 17:38 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2743 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH14JL1493 | 2942 | 2025-03-29 20:06 | 8:06 PM | 2025-03-29 20:32 | 8:32 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 17:38
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52422 | 2025-04-04 17:34 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2742 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH12HD4750 | 2941 | 2025-03-29 19:37 | 7:37 PM | 2025-03-29 20:10 | 8:10 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 17:34
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52421 | 2025-04-04 17:29 | Purchase | GREY CORE INFRA LLP | 6.86 | CUM | 41ORANGE KRISALA STORE | 31393.2122 | 9917 | 270 | 4576.27 | 0 | GC2759 | 2025-03-30 | 1365 | 2025-03-30 | Billed | MH14/LL 8687 | 2954 | 2025-03-30 13:19 | 1:19 PM | 2025-03-30 13:30 | 1:30 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 6.86 | 2025-04-04 17:29
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52367 | 2025-03-31 10:23 | Purchase | GREY CORE INFRA LLP | 5 | CUM | 41ORANGE KRISALA STORE | 22881.35 | 9917 | 270 | 4576.27 | 0 | GC2761 | 2025-03-31 | 1366 | 2025-03-31 | Billed | MH12PQ5483 | 2956 | 2025-03-31 10:23 | 10:23 AM | 2025-03-31 11:00 | 11:00 AM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 5 | 2025-04-04 12:35
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52368 | 2025-03-30 12:27 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2758 | 2025-03-30 | 1365 | 2025-03-30 | Billed | MH12SX9138 | 2953 | 2025-03-30 12:27 | 12:27 PM | 2025-03-30 12:59 | 12:59 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 12:38
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52397 | 2025-03-29 18:24 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2737 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH 12 KP 8181 | 2939 | 2025-03-29 18:25 | 6:25 PM | 2025-03-29 19:12 | 7:12 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 14:26
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52395 | 2025-03-29 18:18 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2736 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH14JL1493 | 2938 | 2025-03-29 18:17 | 6:17 PM | 2025-03-29 19:00 | 7:00 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 14:21
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52391 | 2025-03-29 17:59 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2734 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH12HD4750 | 2934 | 2025-03-29 17:59 | 5:59 PM | 2025-03-29 18:28 | 6:28 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 13:17
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52393 | 2025-03-29 17:44 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2733 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH12 SX9138 | 2933 | 2025-03-29 17:44 | 5:44 PM | 2025-03-29 18:13 | 6:13 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 13:19
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52392 | 2025-03-29 17:07 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2730 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH 12 KP 8181 | 2932 | 2025-03-29 17:08 | 5:08 PM | 2025-03-29 17:32 | 5:32 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 13:18
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52389 | 2025-03-29 16:11 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2726 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH12 SX9138 | 2930 | 2025-03-29 16:11 | 4:11 PM | 2025-03-29 16:35 | 4:35 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 13:15
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52390 | 2025-03-29 16:00 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2725 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH14JL1493 | 2929 | 2025-03-29 16:00 | 4:00 PM | 2025-03-29 16:23 | 4:23 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 13:16
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52386 | 2025-03-29 15:38 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2722 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH 12 KP 8181 | 2928 | 2025-03-29 15:38 | 3:38 PM | 2025-03-29 16:03 | 4:03 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 13:11
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52387 | 2025-03-29 15:13 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2720 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH12 SX9138 | 2927 | 2025-03-29 15:13 | 3:13 PM | 2025-03-29 16:03 | 4:03 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 13:13
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52385 | 2025-03-29 15:00 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2719 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH12HD4750 | 2926 | 2025-03-29 15:00 | 3:00 PM | 2025-03-29 15:24 | 3:24 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 13:10
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52384 | 2025-03-29 14:30 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2717 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH 12 KP 8181 | 2925 | 2025-03-29 14:30 | 2:30 PM | 2025-03-29 14:44 | 2:44 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 13:07
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52394 | 2025-03-29 14:17 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2740 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH12SX9138 | 2940 | 2025-03-29 14:15 | 2:15 PM | 2025-03-29 14:15 | 2:15 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 14:19
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52381 | 2025-03-29 13:33 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2713 | 2025-03-29 | 1364 | 2025-03-29 | Billed | MH12HD4750 | 2923 | 2025-03-29 13:33 | 1:33 PM | 2025-03-29 13:52 | 1:52 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 12:58
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52382 | 2025-03-29 13:20 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2712 | 2025-03-29 | 1364 | 2025-03-29 | Billed | MH 12 KP 8181 | 2922 | 2025-03-29 13:20 | 1:20 PM | 2025-03-29 13:40 | 1:40 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 13:01
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52383 | 2025-03-29 13:02 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2715 | 2025-03-29 | 1364 | 2025-03-29 | Billed | MH12 SX9138 | 2924 | 2025-03-29 13:20 | 1:20 PM | 2025-03-29 13:40 | 1:40 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 13:04
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52378 | 2025-03-29 12:29 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2708 | 2025-03-29 | 1364 | 2025-03-29 | Billed | MH12 SX9138 | 2921 | 2025-03-29 12:29 | 12:29 PM | 2025-03-29 13:03 | 1:03 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 12:53
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52380 | 2025-03-29 11:59 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2704 | 2025-03-29 | 1364 | 2025-03-29 | Billed | MH12HD4750 | 2920 | 2025-03-29 11:59 | 11:59 AM | 2025-03-29 12:39 | 12:39 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 12:57
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52379 | 2025-03-29 11:55 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2705 | 2025-03-29 | 1364 | 2025-03-29 | Billed | MH 12 KP 8181 | 2919 | 2025-03-29 11:55 | 11:55 AM | 2025-03-29 12:25 | 12:25 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 12:55
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52372 | 2025-03-29 11:26 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2702 | 2025-03-29 | 1364 | 2025-03-29 | Billed | MH12HD4752 | 2917 | 2025-03-29 11:26 | 11:26 AM | 2025-03-29 11:40 | 11:40 AM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 12:45
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52369 | 2025-03-29 11:12 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2703 | 2025-03-29 | 1364 | 2025-03-29 | Billed | MH12SX9138 | 2918 | 2025-03-29 11:29 | 11:29 AM | 2025-03-29 12:02 | 12:02 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PART 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 12:41
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52373 | 2025-03-29 10:30 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2699 | 2025-03-29 | 1364 | 2025-03-29 | Billed | MH14/LL 8687 | 1916 | 2025-03-29 10:30 | 10:30 AM | 2025-03-29 10:56 | 10:56 AM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 12:47
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52374 | 2025-03-29 09:55 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2698 | 2025-03-29 | 1364 | 2025-03-29 | Billed | MH 12 KP 8181 | 2914 | 2025-03-29 09:55 | 9:55 AM | 2025-03-29 10:28 | 10:28 AM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 12:49
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52375 | 2025-03-29 09:35 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2697 | 2025-03-29 | 1364 | 2025-03-29 | Billed | MH12HD4752 | 2913 | 2025-03-29 09:35 | 9:35 AM | 2025-03-29 10:12 | 10:12 AM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 12:50
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52376 | 2025-03-29 09:19 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2696 | 2025-03-29 | 1364 | 2025-03-29 | Billed | MH12HD4750 | 2912 | 2025-03-29 09:19 | 9:19 AM | 2025-03-29 09:50 | 9:50 AM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 12:51
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52377 | 2025-03-29 08:15 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9917 | 270 | 4576.27 | 0 | GC2695 | 2025-03-29 | 1364 | 2025-03-29 | Billed | MH12 SX9138 | 2911 | 2025-03-29 08:15 | 8:15 AM | 2025-03-29 09:00 | 9:00 AM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 7 | 2025-04-04 12:52
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 52388 | 2025-03-29 04:39 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9917 | 270 | 4576.27 | 0 | GC2728 | 2025-03-29 | 1362 | 2025-03-29 | Billed | MH12HD4750 | 2931 | 2025-03-29 04:39 | 4:39 AM | 2025-03-29 16:54 | 4:54 PM | 2025-03-28 18:56 | E BLDG 18 SLAB PAET 1 CASTING | Approved |  | 0 | Ashoks | 6 | 2025-04-04 13:14
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51726 | 2025-03-27 14:44 | Purchase | GREY CORE INFRA LLP | 1 | CUM | 41ORANGE KRISALA STORE | 4576.27 | 9767 | 304 | 4576.27 | 0 | GC2656 | 2025-03-27 | 1351 | 2025-03-27 | Billed | MH12HD4750 | 2890 | 2025-03-27 14:44 | 2:44 PM | 2025-03-27 16:02 | 4:02 PM | 2025-03-18 17:50 |  | Approved |  | 0 | Ashoks | 1 | 2025-03-27 17:13
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51237 | 2025-03-24 20:23 | Purchase | GREY CORE INFRA LLP | 2.5 | CUM | 41ORANGE KRISALA STORE | 11440.675 | 9767 | 304 | 4576.27 | 0 | GC2561 | 2025-03-21 | 1312 | 2025-03-21 | Billed | MH12 SX9138 |  | 2025-03-21 20:22 | 8:22 PM | 2025-03-21 20:22 | 8:22 PM | 2025-03-18 17:50 |  | Approved |  | 0 | Ashoks | 2.5 | 2025-03-24 20:24
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51020 | 2025-03-20 16:06 | Purchase | GREY CORE INFRA LLP | 2 | CUM | 41ORANGE KRISALA STORE | 9152.54 | 9767 | 304 | 4576.27 | 0 | GC2551 | 2025-03-20 | 1303 | 2025-03-20 | Billed | MH12 SX9138 | 2844 | 2025-03-20 16:05 | 4:05 PM | 2025-03-20 16:50 | 4:50 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 2 | 2025-03-23 14:40
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51019 | 2025-03-20 15:22 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2550 | 2025-03-20 | 1303 | 2025-03-20 | Billed | MH14JL1493 | 2843 | 2025-03-20 15:33 | 3:33 PM | 2025-03-20 15:47 | 3:47 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:39
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51042 | 2025-03-20 15:16 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2528 | 2025-03-20 | 1294 | 2025-03-19 | Billed | MH14/LL 8687 | 2824 | 2025-03-20 11:58 | 11:58 AM | 2025-03-20 15:00 | 3:00 PM | 2025-03-18 17:50 | E BLDG 17 SALB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 15:18
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51021 | 2025-03-20 14:38 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2547 | 2025-03-20 | 1300 | 2025-03-20 | Billed | MH14/LL 8687 | 2842 | 2025-03-20 14:38 | 2:38 PM | 2025-03-20 15:23 | 3:23 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:41
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51022 | 2025-03-20 14:22 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2546 | 2025-03-20 | 1300 | 2025-03-20 | Billed | MH14JL1493 | 2841 | 2025-03-20 14:22 | 2:22 PM | 2025-03-20 14:54 | 2:54 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:42
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51023 | 2025-03-20 13:52 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2544 | 2025-03-20 | 1298 | 2025-03-20 | Billed | MH12 SX9138 | 2840 | 2025-03-20 13:53 | 1:53 PM | 2025-03-20 14:24 | 2:24 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:44
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51024 | 2025-03-20 13:07 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2542 | 2025-03-20 | 1296 | 2025-03-20 | Billed | MH14LL8687 | 2839 | 2025-03-20 13:07 | 1:07 PM | 2025-03-20 14:04 | 2:04 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:45
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51026 | 2025-03-20 12:48 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9767 | 304 | 4576.27 | 0 | GC2541 | 2025-03-20 | 1296 | 2025-03-20 | Billed | MH46AR4311 | 2837 | 2025-03-20 12:48 | 12:48 PM | 2025-03-20 13:12 | 1:12 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 6 | 2025-03-23 14:47
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51025 | 2025-03-20 12:46 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2540 | 2025-03-20 | 1296 | 2025-03-20 | Billed | MH14JL1493 | 2838 | 2025-03-20 12:46 | 12:46 PM | 2025-03-20 13:16 | 1:16 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:46
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51027 | 2025-03-20 12:13 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2539 | 2025-03-20 | 1296 | 2025-03-20 | Billed | MH12 SX9138 | 2835 | 2025-03-20 12:13 | 12:13 PM | 2025-03-20 12:40 | 12:40 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:48
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51028 | 2025-03-20 11:18 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2537 | 2025-03-20 | 1294 | 2025-03-19 | Billed | MH14/LL 8687 | 2834 | 2025-03-20 11:18 | 11:18 AM | 2025-03-20 12:32 | 12:32 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:50
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51029 | 2025-03-20 10:47 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2536 | 2025-03-20 | 1294 | 2025-03-19 | Billed | MH14JL1493 | 2833 | 2025-03-20 10:47 | 10:47 AM | 2025-03-20 12:06 | 12:06 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:51
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51030 | 2025-03-20 09:30 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2535 | 2025-03-20 | 1294 | 2025-03-19 | Billed | MH12 SX9138 | 2831 | 2025-03-20 09:30 | 9:30 AM | 2025-03-20 10:10 | 10:10 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:52
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51031 | 2025-03-20 09:07 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9767 | 304 | 4576.27 | 0 | GC2534 | 2025-03-20 | 1294 | 2025-03-19 | Billed | MH12HD4750 | 2830 | 2025-03-20 09:07 | 9:07 AM | 2025-03-20 09:30 | 9:30 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 6 | 2025-03-23 14:53
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51032 | 2025-03-20 08:51 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9767 | 304 | 4576.27 | 0 | GC2533 | 2025-03-20 | 1294 | 2025-03-19 | Billed | MH12PQ5483 | 2829 | 2025-03-20 08:51 | 8:51 AM | 2025-03-20 09:30 | 9:30 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 6 | 2025-03-23 14:54
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51033 | 2025-03-20 08:37 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2532 | 2025-03-20 | 1294 | 2025-03-19 | Billed | MH14/LL 8687 | 2828 | 2025-03-20 08:37 | 8:37 AM | 2025-03-20 09:20 | 9:20 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:55
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51034 | 2025-03-20 08:23 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2531 | 2025-03-20 | 1294 | 2025-03-19 | Billed | MH14JL1493 | 2827 | 2025-03-20 08:23 | 8:23 AM | 2025-03-20 09:12 | 9:12 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:56
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51035 | 2025-03-20 08:07 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2530 | 2025-03-20 | 1294 | 2025-03-19 | Billed | MH12 SX9138 | 2826 | 2025-03-20 08:07 | 8:07 AM | 2025-03-20 08:45 | 8:45 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:57
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51037 | 2025-03-20 07:54 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9674 | 270 | 4576.27 | 0 | GC2529 | 2025-03-20 | 1294 | 2025-03-19 | Billed | MH12HD4750 | 2825 | 2025-03-20 07:54 | 7:54 AM | 2025-03-20 08:15 | 8:15 AM | 2025-03-10 11:54 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 6 | 2025-03-23 15:02
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51018 | 2025-03-19 17:00 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2522 | 2025-03-19 | 1288 | 2025-03-19 | Billed | MH14JL1493 | 2823 | 2025-03-19 17:00 | 5:00 PM | 2025-03-19 17:28 | 5:28 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:38
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51016 | 2025-03-19 16:34 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2520 | 2025-03-19 | 1288 | 2025-03-19 | Billed | MH12 SX9138 | 2817 | 2025-03-19 16:34 | 4:34 PM | 2025-03-19 17:00 | 5:00 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:35
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51013 | 2025-03-19 16:00 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2518 | 2025-03-19 | 1286 | 2025-03-19 | Billed | MH14JL1493 | 2811 | 2025-03-19 16:00 | 4:00 PM | 2025-03-19 16:35 | 4:35 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:32
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51014 | 2025-03-19 15:54 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2517 | 2025-03-19 | 1286 | 2025-03-19 | Billed | MH14/LL 8687 | 2810 | 2025-03-19 15:54 | 3:54 PM | 2025-03-19 16:08 | 4:08 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:33
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51015 | 2025-03-19 15:29 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2516 | 2025-03-19 | 1286 | 2025-03-19 | Billed | MH12SX9138 | 2809 | 2025-03-19 15:29 | 3:29 PM | 2025-03-19 16:08 | 4:08 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:34
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51011 | 2025-03-19 15:16 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2515 | 2025-03-19 | 1286 | 2025-03-19 | Billed | MH14JL1493 | 2808 | 2025-03-19 15:16 | 3:16 PM | 2025-03-19 15:39 | 3:39 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:30
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51017 | 2025-03-19 14:45 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2521 | 2025-03-19 | 1288 | 2025-03-19 | Billed | MH14/LL 8687 | 2819 | 2025-03-19 16:45 | 4:45 PM | 2025-03-19 17:04 | 5:04 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:37
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51010 | 2025-03-19 14:45 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2513 | 2025-03-19 | 1284 | 2025-03-19 | Billed | MH14/LL 8687 | 2807 | 2025-03-19 14:45 | 2:45 PM | 2025-03-19 15:22 | 3:22 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:28
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51009 | 2025-03-19 14:40 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2512 | 2025-03-19 | 1284 | 2025-03-19 | Billed | MH12 SX9138 | 2806 | 2025-03-19 14:40 | 2:40 PM | 2025-03-19 15:05 | 3:05 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:27
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50992 | 2025-03-19 14:06 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9767 | 304 | 4576.27 | 0 | GC2508 | 2025-03-19 | 1282 | 2025-03-19 | Billed | MH46AR4311 | 2804 | 2025-03-19 14:06 | 2:06 PM | 2025-03-19 14:06 | 2:06 PM | 2025-03-18 17:50 | E BLDG 17 SLAB CASTING | Approved |  | 0 | Ashoks | 6 | 2025-03-23 14:08
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51007 | 2025-03-19 14:05 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2510 | 2025-03-19 | 1282 | 2025-03-19 | Billed | MH14JL1493 | 2805 | 2025-03-19 14:05 | 2:05 PM | 2025-03-19 15:39 | 3:39 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:25
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50993 | 2025-03-19 13:29 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9767 | 304 | 4576.27 | 0 | GC2509 | 2025-03-19 | 1282 | 2025-03-19 | Billed | MH12HD4750 | 2803 | 2025-03-19 13:29 | 1:29 PM | 2025-03-19 13:58 | 1:58 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 6 | 2025-03-23 14:10
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50994 | 2025-03-19 13:07 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2507 | 2025-03-19 | 1282 | 2025-03-19 | Billed | MH14/LL 8687 | 2802 | 2025-03-19 13:07 | 1:07 PM | 2025-03-19 14:07 | 2:07 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:11
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50995 | 2025-03-19 12:46 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2506 | 2025-03-19 | 1282 | 2025-03-19 | Billed | MH12 SX9138 | 2801 | 2025-03-19 12:46 | 12:46 PM | 2025-03-19 13:35 | 1:35 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:12
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50996 | 2025-03-19 12:26 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2505 | 2025-03-19 | 1282 | 2025-03-19 | Billed | MH14JL1493 | 2800 | 2025-03-19 12:26 | 12:26 PM | 2025-03-19 13:09 | 1:09 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:13
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50997 | 2025-03-19 12:15 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9767 | 304 | 4576.27 | 0 | GC2504 | 2025-03-19 | 1282 | 2025-03-19 | Billed | MH46AR4311 | 2900 | 2025-03-19 12:15 | 12:15 PM | 2025-03-19 12:45 | 12:45 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 6 | 2025-03-23 14:14
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51001 | 2025-03-19 12:01 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2503 | 2025-03-19 | 1282 | 2025-03-19 | Billed | MH14/LL 8687 | 2798 | 2025-03-19 12:01 | 12:01 PM | 2025-03-19 12:22 | 12:22 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:18
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50998 | 2025-03-19 11:57 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2502 | 2025-03-19 | 1282 | 2025-03-19 | Billed | MH12SX9138 | 2797 | 2025-03-19 11:57 | 11:57 AM | 2025-03-19 12:12 | 12:12 PM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:15
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51002 | 2025-03-19 11:25 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2501 | 2025-03-19 | 1282 | 2025-03-19 | Billed | MH14JL1493 | 2796 | 2025-03-19 11:25 | 11:25 AM | 2025-03-19 11:59 | 11:59 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:19
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51004 | 2025-03-19 10:51 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9767 | 304 | 4576.27 | 0 | GC2500 | 2025-03-19 | 1282 | 2025-03-19 | Billed | MH46AR4311 | 2795 | 2025-03-19 10:51 | 10:51 AM | 2025-03-19 11:47 | 11:47 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 6 | 2025-03-23 14:22
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51005 | 2025-03-19 10:28 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2498 | 2025-03-19 | 1280 | 2025-03-19 | Billed | MH14/LL 8687 | 2794 | 2025-03-19 10:28 | 10:28 AM | 2025-03-19 11:45 | 11:45 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:23
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51006 | 2025-03-19 09:12 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2497 | 2025-03-19 | 1280 | 2025-03-19 | Billed | MH12 SX9138 | 2793 | 2025-03-19 09:12 | 9:12 AM | 2025-03-19 11:40 | 11:40 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:24
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51008 | 2025-03-19 08:58 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2496 | 2025-03-19 | 1280 | 2025-03-19 | Billed | MH14JL1493 | 2792 | 2025-03-19 08:57 | 8:57 AM | 2025-03-19 10:00 | 10:00 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:26
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50999 | 2025-03-19 08:42 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9767 | 304 | 4576.27 | 0 | GC2495 | 2025-03-19 | 1280 | 2025-03-19 | Billed | MH46AR4311 | 2791 | 2025-03-19 08:42 | 8:42 AM | 2025-03-19 09:31 | 9:31 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 6 | 2025-03-23 14:16
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51000 | 2025-03-19 08:24 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9767 | 304 | 4576.27 | 0 | GC2494 | 2025-03-19 | 1280 | 2025-03-19 | Billed | MH14/LL 8687 | 2790 | 2025-03-19 08:24 | 8:24 AM | 2025-03-19 08:56 | 8:56 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 14:17
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51003 | 2025-03-19 07:13 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9767 | 304 | 4576.27 | 0 | GC2493 | 2025-03-19 | 1280 | 2025-03-19 | Billed | MH12HD4750 | 2789 | 2025-03-19 07:13 | 7:13 AM | 2025-03-19 08:25 | 8:25 AM | 2025-03-18 17:50 | E BLDG 17TH SLAB CASTING | Approved |  | 0 | Ashoks | 6 | 2025-03-23 14:20
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50988 | 2025-03-18 18:44 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9742 | 93 | 4576.27 | 0 | GC2490 | 2025-03-18 | 1277 | 2025-03-18 | Billed | MH14/LL 8687 | 2787 | 2025-03-18 18:44 | 6:44 PM | 2025-03-18 19:30 | 7:30 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:50
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50989 | 2025-03-18 18:18 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9742 | 93 | 4576.27 | 0 | GC2489 | 2025-03-18 | 1277 | 2025-03-18 | Billed | MH14 PQ5483 | 2786 | 2025-03-18 18:18 | 6:18 PM | 2025-03-18 19:00 | 7:00 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 6 | 2025-03-23 13:52
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50990 | 2025-03-18 18:02 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9742 | 93 | 4576.27 | 0 | GC2488 | 2025-03-18 | 1277 | 2025-03-18 | Billed | MH14JL1493 | 2785 | 2025-03-18 18:02 | 6:02 PM | 2025-03-18 18:38 | 6:38 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:53
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50991 | 2025-03-18 17:34 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9742 | 93 | 4576.27 | 0 | GC2486 | 2025-03-18 | 1275 | 2025-03-18 | Billed | MH12HD4750 | 2784 | 2025-03-18 17:34 | 5:34 PM | 2025-03-18 18:28 | 6:28 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 6 | 2025-03-23 13:54
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50987 | 2025-03-18 17:18 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9742 | 93 | 4576.27 | 0 | GC2485 | 2025-03-18 | 1275 | 2025-03-18 | Billed | MH14LL8687 | 2783 | 2025-03-18 17:01 | 5:01 PM | 2025-03-18 18:15 | 6:15 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:49
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50980 | 2025-03-18 17:14 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9742 | 93 | 4576.27 | 0 | GC2484 | 2025-03-18 | 1275 | 2025-03-18 | Billed | MH12PQ5483 | 2782 | 2025-03-18 17:14 | 5:14 PM | 2025-03-18 17:56 | 5:56 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 6 | 2025-03-23 13:41
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50986 | 2025-03-18 17:03 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9742 | 93 | 4576.27 | 0 | GC2483 | 2025-03-18 | 1275 | 2025-03-18 | Billed | MH14JL1493 | 2781 | 2025-03-18 17:03 | 5:03 PM | 2025-03-18 17:21 | 5:21 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:48
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50984 | 2025-03-18 16:23 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9742 | 93 | 4576.27 | 0 | GC2482 | 2025-03-18 | 1275 | 2025-03-18 | Billed | MH12HD4750 | 2780 | 2025-03-18 16:23 | 4:23 PM | 2025-03-18 16:53 | 4:53 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 6 | 2025-03-23 13:46
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50982 | 2025-03-18 16:05 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9742 | 93 | 4576.27 | 0 | GC2481 | 2025-03-18 | 1275 | 2025-03-18 | Billed | MH14/LL 8687 | 2779 | 2025-03-18 16:06 | 4:06 PM | 2025-03-18 16:37 | 4:37 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:44
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50978 | 2025-03-18 15:43 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9742 | 93 | 4576.27 | 0 | GC2480 | 2025-03-18 | 1275 | 2025-03-18 | Billed | MH12PQ5483 | 2777 | 2025-03-18 15:43 | 3:43 PM | 2025-03-18 16:12 | 4:12 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 6 | 2025-03-23 13:39
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50985 | 2025-03-18 15:31 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9742 | 93 | 4576.27 | 0 | GC2479 | 2025-03-18 | 1275 | 2025-03-18 | Billed | MH14JL1493 | 2776 | 2025-03-18 15:31 | 3:31 PM | 2025-03-18 16:20 | 4:20 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:47
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50981 | 2025-03-18 15:05 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9742 | 93 | 4576.27 | 0 | GC2478 | 2025-03-18 | 1275 | 2025-03-18 | Billed | MH14LL8687 | 2775 | 2025-03-18 15:05 | 3:05 PM | 2025-03-18 15:23 | 3:23 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:43
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 51038 | 2025-03-18 15:02 | Purchase | GREY CORE INFRA LLP | 4.5 | CUM | 41ORANGE KRISALA STORE | 20593.215 | 9564 | 115 | 4576.27 | 0 | GC2492 | 2025-03-18 | 1279 | 2025-03-18 | Billed | MH12HD4750 | 2788 | 2025-03-18 07:54 | 7:54 AM | 2025-03-18 08:15 | 8:15 AM | 2025-03-03 13:48 | FBLDG 7TH SLAB CASTING | Approved |  | 0 | Ashoks | 4.5 | 2025-03-23 15:05
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50979 | 2025-03-18 14:08 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 27457.62 | 9742 | 93 | 4576.27 | 0 | GC2476 | 2025-03-18 | 1273 | 2025-03-18 | Billed | NH12 PQ 5483 | 2774 | 2025-03-18 14:09 | 2:09 PM | 2025-03-18 15:00 | 3:00 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 6 | 2025-03-23 13:40
41 COSMO NXT | 00 RMC | RMC M30FF (Out Source) |  | 50983 | 2025-03-18 13:56 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 32033.89 | 9742 | 93 | 4576.27 | 0 | GC2475 | 2025-03-18 | 1273 | 2025-03-18 | Billed | MH14JL1493 | 2773 | 2025-03-18 13:56 | 1:56 PM | 2025-03-18 14:40 | 2:40 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:45