## GRNRegisteritemwise638820587845
Material Wise GRN Report
From 01-04-2025 To 30-04-2025
Page 1 of 1
Total Records: 18 Records 1 to 18
Project_Name | Material_Category1 | Material_Name | Brand | GRN_No | GRN_Date | GRNType | Supplier_Issue_Store | Good_Qty | Unit_Name | Received_Store | Amount | PO_SrNo | PO_Qty | Rate | Transport_Others | Challan_No | Challan_Date | Bill_No | Bill_date | Billing_Status | VehicleNo | GateReg_No | GateReg date | GateReg Time | GateReg Out Date | GateReg Out Time | Po_Date | GRN_Remark | GRN_Status | Material_Category2 | GTN_SrNo | Created_BY | Challan_Qty | Entry_Date
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 54683 | 2025-04-29 11:19 | Purchase | GREY CORE INFRA LLP | 2 | CUM | 41 RIZZ STORE | 9322.0338 | 10137 | 15 | 4661.0169 | 0 | GC2775. | 2025-03-31 | 0 |  | Unbilled | MH14JL1493 |  | 2025-03-31 11:09 | 11:09 AM | 2025-03-31 11:09 | 11:09 AM | 2025-04-19 10:53 |  | Approved |  | 0 | Sampat.Thopate | 6 | 2025-04-29 11:19
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 54682 | 2025-04-29 11:13 | Purchase | GREY CORE INFRA LLP | 4 | CUM | 41 RIZZ STORE | 18644.0676 | 10125 | 10 | 4661.0169 | 0 | GC2775 | 2025-03-31 | 0 |  | Unbilled | MH14JL1493 |  | 2025-03-31 11:09 | 11:09 AM | 2025-03-31 11:09 | 11:09 AM | 2025-04-18 17:07 |  | Approved |  | 0 | Sampat.Thopate | 6 | 2025-04-29 11:13
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 54657 | 2025-04-28 17:21 | Purchase | GREY CORE INFRA LLP | 5 | CUM | 41 RIZZ STORE | 23305.0845 | 10137 | 15 | 4661.0169 | 0 | 113 | 2025-04-11 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-11 17:07 | 5:07 PM | 2025-04-11 17:07 | 5:07 PM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 5 | 2025-04-28 17:21
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 54419 | 2025-04-25 07:51 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 27966.1014 | 10137 | 15 | 4661.0169 | 0 | 277 | 2025-04-23 | 0 |  | Unbilled | MH12SX9138 |  | 2025-04-23 07:40 | 7:40 AM | 2025-04-23 07:40 | 7:40 AM | 2025-04-19 10:53 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-25 07:51
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 54418 | 2025-04-25 07:49 | Purchase | GREY CORE INFRA LLP | 3 | CUM | 41 RIZZ STORE | 13983.0507 | 10164 | 15 | 4661.0169 | 0 | 281 | 2025-04-23 | 0 |  | Unbilled | MH14LL8687 |  | 2025-04-23 07:40 | 7:40 AM | 2025-04-23 07:40 | 7:40 AM | 2025-04-23 14:52 |  | Approved |  | 0 | RIZZ.STORE | 3 | 2025-04-25 07:49
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 54417 | 2025-04-25 07:48 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 27966.1014 | 10164 | 15 | 4661.0169 | 0 | 278 | 2025-04-23 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-23 07:40 | 7:40 AM | 2025-04-23 07:40 | 7:40 AM | 2025-04-23 14:52 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-25 07:48
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 54416 | 2025-04-25 07:47 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 27966.1014 | 10164 | 15 | 4661.0169 | 0 | 246 | 2025-04-21 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-21 07:40 | 7:40 AM | 2025-04-21 07:40 | 7:40 AM | 2025-04-23 14:52 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-25 07:47
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 54415 | 2025-04-25 07:44 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 27966.1014 | 10125 | 10 | 4661.0169 | 0 | 244 | 2025-04-21 | 0 |  | Unbilled | mh14gd4834 |  | 2025-04-21 07:40 | 7:40 AM | 2025-04-21 07:40 | 7:40 AM | 2025-04-18 17:07 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-25 07:44
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 53621 | 2025-04-20 23:01 | Purchase | GREY CORE INFRA LLP | 3 | CUM | 41 RIZZ STORE | 13983.0507 | 9964 | 50 | 4661.0169 | 0 | 229 | 2025-04-19 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-19 22:53 | 10:53 PM | 2025-04-19 22:53 | 10:53 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 4 | 2025-04-20 23:01
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 53620 | 2025-04-20 23:00 | Purchase | GREY CORE INFRA LLP | 4 | CUM | 41 RIZZ STORE | 18644.0676 | 9964 | 50 | 4661.0169 | 0 | 227 | 2025-04-19 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-19 22:53 | 10:53 PM | 2025-04-19 22:53 | 10:53 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 4 | 2025-04-20 23:00
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 53619 | 2025-04-20 22:59 | Purchase | GREY CORE INFRA LLP | 5 | CUM | 41 RIZZ STORE | 23305.0845 | 9964 | 50 | 4661.0169 | 0 | 213 | 2025-04-18 | 0 |  | Unbilled | MH14/LL 8687 |  | 2025-04-18 22:53 | 10:53 PM | 2025-04-18 22:53 | 10:53 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 5 | 2025-04-20 22:59
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 53618 | 2025-04-20 22:58 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 27966.1014 | 9964 | 50 | 4661.0169 | 0 | 193 | 2025-04-16 | 0 |  | Unbilled | MH12PQ5483 |  | 2025-04-16 22:53 | 10:53 PM | 2025-04-16 22:53 | 10:53 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-20 22:58
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 53332 | 2025-04-16 18:06 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41 RIZZ STORE | 32627.1183 | 9964 | 50 | 4661.0169 | 0 | 69 | 2025-04-09 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-09 18:04 | 6:04 PM | 2025-04-09 18:04 | 6:04 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 7 | 2025-04-16 18:06
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 53262 | 2025-04-15 08:09 | Purchase | GREY CORE INFRA LLP | 5 | CUM | 41 RIZZ STORE | 23305.0845 | 9964 | 50 | 4661.0169 | 0 | 135 | 2025-04-12 | 0 |  | Unbilled | MH12 SX9138 |  | 2025-04-12 08:01 | 8:01 AM | 2025-04-12 08:01 | 8:01 AM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 5 | 2025-04-15 08:09
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 53261 | 2025-04-15 08:04 | Purchase | GREY CORE INFRA LLP | 5 | CUM | 41 RIZZ STORE | 23305.0845 | 9964 | 50 | 4661.0169 | 0 | 135 | 2025-04-14 | 0 |  | Unbilled | MH12 SX9138 |  | 2025-04-14 08:01 | 8:01 AM | 2025-04-14 08:01 | 8:01 AM | 2025-04-04 14:31 |  | Deleted |  | 0 | RIZZ.STORE | 5 | 2025-04-15 08:04
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 52926 | 2025-04-10 16:46 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41 RIZZ STORE | 27966.1014 | 9964 | 50 | 4661.0169 | 0 | 48 | 2025-04-07 | 0 |  | Unbilled | MH12HD4750 |  | 2025-04-07 16:40 | 4:40 PM | 2025-04-07 16:40 | 4:40 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 6 | 2025-04-10 16:46
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 52925 | 2025-04-10 16:45 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41 RIZZ STORE | 32627.1183 | 9964 | 50 | 4661.0169 | 0 | 49 | 2025-04-07 | 0 |  | Unbilled | MH14JL1493 |  | 2025-04-07 16:40 | 4:40 PM | 2025-04-07 16:40 | 4:40 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 7 | 2025-04-10 16:45
41 ZILLENIA PHASE 2 | 00 RMC | RMC M30 (Out Source) |  | 52924 | 2025-04-10 16:44 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41 RIZZ STORE | 32627.1183 | 9964 | 50 | 4661.0169 | 0 | 51 | 2025-04-07 | 0 |  | Unbilled | MH12 SX9138 |  | 2025-04-07 16:40 | 4:40 PM | 2025-04-07 16:40 | 4:40 PM | 2025-04-04 14:31 |  | Approved |  | 0 | RIZZ.STORE | 7 | 2025-04-10 16:44