## GRNRegisteritemwise638820592177
Material Wise GRN Report
From 12-03-2025 To 05-05-2025
Page 1 of 1
Total Records: 45 Records 1 to 45
Project_Name | Material_Category1 | Material_Name | Brand | GRN_No | GRN_Date | GRNType | Supplier_Issue_Store | Good_Qty | Unit_Name | Received_Store | Amount | PO_SrNo | PO_Qty | Rate | Transport_Others | Challan_No | Challan_Date | Bill_No | Bill_date | Billing_Status | VehicleNo | GateReg_No | GateReg date | GateReg Time | GateReg Out Date | GateReg Out Time | Po_Date | GRN_Remark | GRN_Status | Material_Category2 | GTN_SrNo | Created_BY | Challan_Qty | Entry_Date
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 54757 | 2025-04-30 12:47 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 33961.83 | 10180 | 70 | 4851.69 | 0 | 3PU25BP1-652 | 2025-04-28 | 0 |  | Unbilled | AP39 UD2010 | 3146 | 2025-04-29 13:48 | 1:48 PM | 2025-04-29 14:24 | 2:24 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 12:47
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 54748 | 2025-04-30 12:32 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 33961.83 | 10180 | 70 | 4851.69 | 0 | 3PU25BP1-651 | 2025-04-28 | 0 |  | Unbilled | MH12UM 2890 | 3144 | 2025-04-28 13:10 | 1:10 PM | 2025-04-28 14:08 | 2:08 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 12:32
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 54747 | 2025-04-30 12:30 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 33961.83 | 10180 | 70 | 4851.69 | 0 | 3PU25BP1-650 | 2025-04-28 | 0 |  | Unbilled | AP39 UD2011 | 3143 | 2025-04-28 12:50 | 12:50 PM | 2025-04-28 13:13 | 1:13 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 12:30
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 54746 | 2025-04-30 12:27 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 33961.83 | 10180 | 70 | 4851.69 | 0 | 3PU25BP1-649 | 2025-04-28 | 0 |  | Unbilled | MH12/UM 7849 | 3142 | 2025-04-28 12:50 | 12:50 PM | 2025-04-28 13:24 | 1:24 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 12:27
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 54745 | 2025-04-30 12:23 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 33961.83 | 10180 | 70 | 4851.69 | 0 | 3PU25BP1-648 | 2025-04-28 | 0 |  | Unbilled | AP39 UD2009 | 3141 | 2025-04-28 12:18 | 12:18 PM | 2025-04-28 13:16 | 1:16 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 12:23
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 54744 | 2025-04-30 12:21 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 33961.83 | 10180 | 70 | 4851.69 | 0 | 3PU25BP1-647 | 2025-04-28 | 0 |  | Unbilled | MH14KA 0258 | 3140 | 2025-04-28 12:00 | 12:00 PM | 2025-04-28 12:48 | 12:48 PM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 12:21
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 54743 | 2025-04-30 12:18 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 33961.83 | 10180 | 70 | 4851.69 | 0 | 3PU25BP1-646 | 2025-04-28 | 0 |  | Unbilled | AP39 UD2010 | 3139 | 2025-04-28 11:42 | 11:42 AM | 2025-04-28 12:31 | 12:31 PM | 2025-04-24 15:01 | G BLDG | Approved |  | 0 | Ashoks | 7 | 2025-04-30 12:18
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 54742 | 2025-04-30 12:16 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 33961.83 | 10180 | 70 | 4851.69 | 0 | 3PU25BP1-644 | 2025-04-28 | 0 |  | Unbilled | MH12UM 2890 | 3136 | 2025-04-28 11:22 | 11:22 AM | 2025-04-28 11:56 | 11:56 AM | 2025-04-24 15:01 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-30 12:16
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 54741 | 2025-04-30 12:14 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 33961.83 | 10180 | 70 | 4851.69 | 0 | 3PU25BP1-643 | 2025-04-28 | 0 |  | Unbilled | MH12/UM 7849 | 3135 | 2025-04-28 10:18 | 10:18 AM | 2025-04-30 11:03 | 11:03 AM | 2025-04-24 15:01 | G BLDG | Approved |  | 0 | Ashoks | 7 | 2025-04-30 12:14
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 54740 | 2025-04-30 12:05 | Purchase | RDC Concrete India Pvt. Ltd. | 7 | CUM | 41ORANGE KRISALA STORE | 33961.83 | 10180 | 70 | 4851.69 | 0 | 3PU25BP1-642 | 2025-04-28 | 0 |  | Unbilled | UP39 UD2011 |  | 2025-04-28 09:52 | 9:52 AM | 2025-04-30 11:08 | 11:08 AM | 2025-04-24 15:01 | G BLDG | Approved |  | 0 | Ashoks | 7 | 2025-04-30 12:05
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53243 | 2025-04-14 18:10 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 38983.04 | 10039 | 127 | 4872.88 | 0 | UNIT III/24-25/5930 | 2025-04-11 | 260 | 2025-04-16 | Billed | MH12TV 7655 | 3042 | 2025-04-11 12:40 | 12:40 PM | 2025-04-11 13:33 | 1:33 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 8 | 2025-04-14 18:10
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53241 | 2025-04-14 18:02 | Purchase | RVK INFRATECH | 3 | CUM | 41ORANGE KRISALA STORE | 14618.64 | 10039 | 127 | 4872.88 | 0 | UNIT III/24-25/5940 | 2025-04-11 | 264 | 2025-04-16 | Billed | MH 12 TV 1755 | 3056 | 2025-04-11 21:00 | 9:00 PM | 2025-04-11 21:50 | 9:50 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 3 | 2025-04-14 18:02
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53240 | 2025-04-14 18:00 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 34110.16 | 10039 | 127 | 4872.88 | 0 | UNIT III/24-25/5939 | 2025-04-11 | 264 | 2025-04-16 | Billed | MH 12 TV 5516 | 3053 | 2025-04-11 18:52 | 6:52 PM | 2025-04-11 19:50 | 7:50 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-14 18:00
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53239 | 2025-04-14 17:59 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 34110.16 | 10039 | 127 | 4872.88 | 0 | UNIT III/24-25/5938 | 2025-04-11 | 263 | 2025-04-16 | Billed | MH 12 TV 1755 | 3052 | 2025-04-11 18:36 | 6:36 PM | 2025-04-11 19:53 | 7:53 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-14 17:59
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53238 | 2025-04-14 17:57 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 38983.04 | 10039 | 127 | 4872.88 | 0 | UNIT III/24-25/5937 | 2025-04-11 | 263 | 2025-04-16 | Billed | MH12TV 7655 | 3051 | 2025-04-11 18:32 | 6:32 PM | 2025-04-11 17:17 | 5:17 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 8 | 2025-04-14 17:57
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53236 | 2025-04-14 17:55 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 38983.04 | 10039 | 127 | 4872.88 | 0 | 228 | 2025-04-11 | 258 | 2025-04-16 | Billed | MH12 XM0255 | 3050 | 2025-04-11 18:22 | 6:22 PM | 2025-04-11 18:54 | 6:54 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 8 | 2025-04-14 17:55
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53233 | 2025-04-14 17:54 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 34110.16 | 10039 | 127 | 4872.88 | 0 | 225 | 2025-04-11 | 257 | 2025-04-16 | Billed | MH 12 TV 5516 | 3049 | 2025-04-11 17:27 | 5:27 PM | 2025-04-11 18:26 | 6:26 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-14 17:54
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53232 | 2025-04-14 17:53 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 34110.16 | 10039 | 127 | 4872.88 | 0 | 224 | 2025-04-11 | 257 | 2025-04-16 | Billed | MH 12 TV 1755 | 3048 | 2025-04-11 17:16 | 5:16 PM | 2025-04-11 17:42 | 5:42 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-14 17:53
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53230 | 2025-04-14 17:52 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 34110.16 | 10039 | 127 | 4872.88 | 0 | UNIT III/24-25/5935 | 2025-04-11 | 262 | 2025-04-16 | Billed | MH12TV5519 | 3047 | 2025-04-11 15:22 | 3:22 PM | 2025-04-11 16:06 | 4:06 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-14 17:52
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53229 | 2025-04-14 17:50 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 34110.16 | 10039 | 127 | 4872.88 | 0 | UNIT III/24-25/5934 | 2025-04-11 | 262 | 2025-04-16 | Billed | MH 12 TV 1755 | 3046 | 2025-04-11 15:01 | 3:01 PM | 2025-04-11 15:30 | 3:30 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-14 17:50
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53228 | 2025-04-14 17:49 | Purchase | RVK INFRATECH | 8 | CUM | 41ORANGE KRISALA STORE | 38983.04 | 10039 | 127 | 4872.88 | 0 | UNIT III/24-25/5933 | 2025-04-11 | 261 | 2025-04-16 | Billed | MH12 XM0255 | 3045 | 2025-04-11 14:38 | 2:38 PM | 2025-04-11 15:07 | 3:07 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 8 | 2025-04-14 17:49
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53227 | 2025-04-14 17:47 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 34110.16 | 10039 | 127 | 4872.88 | 0 | UNIT III/24-25/5931 | 2025-04-11 | 261 | 2025-04-16 | Billed | MH 12 TV 5516 | 3044 | 2025-04-11 13:05 | 1:05 PM | 2025-04-11 14:41 | 2:41 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-14 17:47
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53224 | 2025-04-14 17:46 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 34110.16 | 10039 | 127 | 4872.88 | 0 | 214 | 2025-04-11 | 256 | 2025-04-16 | Billed | MH 12 TV 1755 | 3043 | 2025-04-11 12:44 | 12:44 PM | 2025-04-11 13:28 | 1:28 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-14 17:46
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53220 | 2025-04-14 17:43 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 34110.16 | 10039 | 127 | 4872.88 | 0 | UNIT III/24-25/5929 | 2025-04-11 | 260 | 2025-04-16 | Billed | MH12TV5519 | 3041 | 2025-04-11 12:14 | 12:14 PM | 2025-04-11 13:29 | 1:29 PM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-14 17:43
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53216 | 2025-04-14 17:41 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 34110.16 | 10039 | 127 | 4872.88 | 0 | UNIT III/24-25/5928 | 2025-04-11 | 259 | 2025-04-16 | Billed | MH12TV 7655 |  | 2025-04-11 11:16 | 11:16 AM | 2025-04-11 11:51 | 11:51 AM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-14 17:41
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53214 | 2025-04-14 17:39 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 34110.16 | 10039 | 127 | 4872.88 | 0 | UNIT III/24-25/5927 | 2025-04-11 | 259 | 2025-04-16 | Billed | MH12TV 7655 | 3038 | 2025-04-11 11:16 | 11:16 AM | 2025-04-11 11:51 | 11:51 AM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-14 17:39
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 53210 | 2025-04-14 17:34 | Purchase | RVK INFRATECH | 7 | CUM | 41ORANGE KRISALA STORE | 34110.16 | 10039 | 127 | 4872.88 | 0 | 207 | 2025-04-11 | 256 | 2025-04-16 | Billed | MH12TV5519 | 3036 | 2025-04-11 10:28 | 10:28 AM | 2025-04-11 11:04 | 11:04 AM | 2025-04-10 12:38 |  | Approved |  | 0 | Ashoks | 7 | 2025-04-14 17:34
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50962 | 2025-03-18 13:18 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2469 | 2025-03-18 | 1272 | 2025-03-18 | Billed | MH14LL8687 | 2765 | 2025-03-18 12:20 | 12:20 PM | 2025-03-18 13:00 | 1:00 PM | 2025-03-17 11:32 | F BLDG 7TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:19
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50977 | 2025-03-18 13:13 | Purchase | GREY CORE INFRA LLP | 5 | CUM | 41ORANGE KRISALA STORE | 24364.5 | 9742 | 121 | 4872.9 | 0 | GC2474 | 2025-03-18 | 1272 | 2025-03-18 | Billed | MH12HD4750 | 2771 | 2025-03-18 13:13 | 1:13 PM | 2025-03-18 14:10 | 2:10 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 5 | 2025-03-23 13:37
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50976 | 2025-03-18 12:52 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2473 | 2025-03-18 | 1272 | 2025-03-18 | Billed | MH14/LL 8687 | 2770 | 2025-03-18 12:52 | 12:52 PM | 2025-03-18 13:47 | 1:47 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:36
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50975 | 2025-03-18 12:37 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2472 | 2025-03-18 | 1272 | 2025-03-18 | Billed | MH12 SX9138 | 2768 | 2025-03-18 12:37 | 12:37 PM | 2025-03-18 13:30 | 1:30 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:35
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50961 | 2025-03-18 12:20 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 29237.4 | 9742 | 121 | 4872.9 | 0 | GC2471 | 2025-03-18 | 1272 | 2025-03-18 | Billed | MH12PQ5483 | 2767 | 2025-03-18 12:20 | 12:20 PM | 2025-03-18 13:00 | 1:00 PM | 2025-03-17 11:32 | F BLDG 7TH SLAB CASTING | Approved |  | 0 | Ashoks | 6 | 2025-03-23 13:18
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50960 | 2025-03-18 12:07 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2470 | 2025-03-18 | 1272 | 2025-03-18 | Billed | MH14JL1493 | 2766 | 2025-03-18 12:07 | 12:07 PM | 2025-03-18 12:51 | 12:51 PM | 2025-03-17 11:32 | F BLDG 7TH SLAB CASTING | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:17
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50964 | 2025-03-18 11:49 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2468 | 2025-03-18 | 1272 | 2025-03-18 | Billed | MH12SX9138 | 2764 | 2025-03-18 11:49 | 11:49 AM | 2025-03-18 12:15 | 12:15 PM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:22
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50963 | 2025-03-18 11:18 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2467 | 2025-03-18 | 1272 | 2025-03-18 | Billed | MH14JL1493 | 2763 | 2025-03-18 11:18 | 11:18 AM | 2025-03-18 11:39 | 11:39 AM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:21
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50965 | 2025-03-18 10:14 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2466 | 2025-03-18 | 1272 | 2025-03-18 | Billed | MH14LL8687 | 2762 | 2025-03-18 10:45 | 10:45 AM | 2025-03-18 11:25 | 11:25 AM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:23
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50966 | 2025-03-18 10:13 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2464 | 2025-03-18 | 1270 | 2025-03-18 | Billed | MH12SX9138 | 2761 | 2025-03-18 10:13 | 10:13 AM | 2025-03-18 11:11 | 11:11 AM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:24
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50968 | 2025-03-18 10:05 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2463 | 2025-03-18 | 1270 | 2025-03-18 | Billed | MH14JL1493 | 2760 | 2025-03-18 10:05 | 10:05 AM | 2025-03-18 10:42 | 10:42 AM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:27
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50969 | 2025-03-18 09:50 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2462 | 2025-03-18 | 1270 | 2025-03-18 | Billed | MH14/LL 8687 | 2759 | 2025-03-18 09:50 | 9:50 AM | 2025-03-18 10:26 | 10:26 AM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:28
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50974 | 2025-03-18 09:12 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 29237.4 | 9742 | 121 | 4872.9 | 0 | GC2461 | 2025-03-18 | 1270 | 2025-03-18 | Billed | MH12HD4750 | 2755 | 2025-03-18 09:12 | 9:12 AM | 2025-03-18 10:11 | 10:11 AM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 6 | 2025-03-23 13:34
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50967 | 2025-03-18 09:02 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2460 | 2025-03-18 | 1270 | 2025-03-18 | Billed | MH12SX9138 | 2754 | 2025-03-18 09:02 | 9:02 AM | 2025-03-18 09:54 | 9:54 AM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:26
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50970 | 2025-03-18 08:45 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2459 | 2025-03-18 | 1270 | 2025-03-18 | Billed | MH14JL1493 | 2753 | 2025-03-18 08:45 | 8:45 AM | 2025-03-18 09:25 | 9:25 AM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:29
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50971 | 2025-03-18 08:05 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2458 | 2025-03-18 | 1270 | 2025-03-18 | Billed | MH14/LL 8687 | 2752 | 2025-03-18 08:05 | 8:05 AM | 2025-03-18 09:05 | 9:05 AM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:30
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50972 | 2025-03-18 08:03 | Purchase | GREY CORE INFRA LLP | 6 | CUM | 41ORANGE KRISALA STORE | 29237.4 | 9742 | 121 | 4872.9 | 0 | GC2457 | 2025-03-18 | 1270 | 2025-03-18 | Billed | MH12HD4750 | 2751 | 2025-03-18 08:03 | 8:03 AM | 2025-03-18 08:25 | 8:25 AM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 6 | 2025-03-23 13:31
41 COSMO NXT | 00 RMC | RMC M35FF (Out Source) |  | 50973 | 2025-03-18 07:05 | Purchase | GREY CORE INFRA LLP | 7 | CUM | 41ORANGE KRISALA STORE | 34110.3 | 9742 | 121 | 4872.9 | 0 | GC2456 | 2025-03-18 | 1270 | 2025-03-18 | Billed | MH14JL1493 | 2750 | 2025-03-18 07:05 | 7:05 AM | 2025-03-18 07:50 | 7:50 AM | 2025-03-17 11:32 | F BLDG 7TH slab casting | Approved |  | 0 | Ashoks | 7 | 2025-03-23 13:33