## Project_Work_Order6388205706318
Project Work Order
From 01 Apr 2010 To 06 May 2025
Page 1 of 1
Total Records: 202 Records 1 To 202
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Debit_Amt | Credit_Amt | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 15 | 55 | 825 | 148.5 | 973.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR Staircase Riser (ZIL) | Ready Made Tread Riser Fixing | Rft | 177.12 | 55 | 9741.6 | 1753.48 | 11495.08 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 177.12 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR Staircase Tread (ZIL) | Ready Made Tread Riser Fixing | Rft | 172.2 | 55 | 9471 | 1704.78 | 11175.78 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 948 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 855.3785 | 19673.71 | 0 | 0 | 3541.26 | 23214.97 | 92.6215 | 2513.75 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 90.2298
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 855.3785 | 19673.71 | 0 | 0 | 3541.26 | 23214.97 | 92.6215 | 2513.75 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 90.2298
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 855.3785 | 19673.71 | 0 | 0 | 3541.26 | 23214.97 | 92.6215 | 2513.75 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 90.2298
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 855.3785 | 19673.71 | 0 | 0 | 3541.26 | 23214.97 | 92.6215 | 2513.75 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 90.2298
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 855.5 | 19676.5 | 0 | 0 | 3541.78 | 23218.28 | 92.5 | 2510.44 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 90.2426
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 855.3785 | 19673.71 | 0 | 0 | 3541.26 | 23214.97 | 92.6215 | 2513.75 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 90.2298
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 948 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 948 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 948 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 948 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 948 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 948 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR Master Toilet Dado (ZIL) | Tile Dado Labour (300x600) | Sq.ft | 948 | 23 | 21804 | 3924.72 | 25728.72 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 948 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 176 | 23 | 4048 | 728.64 | 4776.64 | 5 | 170 | 3910 | 0 | 0 | 703.8 | 4613.8 | 6 | 162.84 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 96.5909
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 176 | 23 | 4048 | 728.64 | 4776.64 | 5 | 170 | 3910 | 0 | 0 | 703.8 | 4613.8 | 6 | 162.84 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 96.5909
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 176 | 23 | 4048 | 728.64 | 4776.64 | 5 | 170 | 3910 | 0 | 0 | 703.8 | 4613.8 | 6 | 162.84 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 96.5909
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 176 | 23 | 4048 | 728.64 | 4776.64 | 5 | 170 | 3910 | 0 | 0 | 703.8 | 4613.8 | 6 | 162.84 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 96.5909
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 176 | 23 | 4048 | 728.64 | 4776.64 | 5 | 170 | 3910 | 0 | 0 | 703.8 | 4613.8 | 6 | 162.84 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 96.5909
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 176 | 23 | 4048 | 728.64 | 4776.64 | 5 | 170 | 3910 | 0 | 0 | 703.8 | 4613.8 | 6 | 162.84 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 96.5909
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 176 | 23 | 4048 | 728.64 | 4776.64 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 176 | 23 | 4048 | 728.64 | 4776.64 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 176 | 23 | 4048 | 728.64 | 4776.64 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 176 | 23 | 4048 | 728.64 | 4776.64 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 176 | 23 | 4048 | 728.64 | 4776.64 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 176 | 23 | 4048 | 728.64 | 4776.64 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 176 | 23 | 4048 | 728.64 | 4776.64 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR Master Bed Toilet Flooring (ZIL) | Tile Flooring Labour (300x300) | SQFT | 79 | 23 | 1817 | 327.06 | 2144.06 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 1592 | 23 | 36616 | 6590.88 | 43206.88 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1592 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 433 | 23 | 9959 | 1792.62 | 11751.62 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 433 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 2012 | 23 | 46276 | 8329.68 | 54605.68 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 2012 | 23 | 46276 | 8329.68 | 54605.68 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 516 | 23 | 11868 | 2136.24 | 14004.24 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 2012 | 23 | 46276 | 8329.68 | 54605.68 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 516 | 23 | 11868 | 2136.24 | 14004.24 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 2012 | 23 | 46276 | 8329.68 | 54605.68 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 516 | 23 | 11868 | 2136.24 | 14004.24 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 2012 | 23 | 46276 | 8329.68 | 54605.68 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 516 | 23 | 11868 | 2136.24 | 14004.24 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 2012 | 23 | 46276 | 8329.68 | 54605.68 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 516 | 23 | 11868 | 2136.24 | 14004.24 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 2012 | 23 | 46276 | 8329.68 | 54605.68 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 516 | 23 | 11868 | 2136.24 | 14004.24 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 2012 | 23 | 46276 | 8329.68 | 54605.68 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 516 | 23 | 11868 | 2136.24 | 14004.24 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | double granite patti fixing |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | double granite patti fixing |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | double granite patti fixing |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | double granite patti fixing |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | double granite patti fixing |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | double granite patti fixing |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | double granite patti fixing |  | Ekta.Agarwal | Tushal.Chavan | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 265 | 55 | 14575 | 2623.5 | 17198.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 265 | 55 | 14575 | 2623.5 | 17198.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 265 | 55 | 14575 | 2623.5 | 17198.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 265 | 55 | 14575 | 2623.5 | 17198.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 265 | 55 | 14575 | 2623.5 | 17198.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 265 | 55 | 14575 | 2623.5 | 17198.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 265 | 55 | 14575 | 2623.5 | 17198.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 265 | 55 | 14575 | 2623.5 | 17198.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 265 | 55 | 14575 | 2623.5 | 17198.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 265 | 55 | 14575 | 2623.5 | 17198.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 265 | 55 | 14575 | 2623.5 | 17198.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 265 | 55 | 14575 | 2623.5 | 17198.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR Window & Ventilator Sill(Zil) | GRANITE SEAL PATTI | Rft | 265 | 55 | 14575 | 2623.5 | 17198.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR GRANITE WORKS | LABOUR FOR TOILET VENTILATOR FRAME | Rft | 81 | 55 | 4455 | 801.9 | 5256.9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR GRANITE WORKS | Umra Patti Fixing Labour | Rft | 47.5 | 55 | 2612.5 | 470.26 | 3082.76 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 7TH FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 8TH FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 9TH FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 10TH FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 11TH FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 12TH FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 13TH FLOOR GRANITE WORKS | Window Sill Labour | Rft | 144 | 55 | 7920 | 1425.6 | 9345.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 |  |  | Ekta.Agarwal | Ritesh.Gotadki | Ekta.agarwal | construction | 08 Mar 2025 | Engineering | TILING WORK | Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 516 | 23 | 11868 | 2136.24 | 14004.24 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 2012 | 23 | 46276 | 8329.68 | 54605.68 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 516 | 23 | 11868 | 2136.24 | 14004.24 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 2012 | 23 | 46276 | 8329.68 | 54605.68 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 516 | 23 | 11868 | 2136.24 | 14004.24 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 2012 | 23 | 46276 | 8329.68 | 54605.68 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 516 | 23 | 11868 | 2136.24 | 14004.24 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 2012 | 23 | 46276 | 8329.68 | 54605.68 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 516 | 23 | 11868 | 2136.24 | 14004.24 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR OFFICE TILING WORKS EVOKE C | Tile Flooring Labour - 600x600mm | Sq.ft | 2012 | 23 | 46276 | 8329.68 | 54605.68 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR Lobby Flooring (ZIL) | Tile Flooring Labour - 600x600mm | Sq.ft | 516 | 23 | 11868 | 2136.24 | 14004.24 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR Lobby Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 260 | 23 | 5980 | 1076.4 | 7056.4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR Flat Main Skirting (ZIL) | Tile Skirting Labour - 600x600mm | Rft | 580 | 23 | 13340 | 2401.2 | 15741.2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 0 | 55 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Cancel | Ritesh.Gotadki | 02 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 0 | 55 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Cancel | Ritesh.Gotadki | 02 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 0 | 55 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Cancel | Ritesh.Gotadki | 02 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 0 | 55 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Cancel | Ritesh.Gotadki | 02 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 0 | 55 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Cancel | Ritesh.Gotadki | 02 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 0 | 55 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Cancel | Ritesh.Gotadki | 02 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 0 | 55 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Cancel | Ritesh.Gotadki | 02 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | UPPER GROUND FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 1ST FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 2ND FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 3RD FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 4TH FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 5TH FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0
41 Evoke C Building | 15 | 0 | 08 Mar 2025 | JANAK LAL MAURYA | 6TH FLOOR TOILET DOOR FRAME ZIL | Toilet Door Frame Fxing | Rft | 155 | 110 | 17050 | 3069 | 20119 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 |  |  |  | Ritesh.Gotadki |  | construction | 08 Mar 2025 | Engineering | TILING WORK | Un-Approve | vyanktrao.vanjari | 05 Apr 2025 | 0